## Sheet2
Problem Statement | Source of Problem | Why 1 | Why 2 | Why 3 | Correction (immidiate Fix) | Corrective Action (Preventive actions) | Responsibility | Action Items
Base line cycle defect count was affected due to higher testing rate of NIRMAL report module at parameter level | Frequent changes in WTP/OHT report parameters and dependency on DHARA & mobile application | Testing for the NIRMAL change request (WTP/OHT report parameter changes and buffer increase to 200 meters) took more time than planned | Because multiple test cases had to be re-tested repeatedly during the same testing cycle | Because report parameters, labels, units, and buffer logic were changed incrementally and were not frozen before testing started | Freeze report parameters and buffer logic before test start; perform one-time end-to-end regression after final CR build | Freeze WTP/OHT report parameters, labels, units, and buffer logic before the start of the test cycle. Introduce a mandatory CR freeze checkpoint prior to QA sign-off. Perform one-time end-to-end regression testing only after the final CR build is delivered. | PM,QA and Dev Team | Create and enforce a “Parameter Freeze” sign-off step before test execution. Update CR workflow to block testing if requirement changes are still in progress.
Cycle time for the Sahbhagita Reports module increased because the work took more calendar days than planned, even though the functional scope was limited | Resource allocation and availability issues during the coding and execution period, along with partial engagement of assigned resources. | Because the assigned resources were not working full-time on the Sahbhagita module throughout the planned duration. | Because resources were shared across multiple modules/projects and had parallel priorities during the same period. | Because project planning assumed continuous availability, but did not account for resource unavailability, leave, or parallel commitments. | Re-prioritized Sahbhagita tasks, aligned available resources on critical activities (coding and testing), and completed the module with adjusted timelines. | Include resource availability and backup planning in estimation Avoid assigning shared resources to cycle-time-sensitive modules Track actual working days vs effort hours during execution Add resource risk buffer in module-level schedules | Dev,Testing tEAM,BA, DBA and PM | Create a resource allocation matrix per module Add resource availability check before freezing timelines Review cycle time weekly against actual participation Update estimation template to include calendar risk factors
Test cycle time increased for Sahbhagita module changes. | Testing was delayed due to dependency on client feedback, late requirement change related to video size, and limited testing resource availability. | Testing was paused while waiting for client feedback, and one tester was unavailable for a full day. | Client was performing parallel testing, and final confirmation on video size change was pending. | Video size requirement was not finalized initially and was communicated only through feedback during client testing. | Resume testing immediately after receiving client confirmation on video size. | Freeze media specifications (video size, format) before test cycle starts Maintain backup tester allocation for critical testing phases. | QA Lead Project Manager Client Coordination Team | Add “media specification freeze” checkpoint before testing sign-off Create tester backup plan to cover planned/unplanned unavailability.
FHTC data was coming from client in excel format | Samagra Data was not mapped with FHTC | Raw data was taken for FHTC module | No structured format available with department |  | Resoved this risk by Treat Mitigation | Predict Risk of FHTC of Samagra API integration was done and now direct samagra data fetching | PM,QA and Dev Team | Integration of Jal rekha FHTC with Samagra