## Sheet1
Action Point | Metric/Category | Phase | Action/Task | Description | Improvements | Expected Outcome | Implementation Date | Accountability | Responsibility | Status | Remarks / Notes | Process, Procedure, Implementation Plan
1 | DRE | All Phase ( SDLC) | Improve Review Efficiency – Requirement, Design, Code, and Test Case Reviews | 1. Requirement Review: Analyze current process, prepare SOP for current vs revised workflow, define checklists, capture review comments in defect tracking sheet. 2. Design Review: Implement structured wireframe and database review process. 3. Code Review: Enforce mandatory checklist-driven code reviews before merge. 4. Unit Test Case Review: Conduct peer review of developer test cases. 5. Functional Test Case Review: Peer review with UAT sign-off before execution. | Expected increase of review defects by 10–15%, enabling early defect detection. | Improved defect leakage prevention and higher product quality across SDLC stages | 4th Week Nov'25 | PM | BA,QA,TL | Complete | Checklists created and implemented for Jal Rekha module. | Establish mandatory review gates in SDLC. No artifact moves to the next phase without review approval. Track review effectiveness monthly.
2 | DRE | Productivity- DRE and Code review rate | Reduce the overall DRE count | 1. UAT Alignment: Ensure customer UAT team tests strictly within approved scope using agreed test cases/scenarios. 2. Production Defect Analysis: Perform RCA on production defects and implement preventive fixes. 3. Strengthen Internal QA: Increase internal testing depth before release. | Reduction in DRE by approx. 2–3%. | To increas or improve the overall performance of DRE by working on total review defects, internal testing defects and code review defects. | 4th Week Nov'25 |  | QA, TL, PM | Complete | UAT and production defects now analyzed jointly by client and internal teams. | 1) UAT Scope of defects added and analyze at both client and at development team level 2) PROD Scope of defects added and analyze at both client and at development team level
3 | Cycle Time | All Phase ( SDLC) | Re-estimate Scope Changes and no last-minute changes | 1.Scope Estimation: Perform detailed effort estimation before development 2.Change Management: Any additional customer request must go through formal change control. • Update scope document. • Re-estimate effort and timeline. • Obtain stakeholder approval 3.Execution: Proceed with coding and testing only after approval 4.Productivity Tracking: Compare planned vs actual effort to measure variance | Productivity improvement of 5–10% through controlled scope and better estimation accuracy. | Faster development throughput and improved coding rate. | 3rd Week Nove'25 |  | Developer, TL, PM | Complete | Version control for all change requests Track versions of change requests | Set up a Change Control Board (CCB) for approvals Freeze sprint scope after planning Track estimation vs actuals and keep past data for better planning
4 | Cycle Time | Test cycle time | Optimize Testing Through Structured Sign-off and Resource Planning | 1. Formal Sign-off: Require requirement sign-off for new features and change requests. Create separate story points and track via versioning (Module–Submodule–vX.X). 2. Resource Planning: Allocate dedicated testers and maintain backup testers for critical cycles. 3. Effort-based Test Planning: Estimate testing effort based on scope complexity. 4. Parallel Activities: Begin test case preparation during development to reduce idle time. 5. Measure Test Consumption: Track planned vs actual testing time. | Test cycle reduction by 5–10%. | 1.Better testing, fewer delays 2.On-time releases | 3rd Week Nove'25 |  | TL, PM, QA | Complete | Backup tester model introduced for high-priority releases. | 1.Ensure build is test-ready before handover 2.Track daily testing progress 3.Daily bug review to avoid delays