## Sheet1
Sr. No. | Metric | Phase | Action | Description | Improvements | Expected Outcome | Implementation Date | Accountability | Responsibility | Status | Remarks / Notes | Process, Procedure, Implementation Plan
1 | Productivity | All Phase ( SDLC) | Improve Review Effeciency - Requirement Review , Design Review , Code Review , Test Cases Review and this will increase productivity | 1. Requirement Review : 1.1. Analyze the Current Process. 1.2 Prepare the SOP - Current Process & Revised Process ( Define Checklist , Review cooments captured ie., defect tracking sheet , Promot - option ) 1.3 Implementation Plan. 2. Design Review 2.1 Wireframe Review Process 2.2 Database Review Process 3. Code Review - Implement Code Review Checklist 4. Unit Test Cases Review - Peer Review unit test cases 5. Test Cases Review - | This will increases the productivity by 10% | To Increase / Improve the productivity rate for coding and testing. | 2025-08-07 | PM | BA,QA,TL | Complete |  | 1. Test Plan & Test Case Review Checklist- JAL REKHA 2. Jal Rekha Code Review Checklist 3. Jal Rekha-DesignReview _ Defects 1.0 4. Jal Rekha_FRS_REVIEW Ver 1.0 5. Mobile Code Review
2 | DRE | DRE | Improve the overall DRE | 1. Align the Customer UAT Team on the Scope of Testing . ( Test Cases / Test Scenarios ) 2.Analyze the Type of defects raised And accordingly decision. | This will improve the overall DRE by 5% | To decrease / reduce total review defects and total internal testing defect | 3rd Week Aug'25 |  | QA, TL, PM | Complete |  | 1) UAT Scope of defects added and analyze at both client and at development team level 2) PROD Scope of defects added and analyze at both client and at development team level
3 | Productivity/Cycle time | Coding | Re-estimate the scope changes | 1. Estimate the Scope 2. Coding 3. Addl. Changes that are requested by Customer/Client. 3.1 Update the Scope document with that changes. 3.2 Re-estimate the Size of the Changes. 3.3 Coding 3.4 Prepare Test Cases and Execution. 4. Sum the Size of the requirements against the total Actuial efforts to Calc Productivity. | This will Improve the Productivity and Cycle time by 5-10%. | To Increase / Improve the productivity rate for coding. | 4th Week Aug'25 |  | Developer, TL, PM | Complete |  | 1. Test Plan & Test Case Review Checklist- JAL REKHA 2. Jal Rekha Code Review Checklist 3. Jal Rekha-DesignReview _ Defects 1.0 4. Jal Rekha_FRS_REVIEW Ver 1.0 5. Mobile Code Review
1 | Cycle Time | Testing | Integrate early testing practices | Begin testing activities in early development phases (unit, integration, and api postman testing) to detect issues sooner, | steps taken to improve to implement increase internal defects - Unit Test in more detail & increase the frequency of Unit test cases, DB testing & System Testing( Functional & Integration Testing) & API Testing 1-2% | Reduced defect leakage and faster resolution. | Existing Phase ( 15 November |  | tester | Planned
Next Phase (15 december)
|  |  | Client side defect minimize | User acceptance and production defects needs to be reduced | steps taken to improve to implement decrease external defects ( Before delivering module to the client we will do round of sanity so that no major defect arises later on)- UAT & Prod defect count 1-2%
| Productivity |  | Establish clear and testable requirements - Prepare BRTM ( Test cases, Use cases and Business Rules mapping at requirement phase only till testing phase and back track them | Define functional, non-functional, use cases, test scenarios defects, & business requirements early to ensure they are complete, clear, and testable ( while and before development begins. | SRS, FRS NFRS, CR Use Case & Test Case should be signoff from client to be implemented - increase productivity rate ( which will decrease coding time period ) 4-5% | Reduced rework and fewer change requests during development. | Next Phase (07th december) |  |  | Planned
| DRE |  | Focus testing on risk-prone areas | Target high-risk, defect-prone components (as identified during defect trend analysis, previous phase retrospectives, or risk assessment). Prioritize modules based on failure impact and likelihood of occurrence. | Develop and update regression test suites & Decrease External defects - Component Dependency testing 1-2% | Minimized critical defects in production. | Next Phase (15 december) |  |  | Planned
2 | Productivity | Coding | Increase or promote code reusability | Maintain reusable components, utilities, and assets to reduce redundant work and save development time. In-Line Comments for new resource reusability & Code versioning tool | Productivity rate increase by decreasing coding and testing time duration - Delivery of coding will become efficient 3-4% | Faster delivery and improved consistency across modules. | Next Phase (15 december) |  | Coder/ PM / Department/ OIC | Planned
| Productivty / Cycle Time |  | Regular Internal & External (Client) review & tracking | 2. Regular mentoring and walkthroughs to minimize coding errors and improve overall quality. | Requirements will be more clear and Productivity will increase then finally cycle time will reduce - Project will complete within given time frame 3-4% | Reduced review iterations and improved code quality metrics. | Existing Phase (15 November) |  |  | Planned
3 | Cycle Time | Overall | Reduce Shared Resource | Utilize resources effectively across project | Productivity rate increase by decreasing coding and testing time duration - Resource will fully focus on a Project | Reduce gaps between resource effort and time consumed | Next Phase( 7 December) |  | PM | Planned
| Cycle Time |  | Define task entry and exit criteria & provide training to Clients (GM, PM, FE, Contractor) | Establish clear start and end (Definition of Ready / Definition of Done) for each task to avoid ambiguity and delays. | Duration time will reduce - Rework reduction and Deliver within time frame | Clear accountability and smoother task transitions. | Next Phase( 7 December)
| Productivity |  | Overall SDLC Agile meetings (SCRUM) | Conduct regular retrospective and review meetings to identify what’s working well and areas for improvement in development and testing. | Foster continuous improvement - Delivery & Mitigation of Old Scenarios efficiently and accurately | Incremental process improvements and enhanced team collaboration. | Next Phase( 15 December) |  |  | Planned