## SOPAN Module
DAR Form
Group Name | Jal Rekha – SOPAN Module |  |  | Project Name |  | Jal Rekha - SOPAN Module
Decision Seeker |  |  |  | Evaluation Date |  | 2025-03-30
Problem Statement | Delays in construction of critical water infrastructure components such as OHTs, WTPs, Intake Wells, and IPS were observed due to lack of structured tracking of contractor commitments, limited visibility to senior officials, and absence of a formal communication and approval trail. Manual and fragmented monitoring methods made it difficult to enforce accountability, validate timelines, and take corrective actions in a timely manner.
Scope of DAR | This DAR evaluates alternative approaches for capturing, monitoring, and approving contractor commitments and construction progress for OHTs, WTPs, Intake, and IPS works, and recommends the most effective system aligned with accountability, transparency, scalability, and governance requirements of the Jal Rekha program.
DAR Team Members | Entire Project Team
Alternatives |  |  | Source of Alternatives |  |  | Remarks
A1(Manual Tracking) –Manual recording of contractor commitments using paper files, registers, and informal communication. |  |  | Existing traditional monitoring practices |  |  | High risk of delays, data loss, and no audit trail
A2(Basic Digital Tracking)–Simple spreadsheet or basic application for entering planned and actual dates without workflow or approvals. |  |  | Partially digitized internal systems. |  |  | Limited validation, weak accountability, no centralized control.
A3(SOPAN Web Module) – Web-based SOPAN module with contractor commitment capture, GM review, approvals, document upload, communication logs, and BRE-driven workflows. |  |  | Designed based on departmental needs, stakeholder consultations, and Jal Rekha governance framework. |  |  | Comprehensive, scalable, and auditable solution.
Criteria for Evaluation |  | Weightage (1 = Least important and 5 = Most important) |  | Rationale for Criteria and Weightage Selection
Legal & Regulatory Compliance |  | 5 |  | Ensures adherence to government processes and audit requirements.
Integration Feasibility |  | 4 |  | Ability to integrate with Jal Rekha portal and future modules.
Process Automation & Efficiency |  | 5 |  | Reduces manual follow-ups and accelerates decision-making.
Data Security & Document Integrity |  | 5 |  | Protects sensitive project data and maintains accountability.
Availability of Technical & Operational Resources |  | 4 |  | Ensures ease of deployment and maintenance.
Scalability & Reusability |  | 4 |  | Supports expansion to other infrastructure projects.
Ease of Adoption for Applicants |  | 3 |  | Minimizes training and resistance to change.
Operational Risk Reduction |  | 4 |  | Mitigates risks related to delays, miscommunication, and non-compliance.
Criteria for Evaluation | A1(Manual Tracking) –Manual recording of contractor commitments using paper files, registers, and informal communication. |  | A2(Basic Digital Tracking)–Simple spreadsheet or basic application for entering planned and actual dates without workflow or approvals. |  | A3(SOPAN Web Module) – Web-based SOPAN module with contractor commitment capture, GM review, approvals, document upload, communication logs, and BRE-driven workflows.
| Score | Weighted Score | Score | Weighted Score | Score | Weighted Score
Legal & Regulatory Compliance | 1 | 5 | 2 | 10 | 5 | 25
Integration Feasibility | 1 | 4 | 3 | 12 | 5 | 20
Process Automation & Efficiency | 1 | 5 | 3 | 15 | 5 | 25
Data Security & Document Integrity | 1 | 5 | 3 | 15 | 5 | 25
Availability of Technical & Operational Resources | 2 | 8 | 3 | 12 | 4 | 16
Scalability & Reusability | 1 | 4 | 3 | 12 | 5 | 20
Ease of Adoption for Applicants | 2 | 6 | 3 | 9 | 4 | 12
Operational Risk Reduction | 1 | 4 | 3 | 12 | 5 | 20
Average Weighted Score |  | 5.125 |  | 12.125 |  | 20.375
Score Range (1 - 5) : ( 1 = Minimum rating and 5 = Maximum rating)
Alternatives |  |  | Order (1 = Highest, 4 = Lowest) |  |  | Result
A1(Manual Tracking) –Manual recording of contractor commitments using paper files, registers, and informal communication. |  |  | 3 |  |  | Reject
A2(Basic Digital Tracking)–Simple spreadsheet or basic application for entering planned and actual dates without workflow or approvals. |  |  | 2 |  |  | Reject
A3(SOPAN Web Module) – Web-based SOPAN module with contractor commitment capture, GM review, approvals, document upload, communication logs, and BRE-driven workflows. |  |  | 1 |  |  | Accept
Solution Decision (Decision Authority) |  | The SOPAN Web Module (Alternative A3) is selected as the preferred solution for monitoring contractor commitments and construction progress of OHTs, WTPs, Intake, and IPS works. The solution provides structured workflows, GM oversight, approval mechanisms, document management, and a complete audit trail, thereby strengthening accountability and improving timely project delivery.
Risk anticipated |  | Delayed updates by contractors. Incorrect date entry or incomplete documentation. Resistance to process change. Delay in approvals or reviews due to workload or availability of concerned officials.
Assumptions |  | Contractors and officials have access to the SOPAN portal. Users are trained on SOPAN workflows. Required approvals and escalation hierarchies are defined. SOPAN is hosted on secure infrastructure with regular backups.
Remarks |  | The SOPAN module significantly enhances transparency, planning accuracy, and accountability in infrastructure construction monitoring. By digitizing contractor commitments and enabling structured GM oversight, the system reduces delays and strengthens governance under the Jal Rekha initiative.
Decision Authority |  | Office of the Jal Rekha Commissioner / Departmental Higher Authority |  |  |  | Date | 2025-03-28