## Jan to June
Sr No | Department | Project Name | Module | Name of Sub Modules | Features/Functionality | CR | Size USP_FP | Hours Consumed | Planned Effort (Person Hours) | Actual Effort (Person Hours) | Planned Start Date (module) | Planned End Date (module) | Actual Start Date (module) | Actual End Date (module) | Requirement Analysis Start Date (module) | Requirement Analysis End Date (module) | Design Start Date (module) | Design End Date (module) | Coding Start Date (module) | Coding End Date (module) | Testing Start Date (module) | Testing End Date (module) | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Testing Review Efforts | Requirement Review Efforts | Design Review Effort | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Productivity | DRE | Requirement Rate | Design Rate | Code Rate | Testing Rate | DRE | Productivity | Req_Rate | Des_Rate | Code_Rate | Test_Rate | Cycle Time | Req_CT | Des_CT | Code_CT | Test_CT | DRE | Internal Defects | External Defects | DRE-1 | Total Review Defects | Internal Testing Defects | Code Review Per Size
1 | Public Health Engineering Department | Jal Rekha | Dhara | Admin | 1) Register Meter under a Scheme. 2) Form design validation with scheme/asset linking. 3) Bulk data Upload of Meter Excel parsing. 4) Validation rules, and multiple meter entry creation. 5) View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report | Yes | 9 | 72 | 82 | 72 | 2025-02-11 | 2025-05-03 | 2025-02-13 | 2025-03-03 | 2025-02-11 | 2025-02-15 | 2025-02-18 | 2025-02-18 | 2025-02-19 | 2025-02-26 | 2025-02-27 | 2025-03-03 | 8 | 6 | 36 | 4 | 14 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 1 | 1.2857 | 0.225 | 0.5625 | 2.2222 | 0.44444 | 0 | 0.77778 | 0.44444 | 0.57143 | 4 | 3 | 0.75 | 0.33333 | 0.11111 | 0.11111
|  |  |  | GM PIU User | 1) The PIU GM maps villages and bulk meters related to the OHT in the master and adds the WTP, Intake meter. 2) Assign Bulk Meter to the FE under a scheme 3) Assign OHT component meter-reading tasks to Field Engineers under a scheme. 4) Assign WTP Components meter-reading tasks to Field Engineers under a scheme. 5) Verify field data reading for each component per day. 6) Check and Edit the reading entries. 7) Approve readings with comments. 8) Development of Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report. 9) OHT Component delete option given PIU GM ID |  | 76 | 624 | 850 | 744 | 2025-02-15 | 2025-04-05 | 2025-02-18 | 2025-04-15 | 2025-02-16 | 2025-02-23 | 2025-02-27 | 2025-03-03 | 2025-03-04 | 2025-04-05 | 2025-04-06 | 2025-04-15 | 64 | 32 | 320 | 36 | 120 | 24 | 16 | 12 | 1 | 3 | 3 | 3 | 4 | 4 | [7 empty] | 0.12179 | 0.95 | 1.7273 | 0.21348 | 0.52778 | 0.76316 | 0.092105 | 0.052632 | 0.42105 | 0.11842 | 0.55556 | 10 | 8 | 0.7 | 0.092105 | 0.039474 | 0.039474
|  |  |  | Change request | 1) Report Format change and Drill down functionality. 2) Change Reading entries - Options provided to GM also after TL & FE. 3) Intake WTP OHT Range functionality for mobile development |  | 15 | 120 |  |  | 2025-05-08 | 2025-05-30 | 2025-05-10 | 2025-05-27 | 2025-05-10 | 2025-05-11 | 2025-05-11 | 2025-05-13 | 2025-05-14 | 2025-05-24 | 2025-05-24 | 2025-05-27 | 16 | 12 | 56 | 12 | 16 | 4 | 2 | 2 | 1 | 1 | 2 | 1 | 0 | 1 | [7 empty] | 0.125 | 0.83333 | 1.0714 | 0.22059 | 0.75 | 1.1333 | 0.066667 | 0.13333 | 0.66667 | 0.2 | 0.83333 | 5 | 1 | 0.8 | 0.26667 | 0.066667 | 0.13333
|  |  |  | TL | 1) The entries are edited by TL if entry are filled wrong by FE . 2) The entries filled by the FE are verified and approved by the TL, and then forwarded to the GM 3) View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report |  | 7 | 52 | 98 | 82 | 20/3/2025 | 2025-10-04 | 25/3/2025 | 2025-04-05 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-04-02 | 2025-04-03 | 2025-04-05 | 8 | 6 | 24 | 2 | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | [7 empty] | 0.13462 | 0.77778 | 1 | 0.26923 | 0.7 | 2.1429 | 0.14286 | 0.14286 | 1.1429 | 0.28571 | 0.5 | 3 | 3 | 1 | 0.42857 | 0 | 0.14286
|  |  |  | Change request | 1) Change Reading entries - All options provided to TL also after FE |  | 4 | 30 |  |  | 2025-06-04 | 2025-12-04 | 2025-07-04 | 2025-04-12 | 2025-04-07 | 2025-04-08 | 2025-04-08 | 2025-04-09 | 2025-04-08 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 6 | 4 | 12 | 2 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [7 empty] | 0.13333 | 0.57143 | 1 | 0.28571 | 0.8 | 1.25 | 0.25 | 0.25 | 0.5 | 0.25 | 1 | 1 | 0 | 1 | 0.25 | 0 | 0.25
0 |  |  |  | FE / Mobile User | 1) Check on 4 parameters of meter - Meter functional, Meter not functional, Meter replace, No water supply) 2) Mobile Dev -Capture meter readings ( with numeric value, date, and remarks (Reading entry with validations, offline cache, and data persistence) & capture and upload photos of the meter ( Verify File/photo capture, compression, and upload workflow) 3) If Network not available - Save readings offline and sync later (Offline-first design, local storage, and sync logic) |  | 26 | 208 | 246 | 208 | 15/2/2025 | 2025-05-04 | 18/02/2025 | 2025-04-15 | 2025-02-16 | 2025-02-23 | 2025-02-27 | 2025-03-03 | 2025-03-04 | 2025-04-05 | 2025-04-06 | 2025-04-15 | 24 | 16 | 104 | 8 | 40 | 8 | 4 | 4 | 1 | 1 | 3 | 2 | 2 | 3 | [7 empty] | 0.125 | 0.92857 | 1.3 | 0.23214 | 0.54167 | 2.2308 | 0.26923 | 0.15385 | 1.2308 | 0.34615 | 0.58333 | 7 | 5 | 0.71429 | 0.19231 | 0.076923 | 0.11538
|  |  |  | Contractor Report View | View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report |  | 2 | 16 | 22 | 16 | 2025-03-06 | 2025-09-06 | 2025-03-06 | 2025-06-08 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2 | 2 | 8 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | [7 empty] | 0.125 | 1 | 1 | 0.25 | 0.5 | 2 | 0 | 0 | 0.5 | 0.5 | 1 | 2 | 0 | 0.5 | 0.5 | 0.5 | 0
2 | Public Health Engineering Department | Jal Rekha | Master | GM | 1) Scheme village master data (Link Scheme, PIU, GP, Village) Bulk Meter village & O&M of village Mapped 2) Edit or deactivate Master records of villages 3) OHT village master - a) associate village mapping of the scheme b) Component data goes to Dhara for assignment to the FE 4) WTP Meter mapping | Yes | 25 | 205 | 260 | 205 | 15/2/2025 | 2025-10-03 | 18/02/2025 | 2025-03-08 | 2025-02-18 | 2025-02-20 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-03-05 | 2025-03-06 | 2025-03-08 | 10 | 16 | 136 | 8 | 22 | 2 | 5 | 6 | 0 | 1 | 2 | 3 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.12195 | 1.6667 | 1.1364 | 0.17361 | 1.0417 | 0.72 | 0.08 | 0.04 | 0.44 | 0.08 | 0.6 | 6 | 4 | 0.5 | 0.12 | 0.12 | 0.08
|  |  |  | All Web Reports | 1) Reports a) CWGM, b) CWPM c) RWPM d) Distribution Pipe 2) Scheme Covered Villages Report |  | 12 | 98 | 116 | 88 | 15/3/2025 | 30/3/2025 | 15/3/2025 | 2025-03-28 | 2025-03-15 | 2025-03-16 | 2025-03-16 | 2025-03-17 | 2025-03-17 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 6 | 14 | 48 | 4 | 10 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 |  | 0 | [5 empty] | 0.12245 | 1.5 | 0.75 | 0.23077 | 1 | 1.0833 | 0.083333 | 0.083333 | 0.75 | 0.16667 | 0.71429 | 5 | 2 | 0.8 | 0.33333 | 0.083333 | 0.16667
|  |  |  | Contractor | 1) Pipe line master details - shown in anusharan module generate request for RFI to contractor (on Mobile) 2) Contractor upload pipeline master component data as per the defiined schema. 3) The GM approves or edits the pipeline master data. |  | 15 | 122 | 148 | 122 | 2025-11-03 | 2025-05-04 | 2025-11-03 | 2025-03-31 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-25 | 2025-03-26 | 2025-03-31 | 8 | 12 | 72 | 9 | 16 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 2 | 1 | [7 empty] | 0.12295 | 1.5 | 1.0714 | 0.18519 | 0.88235 | 1.3333 | 0.066667 | 0.066667 | 0.66667 | 0.33333 | 0.625 | 5 | 3 | 0.6 | 0.2 | 0.13333 | 0.13333
|  |  |  | FE Mobile | 1) Add OHT name in anusharan module generate request for RFI to contractor (on Mobile) |  | 2 | 12 | 24 | 12 | 2025-10-04 | 14/4/2025 | 2025-10-04 | 2025-04-12 | 2025-04-10 | 2025-04-11 | 2025-04-10 | 2025-04-11 | 2025-04-11 | 2025-04-12 | 2025-04-12 | 2025-04-12 | 1 | 1 | 7 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [7 empty] | 0.16667 | 2 | 2 | 0.25 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 1 | 1 | 0 | 1 | 0.5 | 0 | 0.5
|  |  |  | Change request | 1) Modify the schema 2) Mobile app anusharan module changes inside Master |  | 6 | 48 | 32 | 40 | 18/4/2025 | 28/4/2025 | 18/4/2025 | 2025-04-25 | 2025-04-18 | 2025-04-19 | 2025-04-18 | 2025-04-19 | 2025-04-19 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2 | 6 | 22 | 2 | 5 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | [7 empty] | 0.125 | 2 | 0.85714 | 0.25 | 1 | 1.1667 | 0.16667 | 0.16667 | 0.66667 | 0.16667 | 1 | 1 | 0 | 1 | 0.16667 | 0 | 0.16667
4 | Public Health Engineering Department | Jal Rekha | Nirmal | FE Mobile | 1) FE Login - Geofence components for app - API 2) FE login - Collect Water Samples from components 3) FE login - Submit sample and send it to contractor offline 4) FE collect the sample of Intake, WTP, OHT and Benificary |  | 44 | 350 | 324 | 350 | 28/2/2025 | 25/04/2025 | 28/2/2025 | 2025-04-15 | 2025-02-28 | 2025-03-07 | 2025-03-07 | 2025-03-12 | 2025-03-14 | 2025-04-05 | 2025-04-06 | 2025-04-15 | 18 | 34 | 218 | 12 | 42 | 12 | 8 | 6 | 1 | 1 | 2 | 3 | 1 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0.12571 | 1.6923 | 1.1 | 0.1913 | 0.81481 | 1.0455 | 0.15909 | 0.11364 | 0.5 | 0.20455 | 0.77778 | 7 | 2 | 0.57143 | 0.090909 | 0.068182 | 0.045455
|  |  |  | Contractor Login | 1) Contractor login - Check Samples collected from field 2) Contractor login - After Performing Lab test, update it on portal 3) Contractor login - Submit the report on portal |  | 23 | 183 | 160 | 183 | 2025-02-04 | 30/4/2025 | 2025-02-04 | 2025-04-26 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-08 | 2025-04-18 | 2025-04-19 | 2025-04-26 | 12 | 18 | 98 | 8 | 26 | 10 | 6 | 5 | 1 | 1 | 3 | 1 | 1 | 1 | [7 empty] | 0.12568 | 1.2778 | 1 | 0.21698 | 0.63889 | 1.0435 | 0.043478 | 0.13043 | 0.43478 | 0.30435 | 0.75 | 6 | 2 | 0.83333 | 0.21739 | 0.043478 | 0.13043
|  |  |  | GM | GM Login - Shall be able to check the reports - & Defects |  | 3 | 24 | 30 | 24 | 15/4/2025 | 24/4/2025 | 15/4/2025 | 2025-04-21 | 2025-04-15 | 2025-04-15 | 2025-04-16 | 2025-04-16 | 2025-04-17 | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2 | 3 | 14 | 1 | 2 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 3 | 3 |  |  |  | 0 |  |  |  | 0.125 | 1 | 0.75 | 0.2 | 1.5 | 2 | 0 | 0 | 0.66667 | 0.66667 | 0.33333 | 3 | 6 | 1 | 1 | 0 | 0.66667
|  |  |  | Change request | 1) Report parameter changes 2) Mobile app functionality of OHT Intake WTP chnages 3) Nirmal & Dhara contractor functionality and User management |  | 11 | 88 | 96 | 88 | 13/5/2025 | 30/5/2025 | 13/5/2025 | 2025-05-26 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-23 | 2025-05-24 | 2025-05-26 | 6 | 10 | 51 | 2 | 12 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 0 | 1 | [7 empty] | 0.125 | 1.375 | 0.91667 | 0.20755 | 0.73333 | 1.1818 | 0.090909 | 0.090909 | 0.54545 | 0.18182 | 0.83333 | 5 | 1 | 0.8 | 0.36364 | 0.090909 | 0.18182
5 | Public Health Engineering Department | Jal Rekha | Sahbhagita | GM | 1) GM map ISA Project Managers (PMs) to Schemes |  | 6 | 48 | 72 | 40 | 2025-06-19 | 24/6/2025 | 17/6/2025 | 2025-06-23 | 2025-06-17 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-23 | 4 | 6 | 18 | 1 | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.125 | 1 | 0.75 | 0.31579 | 0.85714 | 1 | 0.16667 | 0.16667 | 0.5 | 0 | 0.66667 | 2 | 1 | 0.5 | 0.16667 | 0.16667 | 0
|  |  |  | PM | 2) Sahbhagita report view |  | 2 | 12 | 16 | 12 | 22/6/2025 | 24/6/2025 | 22/6/2025 | 2025-06-24 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 1 | 2 | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [7 empty] | 0.16667 | 1 | 1 | 0.28571 | 2 | 1 | 0 | 0 | 0.5 | 0 | 1 | 1 | 0 | 1 | 0.5 | 0 | 0.5
|  |  |  | FE | 3) Fill the Sahbhagita activity & upload the data activity & changes updated |  | 5 | 36 | 52 | 28 | 15/6/2025 | 30/6/2025 | 17/6/2025 | 2025-06-27 | 2025-06-17 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2 | 3 | 12 | 1 | 7 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 2 | [7 empty] | 0.13889 | 1.6667 | 1.25 | 0.38462 | 0.625 | 2 | 0 | 0.2 | 1 | 0.2 | 0.5 | 3 | 3 | 0.66667 | 0.4 | 0.2 | 0.2
|  |  | Sopan | Contractor | 1) OHT Work plan start, plan end date against each stage and Submit 2) Intake work plan start, plan end date against each stage and Submit 3) WTP work plan start, plan end date against each stage and Submit 4) IPS work plan start, plan end date against each stage and Submit |  | 30 | 248 | 310 | 248 | 25/3/2025 | 2025-05-05 | 28/3/2025 | 2025-04-30 | 2025-03-28 | 2025-03-31 | 2025-04-01 | 2025-04-04 | 2025-04-05 | 2025-04-22 | 2025-04-23 | 2025-04-30 | 12 | 32 | 164 | 6 | 24 | 2 | 4 | 4 | 1 | 0 | 2 | 2 | 2 | 2 | [7 empty] | 0.12097 | 1.875 | 0.83333 | 0.17647 | 1.1538 | 1.1 | 0.1 | 0.1 | 0.56667 | 0.23333 | 0.55556 | 5 | 4 | 0.6 | 0.1 | 0.066667 | 0.066667
|  |  |  | GM | 1) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date OHT 2) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date WTP 3) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date Intake 4) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date IPS |  | 29 | 243 | 290 | 243 | 2025-05-04 | 14/5/2025 | 2025-07-04 | 2025-05-10 | 2025-04-07 | 2025-04-10 | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-05-03 | 2025-05-04 | 2025-05-10 | 12 | 28 | 158 | 4 | 32 | 2 | 4 | 3 | 0 | 1 | 2 | 3 | 2 | 1 | [7 empty] | 0.11934 | 1.8125 | 0.93548 | 0.17901 | 0.85294 | 1.1379 | 0.10345 | 0.10345 | 0.62069 | 0.2069 | 0.66667 | 6 | 3 | 0.5 | 0.10345 | 0.10345 | 0.068966
|  |  |  | Sopan Document Upload & Chat | 1) Upload Panchnama and other supporting documents & Submit 2) Chat functionality with Contractor |  | 14 | 124 | 156 | 124 | 2025-01-05 | 20/5/2025 | 2025-05-02 | 2025-05-16 | 2025-05-02 | 2025-05-03 | 2025-05-03 | 2025-05-04 | 2025-05-04 | 2025-05-12 | 2025-05-13 | 2025-05-16 | 6 | 12 | 78 | 4 | 18 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | [7 empty] | 0.1129 | 1.75 | 1 | 0.17073 | 0.7 | 1 | 0.071429 | 0.071429 | 0.57143 | 0.21429 | 0.71429 | 5 | 2 | 0.8 | 0.28571 | 0.071429 | 0.14286
|  |  |  | All Web User | 1) OHT - Mapping, Monitoring, & Report 2) WTP - Mapping, Monitoring, & Report 3) Intake - Mapping, Monitoring, & Report |  | 18 | 150 | 132 | 150 | 28/5/2025 | 16/6/2025 | 2025-06-05 | 2025-06-28 | 2025-06-05 | 2025-06-07 | 2025-06-08 | 2025-06-10 | 2025-06-11 | 2025-06-22 | 2025-06-23 | 2025-06-28 | 6 | 14 | 90 | 2 | 32 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 0.12 | 2 | 1.125 | 0.19565 | 0.54545 | 1.2778 | 0.11111 | 0.11111 | 0.61111 | 0.27778 | 0.66667 | 4 | 2 | 0.75 | 0.16667 | 0.055556 | 0.055556
[5 empty] | x` | [25 empty] | 14 | 18 | 37 | 28 | 25 | 30
Formulas:
Planned Start Date (module) = +'[1]Jan to June'!S20

## PPM Productivity cycle 1
Productivity | Code_Rate | Test_Rate
0.125 | 0.225 | 0.5625
0.12179 | 0.21348 | 0.52778
0.125 | 0.22059 | 0.75
0.13462 | 0.26923 | 0.7
0.13333 | 0.28571 | 0.8
0.125 | 0.23214 | 0.54167
0.125 | 0.25 | 0.5
0.12195 | 0.17361 | 1.0417
0.12245 | 0.23077 | 1
0.12295 | 0.18519 | 0.88235
0.16667 | 0.25 | 1
0.125 | 0.25 | 1
0.12571 | 0.1913 | 0.81481
0.12568 | 0.21698 | 0.63889
0.125 | 0.2 | 1.5
0.125 | 0.20755 | 0.73333
0.125 | 0.31579 | 0.85714
0.16667 | 0.28571 | 2
0.13889 | 0.38462 | 0.625
0.12097 | 0.17647 | 1.1538
0.11934 | 0.17901 | 0.85294
0.1129 | 0.17073 | 0.7
0.12 | 0.19565 | 0.54545
0.013155
[6 empty] | AS-IS | Productivity | Coding Rate | Testing Rate
[6 empty] | Mean | 0.12843 | 0.2308 | 0.858
|  |  | Regression Equation |  |  | SD | 0.0088267 | 0.03985 | 0.29383
|  |  | Productivity | = | 0.0821 + 0.1296 Code_Rate + 0.01913 Test_Rate | UCL | 0.15491 | 0.3504 | 1.739
[6 empty] | LCL | 0.10195 | 0.1113 | -0.024
[7 empty] | AS-IS | Productivity | Coding Rate | Testing Rate
[7 empty] | Mean | 0.12843 | 0.2308 | 0.858 | 7.7863
[7 empty] | SD | 0.0088267 | 0.03985 | 0.29383
[7 empty] | UCL | 0.15491 | 0.3504 | 1.739
[7 empty] | LCL | 0.10195 | 0.1113 | -0.024
[7 empty] | Target | Productivity
[7 empty] | Mean | 0.14127 |  | 0.012843
[7 empty] | SD | 0.05
[7 empty] | What if | Productivity | Coding Rate | Testing Rate
[7 empty] | Mean | 0.14117 | 0.32 | 0.92 | 3.125 | 1.087
[7 empty] | SD | 0.05 | 0.05 | 0.05
[7 empty] | USL | 0.29117 | 0.47 | 1.07
[7 empty] | LSL | -0.0088284 | 0.17 | 0.77
[13 empty] | 0.1407 | 0.14286
0.14085
0.14085
[14 empty] | 0.15385 | set for cycle 3
0.17241
0.13889

## PPM Cycle Time Cycle 1
Cycle Time | Code_CT | Test_CT
2.22 | 0.77778 | 0.44444
0.76316 | 0.42105 | 0.11842
1.1333 | 0.66667 | 0.2
2.1429 | 1.1429 | 0.28571 | [6 empty] | 0.627
1.25 | 0.5 | 0.25
2.2308 | 1.2308 | 0.34615 | [6 empty] | 1.414 | 0.2114
2 | 0.5 | 0.5 | [6 empty] | -0.16 | 0.6211
0.72 | 0.44 | 0.08 | [7 empty] | -0.1983
1.0833 | 0.75 | 0.16667
1.3333 | 0.66667 | 0.33333
1 | 0.5 | 0
1.1667 | 0.66667 | 0.16667
1.0455 | 0.5 | 0.20455
1.0435 | 0.43478 | 0.30435
2 | 0.66667 | 0.66667
1.1818 | 0.54545 | 0.18182
1 | 0.5 | 0
1 | 0.5 | 0
2 | 1 | 0.2
1.1 | 0.56667 | 0.23333
1.1379 | 0.62069 | 0.2069
1 | 0.57143 | 0.21429
1.2778 | 0.61111 | 0.27778 | Regression Equation
|  |  | Cycle Time | = | 0.129 + 1.312 Code_CT + 1.500 Test_CT
|  |  |  | AS-IS | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 1.3 | 0.643 | 0.234
|  |  |  | SD | 0.43517 | 0.22883 | 0.139
|  |  |  | UCL | 2.606 | 1.329 | 0.651
|  |  |  | LCL | -0.005 | -0.044 | -0.183
|  |  |  | Target | Cycle time
|  |  |  | Mean | 1.17 |  | 0.13
|  |  |  | SD | 0.25 |  |  | 0.90065
|  |  |  | What if | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 1.1708 | 0.554 | 0.21
|  |  |  | SD | 0.25 | 0.1 | 0.5
|  |  |  | USL | 1.9208 | 0.854 | 1.71
|  |  |  | LSL | -0.5 | -0.2 | -1

## PPM - DRE Cycle 1
DRE | Code Review Per Size
0.75 | 0.11111
0.7 | 0.039474
0.8 | 0.13333
1 | 0.14286
1 | 0.25
0.71429 | 0.11538
0.5 | 0
0.5 | 0.08
0.8 | 0.16667
0.6 | 0.13333
1 | 0.5
1 | 0.16667
0.57143 | 0.045455
0.83333 | 0.13043
1 | 0.66667
0.8 | 0.18182
0.5 | 0
1 | 0.5
0.66667 | 0.2
0.6 | 0.066667
0.5 | 0.068966
0.8 | 0.14286
0.75 | 0.055556
Regression Equation
|  | DRE | = | 0.6247 + 0.775 Code Review Per Size
|  |  | AS-IS | DRE | Code Review Per Size
|  |  | Mean | 0.756 | 0.169
|  |  | SD | 0.17967 | 0.15883
|  |  | UCL | 1.295 | 0.646
|  |  | LCL | 0.217 | -0.307
|  |  | Target | DRE
|  |  | Mean | 0.7938 |  | 0.0378
|  |  | SD | 0.1
|  |  | What if | DRE | Code Review Per Size
|  |  | Mean | 0.7952 | 0.22
|  |  | SD | 0.1 | 0.05
|  |  | USL | 1.0952 | 0.37
|  |  | LSL | 0.4952 | 0.07