## DC NtoJ
Sr No | Department | Project Name | Module | Name of Sub Modules | Features/Functionality | CR | Size USP_FP | Hours Consumed | Planned Effort (Person Hours) | Actual Effort (Person Hours) | Planned Start Date (module) | Planned End Date (module) | Actual Start Date (module) | Actual End Date (module) | Requirement Analysis Start Date (module) | Requirement Analysis End Date (module) | Design Start Date (module) | Design End Date (module) | Coding Start Date (module) | Coding End Date (module) | Testing Start Date (module) | Testing End Date (module) | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Testing Review Efforts | Requirement Review Efforts | Design Review Effort | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Productivity | DRE | Requirement Rate | Design Rate | Code Rate | Testing Rate | DRE | Productivity | Req_Rate | Des_Rate | Code_Rate | Test_Rate | Cycle Time | Req_CT | Des_CT | Code_CT | Test_CT | DRE | Code Review Per Size | Total Review Defects | Internal Testing
1 | Public Health Engineering Department | Jal Rekha | Anusharavaan | RFI Stage Updations and Reports Modifications | 1) Redesigning the new inner pages of Jal Rekha 2) RFI : MBR Changes for schemes 3) Update Inline Query to Funtion & Query Type Changes 4) Work On RFI Report - Pending, In Progress or send for approval 5) Database-level analysis and design for activity approval workflow. 6) Anusharavan Report Modification |  | 12 | 69 | 82 | 69 | 2025-11-08 | 22-11-2025 | 2025-11-11 | 2025-11-20 | 2025-11-11 | 2025-11-12 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-20 | 3 | 2 | 41 | 3 | 17 | 2 | 1 | 0 | 1 | 0 | 4 | 1 | 0 | 1 | [7 empty] | 0.17391 | 3 | 6 | 0.27273 | 0.63158 | 0.75 | 0.083333 | 0.083333 | 0.25 | 0.16667 | 0.83333 | 0.33333 | 0.41667 | 0.083333
2 | Public Health Engineering Department | Jal Rekha | Bharosa CR | Factory Testing Web | 1) Redesigning the inner pages of Jal Rekha 2) Wireframe creation for Bharosa module Factory testing 3) Create Web Page for Bharosa FactoryTesting Survey Inspection with All Details 4) Adding additional list of Factory Testing details into - Component, Sub component, Ordered Quantity, Inspected Quantity, Quantity Failed, Remarks and relevant documents, & images for Inspection 8) Development in Bharosa Module Add New option in all Subcomponent and Items and mapped data 9) Creating Test Scenarios for BHAROSA web 10) Creating new function and table in bharosa web module 11) Database Table/ Function Creation 12) Bug fixing at the database level and mapping of new master data records. |  | 27 | 167 | 209 | 192 | 2025-11-01 | 2025-11-26 | 2025-11-03 | 2025-11-25 | 2025-11-03 | 2025-11-06 | 2025-11-06 | 2025-11-09 | 2025-11-10 | 2025-11-20 | 2025-11-21 | 2025-11-25 | 9 | 7 | 98 | 9 | 31 | 9 | 2 | 2 | 2 | 2 | 6 | 2 | 1 | 0 | [7 empty] | 0.16168 | 2.4545 | 3 | 0.25234 | 0.675 | 0.81481 | 0.11111 | 0.11111 | 0.37037 | 0.14815 | 0.83333 | 0.22222 | 0.37037 | 0.074074
|  |  |  | Factory Testing Mobile | 1) Factory testing screens design 2) Factory Testing - Draft Activity 3) Add Scheme In Factory Testing 4) Factory testing api integration 5) Bharosa Factory testing and production deployment 6) Factory testing history api integration for production 7) Bharosa FE login issue & Bharosa Module new Mobile Insert API discussion and creation 8) Create Bharosa Module Insert and Get API foe mobile Application |  | 24 | 149 | 158 | 158 | 2025-11-18 | 2025-12-05 | 2025-11-19 | 2025-12-05 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-23 | 2025-11-24 | 2025-11-30 | 2025-12-01 | 2025-12-05 | 6 | 7 | 93 | 8 | 26 | 7 | 0 | 2 | 1 | 1 | 4 | 2 | 0 | 0 | [7 empty] | 0.16107 | 4 | 2.6667 | 0.23762 | 0.72727 | 0.66667 | 0.041667 | 0.083333 | 0.25 | 0.16667 | 0.75 | 0.16667 | 0.25 | 0.083333
|  |  |  | CR - Report View | 1) Change request in Bharosa Module (Factory Testing) Mobile report 2) Change Request in Bharosa Module Web Report 3) Bharosa Assign components to TPIA function discussion with database team. 4) Change request on existing functions in Database |  | 6 | 34 | 47 | 34 | 2025-12-07 | 2025-12-17 | 2025-12-10 | 2025-12-14 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2 | 1 | 21 | 2 | 5 | 2 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | [7 empty] | 0.17647 | 2 | 6 | 0.26087 | 0.85714 | 0.66667 | 0.16667 | 0.16667 | 0.16667 | 0.16667 | 0.66667 | 0.16667 | 0.33333 | 0.16667
6 | Public Health Engineering Department | Jal Rekha | Material Testing | GM/Contractor Login | 1) Contractor send request to GM for approval. GM can approve or reject 2) GM send to SQC and SQC assign to FE for testing of Material 3) FE submitted inspection send to GM for approval. GM can approve or reject 4) Web UI design and API integration 5) Database schema, master tables design & Function development 6) Material Testing Web Report namely Pending At PiU 7) Development of Insert API for Material Testing and Check on Postman and Database values 8) Test Case Creation-Contractor Workflow(Material Testing) 9) Functions to fetch - ESR details, Scheme list, ESR list , User list and scheme list |  | 22 | 135 | 153 | 135 | 2025-12-08 | 2026-01-02 | 2025-12-12 | 2025-12-30 | 2025-12-12 | 2025-12-15 | 2025-12-15 | 2025-12-17 | 2025-12-17 | 2025-12-25 | 2025-12-26 | 2025-12-30 | 6 | 7 | 77 | 8 | 27 | 7 | 2 | 1 | 2 | 1 | 5 | 2 | 1 | 0 | [7 empty] | 0.16296 | 2.75 | 2.75 | 0.25882 | 0.64706 | 0.81818 | 0.13636 | 0.090909 | 0.36364 | 0.18182 | 0.8 | 0.22727 | 0.36364 | 0.090909
|  |  |  | FE Login | 1) FE Login can perform Material testing at Geofenced Lat/Long of site. 2) Mobile FE login UI design and API integration 3) FE login - Database schema, master tables design & Function development 4) Sync API creation for Material Testing for multiple dropdown. 5) Test Case Creation-Contractor Workflow(Material Testing) 6) Cross-Site Scripting: DOM Bug fixing in Jal Rekha (On JS files) for Security Audit |  | 13 | 78 | 92 | 78 | 2025-12-17 | 2026-01-02 | 2025-12-19 | 2025-12-31 | 2025-12-19 | 2025-12-21 | 2025-12-21 | 2025-12-23 | 2025-12-23 | 2025-12-28 | 2025-12-28 | 2025-12-31 | 3 | 2 | 48 | 3 | 19 | 2 | 1 | 0 | 1 | 1 | 3 | 1 | 0 | 1 | [7 empty] | 0.16667 | 3.25 | 6.5 | 0.2549 | 0.61905 | 0.92308 | 0.15385 | 0.15385 | 0.38462 | 0.23077 | 0.83333 | 0.23077 | 0.38462 | 0.076923
7 | Public Health Engineering Department | Jal Rekha | FHTC | GM / Contractor Reports | 1) Created test scenarios for FETCH Module(FE and GM LOGIN) 2) Report Updates Required for GM and Contractor Modules 3) Analyzed and fixed SQL queries & updated database table and function 4) Performed PostgreSQL query development and optimization. |  | 11 | 67 | 81 | 67 | 2025-11-02 | 2025-11-19 | 2025-11-04 | 2025-11-14 | 2025-11-04 | 2025-11-05 | 2025-11-05 | 2025-11-06 | 2025-11-06 | 2025-11-11 | 2025-11-12 | 2025-11-14 | 3 | 2 | 40 | 3 | 16 | 2 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | [7 empty] | 0.16418 | 2.75 | 5.5 | 0.25581 | 0.61111 | 0.90909 | 0.090909 | 0.090909 | 0.45455 | 0.18182 | 0.75 | 0.18182 | 0.27273 | 0.090909
|  |  |  | CR - FE / Reports | 1) FE Login - Report Modification 2) New web page creation/ Modification 3) FHTC Bug fixing for village scheme mapping 4) FHTC UI Change On Survey Page as requested from department 5) Samagra multiple family id issue |  | 7 | 43 | 58 | 43 | 2025-12-01 | 2025-12-13 | 2025-12-03 | 2025-12-09 | 2025-12-03 | 2025-12-04 | 2025-12-04 | 2025-12-05 | 2025-12-05 | 2025-12-07 | 2025-12-07 | 2025-12-09 | 3 | 2 | 26 | 2 | 5 | 3 | 2 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | [7 empty] | 0.16279 | 1.4 | 3.5 | 0.25 | 0.875 | 0.85714 | 0.14286 | 0.14286 | 0.28571 | 0.28571 | 0.66667 | 0.14286 | 0.28571 | 0.14286
8 | Public Health Engineering Department | Jal Rekha | O&M Billing | Change Request GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit 2) Kapil id should be renamed to - "GM PIU O&M" 3) For 1 village multiple time mapping should not be shown 4) GM PIU and contractor name not coming correctly 5) Agreement value column name and data should come correctly 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) |  | 20 | 123 | 151 | 123 | 2025-11-02 | 2025-11-28 | 2025-11-06 | 2025-11-22 | 2025-11-06 | 2025-11-08 | 2025-11-08 | 2025-11-10 | 2025-11-13 | 2025-11-19 | 2025-11-20 | 2025-11-22 | 5 | 4 | 72 | 7 | 26 | 6 | 2 | 1 | 1 | 2 | 4 | 2 | 1 | 0 | [7 empty] | 0.1626 | 2.8571 | 4 | 0.25316 | 0.625 | 0.8 | 0.1 | 0.1 | 0.3 | 0.1 | 0.77778 | 0.2 | 0.35 | 0.1
|  |  |  | Change Request Contractor | 1) Contractor -Billing 2) CPI Base year and month calculation happen instantly 3) Remark should come at the end in below report columns 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report 5) Complaint resolved date - it is "Resolved" word please check 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement 7) Event before 48 hours should not get edited and count increase happen after 48 hours 8) Reason for relaxation only become mandatory after clicking YES 9) Penalty Relaxation spelling correct it 10) All above fields should be visible in below reports and upload documents show in report 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label 14) Bulk User MWSR , Dhara Report To Implement 15) Implement New Functionality & New Pages Database Side |  | 35 | 214 | 233 | 214 | 2025-11-27 | 2026-01-07 | 2025-12-01 | 2026-01-02 | 2025-12-01 | 2025-12-04 | 2025-12-04 | 2025-12-07 | 2025-12-10 | 2025-12-24 | 2025-12-26 | 2026-01-02 | 8 | 6 | 142 | 12 | 34 | 7 | 3 | 2 | 1 | 2 | 3 | 2 | 0 | 0 | [7 empty] | 0.16355 | 3.1818 | 4.375 | 0.22727 | 0.85366 | 0.91429 | 0.085714 | 0.085714 | 0.4 | 0.2 | 0.75 | 0.085714 | 0.17143 | 0.057143
|  |  |  | Security Vulnerability - Sonarcube & SVN | 1) Analyzed and fixed SQL queries & updated database table and function 2) Performed PostgreSQL query development and optimization. 3) Security Sanitization - Cross-Site Scripting: DOM Bug fixing in Jal Rekha (On JS files) for Security Audit |  | 4 | 23 | 31 | 23 | 2025-12-09 | 2025-12-16 | 2025-12-10 | 2025-12-14 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-13 | 2025-12-14 | 2 | 1 | 10 | 2 | 4 | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | [7 empty] | 0.17391 | 1.3333 | 4 | 0.33333 | 0.57143 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 0.25 | 0.5 | 0
9 | Public Health Engineering Department | Jal Rekha | Dhara CR | Change Request - Dhara Reports | 1) Redesigning the pages of Jal Rekha 2) View Updated / Changed Water Supply Reports - a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report 3) Updating Meter Mapping as per Department 4) work on dhara module wtp to village meter reading |  | 8 | 46 | 69 | 46 | 2025-11-08 | 2025-11-15 | 2025-11-08 | 2025-11-13 | 2025-11-08 | 2025-11-09 | 2025-11-09 | 2025-11-10 | 2025-11-10 | 2025-11-12 | 2025-11-12 | 2025-11-13 | 3 | 2 | 28 | 2 | 6 | 3 | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | [7 empty] | 0.17391 | 1.6 | 4 | 0.26667 | 0.88889 | 0.625 | 0.125 | 0.125 | 0.25 | 0.125 | 0.75 | 0.25 | 0.375 | 0.125
|  |  |  | Security Vulnerability - Sonarcube & SVN | 1) Play console crashlytics & vulnerability 2) Testing- All Module UI 3) Created and updated PostgreSQL Queries . 4) Implement Password Encryption in jal rekha database for all users 5) Function/SP development and modification 6) Dhara Report Query Optimization, Validation, and Approved Report generation. 7) Redesigning & deployment page on live server of Jal Rekha |  | 10 | 61 | 63 | 61 | 2025-12-07 | 2025-12-24 | 2025-12-10 | 2025-12-18 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-11-12 | 2025-12-13 | 2025-12-16 | 2025-12-16 | 2025-12-18 | 3 | 2 | 36 | 3 | 14 | 2 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | [7 empty] | 0.16393 | 2.5 | 5 | 0.25641 | 0.625 | 0.8 | 0.1 | -2.9 | 0.3 | 0.2 | 0.75 | 0.2 | 0.3 | 0.1
10 | Public Health Engineering Department | Jal Rekha | Nirmal | Change request - WTP, OHT, Beneficiary Report | 1) WTP Report parameter changes 2) Nirmal Reports (Beneficiary, OHT, WTP, RawWater) 3) Change Request in Nirmal Reports all OHT,WTP and Raw Water addition of 2 more drill down 4) Beneficiary Report water test report changes at different parameter level 5) Change Request in Beneficiary Report addition of Action remarks 6) Change Request in Nirmal Reports addition of 2 more drill down Beneficiary Water Test report 7) Increase filter of components in existing filter, show reports accordingly. 8) Show OHT with OHT village mapping in reports. 9) Addition of Action remarks by contractor and GM in drill down reports . UI Changes of Reports on link button click, UI Changes for Action Remarks as per chat box and one more drill down reports to be shown for "still pending test cases". 10) Popup tables are applied on action button for both contractor and GM. 11) Search options & comments box on all reports 12) Removal of Inline queries from Jal Nigam Service Database class for Web all pages and check them in Postman as well check the Jalnigam Portal. Almost 25 inline queries are removed and checked in postman. 13) New Query Type in the Nirmal module to fetch Component Master Details – Based on Scheme ID And PIU ID 14) New query in jalnigam nirmal data maping - WTP_Samples_Tested_Detail – To display detailed testing data for samples collected from Water Treatment Plants (WTP). 15) New query type to get - Beneficiary_Testing_Report_Tested_List – To fetch tested water sample details collected from beneficiary points and same with OHT | yes | 24 | 149 | 177 | 149 | 2025-11-03 | 2025-11-30 | 2025-11-05 | 2025-11-27 | 2025-11-05 | 2025-11-07 | 2025-11-08 | 2025-11-10 | 2025-11-11 | 2025-11-22 | 2025-11-23 | 2025-11-27 | 6 | 7 | 91 | 8 | 27 | 6 | 3 | 1 | 2 | 1 | 4 | 1 | 1 | 1 | [7 empty] | 0.16107 | 2.6667 | 3 | 0.24242 | 0.72727 | 0.91667 | 0.083333 | 0.083333 | 0.45833 | 0.16667 | 0.875 | 0.16667 | 0.29167 | 0.041667
|  |  |  | Change Request - Raw water Report | 1) Range facility provided for Date option 2) 5) Nirmal Raw water testing and WTP reports discussion and creation on Web 2) According to Water sample ID provided search option in the report 3) Nirmal Raw water data mapping - RawWater_Samples_Tested_Detail – To fetch testing details of raw water samples before treatment. 6) Addition of 2 columns and drill down also for the same passed and failed records. 7) Addition of bell icon on all comments popup. Text change from remarks to FE Remarks in all reports and all popup. 8) Search options & comments box on all reports 9) Contractor/FE login - WTP, Intake buffer increase to 200 meter for Raw water sample collection. |  | 16 | 96 | 116 | 96 | 2025-12-03 | 2025-12-17 | 2025-12-05 | 2025-12-14 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-08 | 2025-12-08 | 2025-12-12 | 2025-12-12 | 2025-12-14 | 6 | 2 | 53 | 5 | 21 | 5 | 2 | 2 | 2 | 1 | 4 | 2 | 1 | 0 | [7 empty] | 0.16667 | 2 | 4 | 0.27586 | 0.61538 | 0.5625 | 0.0625 | 0.125 | 0.25 | 0.125 | 0.77778 | 0.25 | 0.4375 | 0.125
11 | Public Health Engineering Department | Jal Rekha | Sahbhagita | Sahbhagita Reports | 1) Report Modification shown 2) Sahbhagita New Page for Approval of Survey Reports 3) Sahabhagita Video Functionality updations for size, format 4) Sahbhagita Page : Frm_Ngo_Summary_Reports As per discussion need Approved , Rejected and No Action on the report count . 5) Update with new service for dropdown of Village on the basis of dist_cd and video enhancements |  | 11 | 68 | 77 | 68 | 2025-11-19 | 2025-12-03 | 2025-11-22 | 2025-12-01 | 2025-11-22 | 2025-11-23 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-28 | 2025-11-28 | 2025-12-01 | 3 | 2 | 41 | 3 | 16 | 2 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | [7 empty] | 0.16176 | 2.75 | 5.5 | 0.25 | 0.61111 | 0.81818 | 0.090909 | 0.090909 | 0.27273 | 0.27273 | 0.66667 | 0.090909 | 0.18182 | 0.090909
|  |  |  | Change Request -GM / PM | 1) Sahbhagita report view chnages village wise triggers - Get_VillageForApproval 2) Need extra dropdown for Village in the page : Frm_Ngo_Survey_Approval 3) Update with a new service and functionality to make ISA dependent on Scheme and District (filter flow: PIU → Scheme → ISA → Village). 4) Update Shabhagita ISA Bill Form |  | 9 | 51 | 69 | 51 | 2025-12-02 | 2025-12-14 | 2025-12-04 | 2025-12-11 | 2025-12-04 | 2025-12-05 | 2025-12-05 | 2025-12-06 | 2025-12-06 | 2025-12-09 | 2025-12-09 | 2025-12-11 | 2 | 1 | 30 | 2 | 13 | 2 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | [7 empty] | 0.17647 | 3 | 9 | 0.28125 | 0.6 | 0.77778 | 0.11111 | 0.11111 | 0.33333 | 0.22222 | 0.75 | 0.22222 | 0.33333 | 0.11111
[31 empty] | 20 | 12 | 49 | 22 | 5 | 3
12 |  |  | CMMI Doc | Documentation | 1) Data Collection for Cycle 3 2) Baseline 2 and RCA documentation 3) Document Creation & CMMI Review Meeting Baseline RCA & Plan 4) CMMI Documentation for Cycle 2 5) CMMI Documentation RCA, Action Plan, Artifact, and DC Sheet 6) CMMI Documentation & SEPG meeting & induction training 7) CMMI L5 Document (5 Why Analysis) 8) Working on CMMIL5 cycle 2 document & DRE Defect sheet 9) CMMIL5 Estimation Sheet for all modules 10) CMMIL5 Documentation- Requirement, Code and Design defects update |  | 33 | 204 | 241 | 204 | 2025-12-02 | 2026-01-03 | 2025-12-04 | 2026-01-02 | 2025-12-04 | 2025-12-06 | 2025-12-07 | 2025-12-09 | 2025-12-11 |  |  |  | 8 | 6 | 135 | 11 | 32 | 7 | 3 | 2 | 2 | 1 | 6 | 2 | [9 empty] | 0.16176 | 3 | 4.125 | 0.22603 | 0.84615 | -1393.7879 | 0.060606 | 0.060606 | -1394 | 0 | 0.81818 | 0.18182 | 0.27273 | 0.060606
13 | Public Health Engineering Department | Jal Rekha | Bharosa /Anusharavan RFI - Cube Testing | Cube Testing Requirement & Sanitization | 1) Cube testing requirement gathering and analysis 2) Cube testing wireframe creation |  | 8 | 44 | 56 | 44 | 2025-12-23 | 2025-12-31 | 2025-12-24 | 2025-12-30 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 |  |  |  | 3 | 2 | [6 empty] | 2 | [12 empty] | 0.18182 | 2.6667 | 4 | #DIV/0! | #DIV/0! | -5751.875 | 0.125 | 0.125 | -5752.375 | 0 | 1 | 0 | 0.25 | 0

## PPM Prod
Productivity | Code_Rate | Test_Rate
0.17391 | 0.27273 | 0.63158
0.16168 | 0.25234 | 0.675
0.16107 | 0.23762 | 0.72727
0.17647 | 0.26087 | 0.85714
0.16176 | 0.22603 | 0.84615
0.18182 | 0.27586 | 1
0.16296 | 0.25882 | 0.64706
0.16667 | 0.2549 | 0.61905
0.16418 | 0.25581 | 0.61111
0.16279 | 0.25 | 0.875
0.1626 | 0.25316 | 0.625
0.16355 | 0.22727 | 0.85366
0.17391 | 0.33333 | 0.57143
0.17391 | 0.26667 | 0.88889
0.16393 | 0.25641 | 0.625
0.16107 | 0.24242 | 0.72727
0.16667 | 0.27586 | 0.61538
0.16176 | 0.25 | 0.61111
0.17647 | 0.28125 | 0.6
Regression Equation
|  |  | Productivity | = | 0.0974 + 0.2080 Code_Rate + 0.0219 Test_Rate
[5 empty] | AS-IS | Productivity | Code_Rate | Test_Rate
[5 empty] | Mean | 0.1668 | 0.2606 | 1.0753 |  | 5.9952
[5 empty] | SD | 0.0054783 | 0.021483 | 0.063917
[5 empty] | UCL | 0.18312 | 0.325 | 0.6918 |  | 5.4609
[5 empty] | LCL | 0.15025 | 0.1961 | 0.3083 |  | 6.6556
[5 empty] | Target | Productivity
[5 empty] | Mean | 0.18348 |  | 0.01668 | mean | 5.4502
[5 empty] | SD | 0.05 |  |  | ucl | 0.172
[9 empty] | lcl | 0.138
[5 empty] | What if | Productivity | Code_Rate | Test_Rate | sd | 0.051667
[5 empty] | Mean | 0.17929 | 0.32 | 0.7
[5 empty] | SD | 0.05 | 0.05 | 0.05
[5 empty] | USL | 0.32929 | 0.47 | 0.85
[5 empty] | LSL | 0.02929 | 0.17 | 0.55
Action Plan
|  |  |  | 1 | How to Improve Code Rate
|  |  |  | 2 | How to Improve Test Rate
1. Outlier Analysis
2. Action Plan for Improvement

## PPM CT
Cycle Time | Code_CT | Test_CT
0.75 | 0.25 | 0.16667
0.81481 | 0.37037 | 0.14815
0.66667 | 0.25 | 0.16667
0.66667 | 0.16667 | 0.16667
0.81818 | 0.36364 | 0.18182
0.92308 | 0.38462 | 0.23077
0.90909 | 0.45455 | 0.18182
0.85714 | 0.28571 | 0.28571
0.8 | 0.3 | 0.1
0.91429 | 0.4 | 0.2
1 | 0.25 | 0.25
0.625 | 0.25 | 0.125
0.8 | 0.3 | 0.2
0.91667 | 0.45833 | 0.16667
0.5625 | 0.25 | 0.125
0.81818 | 0.27273 | 0.27273
0.77778 | 0.33333 | 0.22222
Regression Equation
|  |  | Cycle Time | = | 0.3011 + 0.875 Code_CT + 1.201 Test_CT
|  |  |  | AS-IS | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 0.8012 | 0.3141 | 0.1876
|  |  |  | SD | 0.11687 | 0.0856 | 0.058883
|  |  |  | UCL | 1.1518 | 0.5709 | 0.3643
|  |  |  | LCL | 0.4506 | 0.0573 | 0.011
|  |  |  | Target | Cycle time
|  |  |  | Mean | 0.72108 |  | 0.08012
|  |  |  | SD | 0.25
|  |  |  | What if | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 0.72402 | 0.25 | 0.17
|  |  |  | SD | 0.25 | 0.1 | 0.5
|  |  |  | USL | 1.474 | 0.55 | 1.67
|  |  |  | LSL | -0.02598 | -0.05 | -1.33

## PPM DRE
DRE | Code Review Per Size
0.83333 | 0.33333
0.83333 | 0.22222
0.75 | 0.16667
0.66667 | 0.16667
0.8 | 0.22727
0.83333 | 0.23077
0.75 | 0.18182
0.66667 | 0.14286
0.77778 | 0.2
0.75 | 0.085714
1 | 0.25
0.75 | 0.25
0.75 | 0.2
0.875 | 0.16667
0.77778 | 0.25
0.66667 | 0.090909
0.75 | 0.22222
Regression Equation
|  | DRE | = | 0.6331 + 0.729 Code Review Per Size
|  | AS-IS | DRE | Code Review Per Size
|  | Mean | 0.778 | 0.1992
|  | SD | 0.086183 | 0.061583
|  | UCL | 1.0368 | 0.384
|  | LCL | 0.5197 | 0.0145
|  | Target | DRE
|  | Mean | 0.8 |  | 0.0389
|  | SD | 0.1
|  | What if | DRE | Code Review Per Size
|  | Mean | 0.79348 | 0.22
|  | SD | 0.1 | 0.05
|  | USL | 1.0935 | 0.37
|  | LSL | 0.49348 | 0.07

## Merge CT 2&3
Cycle Time | Code_CT | Test_CT
1.1818 | 0.45455 | 0.21212
0.9375 | 0.3125 | 0.1875
0.78049 | 0.34146 | 0.17073
0.5625 | 0.25 | 0.15625
0.5 | 0.1875 | 0.1875
0.7619 | 0.28571 | 0.16667
0.6 | 0.2 | 0.1
0.8 | 0.3 | 0.2
0.43478 | 0.1413 | 0.11957
0.36585 | 0.14634 | 0.097561
0.8 | 0.3 | 0.16667
0.47368 | 0.21053 | 0.10526
0.8 | 0.4 | 0.1
0.83333 | 0.5 | 0.33333
1 | 0.2 | 0.2
1.6 | 0.4 | 0.2
1.4 | 0.4 | 0.4
0.60714 | 0.25 | 0.16071
1.04 | 0.36 | 0.16
0.75 | 0.25 | 0.16667
0.81481 | 0.37037 | 0.14815
0.66667 | 0.25 | 0.16667
0.66667 | 0.16667 | 0.16667
0.81818 | 0.36364 | 0.18182
0.92308 | 0.38462 | 0.23077
0.90909 | 0.45455 | 0.18182
0.85714 | 0.28571 | 0.28571
0.8 | 0.3 | 0.1
0.91429 | 0.4 | 0.2
1 | 0.25 | 0.25
0.625 | 0.25 | 0.125
0.8 | 0.3 | 0.2
0.91667 | 0.45833 | 0.16667
0.5625 | 0.25 | 0.125
0.81818 | 0.27273 | 0.27273
0.77778 | 0.33333 | 0.22222
Regression Equation
|  |  | Cycle Time | = | 0.150 + 1.327 Code_CT + 1.378 Test_CT
|  |  |  | AS-IS | Cycle time | Code_CT | Test_CT | AS-IS | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 0.808 | 0.305 | 0.1837 | Mean | 0.815 | 0.2968 | 0.1717
|  |  |  | SD | 0.18883 | 0.094233 | 0.060517 | SD | 0.24883 | 0.10172 | 0.0528
|  |  |  | UCL | 1.375 | 0.5877 | 0.3653 | UCL | 1.561 | 0.602 | 0.3301
|  |  |  | LCL | 0.242 | 0.0223 | 0.0022 | LCL | 0.068 | -0.0083 | 0.0133
|  |  |  | Target | Cycle time
|  |  |  | Mean | 0.7272 |  | 0.0808
|  |  |  | SD | 0.25
|  |  |  | What if | Cycle time | Code_CT | Test_CT
|  |  |  | Mean | 0.72928 | 0.26 | 0.17
|  |  |  | SD | 0.25 | 0.1 | 0.5
|  |  |  | USL | 1.4793 | 0.56 | 1.67
|  |  |  | LSL | -0.02072 | -0.04 | -1.33

## Combine CT 2&3
Cycle Time | Req_CT | Des_CT | Code_CT | Test_CT
0.75 | 0.083333 | 0.083333 | 0.25 | 0.16667
0.81481 | 0.11111 | 0.11111 | 0.37037 | 0.14815
0.66667 | 0.041667 | 0.083333 | 0.25 | 0.16667
0.66667 | 0.16667 | 0.16667 | 0.16667 | 0.16667
0.81818 | 0.13636 | 0.090909 | 0.36364 | 0.18182
0.92308 | 0.15385 | 0.15385 | 0.38462 | 0.23077
0.90909 | 0.090909 | 0.090909 | 0.45455 | 0.18182
0.85714 | 0.14286 | 0.14286 | 0.28571 | 0.28571
0.8 | 0.1 | 0.1 | 0.3 | 0.1
0.91429 | 0.085714 | 0.085714 | 0.4 | 0.2
1 | 0.25 | 0.25 | 0.25 | 0.25
0.625 | 0.125 | 0.125 | 0.25 | 0.125
0.8 | 0.1 | -2.9 | 0.3 | 0.2
0.91667 | 0.083333 | 0.083333 | 0.45833 | 0.16667
0.5625 | 0.0625 | 0.125 | 0.25 | 0.125
0.81818 | 0.090909 | 0.090909 | 0.27273 | 0.27273
0.77778 | 0.11111 | 0.11111 | 0.33333 | 0.22222
1.1818 | 0.12121 | 0.090909 | 0.45455 | 0.21212
0.9375 | 0.125 | 0.125 | 0.3125 | 0.1875
0.78049 | 0.14634 | 0.073171 | 0.34146 | 0.17073
0.5625 | 0.0625 | 0.0625 | 0.25 | 0.15625
0.5 | 0.0625 | 0.0625 | 0.1875 | 0.1875
0.7619 | 0.095238 | 0.095238 | 0.28571 | 0.16667
0.6 | 0.1 | 0.1 | 0.2 | 0.1
0.8 | 0.1 | 0.1 | 0.3 | 0.2
0.43478 | 0.086957 | 0.065217 | 0.1413 | 0.11957
0.36585 | 0.073171 | 0.073171 | 0.14634 | 0.097561
0.8 | 0.066667 | 0.066667 | 0.3 | 0.16667
0.47368 | 0.078947 | 0.052632 | 0.21053 | 0.10526
0.8 | 0.1 | 0.1 | 0.4 | 0.1
0.83333 | 0.16667 | 0.16667 | 0.5 | 0.33333
1 | 0.2 | 0.2 | 0.2 | 0.2
1.6 | 0.2 | 0.2 | 0.4 | 0.2
1.4 | 0.2 | 0.2 | 0.4 | 0.4
0.60714 | 0.071429 | 0.089286 | 0.25 | 0.16071
1.04 | 0.04 | 0.08 | 0.36 | 0.16
Regression Equation
[6 empty] | Cycle Time | = | 0.057 + 2.133 Req_CT + 1.397 Code_CT + 0.469 Test_CT
|  |  | Regression Equation | [5 empty] | AS-IS | Cycle time | Req_CT | Code_CT | Test_CT
|  |  | Cycle Time | = | 0.0749 + 2.440 Req_CT + 1.509 Code_CT |  |  |  | Mean | 0.808 | 0.112 | 0.305 | 0.1837
[9 empty] | SD | 0.18883 | 0.033567 | 0.094517 | 0.0606
[9 empty] | UCL | 1.375 | 0.2127 | 0.5885 | 0.3655
[9 empty] | LCL | 0.242 | 0.0113 | 0.0214 | 0.0019
[9 empty] | Target | Cycle time
[9 empty] | Mean | 0.7272 |  | 0.0808
[9 empty] | SD | 0.25
[9 empty] | What if | Cycle time | Req_CT | Code_CT | Test_CT
[9 empty] | Mean | 0.93593 | 0.2 | 0.26 | 0.19
[9 empty] | SD | 0.25 | 0.1 | 0.1 | 0.5
[9 empty] | USL | 1.6859 | 0.5 | 0.56 | 1.69
[9 empty] | LSL | 0.18593 | -0.1 | -0.04 | -1.31
[9 empty] | What if | Cycle time | Req_CT | Code_CT
[9 empty] | Mean | 0.72145 | 0.098 | 0.27
[9 empty] | SD | 0.25 | 0.1 | 0.1
[9 empty] | USL | 1.4714 | 0.398 | 0.57
[9 empty] | LSL | -0.02855 | -0.202 | -0.03