## Sheet1
Action Plan
S. No. | Module/Activity | Tasks | Owner
1 | FHTC | 1. Samagra API integration with FHTC | Development Team
2. Connection installed? (Radio button) i) Inside Premise & ii) Outside Premise
3. Accept or Reject ( Remark Mandatory for Reject option)
4. Reject Remark visible to Contractor
2 | Nirmal | 1. Raw water sample ( No limit to parameter) -> remove validation of Pass or Fail | Development Team
2. PPM b/w <0.2 to 5/10 from WTP
3. No Provision of Weekly & Monthly report - Report FE
4. Provide range for WTP till 200 meter and OHT till 50 meter.
3 | Bharosa | 1. Vendor where component wise material visible & provide one more option for vendor– “Any Other” | Development Team
2. FE can upload video upto 5 MB size only.
4 | Sahabhagita | 1. FE can upload video upto 5 MB of the Village – Activity of work & can upload photo as well. | Development Team
2. Can upload video on both mobile app and web portal as well.

## Sheet2
S. No. | Module/Activity | Tasks | Status
1 | FHTC | 1. Samagra API integration with FHTC | Done
2. Connection installed? (Radio button) i) Inside Premise & ii) Outside Premise
3. Accept or Reject ( Remark Mandatory for Reject option) Change to YES /NO
4. Reject Remark visible to Contractor
2 | Nirmal | 1. Raw water sample ( No limit to parameter) -> remove validation of Pass or Fail | Done
|  | 2. PPM b/w <0.2 to 5/10 from WTP | Done
|  | 3. New Formet Report Nirmal | Done
|  | 4. Provide range for WTP till 200 meter and OHT till 50 meter. | Done
3 | Bharosa | 1. Factory Testing : Vendor where component wise material visible & provide one more option for vendor– “Any Other” | Done
|  | 2. Factory Testing: Mobile apk | Done
4 | Sahabhagita | 1. FE can upload video upto 5 MB of the Village – Activity of work & can upload photo as well. | Done
|  | 2. Can upload video on both mobile app. | UAT
|  | 3. Sahabhagita Report count mismatch | Done
|  | 4 The Accept/Reject activity for the Sahbhagita module -CP Manager iD | Done
5 | Dhara | 1. Village Mapping to multiple OHTs - Validation | Done
|  | 2. Habitation update in 540 Villages | Done
6 | Reports | 1. All reports view CGM ,MD sir ID,Contractor | Done
7 | O&M Billing | 1. GM | Done
|  | 2. Contractor -Billing Part | Done