Name of Document: Project Charter

Template Version No. 1.0					    Effective Date: 1/01/2024

| Date | Version | Description | Prepared by | Reviewed & approved by |
| --- | --- | --- | --- | --- |
| 1/01/2024 | 1.0 | First Baseline Version | Ms. Ekta Saxena | Mr. Tapan Khandelwal |

| Project Name: | Jal Rekha |
| --- | --- |
| Project Code: |  |
| Document Nature: | Internal Circulation |
| Intended User | PM, BA and Technical Team |
| Last Updated Date: |  |
| Document Status: | Initial Draft |
| Document Creation Date: |  |
| Author: | Ms. Ekta Saxena |
| Reviewer(s): | Mr. Tapan Khandelwal |
| Approver: | Dr. Rakesh Dubey |
| Document Reference: | FRS V1.0 |

Change History

A-Addition, M- Modification, D- Deletion

| Revision No. | Date | Change Mode (A/M/D) | Description | Reason for Change |
| --- | --- | --- | --- | --- |

# Purpose

Jal Rekha is a comprehensive GIS-based solution developed for MP Jal Nigam Maryadit to enable efficient planning, monitoring, and management of water supply schemes across Madhya Pradesh. The system consists of a web portal and a mobile application designed to facilitate seamless data collection, asset mapping, progress tracking, and performance monitoring of various water supply projects. By integrating advanced geospatial technologies, Jal Rekha ensures accurate visualization and real-time status reporting of ongoing works.

The primary objective of Jal Rekha is to streamline departmental operations by enabling effective task assignment, work progress monitoring, and data-driven decision-making. The platform empowers field engineers, contractors, and department officials to collaborate effectively through features like asset mapping, RFI management, inspections, and reporting dashboards. This Functional Requirements Specification (FRS) document defines the detailed requirements, functionalities, and workflows necessary for the successful implementation and operation of the Jal Rekha system.

# PROJECT DETAILS

| Project Name: | Jal Rekha | Project Code: |  |
| --- | --- | --- | --- |
| Project Category: |  |  |  |
| PIN Number: | V 1.0 | PIN Issue date: | 22/12/2023 |
| Planned Start Date: | 25/12/2024 | Planned Closure Date: |  |

# Project Size, Type and Composition

  - Project Size:

  - Estimated Effort: 140 Days Approx.

  - Project Duration (Timeline) in Months: 12 Months (including development, integration, UAT, training, and Go-Live)

  - Project Type:

| S. No | Project Type | Status of Current Project (Check as applicable) | Remark |
| --- | --- | --- | --- |
| 1. | Project | ✔ | Full-scale e-Governance initiative |
| 2. | Product |  |  |
| 3. | Consultancy / Advisory |  |  |
| 4. | O&M |  |  |
| 5. | Managed Services including AMC |  |  |
| 6. | Any Other |  |  |

  - Project Composition:

| S. No | Project Composition | Status of Current Project (Check as applicable) | Remark |
| --- | --- | --- | --- |
| 1. | Data Development | ✔ | GIS data integration, colony layouts, inspection data |
| 2. | Software Development | ✔ | Web portal (colonizer + department) & Mobile app |
| 3. | COTS Product |  |  |
| 4. | O&M |  |  |
| 5. | Managed Services including AMC |  |  |
| 6. | Any Other |  |  |

# PROJECT STAKEHOLDERS

| Stakeholder | Role / Responsibility |
| --- | --- |
| Principal Secretary, MPPHE | Project Sponsor |
| MP Jal Nigam (MPJN) | Nodal Agency & Policy Oversight |
| PIUs | Scheme-level monitoring and reporting |
| Field Engineers (FEs) | Ground-level data collection |
| SQC / TPIA Teams | Quality checks and approval workflows |
| System Integrator | Development, deployment, and support |
| NIC / MPSEDC | Infrastructure hosting & security |

# Scope

Mobile Application Functionality:

- Registration - Users can register their Android smartphones by completing a registration form within the app.

- Asset Mapping - Users can map assets/Component Point data (Intake well, OHT, BPT,WTP etc.) across different schemes and capture geo-tagged photographs associated with these components.

- Traverse functionality - The Traverse functionality enables users to move through the pipeline like CWGM, CWPM, Distribution Pipe and RWPM.

- Geofencing - All map/traverse data has been geofenced for inspections.

- Anusharvan - RFI (Request for Inspection) - Work Monitoring Module have two module Inspection request (RFI) and Inspection History.

- Anusharvan - Daily Inspection - End to end module for reporting, monitoring, approval and notification

- Dhara for Quantity of water - The Dhara Module under Jal Nigam's scheme ensures continuous monitoring and maintenance of water quantity across various regions.

- Nirmal for Quality of water - Ensures water quality in various schemes for safe drinking water. Conducts regular tests to detect contaminants or pollutants.

Web Application Functionality:

- Upload .shp - Contractors/PIUs upload design & drawing scheme wise planned data .shp files with detailed schema.

- Login - Department officers’ login PIU wise, admin login, SQC login, TPIA login, contractor login.

- User management - User role management, role assignment, user validation etc. User data fetched from Sarthak.

- Spatial Layers visualization – MP Jal Nigam layers along with other departmental layers for better decision. Planned and Actual drawings. Auto calculated length from spatial data.

- Reports - Generate detailed reports based on department requirement.

- Anusharvan - Daily Inspection - End to end module for reporting, monitoring, approval and notification

- Anusharvan - RFI (Request for Inspection) - Upon receiving an inspection request, PIU assigns the task to either SQC or TPIA. The PIU tracks the progress and can reassign if needed, ensuring efficient monitoring and completion of all inspections.

- Dhara for Quantity of water - The Dhara Module under Jal Nigam's scheme ensures continuous monitoring and maintenance of water quantity across various regions.

- Nirmal for Quality of water - Ensures water quality in various schemes for safe drinking water. Conducts regular tests to detect contaminants or pollutants.

- GIS Integration: Integration of Geographic Information System (GIS) technology will allow for the visualization of spatial data related to water infrastructure on interactive maps within the app. Users can access detailed information about the location, status, and condition of assets.

- Spatial Analysis Tools: Offer tools and algorithms for spatial analysis within the app, such as network tracing, proximity analysis, and spatial querying, to support decision-making processes related to asset management, infrastructure planning, and resource allocation.

# PROJECT BUDGET/EFFORT

•	1 Year = 1 March 2024 to 28 February 2025

  - Resource Effort & Cost (Development Phase):

| S.No | Resource | No of Resources | ManMonth | Expenditure considering on shared basis (INR.) | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 1 | 3 | 0 | Shared |
| 2 | Business Analyst | 1 | 6 | 665885/- | Shared |
| 3 | GIS Executive | 1 | 12 | 304903/- | full time |
| 4 | Database Administrator | 1 | 6 | 0/- | Shared |
| 5 | Mobile Developer | 1 | 12 | 1312200/- | full time |
| 6 | Mobile Tech Lead | 1 | 3 | 0/- | Shared |
| 7 | Dot Net Developer | 1 | 12 | 1065416/- | full time |
| 8 | Software Tester | 1 | 12 | 300,000/- | Full time |
| 9 | UI/UX | 1 | 1 | 0/- | Shared |
| Total |  | 9 |  | 3,648,403/- |  |
| Administrative Cost @ 5% (INR.) |  |  |  | 182,420.15 /- |  |
| Project Cost (INR.) |  |  |  | 3,830,823.15 /- |  |
| GST @ 18% (INR.) |  |  |  | 689,548.17/- |  |
| Total Cost with GST (INR.) |  |  |  | 4,520,371/- |  |

Note: Charges of Utilities and Value-Added Services (SMS, WhatsApp, E-sign, Drone Services) will be applicable as per actuals.

  - Payment Plan:

| S.No | Payment Milestone | %of Amount | Total Amount in Lakhs (INR.) |  |
| --- | --- | --- | --- | --- |
| 1 | Advance for Project Initiation | 50% |  | 2,260,185/- |
| 2 | UAT of Web portal and Mobile APP | 30% |  | 1,356,111/- |
| 3 | Go live of Jal Rekha Portal and Mobile App | 20% |  | 904,074/- |
| Total |  | 100% |  | 4,520,371/- |

# DELIVERABLES

- Jal Rekha Mobile and Web Application – Mobile and web application with all modules outlined in the above scope. Each module will be tested to ensure functionality and ease of use.

- User Manual – A detailed user manual for both the mobile and web application.

# PROJECT MILESTONES

The significant milestones for the CROPS project are as follows:

| S. No | Milestone | Description | Tentative Timeline | Deliverable / Outcome |
| --- | --- | --- | --- | --- |
| 1 | Project Initiation & Kick-off | Formal approval of Project Charter, team onboarding, and kickoff meeting with stakeholders | Month 0 | Approved Project Charter & Kick-off Report |
| 2 | Requirement Gathering & FRS Approval | Conduct requirement workshops, prepare Functional Requirement Specification (FRS), and obtain sign-off | Month 1 | Signed-off FRS Document |
| 3 | System Design & Architecture | Finalize system architecture, UI/UX wireframes, database schema, and integration design | Month 2 | Approved Design Document & Wireframes |
| 4 | Module Development – Phase 1 | Data visualization, Daily Inspection & Asset Mapping | Months 2–4 | Tested Phase-1 Modules |
| 5 | Module Development – Phase 2 | Anusharavan, Dashboard | Months 3–5 | Tested Phase-2 Modules |
| 6 | Module Development – Phase 3 | Dhara, Nirmal, Jal Samdhan | Months 4–6 | Tested Phase-3 Modules |
| 7 | Mobile Application Development | Develop and test GIS-enabled inspection app | Months 4–6 | Tested Mobile Application |
| 8 | System Integration & Security Testing | Integrate with external systems (PHE, MP Bhulekh, NIC, PM Gatishakti) | Month 6 | Integrated & Secured System |
| 9 | User Acceptance Testing (UAT) | Conduct UAT | Month 7 | UAT Sign-off Report |
| 10 | Capacity Building & Training | Deliver training sessions, manuals, FAQs, and helpdesk readiness | Month 8 | Trained Users & Knowledge Materials |
| 11 | Go-Live | Production deployment Web Portal & Mobile App | Month 9 | Live Application |
| 12 | Post Go-Live Support & Stabilization | Provide 3 months of hyper-care support, bug fixes, and monitoring | Months 9–12 | Stabilized System & Support Reports |

# Process Milestone

| S. No. | Milestone Name | Target Date/ Frequency | Responsibility |
| --- | --- | --- | --- |
| 1 | Project Kick-off Meeting | Month 0 (once). | Project Head & BA. |
| 2 | Project Governance and Communication Structure | Month 0 (once, during initiation). | Project Manager. |
| 3 | Draft project Plan | Month 0–1. | Project Manager with BA & Tech Lead.. |
| 4 | Final Project Plan | Month 1. | Project Head & Approver. |
| 5 | Budget Note | Month 1. | BA. |
| 6 | Project Execution | Months 2–8 (continuous). | Project Manager & Development Team. |
| 7 | Project Review | Monthly (Month 2–8). | PMU Coordinator & Project Head. |
| 8 | Project Compliance Review | Mid-project (Month 5) & Pre-Go-Live (Month 8). | Quality Manager & Risk/Legal Manager. |
| 9 | Project Delivery Note | Month 9. | Project Manager. |
| 10 | Project Completion Certificate | Month 9. | Project Head & Approver.. |

# Project Milestone

| S. No. | Milestone Name | Target Date | Responsibility |
| --- | --- | --- | --- |
| 1 | Requirement Gathering & FRS Sign-off. | End of Month 1. | Business Analyst & Project Manager. |
| 2 | System Development & Testing Completion. | End of Month 6. | Tech Lead & Development Team. |
| 3 | Go-Live & Capacity Building. | End of Month 9. | Project Head & Project Manager |

# ASSUMPTIONS, Risk & DEPENDENCIES

# Assumptions:

- PIUs will provide timely scheme-level data for Dhara mapping.

- TPIAs and FEs will ensure on-time RFI submissions.

- Hosting and infrastructure support will be provisioned by MPSEDC/NIC.

- Mobile and web portals will share a centralized database for synchronization.

# Risk:

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Delay in RFI workflow approval | Medium | High | Escalation matrix with PIUs |
| Mobile app offline sync failure | Low | High | Local caching & retry logic |
| GIS integration delays | Medium | Medium | Parallel dev + dummy datasets |
| API dependency on external sources | High | High | Early API mock & coordination |
| Data inconsistency issues | Medium | Medium | Automated validations + audits |

# ROLE & RESPONSIBILITY MATRIX

| Role & Responsibility Charting - RASCI Matrix |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| S. No | Functions | BDU coordinator | PMU coordinator | Project Team | IT/System Department | Division Head |
| 1 | Project Initiation | S | R | - | C | A |
| 2 | Project Execution | I | A | R | S | C |
| 3 | Customer Communication | R | A | S | - | I |
| 4 | Shipment | C | R | A | S | I |
| 5 | Approvals | I | R | S | - | A |
| 6 | Project Reviews | S | R | S | C | A |
| 7 | SME | - | C | R | - | S |
| 8 | Vendor Management | R | A | S | - | I |

R- Responsible, A-Accountable, S- Supported, C- Consulted, I- Informed

Note:

- Only one “A” can be assigned to an action

- RASCI chart should be independent of personal relationships so the chart would still be valid if all new people filled the roles tomorrow

- As a rule, first assign R’s then determine who has the A, then complete S’s, C’s and I’s

- Minimize the number of Consults (C) and Informs (I)

- (R) Responsibility can be shared

# PROJECT AUTHORIZATION

| Prepared by: Business Analyst | Ms. Ekta Saxena | Date: |  |
| --- | --- | --- | --- |
| Reviewed by: Project Manager | Mr. Tapan Khandelwal | Date: |  |
| Approved by: Project Head | Dr. Rakesh Dubey | Date: |  |