## Version History
Version History
Version number | Version Date | Change Description | Author/Revised by | Reviewed/Approved by
V 1.0 | 2025-01-10 | Initial Draft RASCI Matrix | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal
V 1.1 | 2025-07-10 | Initial Draft RASCI Matrix | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal

## Notes-RACI Guidelines
Notes- RACI Guidelines
Responsible - "The doer" | - Works on the activity - Typically one role is responsible for one type of work - Typically one person is responsible for individual unit of work. He carries out action/implementation - It is possible that One/Many person(s) or teams may be responsible for a group of activities
Accountable - (also Approver or final Approving authority) - "Buck stops here" | - Has YES & NO authority - Ultimately accountable for the correct and thorough completion of the deliverable or task - the one to whom Responsible is accountable. In other words, an Accountable must sign off (Approve) on work that Responsible provides. - Only one person can be Accountable to avoid blames
Consulted - In the loop for decision making | - Involved prior to decision - Their opinions are sought - Involved through two-way communication.
Informed - "Keep posted" | - Who needs to be informed after decision or action is taken - This incorporates one-way communication - Receives information about process execution and quality - Are kept up-to-date on progress
Verifies | Those who check whether the product meets the acceptance criteria set forth in the product description.
Signatory | Those who approve the Verify decision and authorize the product hand-off. It seems to make sense that the Signatory should be the party with the Accountable for its successor.

## RACI Chart
Jal Rekha - Jal Nigam, M.P.
Integrated teams | PMU Coordinator | Project Head | Project Manager | Business Analyst | Tech Lead | Developer | DBA | QA | UI/UX | Customer
Team Charter / Deliverables/Activities
Kick-off Meeting | A | R | R | C | I | I | I | I | I | I
Requirement Gathering | C | A | R | R | C | I | I | I | I | R
FRS Preparation & Sign-off | C | A | R | R | C | I | I | I | I | R
System Design & Architecture | I | C | A | C | R | I | R | C | R | I
UI/UX Wireframes | I | I | C | C | C | I | I | I | R | I
Database Schema | I | I | C | C | C | I | R | I | I | I
Module Development (Colonizer Registration, License, Fees, etc.) | I | I | A | C | R | R | R | I | C | I
Mobile App Development (RI Login, Site Inspection) | I | I | A | C | R | R | I | I | R | I
Integration (e-Sign, SMS, TNCP, Dept APIs) | I | I | A | C | R | R | R | I | I | I
Testing (Unit, Integration, UAT) | I | I | A | C | C | R | R | R | I | I
UAT with Department | C | A | R | R | C | I | I | R | I | R
Go-Live Preparation | I | C | A | C | R | R | R | R | I | I
Production Deployment | I | C | A | C | R | R | R | C | I | I
Training & Capacity Building | C | A | R | R | I | I | I | C | I | R
Post-Go-Live Support & AMC | C | A | R | C | R | R | R | R | I | R
Infrastructure | bar: I I I I C I I C C to I I I R R R C C R
Integrated teams | OIC | Project Head | Project Manager | Project/Team Lead | Business Analyst | QA | Client
| Dr. Sandeep Goyal | Dr. Rakesh Dubey | Mr. Tapan Khandelwal | Mr. Sunil Thakur | Mr. Dheeraj Motiyani | Mr. Nitin Patel | Jal Nigam
Infrastructure | I | A | R | R | R | R | I
Fill the above matrix in terms of R - Responsible A - Accountable C - Consulted I - Informed

## Sheet1
ROLE & RESPONSIBILITY MATRIX
Role & Responsibility Charting - RASCI Matrix
S. No | Functions | BDU coordinator | PMU coordinator | Project Team | IT/System Department | Division Head
1 | Project Initiation | S | R | - | C | A
2 | Project Execution | I | A | R | S | C
3 | Customer Communication | R | A | S | - | I
4 | Shipment | C | R | A | S | I
5 | Approvals | I | R | S | - | A
6 | Project Reviews | S | R | S | C | A
7 | SME | - | C | R | - | S
8 | Vendor Management | R | A | S | - | I
R- Responsible, A-Accountable, S- Supported, C- Consulted, I- Informed
Note:
1. Only one “A” can be assigned to an action
2. RASCI chart should be independent of personal relationships so the chart would still be valid if all new people filled the roles tomorrow
3. As a rule, first assign R’s then determine who has the A, then complete S’s, C’s and I’s
4. Minimize the number of Consults (C) and Informs (I)
5. (R) Responsibility can be shared