## Sheet1
Requirement Review
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
S.no. | Requirement gathering | Project Name | Module | Name of Sub Modules | Risk Analysis | Recommendation of Review | Compliance Status | Date
1 | Capture citizen grievances (water leakage, water quality, regularity, pressure and other issues) from web, mobile and call‑center channels with unique complaint ID and SLA tracking. | Jal Rekha | Jal Samadhan | Citizen Grievance | Medium – High impact if complaint categories, priorities or SLAs are incomplete or inconsistent, leading to delayed or mis‑routed grievances. | Finalize standard list of grievance types, priority matrix and SLA; enforce mandatory fields for location, scheme, village and contact details; run pilot in selected districts before state‑wide rollout. | Compliant | 2/12[/2025
2 | During grievance handling, allow field staff to view laid pipeline and related components on mobile map, using corrected survey data for accurate asset location. | Jal Rekha | Jal Samadhan | Grievance Survey & Asset Visualization | High – If survey data is inaccurate or incomplete, wrong pipeline/asset may be shown, causing incorrect resolution, citizen dissatisfaction and possible safety issues during field work. Citizen will not able to reach their and complaint issue where exactly pipeline is led | Complete and cleanse survey of pipeline data Jal Samadhan with asset mapping/GIS; | Under Review | 2025-07-12
1 | Citizen complaints and feedback collection requirements reviewed with PHED, call‑center team and district users. | Jal Rekha | Jal Samadhan | Citizen Complaint Intake & Tracking | Medium – High impact on citizen satisfaction and reputation; risk of incomplete categorization of issues (leakage, quality, pressure, regularity, others) and SLAs if requirements are unclear. | Freeze clear complaint categories, priority and SLA fields; integrate with mobile/web channels; mandate validation for location, contact, and issue type; plan pilot in 1–2 districts before state‑wide roll‑out. | Compliant | 2025-02-12