## Revision History
Revision History
Version | Date | Description | Prepared by | Reviewed by
1

## Anushravan CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify redesigned Anusharavan inner page loads successfully | Page loads without UI break | Page loads without UI break | 2025-11-18 | Pass | Low |  | NA
TC.002 | Verify updated layout alignment (labels, buttons, sections) | UI elements aligned properly | UI elements aligned properly | 2025-11-18 | Pass | Minor |  | NA
TC.003 | Verify redesigned page responsiveness on different resolutions | Page adapts correctly | Page adapts correctly | 2025-11-18 | Pass | Minor |  | NA
TC.004 | Verify old UI elements are not visible after redesign | Only new UI is displayed | Only new UI is displayed | 2025-11-18 | Pass | Low |  | NA
TC.005 | Verify navigation between Anusharavan pages after UI change | Navigation works smoothly | Navigation works smoothly | 2025-11-18 | Pass | Major |  | NA
TC.006 | Verify action buttons (Save, Submit, Cancel) visibility | Buttons displayed correctly | Buttons displayed correctly | 2025-11-18 | Pass | Major |  | NA
TC.007 | Verify form validations still work after UI redesign | Validations trigger correctly | Validations trigger correctly | 2025-11-18 | Pass | Low |  | NA
TC.008 | Verify no regression in existing Anusharavan functionality | Existing flows work as expected | Existing flows work as expected | 2025-11-18 | Pass | Minor |  | NA
TC.009 | Verify RFI generation without entering MBR for schemes where MBR is mandatory | RFI generation blocked | RFI generation blocked | 2025-11-18 | Pass | Minor |  | NA
TC.010 | Verify validation message when MBR is missing | Proper error message shown | Proper error message shown | 2025-11-19 | Pass | Low |  | NA
TC.011 | Verify RFI generation after entering valid MBR | RFI generated successfully | RFI generated successfully | 2025-11-19 | Pass | Major |  | NA
TC.012 | Verify MBR field is marked mandatory in UI | Mandatory indicator shown | Mandatory indicator shown | 2025-11-19 | Pass | Minor |  | NA
TC.013 | Verify MBR value saved correctly with RFI | Correct value stored | Correct value stored | 2025-11-19 | Pass | Minor |  | NA
TC.014 | Verify MBR field is not mandatory for the 6 identified schemes | MBR not required | Validation was removed from stages as well | 2025-11-19 | FAIL | Minor | 2025-11-19 | NA
TC.015 | Verify RFI generation without entering MBR for these schemes | RFI generated successfully | RFI generated successfully | 2025-11-19 | Pass | Low |  | NA
TC.016 | Verify system does not show MBR validation error | No validation error | No validation error | 2025-11-19 | Pass | Major |  | NA
TC.017 | Verify RFI generated correctly for schemes without MBR | RFI created successfully | RFI created successfully | 2025-11-19 | Pass | Major |  | NA
TC.018 | Verify other mandatory fields still enforced | Validations work correctly | Validations work correctly | 2025-11-19 | Pass | Low |  | NA
TC.019 | Verify MBR field hidden/disabled if designed so | UI behaves as designed | UI behaves as designed | 2025-11-19 | Pass | Minor |  | NA
TC.020 | Verify MBR rule changes apply only to the specified 6 scheme IDs | Logic applied correctly | Logic applied correctly | 2025-11-19 | Pass | Minor |  | NA
TC.021 | Verify remaining schemes still require MBR | No unintended impact | No unintended impact | 2025-11-19 | Pass | Low |  | NA
TC.022 | Verify switching scheme updates MBR requirement dynamically | UI refreshes correctly | UI refreshes correctly | 2025-11-19 | Pass | Major |  | NA
TC.023 | Verify backend validation matches UI validation | Consistent behavior | Consistent behavior | 2025-11-19 | Pass | Minor |  | NA
TC.024 | Verify RFI workflow progresses after generation | Workflow continues correctly | Workflow continues correctly | 2025-11-19 | Pass | Minor |  | NA
TC.025 | Verify generated RFI appears in contractor list | RFI listed correctly | RFI listed correctly | 2025-11-19 | Pass | Low |  | NA
TC.026 | Verify GM/PIU can view RFI generated without MBR | RFI visible | RFI visible | 2025-11-19 | Pass | Major |  | NA
TC.027 | Verify RFI approval flow unaffected by MBR change | Approval works normally | Approval works normally | 2025-11-19 | Pass | Major |  | NA
TC.028 | Verify Anusharavan report page loads after modification | Report loads successfully | Report loads successfully | 2025-11-19 | Pass | Low |  | NA
TC.029 | Verify newly added search filters are visible | Filters displayed correctly | Filters was not displayed correctly for range filter | 2025-11-19 | FAIL | Low | 2025-11-20 | NA
TC.030 | Verify filtering by Scheme works correctly | Correct records shown | Correct records shown | 2025-11-19 | Pass | Major |  | NA
TC.031 | Verify filtering by Village works correctly | Correct data displayed | Correct data displayed | 2025-11-19 | Pass | Major |  | NA
TC.032 | Verify filtering by RFI status works correctly | Data filtered accurately | Data filtered accurately | 2025-11-19 | Pass | Low |  | NA
TC.033 | Verify multiple filters applied together | Combined filters work | Combined filters work | 2025-11-19 | Pass | Minor |  | NA
TC.034 | Verify filter reset/clear functionality | Filters reset properly | Filters reset properly | 2025-11-20 | Pass | Low |  | NA
TC.035 | Verify search performance with increased filters | Acceptable response time | Acceptable response time | 2025-11-20 | Pass | Major |  | NA
TC.036 | Verify report data matches backend records | Data consistent | Data consistent | 2025-11-20 | Pass | Major |  | NA
TC.037 | Verify RFI records without MBR appear correctly | Records visible | Records visible | 2025-11-20 | Pass | Low |  | NA
TC.038 | Verify RFI records with MBR appear correctly | Records visible | Records visible | 2025-11-20 | Pass | Minor |  | NA
TC.039 | Verify no duplicate records shown in reports | No duplication | No duplication | 2025-11-20 | Pass | Low |  | NA
TC.040 | Verify pagination works with filtered results | Pagination correct | Pagination correct | 2025-11-20 | Pass | Major |  | NA
TC.041 | Verify role-based access to RFI and reports | Access controlled | Access controlled | 2025-11-20 | Pass | Major |  | NA
TC.042 | Verify unauthorized user cannot generate RFI | Access denied | Access denied | 2025-11-20 | Pass | Low |  | NA
TC.043 | Verify report export (if applicable) | Export works correctly | Export works correctly | 2025-11-20 | Pass | Minor |  | NA
TC.044 | Verify system behavior on slow network | Graceful handling | Graceful handling | 2025-11-20 | Pass | Minor |  | NA
TC.045 | Verify no regression in other modules due to changes | Other modules unaffected | Other modules unaffected | 2025-11-20 | Pass | Low |  | NA

## Bharosa CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify GM can log in and access BHAROSA → Factory Testing module | GM should be able to log in successfully and Factory Testing module should be visible | GM should be able to log in successfully and Factory Testing module should be visible | 2025-11-21 | Pass | Minor |  | NA
TC.002 | Verify redesigned Factory Testing page loads as per wireframe | Page should load with updated UI layout and controls | Page should load with updated UI layout and controls | 2025-11-21 | Pass | Major |  | NA
TC.003 | Verify Factory Testing Survey Inspection page fields | All required inspection fields should be displayed | All required inspection fields should be displayed | 2025-11-21 | Pass | Minor |  | NA
TC.004 | Verify Component dropdown loads master data | Component dropdown should show all valid components | Component dropdown should show all valid components | 2025-11-24 | Pass | Major |  | NA
TC.005 | Verify Sub Component dropdown filters correctly | Only related sub-components should be displayed | Only related sub-components should be displayed | 2025-11-24 | Pass | Low |  | NA
TC.006 | Verify Add New Sub Component option | System should allow adding new sub-component | System should allow adding new sub-component | 2025-11-24 | Pass | Minor |  | NA
TC.007 | Verify Add New Item option | System should allow adding new item and mapping | System should allow adding new item and mapping | 2025-11-24 | Pass | Low |  | NA
TC.008 | Verify Ordered Quantity validation | Only numeric values should be accepted | Only numeric values should be accepted | 2025-11-24 | Pass | Minor |  | NA
TC.009 | Verify Inspected Quantity validation | Inspected quantity should not exceed ordered quantity | Inspected quantity should not exceed ordered quantity | 2025-11-25 | Pass | Major |  | NA
TC.010 | Verify Quantity Failed validation | Failed quantity should not exceed inspected quantity | Failed quantity should not exceed inspected quantity | 2025-11-25 | Pass | Minor |  | NA
TC.011 | Verify Remarks field input | Remarks should accept text and special characters | Remarks should accept text and special characters | 2025-11-25 | Pass | Major |  | NA
TC.012 | Verify Inspector image correctly uploaded on web | Image should be upload successfully | Inspector and other inpection images are upload in inspector image column | 2025-11-25 | Fail | Minor | 2025-11-25 | NA
TC.013 | Verify Factory Testing submission | Record should be saved successfully | Record should be saved successfully | 2025-11-25 | Pass | Minor |  | NA
TC.014 | Verify duplicate submission prevention | System should prevent duplicate records | System should prevent duplicate records | 2025-12-01 | Pass | Minor |  | NA
TC.015 | Verify Factory Testing record appears in list | New record should appear in listing | New record should appear in listing | 2025-12-01 | Pass | Major |  | NA
TC.016 | Verify Inspector record can not be added more than maxium allowed | Only 5 Inspector sjould be added | Sysle allow to add more than 5 Inspector record | 2025-12-01 | Fail | Major | 2025-12-01 | NA
TC.017 | Verify assigned Factory Testing records visible | Assigned tasks should be visible | Assigned tasks should be visible | 2025-12-01 | Pass | Major |  | NA
TC.018 | Verify Factory Testing screen UI on mobile | UI should load correctly on mobile | UI should load correctly on mobile | 2025-12-02 | Pass | Low |  | NA
TC.019 | Verify Add Scheme in mobile Factory Testing | Scheme should be selectable | Scheme should be selectable | 2025-12-02 | Pass | Minor |  | NA
TC.020 | Verify save Factory Testing as Draft | Draft should be saved locally | Draft should be saved locally | 2025-12-02 | Pass | Low |  | NA
TC.021 | Verify Draft persists after relaunch | Draft should remain available | Draft should remain available | 2025-12-04 | Pass | Low |  | NA
TC.022 | Verify submit Factory Testing from mobile | Data should sync successfully | Data should sync successfully | 2025-12-04 | Pass | Minor |  | NA
TC.023 | Verify inspection document/image/video from mobile | Inspection document/image/video should be uploaded from mobile and it should be viewed on web report | Inspection document/image/video should not be uploaded from mobile. | 2025-12-04 | Fail | Major | 2025-12-05 | NA
TC.024 | Verify invalid file upload validation | System should show validation error | System should show validation error | 2025-12-05 | Pass | Minor |  | NA
TC.025 | Verify Insert API triggered on submit | Insert API should be called successfully | Insert API should be called successfully | 2025-12-05 | Pass | Major |  | NA
TC.026 | Verify Factory Testing history API | History should show past records | History should show past records | 2025-12-05 | Pass | Low |  | NA
TC.027 | Verify API failure handling on mobile | User-friendly error should be shown | User-friendly error should be shown | 2025-12-13 | Pass | Minor |  | NA
TC.028 | Verify web Factory Testing Inspection data | Inspection data should show all inspection details | Inspection data should not displayed in History tab | 2025-12-13 | Fail | Major | 2025-12-14 | NA
TC.029 | Verify mobile Factory Testing report | Factory testing report containing Mobile data should match and refect on web | Factory testing report containing Mobile data should not be matching and refecting on web | 2025-12-13 | Fail | Major | 2025-12-13 | NA
TC.030 | Verify rotate functionality for documents/images | User should be able to rotate document/Images on web repot | User should not be able to rotate document/Images on web repot | 2025-12-13 | Fail | Major | 2025-12-14 | NA
TC.031 | Verify report handles missing data | Report should show placeholders | Report should show placeholders | 2025-12-13 | Pass | Minor |  | NA
TC.032 | Verify report matches database data | Report data should be consistent | Report data should be consistent | 2025-12-13 | Pass | Major |  | NA
TC.033 | Verify Insert Factory Testing API | API should insert records correctly | API should insert records correctly | 2025-12-14 | Pass | Minor |  | NA
TC.034 | Verify Get Factory Testing API | API should return correct data | API should return correct data | 2025-12-14 | Pass | Major |  | NA
TC.035 | Verify Assign Component to TPIA API | Assigned components should map to inspector | Assigned components should map to inspector | 2025-12-14 | Pass | Low |  | NA
TC.036 | Verify new DB tables/functions | Tables/functions should exist and work | Tables/functions should exist and work | 2025-12-14 | Pass | Minor |  | NA
TC.037 | Verify master data mapping after DB fix | Master data should map correctly | Master data should map correctly | 2025-12-14 | Pass | Minor |  | NA
TC.038 | Verify no regression in Bharosa module | Existing functionality should work | Existing functionality should work | 2025-12-14 | Pass | Low |  | NA

## FHTC CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify GM login with valid credentials | GM should be authenticated successfully and redirected to the GM dashboard without any error messages | GM should be authenticated successfully and redirected to the GM dashboard without any error messages | 2025-11-12 | Pass | Major
TC.002 | Verify GM login with invalid credentials | System should display a clear “Invalid Credentials” message and deny access | System should display a clear “Invalid Credentials” message and deny access | 2025-11-12 | Pass | Minor
TC.003 | Verify GM session timeout handling | Expired session should redirect GM to the login page and prompt re-authentication | Expired session should redirect GM to the login page and prompt re-authentication | 2025-11-12 | Pass | Major
TC.004 | Verify GM can access FHTC module | FHTC module should be visible and clickable and load without UI or API errors | FHTC module should be visible and clickable and load without UI or API errors | 2025-11-12 | Pass | Low
TC.005 | Verify FHTC report page loads | Report page should display Scheme dropdown, Search and Reset buttons, and data table | Report page should display Scheme dropdown, Search and Reset buttons, and data table | 2025-11-12 | Pass | Minor
TC.006 | Verify Scheme dropdown data | Dropdown should populate with correct schemes fetched from Samagra without duplicates | Dropdown should populate with correct schemes fetched from Samagra without duplicates | 2025-11-12 | Pass | Low
TC.007 | Verify search without scheme | System should display validation message requesting Scheme selection | System should display validation message requesting Scheme selection | 2025-11-12 | Pass | Low
TC.008 | Verify search with valid scheme | Only FE-submitted records for the selected scheme should be displayed | Only FE-submitted records for the selected scheme should be displayed | 2025-11-13 | Pass | Minor
TC.009 | Verify Reset functionality | Reset should clear all filters and reload the default unfiltered dataset | Reset should clear all filters and reload the default unfiltered dataset | 2025-11-13 | Pass | Major
TC.010 | Verify Accept record visibility | Records submitted as Accept by FE should show Accept status with correct FE details | Records submitted as Accept by FE should show Accept status with correct FE details | 2025-11-13 | Pass | Minor
TC.011 | Verify Reject record visibility | Rejected records should be visible to GM and Contractor with correct status | Rejected records should be visible to GM and Contractor with correct status | 2025-11-13 | Pass | Major
TC.012 | Verify image thumbnail display | Image thumbnail should be visible for records with uploaded photos | Image thumbnail should be visible for records with uploaded photos | 2025-11-13 | Pass | Low
TC.013 | Verify image viewer | Clicking image thumbnail should open full-size image matching FE submission | Clicking image thumbnail should open full-size image matching FE submission | 2025-11-13 | Pass | Minor
TC.014 | Verify missing photo handling | System should display “Photo Missing” flag for records without image | System should display “Photo Missing” flag for records without image | 2025-11-14 | Pass | Major
TC.015 | Verify dashboard counts | Dashboard FHTC counts should match the number of records in report table | Dashboard FHTC counts should match the number of records in report table | 2025-11-14 | Pass | Major
TC.016 | Verify FE login with valid credentials | FE should log in successfully and land on Jal Rekha profile page | FE should log in successfully and land on Jal Rekha profile page | 2025-11-14 | Pass | Major
TC.017 | Verify HSC module access | HSC module should be visible and accessible after login | HSC module should be visible and accessible after login | 2025-11-14 | Pass | Minor
TC.018 | Verify village data download | Household list should be downloaded successfully for selected village | Household list should be downloaded successfully for selected village | 2025-11-14 | Pass | Major
TC.019 | Verify household list display | All households should display with correct family and member identifiers | All households should display with correct family and member identifiers | 2025-11-14 | Pass | Minor
TC.020 | Verify survey page opens | Household survey page should open with all mandatory fields visible | Household survey page should open with all mandatory fields visible | 2025-11-14 | Pass | Major
TC.021 | Verify Tap Connection = Yes flow | Connection Installed and Tap Installed Properly fields should appear | Connection Installed and Tap Installed Properly fields should appear | 2025-11-14 | Pass | Low
TC.022 | Verify Tap Connection = No flow | Additional fields should remain hidden and non-editable | Additional fields should remain hidden and non-editable | 2025-11-14 | Pass | Minor
TC.023 | Verify beneficiary photo capture | Camera should open and captured photo should attach successfully | Camera should open and captured photo should attach successfully | 2025-12-08 | Pass | Minor
TC.024 | Verify photo mandatory validation | System should block submission and show validation message if photo missing | System should block submission and show validation message if photo missing | 2025-12-08 | Pass | Low
TC.025 | Verify GPS mandatory validation | System should block submission if GPS location is not captured | System should block submission if GPS location is not captured | 2025-12-08 | Pass | Major
TC.026 | Verify online draft save | Draft should be saved successfully and visible in Draft tab | Draft should be saved successfully and visible in Draft tab | 2025-12-08 | Pass | Low
TC.027 | Verify offline draft save | Draft should be saved locally without any data loss | Draft should be saved locally without any data loss | 2025-12-08 | Pass | Minor
TC.028 | Verify offline sync | Offline records should sync automatically once network is restored | Offline records should sync automatically once network is restored | 2025-12-08 | Pass | Low
TC.029 | Verify Accept submission | Accepted record should sync successfully and reflect on GM web dashboard | Accepted record should sync successfully and reflect on GM web dashboard | 2025-12-08 | Pass | Minor
TC.030 | Verify Reject submission | Rejected record should reflect on both GM and Contractor dashboards | Rejected record should reflect on both GM and Contractor dashboards | 2025-12-08 | Pass | Major
TC.031 | Verify FE submission persistence | Survey data, images, and metadata should be stored correctly in database | Survey data, images, and metadata should be stored correctly in database | 2025-12-08 | Pass | Minor
TC.032 | Verify Accept/Reject status mapping | Status should be correctly stored and retrievable for reports | Status should be correctly stored and retrievable for reports | 2025-12-08 | Pass | Major
TC.033 | Verify Samagra field mapping | Samagra family and member IDs should map correctly to FHTC records | Samagra family and member IDs should map correctly to FHTC records | 2025-12-09 | Pass | Low
TC.034 | Verify duplicate prevention | System should prevent multiple records for same Household/Consumer ID | System should prevent multiple records for same Household/Consumer ID | 2025-12-09 | Pass | Minor
TC.035 | Verify report query accuracy | GM report queries should return accurate and complete data | GM report queries should return accurate and complete data | 2025-12-09 | Pass | Low
TC.036 | Verify dashboard aggregation | Dashboard count queries should match report totals | Dashboard count queries should match report totals | 2025-12-09 | Pass | Minor
TC.037 | Verify API whitelisting | Only whitelisted API calls should be allowed to access FHTC services | Only whitelisted API calls should be allowed to access FHTC services | 2025-12-09 | Pass | Major
TC.038 | Verify FE login regression | FE login should work as earlier without issues | FE login should work as earlier without issues | 2025-12-09 | Pass | Minor
TC.039 | Verify GM login regression | GM login should remain unaffected after CR deployment | GM login should remain unaffected after CR deployment | 2025-12-09 | Pass | Low
TC.040 | Verify old records visibility | Records created before CR should remain visible and correct | Records created before CR should remain visible and correct | 2025-12-09 | Pass | Low
TC.041 | Verify export regression | Export functionality should continue working with correct data | Export functionality should continue working with correct data | 2025-12-09 | Pass | Minor
TC.042 | Verify end-to-end FHTC flow | Complete FE to GM workflow should execute without errors | Complete FE to GM workflow should execute without errors | 2025-12-09 | Pass | Minor

## O&M CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify_KapilSees24PIUs | User verifies Kapil sees all 24 PIU records | User verifies Kapil sees all 24 PIU records | 2025-11-20 | Pass | Major
TC.002 | Verify_Kapil_Permissions | User verifies permissions adhere to spec (read-only/edit) | User verifies permissions adhere to spec (read-only/edit) | 2025-11-20 | Pass | Minor
TC.003 | Verify_Kapil_FiltersPagination | User verifies filters/pagination work and all records present | User verifies filters/pagination work and all records present | 2025-11-20 | Pass | Major
TC.004 | Verify_Kapil_Audit | User verifies access and export logged | User verifies access and export logged | 2025-11-20 | Pass | Low
TC.005 | Verify_Rename_Kapil_UI | User verifies label shows "GM PIU O&M" | User verifies label shows "GM PIU O&M" | 2025-11-20 | Pass | Minor
TC.006 | Verify_Rename_BackwardCompatibility | User verifies old references still resolve to the user | User verifies old references still resolve to the user | 2025-11-20 | Pass | Low
TC.007 | Verify_Prevent_DuplicateVillageMapping | User verifies system blocks duplicate mapping and shows message | User verifies system blocks duplicate mapping and shows message | 2025-11-20 | Pass | Low
TC.008 | Verify_VillageMapping_DifferentComponents | User verifies behavior follows business rule | User verifies behavior follows business rule | 2025-11-21 | Pass | Minor
TC.009 | Verify_Admin_DuplicateCleanupReport | User verifies duplicates flagged for cleanup | User verifies duplicates flagged for cleanup | 2025-11-21 | Pass | Minor
TC.010 | Verify_Display_GM_PIU_Name | User verifies displayed name matches DB | User verifies displayed name matches DB | 2025-11-21 | Pass | Low
TC.011 | Verify_Display_Contractor_Name | User verifies contractor name correct and searchable | User verifies contractor name correct and searchable | 2025-11-21 | Pass | Low
TC.012 | Verify_Name_SpecialCharsHandling | User verifies rendering correct and no truncation | User verifies rendering correct and no truncation | 2025-11-21 | Pass | Minor
TC.013 | Verify_AgreementColumn_Label | User verifies label matches spec (Agreement Value (₹)) | User verifies label matches spec (Agreement Value (₹)) | 2025-11-21 | Pass | Low
TC.014 | Verify_Agreement_DataCorrectness | User verifies numeric values match source and format correct | User verifies numeric values match source and format correct | 2025-11-21 | Pass | Low
TC.015 | Verify_Agreement_SortingNumeric | User verifies numeric sorting (not lexicographic) | User verifies numeric sorting (not lexicographic) | 2025-11-21 | Pass | Low
TC.016 | Verify_AdditionalFacilities_PersistAfterLogout | User verifies data persists after login | User verifies data persists after login | 2025-11-21 | Pass | Low
TC.017 | Verify_SessionExpiry_Recovery | User verifies saved/draft data remains | User verifies saved/draft data remains | 2025-11-21 | Pass | Low
TC.018 | Verify_UnsavedWarning_OnLogout | User verifies unsaved-change warning (if implemented) | User verifies unsaved-change warning (if implemented) | 2025-11-21 | Pass | Low
TC.019 | Verify_SchemeChange_AutoRefresh | User verifies fields reset and new scheme data loaded | User verifies fields reset and new scheme data loaded | 2025-11-21 | Pass | Minor
TC.020 | Verify_SchemeChange_ExplicitRefresh | User verifies UI reloads scheme data | User verifies UI reloads scheme data | 2025-11-21 | Pass | Minor
TC.021 | Verify_SchemeChange_WarnOnDataCopy | User verifies system warns before overwriting previous scheme data | User verifies system warns before overwriting previous scheme data | 2025-11-21 | Pass | Minor
TC.022 | Verify_SchemeID_MappingCorrectness | User verifies correct scheme id mapping and data fetch | User verifies correct scheme id mapping and data fetch | 2025-11-22 | Pass | Low
TC.023 | Verify_EPramanad_Integration | User verifies E-Pramanad value matches or errors handled gracefully | User verifies E-Pramanad value matches or errors handled gracefully | 2025-11-22 | Pass | Low
TC.024 | Verify_Dhara_BulkUser_Mapping | User verifies mapping successful and fallback message shown if missing | User verifies mapping successful and fallback message shown if missing | 2025-11-22 | Pass | Minor
TC.025 | Verify_GoldenBill_Regression | User verifies outputs match golden-bill expected values | User verifies outputs match golden-bill expected values | 2025-11-22 | Pass | Low
TC.026 | Verify_RBAC_Permissions | User verifies each role only performs permitted actions | User verifies each role only performs permitted actions | 2025-11-22 | Pass | Low
TC.027 | Verify_UI_Responsive_Keyboard | User verifies layout intact and keyboard nav accessible | User verifies layout intact and keyboard nav accessible | 2025-11-22 | Pass | Minor
TC.028 | Verify_Perf_SaveNext_FreezeConcurrency | User verifies system handles load without data corruption or major latency | User verifies system handles load without data corruption or major latency | 2025-11-22 | Pass | Minor
TC.029 | Verify_OpenGenerateBillPage | User verifies page loads and scheme/contractor context is pre-filled. | User verifies page loads and scheme/contractor context is pre-filled. | 2025-12-26 | Pass | Low
TC.030 | Verify_CreateNewBill_HappyPath | User verifies bill saved with correct status (Draft/Submitted) and visible in list. | User verifies bill saved with correct status (Draft/Submitted) and visible in list. | 2025-12-26 | Pass | Minor
TC.031 | Verify_SaveDraft_Resume | User verifies saved fields are persisted and restored exactly. | User verifies saved fields are persisted and restored exactly. | 2025-12-26 | Pass | Low
TC.032 | Verify_MandatoryFieldValidation | User verifies inline validation messages shown and save/submit blocked. | User verifies inline validation messages shown and save/submit blocked. | 2025-12-26 | Pass | Low
TC.033 | Verify_FileUpload_TypeSizeValidation | User verifies allowed files accepted and disallowed/oversize files rejected with correct error. | User verifies allowed files accepted and disallowed/oversize files rejected with correct error. | 2025-12-26 | Pass | Low
TC.034 | Verify_PreventDuplicateBill | User verifies system prevents creation of duplicate RA bill entry. | User verifies system prevents creation of duplicate RA bill entry. | 2025-12-29 | Pass | Low
TC.035 | Verify_BillCalculation_Golden | User verifies totals match golden calculation. | User verifies totals match golden calculation. | 2025-12-29 | Pass | Minor
TC.036 | Verify_EditBlocked_AfterSubmitOrFreeze | User verifies edits blocked and proper message shown. | User verifies edits blocked and proper message shown. | 2025-12-29 | Pass | Low
TC.037 | Verify_MobileResponsive_GenerateBill | User verifies layout adapts and fields are usable on smaller screens. | User verifies layout adapts and fields are usable on smaller screens. | 2025-12-29 | Pass | Low
TC.038 | Verify_ExportBill_PDF_Excel | User verifies export contains required fields and new fields appear correctly. | User verifies export contains required fields and new fields appear correctly. | 2025-12-30 | Pass | Minor
TC.039 | Verify_CPIBase_InstantCalc | User verifies Base CPI month/year auto-fetched and displayed instantly. | User verifies Base CPI month/year auto-fetched and displayed instantly. | 2025-12-30 | Pass | Minor
TC.040 | Verify_CPIBase_EdgeDates | User verifies derived CPI month/year are correct for edge dates. | User verifies derived CPI month/year are correct for edge dates. | 2025-12-30 | Pass | low
TC.041 | Verify_CPIBase_ManualOverrideAudit | User verifies recalculation occurs and change logged in audit. | User verifies recalculation occurs and change logged in audit. | 2025-12-30 | Pass | Low
TC.042 | Verify_CPIBase_ReflectedInBill | User verifies new CPI applied to O&M calculations immediately. | User verifies new CPI applied to O&M calculations immediately. | 2025-12-31 | Pass | Minor
TC.043 | Verify_CPIBase_FetchFailureHandling | User verifies UI shows graceful error and retry option. | User verifies UI shows graceful error and retry option. | 2025-12-31 | Pass | Minor
TC.044 | Verify_CPIBase_AuditTrail | User verifies change recorded with user and timestamp. | User verifies change recorded with user and timestamp. | 2025-12-31 | Pass | Minor
TC.045 | Verify_Remarks_Column_Last_Export | User verifies Remarks column is final/right-most column in export. | User verifies Remarks column is final/right-most column in export. | 2025-12-31 | Pass | Minor
TC.046 | Verify_Remarks_Position_UI | User verifies Remarks is last column in table and visible without excessive horizontal scroll. | User verifies Remarks is last column in table and visible without excessive horizontal scroll. | 2025-12-31 | Pass | Minor
TC.047 | Verify_Remarks_ContentCorrect | User verifies exact remark text appears in last column of report. | User verifies exact remark text appears in last column of report. | 2025-12-31 | Pass | Low
TC.048 | Verify_Remarks_LongTextHandling | User verifies remark is truncated with tooltip or expandable view, column still last. | User verifies remark is truncated with tooltip or expandable view, column still last. | 2025-12-31 | Pass | Minor
TC.049 | Verify_HSC_Label_Changed | User verifies column label shows 'Additional affected HSCs' instead of 'No of HSC'. | User verifies column label shows 'Additional affected HSCs' instead of 'No of HSC'. | 2025-12-31 | Pass | Major
TC.050 | Verify_HSC_DataMapping | User verifies displayed values reflect additional affected HSCs per new definition. | User verifies displayed values reflect additional affected HSCs per new definition. | 2025-12-31 | Pass | Low
TC.051 | Verify_HSC_ExportHeaderValues | User verifies exported header and values correspond to 'Additional affected HSCs'. | User verifies exported header and values correspond to 'Additional affected HSCs'. | 2026-01-01 | Pass | Major
TC.052 | Verify_HSC_BackwardCompatibility | User verifies templates map old column to new column without breakage. | User verifies templates map old column to new column without breakage. | 2026-01-01 | Pass | Minor
TC.053 | Verify_ComplaintResolvedDate_Value | User verifies Complaint Resolved Date shows actual date (DD-MM-YYYY) not 'Resolved'. | User verifies Complaint Resolved Date shows actual date (DD-MM-YYYY) not 'Resolved'. | 2026-01-01 | Pass | Major
TC.054 | Verify_ComplaintResolvedDate_Historical | User verifies resolved date displays correctly for historical records. | User verifies resolved date displays correctly for historical records. | 2026-01-01 | Pass | Low
TC.055 | Verify_ComplaintResolvedDate_Export | User verifies resolved date present in export. | User verifies resolved date present in export. | 2026-01-01 | Pass | Minor
TC.056 | Verify_ComplaintResolvedDate_Unresolved | User verifies field is blank or shows 'Not Resolved' per spec. | User verifies field is blank or shows 'Not Resolved' per spec. | 2026-01-01 | Pass | Major
TC.057 | Verify_ComplaintType_TextCorrected | User verifies option text reads 'Demand that cannot be fulfilled as per the agreement' exactly. | User verifies option text reads 'Demand that cannot be fulfilled as per the agreement' exactly. | 2026-01-01 | Pass | Low
TC.058 | Verify_ComplaintType_FilterExport | User verifies corrected text used consistently in filters and export. | User verifies corrected text used consistently in filters and export. | 2026-01-01 | Pass | Minor
TC.059 | Verify_ComplaintType_LegacyMapping | User verifies legacy records map to corrected complaint type. | User verifies legacy records map to corrected complaint type. | 2026-01-01 | Pass | Minor
TC.060 | Verify_Event_EditWithin48hAllowed | User verifies edit allowed for events <48h. | User verifies edit allowed for events <48h. | 2026-01-01 | Pass | Minor
TC.061 | Verify_Event_EditAfter48hBlocked | User verifies edit is blocked and user shown informative message. | User verifies edit is blocked and user shown informative message. | 2026-01-01 | Pass | Minor
TC.062 | Verify_Event_EditUI_DisabledAfter48h | User verifies edit buttons/controls disabled and tooltip explains reason. | User verifies edit buttons/controls disabled and tooltip explains reason. | 2026-01-01 | Pass | Minor
TC.063 | Verify_Event_Count_IncrementsAfter48h | User verifies count increases only after 48h boundary. | User verifies count increases only after 48h boundary. | 2026-01-01 | Pass | Low
TC.064 | Verify_Event_Edit_AuditOnBlockedAttempt | User verifies blocked attempt logged with user/time. | User verifies blocked attempt logged with user/time. | 2026-01-01 | Pass | Minor
TC.065 | Verify_Event_Boundary_48h | User verifies behavior matches spec (allowed or blocked as defined). | User verifies behavior matches spec (allowed or blocked as defined). | 2026-01-01 | Pass | Major
TC.066 | Verify_ReasonMandatory_OnRelaxationYes | User verifies Reason for relaxation becomes mandatory and validation enforces non-empty. | User verifies Reason for relaxation becomes mandatory and validation enforces non-empty. | 2026-01-01 | Pass | Low
TC.067 | Verify_ReasonOptional_OnRelaxationNo | User verifies Reason hidden/optional and not required. | User verifies Reason hidden/optional and not required. | 2026-01-02 | Pass | Minor
TC.068 | Verify_ReasonToggle_PreserveBehavior | User verifies previous value preserved or cleared per spec and validation enforced. | User verifies previous value preserved or cleared per spec and validation enforced. | 2026-01-02 | Pass | Minor
TC.069 | Verify_Reason_ExportWhenYes | User verifies Reason present in export. | User verifies Reason present in export. | 2026-01-02 | Pass | Low
TC.070 | Verify_PenaltyRelaxation_LabelCorrect_UI | User verifies label spelled 'Penalty Relaxation' everywhere. | User verifies label spelled 'Penalty Relaxation' everywhere. | 2026-01-02 | Pass | Minor
TC.071 | Verify_PenaltyRelaxation_Label_Export | User verifies corrected spelling appears in exports. | User verifies corrected spelling appears in exports. | 2026-01-02 | Pass | Major
TC.072 | Verify_PenaltyRelaxation_NoBrokenRefs | User verifies no functional breakage from rename. | User verifies no functional breakage from rename. | 2026-01-02 | Pass | Low
TC.073 | Verify_ReportIncludes_AllNewFields | User verifies CPI base, remarks, additional HSCs, resolved date, reason for relaxation, GST flag and other fields present. | User verifies CPI base, remarks, additional HSCs, resolved date, reason for relaxation, GST flag and other fields present. | 2026-01-02 | Pass | Minor
TC.074 | Verify_Report_ShowsUploadedDocsWithLinks | User verifies report shows uploaded document name and view/download link. | User verifies report shows uploaded document name and view/download link. | 2026-01-02 | Pass | Minor
TC.075 | Verify_ExportDocFileNames | User verifies a column lists uploaded file names (no files embedded). | User verifies a column lists uploaded file names (no files embedded). | 2026-01-02 | Pass | Minor
TC.076 | Verify_PowerCons_SinglePDFUpload | User verifies multi-page PDF accepted and linked to record. | User verifies multi-page PDF accepted and linked to record. | 2026-01-02 | Pass | Major
TC.077 | Verify_PowerCons_FileValidation | User verifies upload rejected and error message shown. | User verifies upload rejected and error message shown. | 2026-01-02 | Pass | Minor
TC.078 | Verify_PowerCons_ViewMultiPagePDF | User verifies PDF viewer displays pages corresponding to Intake/IPS/WTP bills. | User verifies PDF viewer displays pages corresponding to Intake/IPS/WTP bills. | 2025-12-13 | Pass | Major
TC.079 | Verify_PowerCons_LabelText | User verifies label reads 'Upload document (electricity bills of Intake, IPS, WTP)'. | User verifies label reads 'Upload document (electricity bills of Intake, IPS, WTP)'. | 2025-12-13 | Pass | Low
TC.080 | Verify_Manpower_CPIIncrementShown | User verifies Manpower penalty column displays CPI increment detail. | User verifies Manpower penalty column displays CPI increment detail. | 2025-12-13 | Pass | Minor
TC.081 | Verify_Manpower_FreezeAfterSave | User verifies rows become non-editable (frozen). | User verifies rows become non-editable (frozen). | 2025-12-13 | Pass | Low
TC.082 | Verify_Manpower_UnfreezeWorkflow | User verifies unfreeze request workflow initiated, approvals required and audit recorded. | User verifies unfreeze request workflow initiated, approvals required and audit recorded. | 2025-12-13 | Pass | Low
TC.083 | Verify_MobileCount_Validation | User verifies server & client validation blocks save with message. | User verifies server & client validation blocks save with message. | 2025-12-13 | Pass | Minor
TC.084 | Verify_MobileCount_BoundaryChecks | User verifies accepted/rejected values per rule. | User verifies accepted/rejected values per rule. | 2025-12-13 | Pass | Minor
TC.085 | Verify_Freeze_PersistsAcrossRoles | User verifies freeze state preserved and enforcing edit restrictions. | User verifies freeze state preserved and enforcing edit restrictions. | 2025-12-13 | Pass | Low
TC.086 | Verify_SubMeterLabel_Updated | User verifies label reads 'Upload supporting doc (Sub Meter Reading Proof)'. | User verifies label reads 'Upload supporting doc (Sub Meter Reading Proof)'. | 2025-12-13 | Pass | Low
TC.087 | Verify_SubMeterFile_Reported | User verifies uploaded filename appears mapped under the label. | User verifies uploaded filename appears mapped under the label. | 2025-12-13 | Pass | Minor
TC.088 | Verify_MWSR_BulkUser_Report | User verifies report shows expected columns and per-user volumes. | User verifies report shows expected columns and per-user volumes. | 2025-12-13 | Pass | Low
TC.089 | Verify_DharaBulkUser_Report | User verifies Dhara-sourced values appear and match external service values. | User verifies Dhara-sourced values appear and match external service values. | 2025-12-13 | Pass | Low
TC.090 | Verify_MWSR_Dhara_Reconciliation | User verifies differences flagged and metrics shown. | User verifies differences flagged and metrics shown. | 2025-12-13 | Pass | Low
TC.091 | Verify_MWSR_Report_RolesAccess | User verifies access and export behavior aligns with role permissions. | User verifies access and export behavior aligns with role permissions. | 2026-01-14 | Pass | Low
TC.092 | Verify_DB_Migration_TablesCreated | User verifies new tables/columns created and constraints applied. | User verifies new tables/columns created and constraints applied. | 2026-01-14 | Pass | Low
TC.093 | Verify_DB_Backfill_DataCorrect | User verifies legacy data populated correctly and no duplicates introduced. | User verifies legacy data populated correctly and no duplicates introduced. | 2026-01-14 | Pass | Low
TC.094 | Verify_API_NewPages_ResponseContract | User verifies JSON contains required fields and correct data types. | User verifies JSON contains required fields and correct data types. | 2026-01-14 | Pass | Minor
TC.095 | Verify_DB_FK_Constraints | User verifies FK prevents orphan inserts. | User verifies FK prevents orphan inserts. | 2026-01-14 | Pass | Minor
TC.096 | Verify_DB_Perf_NewEndpoints | User verifies acceptable latency and DB indices used. | User verifies acceptable latency and DB indices used. | 2026-01-14 | Pass | Minor
TC.097 | Verify_SQL_Correctness_PostFix | User verifies correctness and performance improved. | User verifies correctness and performance improved. | 2026-01-14 | Pass | Low
TC.098 | Verify_SQLInjection_Parameterized | User verifies system parameterizes queries and injection fails. | User verifies system parameterizes queries and injection fails. | 2026-01-14 | Pass | Low
TC.099 | Verify_XSS_DomSanitization | User verifies outputs are escaped and no DOM script executed. | User verifies outputs are escaped and no DOM script executed. | 2026-01-14 | Pass | Minor
TC.100 | Verify_FileUpload_Security | User verifies server-side MIME checks and scanning block malicious uploads. | User verifies server-side MIME checks and scanning block malicious uploads. | 2026-01-14 | Pass | Low
TC.101 | Verify_Sonar_Scan_Results | User verifies no critical issues remain and code smells reduced per target. | User verifies no critical issues remain and code smells reduced per target. | 2026-01-14 | Pass | Low
TC.102 | Verify_RBAC_PrivilegeEscalation | User verifies server denies request and logs event. | User verifies server denies request and logs event. | 2026-01-14 | Pass | Minor
TC.103 | Verify_GoldenBill_Regression | User verifies outputs match expected golden results. | User verifies outputs match expected golden results. | 2026-01-14 | Pass | Minor
TC.104 | Verify_UI_Regression_Layout_A11y | User verifies layout stable and keyboard navigation works. | User verifies layout stable and keyboard navigation works. | 2026-01-14 | Pass | Low
TC.105 | Verify_RoleBasedFlow_FreezeUnfreeze | User verifies each role behaves per spec with correct permissions. | User verifies each role behaves per spec with correct permissions. | 2026-01-14 | Pass | Minor
TC.106 | Verify_EndToEnd_ContractToApproval | User verifies end-to-end flow completes; state transitions, freeze behavior and audit trail recorded. | User verifies end-to-end flow completes; state transitions, freeze behavior and audit trail recorded. | 2026-01-14 | Pass | Low

## DHARA CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify redesigned Jal Rekha home and DHARA report pages load correctly | Pages load successfully with updated UI layout, fonts, colors, and alignment | Pages load successfully with updated UI layout, fonts, colors, and alignment | 2025-11-12 | Pass | Minor
TC.002 | Verify redesigned pages are responsive on different screen resolutions | UI adjusts correctly without overlap or broken components | UI adjusts correctly without overlap or broken components | 2025-11-12 | Pass | Major
TC.003 | Verify navigation from dashboard to DWSR report after redesign | User is navigated to DWSR report without error | User is navigated to DWSR report without error | 2025-11-12 | Pass | Major
TC.004 | Verify DWSR report displays updated columns and parameters | All updated parameters are visible with correct labels and units | All updated parameters are visible with correct labels and units | 2025-11-12 | Pass | Major
TC.005 | Verify MWSR report displays correct monthly aggregation | Monthly values are calculated and displayed correctly | Monthly values are calculated and displayed correctly | 2025-11-12 | Pass | Minor
TC.006 | Verify Scheme-wise report displays schemes with correct data mapping | Schemes show correct water supply and meter data | Schemes show correct water supply and meter data | 2025-11-13 | Pass | Major
TC.007 | Verify Village-wise report displays villages under correct scheme | Villages are mapped to the correct scheme and data | Villages are mapped to the correct scheme and data | 2025-11-13 | Pass | Minor
TC.008 | Verify Bulk User report shows correct bulk consumer readings | Bulk user data matches submitted readings | Bulk user data matches submitted readings | 2025-11-13 | Pass | Major
TC.009 | Verify UFW report calculation after CR | UFW percentage and volume are calculated as per defined formula | UFW percentage and volume are calculated as per defined formula | 2025-11-13 | Pass | Low
TC.010 | Verify report filters (Date, Scheme, Village) work correctly | Filtered results match selected criteria | Filtered results match selected criteria | 2025-11-13 | Pass | Minor
TC.011 | Verify drill-down from Scheme → Village → OHT/WTP | Drill-down loads next level data correctly | Drill-down loads next level data correctly | 2025-11-13 | Pass | Minor
TC.012 | Verify updated reports load within acceptable performance time | Reports load within defined SLA time | Reports load within defined SLA time | 2025-12-16 | Pass | Low
TC.013 | Verify export to Excel/PDF for all DHARA reports | Exported files download successfully with correct data | Exported files download successfully with correct data | 2025-12-16 | Pass | Major
TC.014 | Verify updated meter mapping reflects in all DHARA reports | Reports show updated meter-to-village mapping | Reports show updated meter-to-village mapping | 2025-12-16 | Pass | Low
TC.015 | Verify WTP-to-village meter reading flow after CR | WTP readings are correctly mapped and reflected at village level | WTP readings are correctly mapped and reflected at village level | 2025-12-16 | Pass | Minor
TC.016 | Verify updated meter mapping as per department configuration | Meter mappings are saved and displayed correctly | Meter mappings are saved and displayed correctly | 2025-12-16 | Pass | Low
TC.017 | Verify incorrect meter mapping cannot be saved | Validation message is displayed | Validation message is displayed | 2025-12-16 | Pass | Minor
TC.018 | Verify WTP meter reading entry flows to village level | Village readings reflect correct WTP data | Village readings reflect correct WTP data | 2025-12-17 | Pass | Minor
TC.019 | Verify changes in meter mapping update historical and current reports | Reports reflect updated mapping correctly | Reports reflect updated mapping correctly | 2025-12-17 | Pass | Major
TC.020 | Verify removal/update of meter mapping updates reports | Old mapping data is not shown | Old mapping data is not shown | 2025-12-17 | Pass | Major
TC.021 | Verify application crash handling via Crashlytics | Crashes are logged with proper error details | Crashes are logged with proper error details | 2025-12-17 | Pass | Major
TC.022 | Verify vulnerability scan findings are resolved | No critical/high vulnerabilities reported | No critical/high vulnerabilities reported | 2025-12-17 | Pass | Minor
TC.023 | Verify all UI modules load without console errors | No JavaScript or runtime errors observed | No JavaScript or runtime errors observed | 2025-12-17 | Pass | Major
TC.024 | Verify PostgreSQL queries return correct results | Queries execute successfully with correct data | Queries execute successfully with correct data | 2025-12-18 | Pass | Minor
TC.025 | Verify optimized report queries improve performance | Report load time is reduced | Report load time is reduced | 2025-12-18 | Pass | Major
TC.026 | Verify password encryption in database for all users | Passwords are stored in encrypted/hashed format | Passwords are stored in encrypted/hashed format | 2025-12-18 | Pass | Low
TC.027 | Verify login works with encrypted passwords | Users can log in successfully | Users can log in successfully | 2025-12-18 | Pass | Minor
TC.028 | Verify Function/SP changes do not break existing flows | All dependent features work correctly | All dependent features work correctly | 2025-12-18 | Pass | Minor
TC.029 | Verify report query validation handles incorrect input | System prevents SQL errors and invalid queries | System prevents SQL errors and invalid queries | 2025-12-18 | Pass | Low
TC.030 | Verify redesigned pages are successfully deployed on live server | Latest version is visible on production | Latest version is visible on production | 2025-12-18 | Pass | Major
TC.031 | Verify rollback is not required after deployment | System is stable post-deployment | System is stable post-deployment | 2025-12-18 | Pass | Low

## NIRMAL CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify updated WTP report parameters are displayed | All new/modified parameters appear correctly | All new/modified parameters appear correctly | 2025-11-24 | Pass | Minor
TC.002 | Verify removed parameters are no longer shown in WTP report | Deprecated parameters are not visible | Deprecated parameters are not visible | 2025-11-24 | Pass | Major
TC.003 | Verify parameter labels and units in WTP report | Labels and units are correct as per CR | Labels and units are correct as per CR | 2025-11-24 | Pass | Low
TC.004 | Verify OHT report loads with updated parameters | OHT report loads without error | OHT report loads without error | 2025-11-24 | Pass | Minor
TC.005 | Verify Beneficiary report parameter-level changes | Parameter values display correctly | Parameter values display correctly | 2025-11-24 | Pass | Minor
TC.006 | Verify Raw Water report parameters | Raw Water parameters match backend data | Raw Water parameters match backend data | 2025-11-25 | Pass | Low
TC.007 | Verify data consistency across WTP, OHT, Beneficiary reports | Same sample shows consistent values | Same sample shows consistent values | 2025-11-25 | Pass | Major
TC.008 | Verify report load time after parameter changes | Reports load within acceptable time | Reports load within acceptable time | 2025-11-25 | Pass | Low
TC.009 |  |  |  | 2025-11-25 | Pass | Minor
TC.010 | Verify first-level drill-down in WTP report | Drill-down opens correct detail view | Drill-down opens correct detail view | 2025-11-25 | Pass | Low
TC.011 | Verify second-level drill-down in WTP report | Second drill-down shows deeper details | Second drill-down shows deeper details | 2025-11-26 | Pass | Minor
TC.012 | Verify drill-down for OHT report | OHT drill-down shows mapped data | OHT drill-down shows mapped data | 2025-11-26 | Pass | Minor
TC.013 | Verify Raw Water drill-down report | Raw water sample details are visible | Raw water sample details are visible | 2025-11-26 | Pass | Minor
TC.014 | Verify Beneficiary water test drill-down | Beneficiary test details load correctly | Beneficiary test details load correctly | 2025-11-26 | Pass | Major
TC.015 | Verify drill-down for passed records | Passed samples show correct status | Passed samples show correct status | 2025-11-26 | Pass | Low
TC.016 | Verify drill-down for failed records | Failed samples show correct reason | Failed samples show correct reason | 2025-11-26 | Pass | Minor
TC.017 | Verify drill-down navigation back action | User returns to parent report | User returns to parent report | 2025-11-27 | Pass | Minor
TC.018 | Verify Action Remarks option visible for Contractor | Action Remarks button is visible | Action Remarks button is visible | 2025-11-27 | Pass | Low
TC.019 | Verify Action Remarks option visible for GM | GM can add remarks | GM can add remarks | 2025-11-27 | Pass | Major
TC.020 | Verify Action Remarks popup opens | Popup opens without UI issues | Popup opens without UI issues | 2025-11-27 | Pass | Low
TC.021 | Verify adding remarks by Contractor | Remarks are saved successfully | Remarks are saved successfully | 2025-11-27 | Pass | Minor
TC.022 | Verify adding remarks by GM | Remarks are saved and visible | Remarks are saved and visible | 2025-11-27 | Pass | Low
TC.023 | Verify remarks appear in drill-down report | Remarks are displayed correctly | Remarks are displayed correctly | 2025-11-27 | Pass | Minor
TC.024 | Verify chat-style UI for remarks | Chat UI aligns properly | Chat UI aligns properly | 2025-11-27 | Pass | Minor
TC.025 | Verify bell icon on remarks popup | Bell icon is visible and clickable | Bell icon is visible and clickable | 2025-11-27 | Pass | Minor
TC.026 | Verify component filter expansion | Additional components appear | Additional components appear | 2025-12-12 | Pass | Major
TC.027 | Verify filter-based report refresh | Report updates based on filter | Report updates based on filter | 2025-12-12 | Pass | Low
TC.028 | Verify scheme filter | Data loads for selected scheme | Data loads for selected scheme | 2025-12-12 | Pass | Minor
TC.029 | Verify PIU filter | Data loads for selected PIU | Data loads for selected PIU | 2025-12-12 | Pass | Minor
TC.030 | Verify OHT village mapping in reports | Correct OHT–village mapping shown | Correct OHT–village mapping shown | 2025-12-12 | Pass | Low
TC.031 | Verify search by Water Sample ID | Correct record is returned | Correct record is returned | 2025-12-12 | Pass | Major
TC.032 | Verify invalid Water Sample ID search | No Records Found message shown | No Records Found message shown | 2025-12-12 | Pass | Low
TC.033 | Verify comments box visibility | Comments box available on report | Comments box available on report | 2025-12-12 | Pass | Minor
TC.034 | Verify comments persistence after refresh | Comments remain saved | Comments remain saved | 2025-12-12 | Pass | Low
TC.035 | Verify popup table opens on action button | Popup table loads correctly | Popup table loads correctly | 2025-12-12 | Pass | Minor
TC.036 | Verify popup table data accuracy | Data matches report | Data matches report | 2025-12-12 | Pass | Minor
TC.037 | Verify popup table pagination | Pagination works correctly | Pagination works correctly | 2025-12-12 | Pass | Minor
TC.038 | Verify “Still Pending Test Cases” drill-down | Pending tests list is accurate | Pending tests list is accurate | 2025-12-12 | Pass | Major
TC.039 | Verify pending status updates after action | Status updates correctly | Status updates correctly | 2025-12-12 | Pass | Low
TC.040 | Verify removal of inline queries does not break UI | All pages load correctly | All pages load correctly | 2025-12-12 | Pass | Minor
TC.041 | Verify new Component Master query (Scheme + PIU) | Correct components returned | Correct components returned | 2025-12-12 | Pass | Minor
TC.042 | Verify WTP_Samples_Tested_Detail query | Detailed WTP test data shown | Detailed WTP test data shown | 2025-12-13 | Pass | Low
TC.043 | Verify Beneficiary_Testing_Report_Tested_List query | Beneficiary data fetched correctly | Beneficiary data fetched correctly | 2025-12-13 | Pass | Major
TC.044 | Verify same query for OHT samples | OHT data fetched correctly | OHT data fetched correctly | 2025-12-13 | Pass | Low
TC.045 | Verify API response in Postman | API returns expected response | API returns expected response | 2025-12-13 | Pass | Minor
TC.046 | Verify data consistency between Postman & UI | UI matches API data | UI matches API data | 2025-12-13 | Pass | Low
TC.047 | Verify date range filter in Raw Water report | Records filter correctly | Records filter correctly | 2025-12-13 | Pass | Minor
TC.048 | Verify start date > end date validation | Validation message shown | Validation message shown | 2025-12-13 | Pass | Minor
TC.049 | Verify RawWater_Samples_Tested_Detail mapping | Raw water test data displayed | Raw water test data displayed | 2025-12-13 | Pass | Minor
TC.050 | Verify additional columns in Raw Water report | New columns visible | New columns visible | 2025-12-13 | Pass | Major
TC.051 | Verify drill-down for new Raw Water columns | Drill-down works correctly | Drill-down works correctly | 2025-12-13 | Pass | Low
TC.052 | Verify WTP sample collection within 200m | Sample submission allowed | Sample submission allowed | 2025-12-13 | Pass | Minor
TC.053 | Verify Intake sample collection within 200m | Sample submission allowed | Sample submission allowed | 2025-12-13 | Pass | Minor
TC.054 | Verify sample collection beyond 200m | Error/validation shown | Error/validation shown | 2025-12-13 | Pass | Low
TC.055 | Verify GPS accuracy handling | Correct distance calculated | Correct distance calculated | 2025-12-13 | Pass | Major
TC.056 | Verify buffer logic for FE login | Buffer rule enforced | Buffer rule enforced | 2025-12-13 | Pass | Low

## Sahbhagita CR
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify Sahbhagita report loads with modified layout | Updated UI is displayed correctly | Updated UI is displayed correctly | 2025-11-28 | Pass | Major
TC.002 | Verify existing report data remains intact after modification | No data loss observed | No data loss observed | 2025-11-28 | Pass | Low
TC.003 | Verify column headers reflect updated report changes | Correct column names shown | Correct column names shown | 2025-11-28 | Pass | Minor
TC.004 | Verify report loads for different date ranges | Data loads correctly | Data loads correctly | 2025-11-28 | Pass | Minor
TC.005 | Verify report pagination after modification | Pagination works correctly | Pagination works correctly | 2025-11-28 | Pass | Low
TC.006 | Verify sorting functionality on modified report | Sorting works as expected | Sorting works as expected | 2025-11-28 | Pass | Major
TC.007 | Verify navigation to new Survey Approval page | Page opens successfully | Page opens successfully | 2025-12-01 | Pass | Low
TC.008 | Verify list of survey records displayed for approval | Correct records displayed | Correct records displayed | 2025-12-01 | Pass | Major
TC.009 | Verify Approved count on approval page | Approved count is accurate | Approved count is accurate | 2025-12-01 | Pass | Low
TC.010 | Verify Rejected count on approval page | Rejected count is accurate | Rejected count is accurate | 2025-12-01 | Pass | Minor
TC.011 | Verify No Action count on approval page | No Action count is accurate | No Action count is accurate | 2025-12-01 | Pass | Minor
TC.012 | Verify counts update after approval action | Counts refresh correctly | Counts refresh correctly | 2025-12-01 | Pass | Low
TC.013 | Verify counts update after rejection action | Counts refresh correctly | Counts refresh correctly | 2025-12-01 | Pass | Major
TC.014 | Verify allowed video file formats | Only supported formats allowed | Only supported formats allowed | 2025-12-01 | Pass | Low
TC.015 | Verify video size limit validation | Error shown for oversized files | Error shown for oversized files | 2025-12-09 | Pass | Minor
TC.016 | Verify successful video upload | Video uploads successfully | Video uploads successfully | 2025-12-09 | Pass | Minor
TC.017 | Verify video preview after upload | Video plays correctly | Video plays correctly | 2025-12-09 | Pass | Low
TC.018 | Verify video remains attached after save | Video is retained | Video is retained | 2025-12-09 | Pass | Major
TC.019 | Verify invalid format upload attempt | Upload is blocked | Upload is blocked | 2025-12-09 | Pass | Major
TC.020 | Verify video upload on slow network | Upload resumes or shows proper error | Upload resumes or shows proper error | 2025-12-09 | Pass | Low
TC.021 | Verify Frm_Ngo_Summary_Reports page load | Page loads without error | Page loads without error | 2025-12-09 | Pass | Minor
TC.022 | Verify Approved count in summary report | Approved count is correct | Approved count is correct | 2025-12-09 | Pass | Minor
TC.023 | Verify Rejected count in summary report | Rejected count is correct | Rejected count is correct | 2025-12-09 | Pass | Low
TC.024 | Verify No Action count in summary report | No Action count is correct | No Action count is correct | 2025-12-09 | Pass | Major
TC.025 | Verify summary counts match detailed report | Counts are consistent | Counts are consistent | 2025-12-09 | Pass | Low
TC.026 | Verify drill-down from summary report | Drill-down works correctly | Drill-down works correctly | 2025-12-09 | Pass | Major
TC.027 | Verify village dropdown loads based on dist_cd | Correct villages shown | Correct villages shown | 2025-12-10 | Pass | Low
TC.028 | Verify village dropdown refresh on district change | Dropdown refreshes correctly | Dropdown refreshes correctly | 2025-12-10 | Pass | Minor
TC.029 | Verify village dropdown works with video uploads | No dependency issues | No dependency issues | 2025-12-10 | Pass | Minor
TC.030 | Verify empty village list handling | User-friendly message shown | User-friendly message shown | 2025-12-10 | Pass | Low
TC.031 | Verify service failure handling | Proper error message displayed | Proper error message displayed | 2025-12-10 | Pass | Major
TC.032 | Verify Get_VillageForApproval service call | Correct villages returned | Correct villages returned | 2025-12-10 | Pass | Low
TC.033 | Verify village-wise triggers update on selection | Trigger counts refresh | Trigger counts refresh | 2025-12-10 | Pass | Major
TC.034 | Verify trigger accuracy for selected village | Data matches backend | Data matches backend | 2025-12-10 | Pass | Low
TC.035 | Verify trigger reset on village change | Old data cleared | Old data cleared | 2025-12-10 | Pass | Minor
TC.036 | Verify extra Village dropdown visibility | Dropdown displayed | Dropdown displayed | 2025-12-10 | Pass | Minor
TC.037 | Verify village selection filters records | Records filtered correctly | Records filtered correctly | 2025-12-10 | Pass | Low
TC.038 | Verify approval actions after village filter | Actions work correctly | Actions work correctly | 2025-12-10 | Pass | Major
TC.039 | Verify rejection actions after village filter | Actions work correctly | Actions work correctly | 2025-12-10 | Pass | Low
TC.040 | Verify PIU dropdown loads | PIU list displayed | PIU list displayed | 2025-12-10 | Pass | Low
TC.041 | Verify Scheme dropdown depends on PIU | Schemes filtered correctly | Schemes filtered correctly | 2025-12-10 | Pass | Minor
TC.042 | Verify ISA dropdown depends on Scheme & District | ISA filtered correctly | ISA filtered correctly | 2025-12-11 | Pass | Minor
TC.043 | Verify Village dropdown depends on ISA | Correct villages shown | Correct villages shown | 2025-12-11 | Pass | Low
TC.044 | Verify full filter reset on PIU change | All dependent dropdowns reset | All dependent dropdowns reset | 2025-12-11 | Pass | Major
TC.045 | Verify invalid combination handling | No invalid data shown | No invalid data shown | 2025-12-11 | Pass | Low
TC.046 | Verify updated ISA Bill Form UI | Updated fields visible | Updated fields visible | 2025-12-11 | Pass | Minor
TC.047 | Verify mandatory field validation | Validation messages shown | Validation messages shown | 2025-12-11 | Pass | Minor
TC.048 | Verify ISA Bill Form save | Data saved successfully | Data saved successfully | 2025-12-11 | Pass | Low
TC.049 | Verify edit functionality for ISA Bill | Data updates correctly | Data updates correctly | 2025-12-11 | Pass | Major
TC.050 | Verify ISA Bill data reflected in reports | Report shows updated data | Report shows updated data | 2025-12-11 | Pass | Low
TC.051 | Verify role-based access for GM/PM | Unauthorized access blocked | Unauthorized access blocked | 2025-12-11 | Pass | Minor
TC.052 | Verify concurrent approvals handling | No duplicate actions | No duplicate actions | 2025-12-11 | Pass | Minor
TC.053 | Verify report performance with large data | Page loads within SLA | Page loads within SLA | 2025-12-11 | Pass | Low
TC.054 | Verify session timeout handling | User redirected correctly | User redirected correctly | 2025-12-11 | Pass | Major
TC.055 | Verify no regression in existing Sahbhagita flows | Existing features work | Existing features work | 2025-12-11 | Pass | Low

## Material
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify contractor can send Material Testing request (RFI) to GM for approval | RFI is successfully submitted and visible to GM in Pending at PIU | RFI is successfully submitted and visible to GM in Pending at PIU | 2025-12-26 | Pass | Major |  | NA
TC.002 | Verify GM can view contractor-submitted RFI in Pending at PIU report | Submitted RFI should be listed with correct details | Submitted RFI is listed with incorrect details | 2025-12-26 | Fail | Minor | 2025-12-29 | NA
TC.003 | Verify GM can approve contractor RFI | RFI status changes to Approved and contractor should be able to see the status of RFI | RFI status changes to Approved but contractor should not be able to see. | 2025-12-26 | Fail | Major | 2025-12-26 | NA
TC.004 | Verify GM can reject contractor RFI | RFI status changes to Rejected and is sent back to contractor | RFI status changes to Rejected and is sent back to contractor | 2025-12-26 | Pass | Low |  | NA
TC.005 | Verify rejected RFI is visible to contractor for re-submission | Contractor can view rejected RFI with rejection status | Contractor can view rejected RFI with rejection status | 2025-12-26 | Pass | Minor |  | NA
TC.006 | Verify GM can assign approved RFI to SQC | RFI is successfully assigned to SQC | RFI is successfully assigned to SQC | 2025-12-26 | Pass | Low |  | NA
TC.007 | Verify SQC can view RFI assigned by GM | Assigned RFI is visible in SQC Pending RFI list | Assigned RFI is visible in SQC Pending RFI list | 2025-12-26 | Pass | Low |  | NA
TC.008 | Verify SQC can assign RFI to FE for material testing | RFI is successfully assigned to selected FE | RFI is successfully assigned to selected FE | 2025-12-26 | Pass | Minor |  | NA
TC.009 | Verify assigned RFI is received by FE | RFI appears in FE assigned inspection list | FE can received RFI but the SQC detailed were incompleted | 2025-12-29 | Fail | Major | 2025-12-30 | NA
TC.010 | Verify FE can submit inspection report to GM | Inspection report is submitted successfully and visible to GM | Inspection report is submitted successfully and visible to GM | 2025-12-29 | Pass | Minor |  | NA
TC.011 | Verify GM can approve FE inspection report | Inspection status changes to Approved and case is closed | Inspection status changes to Approved and case is closed | 2025-12-29 | Pass | Major |  | NA
TC.012 | Verify GM can reject FE inspection report | Inspection status changes to Rejected and workflow loops back | Inspection status changes to Rejected and workflow loops back | 2025-12-29 | Pass | Low |  | NA
TC.013 | Verify Material Testing Web UI loads correctly for GM | UI loads without layout or functional issues | UI loads without layout or functional issues | 2025-12-29 | Pass | Minor |  | NA
TC.014 | Verify Web UI integrates correctly with backend APIs | Data is fetched and submitted correctly | Data is fetched and submitted correctly | 2025-12-29 | Pass | Major |  | NA
TC.015 | Verify database schema supports Material Testing workflow | All required tables and relationships exist | All required tables and relationships exist | 2025-12-29 | Pass | Major |  | NA
TC.016 | Verify master tables are created for Material Testing | Master data loads correctly in UI | Master data loads correctly in UI | 2025-12-30 | Pass | Major |  | NA
TC.017 | Verify Material Testing Pending at PIU report loads | Report displays correct RFIs | Report displays correct RFIs | 2025-12-30 | Pass | Minor |  | NA
TC.018 | Verify Pending at PIU report data accuracy | Report data matches database records | Report data matches database records | 2025-12-30 | Pass | Major |  | NA
TC.019 | Verify Insert API for Material Testing using Postman | API returns success response | API returns success response | 2025-12-30 | Pass | Minor |  | NA
TC.020 | Verify data inserted via API is saved correctly in database | Database records match API payload | Records are getting saved to database even when the mandatory fields were missing | 2025-12-30 | Fail | Major | 2025-12-31 | NA
TC.021 | Verify ESR details fetch function works correctly | ESR details load correctly | ESR details load correctly | 2025-12-30 | Pass | Low |  | NA
TC.022 | Verify Scheme list fetch function works correctly | Scheme list is populated | Scheme list is populated | 2025-12-30 | Pass | Minor |  | NA
TC.023 | Verify User list fetch function works correctly | User list loads correctly | User list loads correctly | 2025-12-30 | Pass | Minor |  | NA
TC.024 | Verify Scheme-wise ESR list fetch works correctly | ESR list matches selected scheme | ESR list matches selected scheme | 2025-12-30 | Pass | Low |  | NA
TC.025 | Verify contractor workflow still works after changes | Contractor can create and submit RFI | Contractor can create and submit RFI | 2025-12-30 | Pass | Major |  | NA
TC.026 | Verify contractor cannot bypass GM approval | Workflow enforces GM approval | Workflow enforces GM approval | 2025-12-30 | Pass | Low |  | NA
TC.027 | Verify contractor cannot edit RFI after submission | RFI becomes read-only | RFI becomes read-only | 2025-12-30 | Pass | Minor |  | NA
TC.028 | Verify FE can login to mobile application | FE login is successful | FE login is successful | 2025-12-30 | Pass | Low |  | NA
TC.029 | Verify FE can perform inspection only within geofenced site location | Inspection allowed only within configured Lat/Long | Inspection allowed only within configured Lat/Long | 2025-12-31 | Pass | Minor |  | NA
TC.030 | Verify inspection submission blocked outside geofence | System blocks submission with message | System should not blocks submission with outside location as API validation was missing | 2025-12-31 | Fail | Major | 2025-12-31 | NA
TC.031 | Verify FE mobile UI loads correctly | UI loads without distortion | UI loads without distortion | 2025-12-31 | Pass | Minor |  | NA
TC.032 | Verify FE mobile UI integrates correctly with APIs | Data syncs correctly | Data syncs correctly | 2025-12-31 | Pass | Major |  | NA
TC.033 | Verify FE database schema supports inspection data | Inspection data stored correctly | Inspection data stored correctly | 2025-12-31 | Pass | Low |  | NA
TC.034 | Verify FE master tables load correctly | Dropdowns load expected values | Dropdowns load expected values | 2025-12-31 | Pass | Minor |  | NA
TC.035 | Verify Sync API fetches multiple dropdown data | All dropdowns populate correctly | All dropdowns populate correctly | 2025-12-31 | Pass | Low |  | NA
TC.036 | Verify offline sync works for FE inspection | Data syncs once network is available | Data syncs once network is available | 2025-12-31 | Pass | Minor |  | NA
TC.037 | Verify FE cannot perform contractor actions | Access is restricted | Access is restricted | 2025-12-31 | Pass | Major |  | NA
TC.038 | Verify FE cannot perform GM approval/rejection | Access is denied | Access is denied | 2025-12-31 | Pass | Minor |  | NA
TC.039 | Verify security audit issues are resolved | Application passes security checks | Application passes security checks | 2025-12-31 | Pass | Minor |  | NA

## Material TestCases
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify Contractor can create Material Testing RFI | Request Inspection screen opens | Request Inspection screen opens | 2025-12-26 | Pass | Major
|  | RFI created successfully | RFI created successfully | 2025-12-26 | Pass | Minor
TC.002 | Verify PIU and Scheme are auto-populated | PIU and Scheme auto-populated and read-only | PIU and Scheme auto-populated and read-only | 2025-12-26 | Pass | Major
TC.003 | Verify Component dropdown loads correctly | All components displayed | All components displayed | 2025-12-26 | Pass | Low
TC.004 | Verify Material Type dropdown displays all configured values | All configured material types displayed | All configured material types displayed | 2025-12-26 | Pass | Minor
TC.005 | Verify RFI submission with all valid inputs | No validation error | No validation error | 2025-12-26 | Pass | Low
|  | RFI submitted successfully | RFI submitted successfully | 2025-12-26 | Pass | Low
TC.006 | Verify photo capture from camera only | Camera opens | Camera opens | 2025-12-26 | Pass | Minor
|  | Gallery option not allowed | Gallery option not allowed | 2025-12-29 | Pass | Major
TC.007 | Verify RFI is submitted successfully to GM | Submitted RFI visible | Submitted RFI visible | 2025-12-29 | Pass | Minor
TC.008 | Verify Sub-component hidden for Distribution Pipeline | Field not displayed | Field not displayed | 2025-12-29 | Pass | Major
TC.009 | Verify Stage, Stretch No, Application Type hidden for Distribution | Fields hidden | Fields hidden | 2025-12-29 | Pass | Low
TC.010 | Verify OHT selection enables Pipeline dropdown | Pipeline dropdown enabled | Pipeline dropdown enabled | 2025-12-29 | Pass | Minor
TC.011 | Verify only pipelines mapped to selected OHT are displayed | Only mapped pipelines displayed | Only mapped pipelines displayed | 2025-12-29 | Pass | Major
TC.012 | Verify same-day inspection date is blocked | Error displayed | Error displayed | 2025-12-29 | Pass | Major
TC.013 | Verify past date is blocked | Error displayed | Error displayed | 2025-12-30 | Pass | Major
TC.014 | Verify next-day inspection date is accepted | Date accepted | Date accepted | 2025-12-30 | Pass | Minor
TC.015 | Verify future inspection date is accepted | Date accepted | Date accepted | 2025-12-30 | Pass | Major
TC.016 | Verify GM can assign RFI to SQC | RFI assigned | RFI assigned | 2025-12-30 | Pass | Minor
TC.017 | Verify GM can assign RFI to TPIA | RFI assigned | RFI assigned | 2025-12-30 | Pass | Major
TC.018 | Verify GM can assign RFI to both SQC & TPIA | RFI assigned to both | RFI assigned to both | 2025-12-30 | Pass | Low
TC.019 | Verify assigned users receive notification | Notification received | Notification received | 2025-12-30 | Pass | Minor
TC.020 | Verify FE can view assigned RFI | Assigned RFI visible | Assigned RFI visible | 2025-12-30 | Pass | Minor
TC.021 | Verify FE can submit Accept recommendation | Recommendation submitted | Recommendation submitted | 2025-12-30 | Pass | Low
TC.022 | Verify FE can submit Reject recommendation | Recommendation submitted | Recommendation submitted | 2025-12-30 | Pass | Major
TC.023 | Verify FE recommendation reaches GM | Recommendation visible | Recommendation visible | 2025-12-30 | Pass | Low
TC.024 | Verify GM can accept RFI | RFI closed as Accepted | RFI closed as Accepted | 2025-12-30 | Pass | Minor
TC.025 | Verify RFI status changes to Closed on acceptance | Status Closed | Status Closed | 2025-12-30 | Pass | Low
TC.026 | Verify GM can reject RFI | RFI closed as Rejected | RFI closed as Rejected | 2025-12-31 | Pass | Minor
TC.027 | Verify rejected RFI is returned to Contractor | Rejected RFI visible | Rejected RFI visible | 2025-12-31 | Pass | Major
TC.028 | Verify submit RFI without Material Type | Error shown | Error shown | 2025-12-31 | Pass | Minor
TC.029 | Verify submit RFI without photo | Submission blocked | Submission blocked | 2025-12-31 | Pass | Major
TC.030 | Verify select same-day inspection date | Error shown | Error shown | 2025-12-31 | Pass | Low
TC.031 | Verify select past inspection date | Error shown | Error shown | 2025-12-31 | Pass | Minor
TC.032 | Verify select Sub-component for Distribution | Not available | Not available | 2025-12-31 | Pass | Low
TC.033 | Verify select OHT without pipeline | Error shown | Error shown | 2025-12-31 | Pass | Minor
TC.034 | Verify FE tries to close RFI | Action not allowed | Action not allowed | 2025-12-31 | Pass | Low
TC.035 | Verify GM tries to skip assignment | System blocks | System blocks | 2025-12-31 | Pass | Minor
TC.036 | Verify Contractor tries GM action | Access denied | Access denied | 2025-12-31 | Pass | Low
TC.037 | Verify FE tries GM final decision | Access denied | Access denied | 2025-12-31 | Pass | Minor
TC.038 | Verify unauthorized user accesses RFI | Access denied | Access denied | 2025-12-31 | Pass | Minor
Severity :
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues
Priority:
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues

## MaterialContr tc
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TS.001 | Verify contractor can login successfully to Jal Rekha mobile application | Login screen is displayed with mobile number and credential input fields | Login screen is displayed with mobile number and credential input fields | 2025-12-26 | Pass | Major
|  | System validates credentials successfully and allows the contractor to log in | System validates credentials successfully and allows the contractor to log in | 2025-12-26 | Pass | Minor
|  | Contractor is logged into the application without any error message | Contractor is logged into the application without any error message | 2025-12-26 | Pass | Major
TS.002 | Verify contractor is redirected to home dashboard after login | Home dashboard is displayed with all authorized modules | Home dashboard is displayed with all authorized modules | 2025-12-26 | Pass | Low
TS.003 | Verify Material Testing module icon is visible on dashboard | Material Testing module icon is clearly visible on the dashboard | Material Testing module icon is clearly visible on the dashboard | 2025-12-26 | Pass | Minor
TS.004 | Verify Sync Data, Work Monitoring, Complaint List, Add Contractor modules are visible | Sync Data, Work Monitoring, Complaint List, and Add Contractor modules are visible | Sync Data, Work Monitoring, Complaint List, and Add Contractor modules are visible | 2025-12-26 | Pass | Low
TS.005 | Verify contractor can click on Material Testing module | System responds and navigates to the Material Testing section | System responds and navigates to the Material Testing section | 2025-12-26 | Pass | Low
TS.006 | Verify system redirects to Work Monitoring screen | Work Monitoring screen is displayed without any delay | Work Monitoring screen is displayed without any delay | 2025-12-26 | Pass | Minor
TS.007 | Verify Inspection Request, Inspection History, Re-Inspection Request options are visible | Inspection Request, Inspection History, and Re-Inspection Request options are visible | Inspection Request, Inspection History, and Re-Inspection Request options are visible | 2025-12-26 | Pass | Major
TS.008 | Verify contractor can click on Inspection Request | System initiates navigation to Request Inspection screen | System initiates navigation to Request Inspection screen | 2025-12-26 | Pass | Minor
TS.009 | Verify system redirects to Request Inspection screen | Request Inspection screen is displayed with all required fields | Request Inspection screen is displayed with all required fields | 2025-12-26 | Pass | Major
TS.010 | Verify back navigation works correctly from Request Inspection screen | System navigates back to Work Monitoring screen | System navigates back to Work Monitoring screen | 2025-12-26 | Pass | Low
TS.011 | Verify PIU field is auto-populated | PIU field is automatically populated based on contractor mapping | PIU field is automatically populated based on contractor mapping | 2025-12-29 | Pass | Minor
TS.012 | Verify Scheme Name field is auto-populated | Scheme Name is auto-populated correctly | Scheme Name is auto-populated correctly | 2025-12-29 | Pass | Major
TS.013 | Verify PIU field is non-editable | PIU field remains non-editable and read-only | PIU field remains non-editable and read-only | 2025-12-29 | Pass | Major
TS.014 | Verify Scheme Name field is non-editable | Scheme Name field is read-only and cannot be modified | Scheme Name field is read-only and cannot be modified | 2025-12-29 | Pass | Major
TS.015 | Verify Component Type dropdown loads correctly | System displays all configured Component Type values | System displays all configured Component Type values | 2025-12-29 | Pass | Minor
TS.016 | Verify Sub-Component dropdown loads based on selected Component Type | Sub-Component dropdown values update based on selected Component Type | Sub-Component dropdown values update based on selected Component Type | 2025-12-29 | Pass | Major
TS.017 | Verify Structural Component dropdown loads correctly | All applicable Structural Components are displayed | All applicable Structural Components are displayed | 2025-12-29 | Pass | Minor
TS.018 | Verify Material Type dropdown displays all configured values | Steel Test, Coarse Aggregate Test, Cement Test, Sand Test, and Brick Test are displayed | Steel Test, Coarse Aggregate Test, Cement Test, Sand Test, and Brick Test are displayed | 2025-12-29 | Pass | Major
TS.019 | Verify only one Material Type can be selected at a time | System allows selection of only one Material Type at a time | System allows selection of only one Material Type at a time | 2025-12-29 | Pass | Low
TS.020 | Verify Block dropdown loads correctly | Block list is loaded correctly as per scheme configuration | Block list is loaded correctly as per scheme configuration | 2025-12-30 | Pass | Minor
TS.021 | Verify Gram Panchayat dropdown loads based on Block selection | Gram Panchayat list loads corresponding to selected Block | Gram Panchayat list loads corresponding to selected Block | 2025-12-30 | Pass | Minor
TS.022 | Verify Village dropdown loads based on Gram Panchayat selection | Village list loads corresponding to selected Gram Panchayat | Village list loads corresponding to selected Gram Panchayat | 2025-12-30 | Pass | Low
TS.023 | Verify Block, GP, Village selection is mandatory | System displays validation message indicating mandatory selection | System displays validation message indicating mandatory selection | 2025-12-30 | Pass | Major
TS.024 | Verify Location field auto-captures current address using GPS | Current address is auto-captured and populated using GPS | Current address is auto-captured and populated using GPS | 2025-12-30 | Pass | Low
TS.025 | Verify Location field is mandatory | System shows validation error for mandatory Location field | System shows validation error for mandatory Location field | 2025-12-30 | Pass | Minor
TS.026 | Verify Description of inspection activity field accepts text input | Entered text is accepted and displayed correctly | Entered text is accepted and displayed correctly | 2025-12-30 | Pass | Low
TS.027 | Verify Description field supports voice input (Tap to speak) | Spoken words are converted into text and populated in Description field | Spoken words are converted into text and populated in Description field | 2025-12-30 | Pass | Minor
TS.028 | Verify Description field is mandatory | System displays validation error for mandatory Description field | System displays validation error for mandatory Description field | 2025-12-30 | Pass | Major
TS.029 | Verify map is displayed on Request Inspection screen | Map is displayed correctly without loading issues | Map is displayed correctly without loading issues | 2025-12-30 | Pass | Minor
TS.030 | Verify map pin shows current location | Map pin accurately represents the current GPS location | Map pin accurately represents the current GPS location | 2025-12-30 | Pass | Major
TS.031 | Verify map zoom in/out functionality works | Map zooms in and out smoothly as expected | Map zooms in and out smoothly as expected | 2025-12-30 | Pass | Low
TS.032 | Verify Inspection Date field is mandatory | System displays validation error for mandatory Inspection Date | System displays validation error for mandatory Inspection Date | 2025-12-30 | Pass | Minor
TS.033 | Verify calendar opens on clicking Inspection Date | Calendar control opens allowing date selection | Calendar control opens allowing date selection | 2025-12-30 | Pass | Low
TS.034 | Verify same-day inspection date selection is blocked | System blocks selection and displays validation message | System blocks selection and displays validation message | 2025-12-30 | Pass | Minor
TS.035 | Verify past date selection is blocked | System prevents selection of past dates | System prevents selection of past dates | 2025-12-30 | Pass | Low
TS.036 | Verify next-day inspection date is allowed | Selected date is accepted successfully | Selected date is accepted successfully | 2025-12-30 | Pass | Minor
TS.037 | Verify future inspection date is allowed | Future date is accepted without validation error | Future date is accepted without validation error | 2025-12-30 | Pass | Low
TS.038 | Verify Enclosure Photo field is mandatory | System displays validation error for mandatory photo upload | System displays validation error for mandatory photo upload | 2025-12-30 | Pass | Minor
TS.039 | Verify camera opens on clicking Capture Photo | Device camera opens successfully | Device camera opens successfully | 2025-12-31 | Pass | Minor
TS.040 | Verify photo can be captured successfully | Photo is captured and attached successfully | Photo is captured and attached successfully | 2025-12-31 | Pass | Major
TS.041 | Verify gallery upload is not allowed (camera only) | Gallery upload option is not available | Gallery upload option is not available | 2025-12-31 | Pass | Minor
TS.042 | Verify captured photo preview is displayed | Captured photo preview is displayed on the screen | Captured photo preview is displayed on the screen | 2025-12-31 | Pass | Major
TS.043 | Verify Submit button is disabled until mandatory fields are filled | Submit button remains disabled until all mandatory fields are completed | Submit button remains disabled until all mandatory fields are completed | 2025-12-31 | Pass | Low
TS.044 | Verify RFI submission with all valid inputs | RFI is submitted successfully without any validation errors | RFI is submitted successfully without any validation errors | 2025-12-31 | Pass | Minor
TS.045 | Verify success message is displayed after submission | Success message confirming RFI submission is displayed | Success message confirming RFI submission is displayed | 2025-12-31 | Pass | Low
TS.046 | Verify submitted RFI is not editable after submission | System does not allow editing of submitted RFI | System does not allow editing of submitted RFI | 2025-12-31 | Pass | Low
TS.047 | Verify error when submitting RFI without Component Type | Validation error message is displayed | Validation error message is displayed | 2025-12-31 | Pass | Minor
TS.048 | Verify error when submitting RFI without Material Type | Validation error message is displayed | Validation error message is displayed | 2025-12-31 | Pass | Major
TS.049 | Verify error when submitting RFI without Block/GP/Village | Validation error message is displayed | Validation error message is displayed | 2025-12-31 | Pass | Minor
TS.050 | Verify error when submitting RFI without Inspection Date | Validation error message is displayed | Validation error message is displayed | 2025-12-31 | Pass | Major
TS.051 | Verify error when submitting RFI without Enclosure Photo | Validation error message is displayed | Validation error message is displayed | 2025-12-31 | Pass | Low
TS.052 | Verify error when Location is not captured | System displays error indicating location is required | System displays error indicating location is required | 2025-12-31 | Pass | Minor
TS.053 | Verify submit action fails when GPS permission is denied | Submission fails and appropriate error message is displayed | Submission fails and appropriate error message is displayed | 2025-12-31 | Pass | Major
TS.054 | Verify contractor cannot access GM/SQC/TPIA actions | Access is denied for contractor role | Access is denied for contractor role | 2025-12-31 | Pass | Major
TS.055 | Verify contractor cannot view internal inspection remarks | Internal inspection remarks are not visible to contractor | Internal inspection remarks are not visible to contractor | 2025-12-31 | Pass | Major
TS.056 | Verify session logout redirects to login screen | User is logged out and redirected to login screen | User is logged out and redirected to login screen | 2025-12-31 | Pass | Minor
TS.057 | Verify data is retained on screen if app is minimized (until submit) | Previously entered data is retained on the screen | Previously entered data is retained on the screen | 2025-12-31 | Pass | Major
Severity :
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues
Priority:
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues

## MaterilGM TC
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TS.001 | Verify GM can login successfully to Jal Rekha web application | GM is authenticated successfully without any error | GM is authenticated successfully without any error | 2025-12-26 | Pass | Major
|  | GM is redirected to dashboard screen | GM is redirected to dashboard screen | 2025-12-26 | Pass | Minor
TS.002 | Verify GM is redirected to dashboard after login | Dashboard is displayed with all permitted menu options | Dashboard is displayed with all permitted menu options | 2025-12-26 | Pass | Major
TS.003 | Verify Material Testing module is visible in left menu | Material Testing module is visible | Material Testing module is visible | 2025-12-26 | Pass | Low
TS.004 | Verify GM can navigate to Material Testing module | Material Testing sub-modules are displayed | Material Testing sub-modules are displayed | 2025-12-26 | Pass | Minor
TS.005 | Verify Pending with PIU sub-module is visible | Pending with PIU sub-module is visible | Pending with PIU sub-module is visible | 2025-12-26 | Pass | Low
TS.006 | Verify Pending with PIU screen loads correctly | Pending with PIU list screen loads successfully | Pending with PIU list screen loads successfully | 2025-12-26 | Pass | Low
TS.007 | Verify Pending with PIU list shows only unassigned RFIs | Only newly submitted and unassigned RFIs are shown | Only newly submitted and unassigned RFIs are shown | 2025-12-26 | Pass | Minor
TS.008 | Verify RFI list displays correct columns | All configured columns are displayed correctly | All configured columns are displayed correctly | 2025-12-26 | Pass | Major
TS.009 | Verify pagination controls work correctly | RFI list updates correctly | RFI list updates correctly | 2025-12-26 | Pass | Minor
TS.010 | Verify GM can view RFI details | Detailed RFI information is displayed | Detailed RFI information is displayed | 2025-12-26 | Pass | Major
TS.011 | Verify GM can view RFI images | Uploaded images are displayed correctly | Uploaded images are displayed correctly | 2025-12-26 | Pass | Low
TS.012 | Verify GM can select single RFI using checkbox | RFI is selected successfully | RFI is selected successfully | 2025-12-29 | Pass | Minor
TS.013 | Verify GM can select multiple RFIs | Multiple RFIs are selected | Multiple RFIs are selected | 2025-12-29 | Pass | Major
TS.014 | Verify Assign options (SQC/TPIA/BOTH) are visible | SQC, TPIA and BOTH options are visible | SQC, TPIA and BOTH options are visible | 2025-12-29 | Pass | Major
TS.015 | Verify GM can assign RFI to SQC | RFI is assigned to SQC successfully | RFI is assigned to SQC successfully | 2025-12-29 | Pass | Major
TS.016 | Verify GM can assign RFI to TPIA | RFI is assigned to TPIA successfully | RFI is assigned to TPIA successfully | 2025-12-29 | Pass | Minor
TS.017 | Verify GM can assign RFI to BOTH | RFI is assigned to both SQC and TPIA | RFI is assigned to both SQC and TPIA | 2025-12-29 | Pass | Major
TS.018 | Verify Assign button disabled until option selected | Assign button remains disabled | Assign button remains disabled | 2025-12-29 | Pass | Minor
TS.019 | Verify success message is displayed after assignment | Success message is displayed | Success message is displayed | 2025-12-29 | Pass | Major
TS.020 | Verify assigned RFI removed from Pending with PIU list | Assigned RFI no longer appears | Assigned RFI no longer appears | 2025-12-29 | Pass | Low
TS.021 | Verify GM can remove RFI request before assignment | System prompts for confirmation | System prompts for confirmation | 2025-12-30 | Pass | Minor
TS.022 | Verify confirmation popup appears on Remove RFI action | Confirmation popup is displayed | Confirmation popup is displayed | 2025-12-30 | Pass | Minor
TS.023 | Verify RFI removed successfully after confirmation | RFI is removed from the list | RFI is removed from the list | 2025-12-30 | Pass | Low
TS.024 | Verify In Progress sub-module is visible | In Progress sub-module is visible | In Progress sub-module is visible | 2025-12-30 | Pass | Major
TS.025 | Verify In Progress screen loads correctly | In Progress screen loads successfully | In Progress screen loads successfully | 2025-12-30 | Pass | Low
TS.026 | Verify RFIs appear in In Progress after assignment | Assigned RFIs are displayed | Assigned RFIs are displayed | 2025-12-30 | Pass | Minor
TS.027 | Verify Action column shows Remove SQC / Remove TPIA | Remove SQC or Remove TPIA buttons visible | Remove SQC or Remove TPIA buttons visible | 2025-12-30 | Pass | Low
TS.028 | Verify GM can remove SQC assignment | Confirmation popup is displayed | Confirmation popup is displayed | 2025-12-30 | Pass | Minor
TS.029 | Verify GM can remove TPIA assignment | Confirmation popup is displayed | Confirmation popup is displayed | 2025-12-30 | Pass | Major
TS.030 | Verify confirmation popup appears before removal | Popup requests confirmation | Popup requests confirmation | 2025-12-30 | Pass | Minor
TS.031 | Verify RFI status updates correctly after removal | Assignment status updates correctly | Assignment status updates correctly | 2025-12-30 | Pass | Major
TS.032 | Verify Pending with PIU for Action sub-module is visible | Pending with PIU for Action is visible | Pending with PIU for Action is visible | 2025-12-30 | Pass | Low
TS.033 | Verify Pending with PIU for Action screen loads correctly | Screen loads successfully | Screen loads successfully | 2025-12-30 | Pass | Minor
TS.034 | Verify RFIs appear only after inspection completion | Only inspected RFIs are displayed | Only inspected RFIs are displayed | 2025-12-30 | Pass | Low
TS.035 | Verify Accepted status displayed | Accepted status is displayed | Accepted status is displayed | 2025-12-30 | Pass | Minor
TS.036 | Verify Re-Inspection Required status displayed | Re-Inspection Required status displayed | Re-Inspection Required status displayed | 2025-12-30 | Pass | Low
TS.037 | Verify GM can view inspection details for Accepted RFI | Inspection details displayed | Inspection details displayed | 2025-12-30 | Pass | Minor
TS.038 | Verify GM can view inspection details for Re-Inspection Required RFI | Inspection details displayed | Inspection details displayed | 2025-12-30 | Pass | Low
TS.039 | Verify Scheme filter dropdown loads correctly | Scheme list displayed correctly | Scheme list displayed correctly | 2025-12-30 | Pass | Minor
TS.040 | Verify Request Date filter works correctly | Results filtered by Request Date | Results filtered by Request Date | 2025-12-31 | Pass | Minor
TS.041 | Verify Component filter works correctly | Results filtered by Component | Results filtered by Component | 2025-12-31 | Pass | Major
TS.042 | Verify Status filter works correctly | Results filtered by Status | Results filtered by Status | 2025-12-31 | Pass | Minor
TS.043 | Verify Date Range filter works correctly | Results filtered by Date Range | Results filtered by Date Range | 2025-12-31 | Pass | Major
TS.044 | Verify Search button returns correct results | Correct filtered results displayed | Correct filtered results displayed | 2025-12-31 | Pass | Low
TS.045 | Verify Reset button clears all filters | All filters cleared | All filters cleared | 2025-12-31 | Pass | Minor
TS.046 | Verify assignment not allowed without selecting RFI | Validation message displayed | Validation message displayed | 2025-12-31 | Pass | Low
TS.047 | Verify assignment not allowed without selecting SQC/TPIA/BOTH | Validation message displayed | Validation message displayed | 2025-12-31 | Pass | Low
TS.048 | Verify GM cannot assign already assigned RFI | System prevents duplicate assignment | System prevents duplicate assignment | 2025-12-31 | Pass | Minor
TS.049 | Verify GM cannot remove assignment without confirmation | Assignment remains unchanged | Assignment remains unchanged | 2025-12-31 | Pass | Major
TS.050 | Verify GM cannot edit contractor-submitted RFI details | Editing is not allowed | Editing is not allowed | 2025-12-31 | Pass | Minor
TS.051 | Verify GM cannot access Contractor-only actions | Access denied | Access denied | 2025-12-31 | Pass | Major
TS.052 | Verify GM cannot perform FE inspection actions | Access denied | Access denied | 2025-12-31 | Pass | Low
TS.053 | Verify unauthorized user cannot access GM Material Testing screens | Access denied or redirected | Access denied or redirected | 2025-12-31 | Pass | Minor
TS.054 | Verify GM session timeout logs out automatically | System logs out GM automatically | System logs out GM automatically | 2025-12-31 | Pass | Major
Severity :
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues
Priority:
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues

## MT SQCTPIABOTH TC
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify SQC/TPIA can login successfully to Jal Rekha web application | User logs in successfully and authentication is completed | User logs in successfully and authentication is completed | 2025-12-26 | Pass | Major
TC.002 | Verify user is redirected to dashboard after login | Dashboard page is displayed | Dashboard page is displayed | 2025-12-26 | Pass | Minor
TC.003 | Verify Material Testing module is visible in left menu | Material Testing module is visible | Material Testing module is visible | 2025-12-26 | Pass | Major
TC.004 | Verify user can navigate to Material Testing module | Material Testing sub-modules are displayed | Material Testing sub-modules are displayed | 2025-12-26 | Pass | Low
TC.005 | Verify Pending RFI List sub-module is visible | Pending RFI List is visible | Pending RFI List is visible | 2025-12-26 | Pass | Minor
TC.006 | Verify Pending RFI List screen loads correctly | Pending RFI List screen loads successfully | Pending RFI List screen loads successfully | 2025-12-26 | Pass | Low
TC.007 | Verify only RFIs assigned by GM are displayed | Only RFIs assigned by GM are shown | Only RFIs assigned by GM are shown | 2025-12-26 | Pass | Low
TC.008 | Verify RFI list displays correct columns | All required columns are displayed correctly | All required columns are displayed correctly | 2025-12-26 | Pass | Minor
TC.009 | Verify pagination works correctly | RFI list updates correctly | RFI list updates correctly | 2025-12-26 | Pass | Major
TC.010 | Verify search functionality works correctly | RFI list is filtered correctly | RFI list is filtered correctly | 2025-12-26 | Pass | Minor
TC.011 | Verify user can view RFI details | RFI details are displayed | RFI details are displayed | 2025-12-26 | Pass | Major
TC.012 | Verify user can view RFI images | RFI images are displayed | RFI images are displayed | 2025-12-26 | Pass | Low
TC.013 | Verify Select Field Engineer dropdown loads correctly | Dropdown loads with FE list | Dropdown loads with FE list | 2025-12-29 | Pass | Minor
TC.014 | Verify only mapped FE users are displayed in dropdown | Only mapped FE users are listed | Only mapped FE users are listed | 2025-12-29 | Pass | Major
TC.015 | Verify FE selection is mandatory before assignment | System shows validation message | System shows validation message | 2025-12-29 | Pass | Major
TC.016 | Verify user can select single RFI using checkbox | RFI is selected | RFI is selected | 2025-12-29 | Pass | Major
TC.017 | Verify user can select multiple RFIs | Multiple RFIs are selected | Multiple RFIs are selected | 2025-12-29 | Pass | Minor
TC.018 | Verify assignment is not allowed without selecting RFI | Assignment is blocked | Assignment is blocked | 2025-12-29 | Pass | Major
TC.019 | Verify assignment is not allowed without selecting FE | Assignment is blocked | Assignment is blocked | 2025-12-29 | Pass | Minor
TC.020 | Verify user can assign RFI to FE successfully | RFI assigned to FE successfully | RFI assigned to FE successfully | 2025-12-29 | Pass | Major
TC.021 | Verify success message is displayed after assignment | Success message is displayed | Success message is displayed | 2025-12-29 | Pass | Low
TC.022 | Verify assigned RFI is removed from Pending RFI List | RFI is removed from Pending list | RFI is removed from Pending list | 2025-12-30 | Pass | Minor
TC.023 | Verify In Progress sub-module is visible | In Progress sub-module is visible | In Progress sub-module is visible | 2025-12-30 | Pass | Minor
TC.024 | Verify In Progress screen loads correctly | In Progress screen loads | In Progress screen loads | 2025-12-30 | Pass | Low
TC.025 | Verify RFIs assigned to FE appear in In Progress | Assigned RFIs are visible | Assigned RFIs are visible | 2025-12-30 | Pass | Major
TC.026 | Verify Action column shows Remove FE button | Remove FE button is visible | Remove FE button is visible | 2025-12-30 | Pass | Low
TC.027 | Verify user can remove FE assignment | Confirmation popup appears | Confirmation popup appears | 2025-12-30 | Pass | Minor
TC.028 | Verify confirmation popup appears before FE removal | Confirmation popup is displayed | Confirmation popup is displayed | 2025-12-30 | Pass | Low
TC.029 | Verify RFI remains in In Progress after FE removal | RFI remains in In Progress | RFI remains in In Progress | 2025-12-30 | Pass | Minor
TC.030 | Verify FE can be re-assigned after removal | FE is reassigned successfully | FE is reassigned successfully | 2025-12-30 | Pass | Major
TC.031 | Verify Complete RFI List sub-module is visible | Complete RFI List is visible | Complete RFI List is visible | 2025-12-30 | Pass | Minor
TC.032 | Verify Complete RFI List screen loads correctly | Complete RFI List loads | Complete RFI List loads | 2025-12-30 | Pass | Major
TC.033 | Verify only inspection-completed RFIs are displayed | Only completed RFIs are displayed | Only completed RFIs are displayed | 2025-12-30 | Pass | Low
TC.034 | Verify all RFI details are displayed correctly | All details are displayed | All details are displayed | 2025-12-30 | Pass | Minor
TC.035 | Verify inspection date and inspection outcome are visible | Inspection info visible | Inspection info visible | 2025-12-30 | Pass | Low
TC.036 | Verify user can view inspection images | Inspection images displayed | Inspection images displayed | 2025-12-30 | Pass | Minor
TC.037 | Verify no edit or assignment actions are available | No actions available | No actions available | 2025-12-30 | Pass | Low
TC.038 | Verify Scheme filter dropdown loads correctly | Scheme list loads | Scheme list loads | 2025-12-30 | Pass | Minor
TC.039 | Verify Request Date filter works correctly | Results filtered | Results filtered | 2025-12-30 | Pass | Low
TC.040 | Verify Search button filters RFIs correctly | Filtered RFIs displayed | Filtered RFIs displayed | 2025-12-30 | Pass | Minor
TC.041 | Verify Reset button clears applied filters | Filters cleared | Filters cleared | 2025-12-31 | Pass | Minor
TC.042 | Verify user cannot assign RFI without FE selection | System blocks assignment | System blocks assignment | 2025-12-31 | Pass | Major
TC.043 | Verify user cannot assign already assigned RFI again | System prevents action | System prevents action | 2025-12-31 | Pass | Minor
TC.044 | Verify user cannot remove FE without confirmation | Assignment unchanged | Assignment unchanged | 2025-12-31 | Pass | Major
TC.045 | Verify user cannot edit contractor-submitted RFI details | Editing disabled | Editing disabled | 2025-12-31 | Pass | Low
TC.046 | Verify user cannot perform GM-level assignment actions | Access denied | Access denied | 2025-12-31 | Pass | Minor
TC.047 | Verify SQC cannot access TPIA-only actions | Access denied | Access denied | 2025-12-31 | Pass | Low
TC.048 | Verify TPIA cannot access SQC-only actions | Access denied | Access denied | 2025-12-31 | Pass | Low
TC.049 | Verify SQC/TPIA cannot perform GM final decision actions | Access denied | Access denied | 2025-12-31 | Pass | Minor
TC.050 | Verify unauthorized user cannot access SQC/TPIA screens | Access denied | Access denied | 2025-12-31 | Pass | Major
TC.051 | Verify session timeout logs out SQC/TPIA automatically | User logged out automatically | User logged out automatically | 2025-12-31 | Pass | Minor
Severity :
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues
Priority:
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues

## MT FEworkflow TC
TEST CASE TEMPLATE
<Type of Testing:Unit/Inegration/System>
Project Name: Jal Rekha
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify FE can login successfully to Jal Rekha mobile application | FE logs in successfully | FE logs in successfully | 2025-12-26 | Pass | Major
TC.002 | Verify FE is redirected to dashboard after login | Dashboard screen is displayed | Dashboard screen is displayed | 2025-12-26 | Pass | Minor
TC.003 | Verify Material Testing module is visible to FE | Material Testing module is visible | Material Testing module is visible | 2025-12-26 | Pass | Major
TC.004 | Verify FE can navigate to Material Testing module | Material Testing screens open | Material Testing screens open | 2025-12-26 | Pass | Low
TC.005 | Verify FE can view list of RFIs assigned by SQC/TPIA | Assigned RFIs are displayed | Assigned RFIs are displayed | 2025-12-26 | Pass | Minor
TC.006 | Verify only FE-assigned RFIs are displayed | Only FE-assigned RFIs shown | Only FE-assigned RFIs shown | 2025-12-26 | Pass | Low
TC.007 | Verify assigned RFI list shows correct details | Correct RFI details displayed | Correct RFI details displayed | 2025-12-26 | Pass | Low
TC.008 | Verify FE can open assigned RFI details | RFI details screen opens | RFI details screen opens | 2025-12-26 | Pass | Minor
TC.009 | Verify all contractor-submitted details are visible in read-only mode | Fields visible and non-editable | Fields visible and non-editable | 2025-12-26 | Pass | Major
TC.010 | Verify location map is visible for inspection site | Map displayed with location pin | Map displayed with location pin | 2025-12-26 | Pass | Minor
TC.011 | Verify FE can enter inspection remarks | Remarks accepted | Remarks accepted | 2025-12-26 | Pass | Major
TC.012 | Verify inspection remarks field is mandatory | Validation message shown | Validation message shown | 2025-12-26 | Pass | Low
TC.013 | Verify FE can capture inspection photos using camera | Photo captured successfully | Photo captured successfully | 2025-12-29 | Pass | Minor
TC.014 | Verify inspection photo upload is mandatory | Validation error shown | Validation error shown | 2025-12-29 | Pass | Major
TC.015 | Verify multiple inspection photos can be captured | Multiple photos attached | Multiple photos attached | 2025-12-29 | Pass | Major
TC.016 | Verify FE can select Accept recommendation | Accept selected | Accept selected | 2025-12-29 | Pass | Major
TC.017 | Verify FE can select Reject recommendation | Reject selected | Reject selected | 2025-12-29 | Pass | Minor
TC.018 | Verify recommendation selection is mandatory | Validation message shown | Validation message shown | 2025-12-29 | Pass | Major
TC.019 | Verify FE can submit inspection report with all valid inputs | Inspection submitted | Inspection submitted | 2025-12-29 | Pass | Minor
TC.020 | Verify submission is blocked if mandatory fields are missing | Submission blocked | Submission blocked | 2025-12-29 | Pass | Major
TC.021 | Verify success message is displayed after submission | Success message displayed | Success message displayed | 2025-12-29 | Pass | Low
TC.022 | Verify submitted inspection becomes non-editable | Fields are non-editable | Fields are non-editable | 2025-12-30 | Pass | Minor
TC.023 | Verify inspection report is sent to GM after submission | Report visible to GM | Report visible to GM | 2025-12-30 | Pass | Minor
TC.024 | Verify FE cannot modify inspection after submission | Modification not allowed | Modification not allowed | 2025-12-30 | Pass | Low
TC.025 | Verify submitted RFI is removed from FE active list | RFI removed from list | RFI removed from list | 2025-12-30 | Pass | Major
TC.026 | Verify FE can view GM-approved inspection as Closed | Status shown as Closed | Status shown as Closed | 2025-12-30 | Pass | Low
TC.027 | Verify FE can view GM-rejected inspection status | Status shown as Rejected | Status shown as Rejected | 2025-12-30 | Pass | Minor
TC.028 | Verify rejected inspection does not allow FE resubmission | Resubmission not allowed | Resubmission not allowed | 2025-12-30 | Pass | Low
TC.029 | Verify new RFI is generated by Contractor on GM rejection | New RFI generated | New RFI generated | 2025-12-30 | Pass | Minor
TC.030 | Verify FE cannot access Contractor RFI creation screens | Access denied | Access denied | 2025-12-30 | Pass | Major
TC.031 | Verify FE cannot perform GM approval/rejection actions | Access denied | Access denied | 2025-12-30 | Pass | Minor
TC.032 | Verify FE cannot assign RFI to another FE | Action restricted | Action restricted | 2025-12-30 | Pass | Major
TC.033 | Verify unauthorized user cannot access FE inspection screens | Access denied | Access denied | 2025-12-30 | Pass | Low
Severity :
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues
Priority:
Critical/Fatal:The work product is not usable.
High/Serious:The work product is usable but with a major inconvenience, or a major functionality/process requirement is missing.
Moderate/Mild:Hardly affects usability of the work product. The work product can be used with only slight inconvenience.
Minor/Cosmetic:Doesn't affect usability of the work product.Typographical and cosmetic issues