## Version History
Version number | Version Date | Description | Author/Revised by | Reviewed/Approved by
1 |  | UAT Defects / Observations | Mrs. Ranjana Yadav

## DHARA
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
Bug ID: 21901 | DHARA | While adding a new meter reading entry under a registered scheme, the system fails to save or validate data correctly. The user encounters inconsistent behavior — such as validation errors, incorrect data mapping, or record not appearing in the meter reading list after submission.. | Testing | Validation | High | 2025-02-28 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 21902 | DHARA | Page disappears after clicking "Update Password" with incorrect OTP and blank "Enter New Password" field. | Testing | Fucntional | Low | 2025-04-06 | Tapan Khandelwal | Closed | Development
BugID: 21903 | DHARA | While registering a meter under a scheme, selecting Scheme does not auto-populate linked PIU and Village fields, allowing incorrect mapping. | UAT | Validation | High | 2025-03-01 | Tapan Khandelwal | Closed | UAT
BugID: 21904 | DHARA | Bulk meter Excel upload succeeds, but uploaded meters are not visible immediately in the meter list until manual page refresh or re-login. | PROD | Validation | Medium | 2025-03-25 | Tapan Khandelwal | Closed | PROD
Bug_01 | DHARA | When the user tries to upload a PDF file as a supporting document under the Bulk Meter section, the upload action fails. The system either shows an error message or does not store the file, resulting in missing attachments for bulk meter records. | Testing | Fucntional | Medium | 2025-04-06 | Tapan Khandelwal | Closed | Requirement Analysis
Bug_02 | DHARA | When the PIU GM assigns an OHT/INTAKE/WTP component to a Field Engineer, the system allows the same OHT to be assigned multiple times to the same engineer. This results in duplicate task entries and confusion during meter reading and approval processes | Testing | Fucntional | Medium | 2025-04-08 | Tapan Khandelwal | Closed | Development
Bug_03 | DHARA | In the drill-down view of the report (Scheme → Village → OHT), the OHT count displayed in the hyperlink is incorrect. When the user clicks on the scheme or village name hyperlink to view OHT details, the number of OHTs shown does not match the actual data in the master or mapped records. | Testing | Data | High | 2025-04-09 | Tapan Khandelwal | Closed | Requirement Analysis
Bug_04 | DHARA | When entering Start and End meter readings, the application intermittently displays a validation error like “End reading must be greater than Start reading” even though the entered End reading is numerically greater than the Start reading. This blocks saving valid readings. | Testing | Validation | High | 2025-05-24 | Tapan Khandelwal | Closed | Requirement Analysis
Bug_05 | DHARA | When the PIU GM attempts to edit an existing meter reading, the system shows inconsistent behavior: In some cases, GM is unable to edit the reading (Edit button disabled or Save not working). In other cases, when GM edits and saves successfully, the Field Engineer (FE) is not able to view the updated value in their dashboard or report. This results in data mismatch between GM and FE recods | Testing | Data | Medium | 2025-04-07 | Tapan Khandelwal | Closed | development
Bug_06 | DHARA | After saving, the remark is displayed under the FE Remark column. If the user clicks the Edit/Add button again and adds another remark, it is displayed under the GM Remark column." | Testing | Fucntional | Medium | 2025-04-08 | Tapan Khandelwal | Closed | Development
Bug_07 | DHARA | If Excel file contains one invalid row, the entire bulk upload fails instead of partially uploading valid records with error summary. | UAT | Data | Medium | 2025-04-13 | Tapan Khandelwal | Closed | UAT
Bug_08 | DHARA | GM assigns bulk meter reading task to FE, but the assignment is not reflected in FE mobile app task list. | UAT | Fucntional | High | 2025-04-13 | Tapan Khandelwal | Closed | UAT
Bug_09 | DHARA | Meter status selection (Functional / Not Functional / Replace / No Water Supply) is not mandatory, allowing reading submission without status selection. | UAT | Validation | High | 2025-04-14 | Tapan Khandelwal | Closed | UAT
Bug_10 | DHARA | When reading is saved in offline mode and synced later, the reading date is replaced with sync date instead of original entry date. | UAT | Data | Medium | 2025-04-14 | Tapan Khandelwal | Closed | UAT
Bug_11 | DHARA | GM approves meter reading with comments, but approval comments are not visible in DWSR and MWSR reports. | UAT | Fucntional | Medium | 2025-04-03 | Tapan Khandelwal | Closed | UAT
Bug_12 | DHARA | Scheme-wise report shows duplicate meter readings for the same date when FE edits and resubmits a reading. | UAT | Fucntional | High | 2025-04-11 | Tapan Khandelwal | Closed | UAT
Bug_13 | DHARA | UFW report calculation does not consider “No Water Supply” meter status, resulting in incorrect UFW percentage. | UAT | Fucntional | Medium | 2025-04-12 | Tapan Khandelwal | Closed | UAT
Bug_14 | DHARA | FE mobile app becomes unresponsive when syncing more than 20 meter readings with photos in a single sync cycle. | PROD | Fucntional | Medium | 2025-04-20 | Tapan Khandelwal | Closed | PROD
Bug_15 | DHARA | GM approval overwrites TL comments instead of appending audit history. | PROD | Fucntional | Medium | 2025-04-25 | Tapan Khandelwal | Closed | PROD
Bug_16 | DHARA | GM rejection does not return task back to FE for correction. | PROD | Fucntional | Critical | 2025-05-05 | Tapan Khandelwal | Closed | PROD
Bug_17 | DHARA | DWSR shows zero supply for meters marked as “Functional” with valid readings. | PROD | Fucntional | Medium | 2025-05-15 | Tapan Khandelwal | Closed | PROD
Bug_18 | DHARA | DWSR export file column order does not match UI display. | PROD | Fucntional | Medium | 18-052025 | Tapan Khandelwal | Closed | PROD
Bug_19 | DHARA | Monthly report aggregates duplicate readings when FE edits same day entry. | PROD | Fucntional | High | 2025-05-28 | Tapan Khandelwal | Closed | PROD
Bug_20 | DHARA | Scheme-wise report shows villages that are deactivated in master data. | PROD | Fucntional | High | 2025-05-29 | Tapan Khandelwal | Closed | PROD
Bug_21 | DHARA | Village-wise report does not reflect newly mapped bulk meters. | PROD | Fucntional | Medium | 2025-06-02 | Tapan Khandelwal | Closed | PROD
Bug_22 | DHARA | Bulk user report missing meter status column after format change. | PROD | Fucntional | Medium | 2025-06-04 | Tapan Khandelwal | Closed | PROD
Bug_23 | DHARA | UFW calculation does not exclude replaced meters from loss calculation. | PROD | Fucntional | Medium | 2025-06-15 | Tapan Khandelwal | Closed | PROD
Bug_24 | DHARA | Drill-down navigation resets applied date filters at each level. | PROD | Fucntional | Medium | 2025-06-16 | Tapan Khandelwal | Closed | PROD
Bug_25 | DHARA | Bulk meter upload implemented without complete validation documentation | Development | Code Review | Medium | 14-02-2025 | Tapan Khandelwal | Closed | Development
Bug_26 | DHARA | Assignment workflow (GM → FE) implemented without formal documented approval matrix | Development | Code Review | Medium | 18/02/2025 | Tapan Khandelwal | Closed | Development
Bug_27 | DHARA | Reading verification and edit functionality implemented without audit trail validation | Development | Code Review | Medium | 25/02/2025 | Tapan Khandelwal | Closed | Development
Bug_28 | DHARA | OHT component delete option added without impact analysis documentation | Development | Code Review | Medium | 15/04/2025 | Tapan Khandelwal | Closed | Development
Bug_29 | DHARA | Report format modification done without updated requirement document | Development | Code Review | Medium | 18-05-2025 | Tapan Khandelwal | Closed | Development
Bug_30 | DHARA | Drill-down functionality implemented without performance validation | Development | Code Review | Medium | 26-05-2025 | Tapan Khandelwal | Closed | Development
Bug_31 | DHARA | TL approval workflow implemented without documented validation checkpoints | Development | Code Review | Medium | 2025-04-04 | Tapan Khandelwal | Closed | Development
Bug_32 | DHARA | Reading change option extended without version-controlled documentation | Development | Code Review | Medium | 2025-11-04 | Tapan Khandelwal | Closed | Development
Bug_33 | DHARA | Offline sync implemented without conflict handling documentation | Development | Code Review | Medium | 20/02/2025 | Tapan Khandelwal | Closed | Development
Bug_34 | DHARA | Photo upload workflow implemented without file validation & compression test record | Development | Code Review | Medium | 2025-03-03 | Tapan Khandelwal | Closed | Development
Bug_35 | DHARA | Meter validation parameters implemented without boundary test documentation | Development | Code Review | Medium | 2025-06-03 | Tapan Khandelwal | Closed | Development
Bug_36 | DHARA | Data-heavy tables have tight spacing, small fonts, and unclear sorting indicators. | UAT | UI/UX | high | 15-02-2025 | Vijay singh | Closed
Bug_37 | DHARA | While adding a new meter reading entry under a registered scheme, the interface does not provide clear validation feedback and user guidance. | UAT | UI/UX | high | 2025-01-03 | Vijay singh | Closed
Bug_38 | DHARA | Sorting icons are small and not easily noticeable, reducing usability and interaction clarity. Long village names with codes appear cluttered without proper spacing or tooltip support, affecting readability. | UAT | UI/UX | high | 2025-07-03 | Vijay singh | Closed
Bug_39 | DHARA | Improper alignment, lack of confirmation before assignment, and limited accessibility reduce overall usability and increase the risk of incorrect task allocation. | UAT | UI/UX | high | 15/3/2025 | Vijay singh | Closed
Bug_40 | DHARA | The Scheme dropdown expands excessively over the table without search support, making selection difficult in long lists. | UAT | UI/UX | Medium | 21/3/2025 | Vijay singh | Closed
Bug_41 | DHARA | The reports section lacks structured navigation and well-grouped filters, reducing overall usability and efficiency. | UAT | UI/UX | Medium | 25/2/2025 | Vijay singh | Closed
Bug_42 | DHARA | Scroll movement is not immediate, reducing responsiveness and affecting data table usability. Delayed scrolling impacts user experience, especially in data-heavy report tables. | UAT | UI/UX | Medium | 20/3/2025 | Vijay singh | Closed
Bug_43 | DHARA | Numeric input field lacks clear validation feedback (min/max range, previous reading comparison). | UAT | UI/UX | Medium | 25/3/2025 | Vijay singh | Closed

## MASTER
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21905 | MASTER | When the user navigates to the OHT selection screen, the ‘Select OHT’ dropdown does not list any OHTs on the first attempt. The OHT list appears only after revisiting or refreshing the mapping screen and updating the data, indicating a delay or missing data fetch from the backend. | Testing | Functional | High | 2025-03-06 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 21906 | MASTER | OHT Name is not reflecting on OHT Village mapping screen | Testing | Functional | High | 2025-03-06 | Tapan Khandelwal | Closed | Development
BugID: 21907 | MASTER | Villages marked as deactivated in Master are still visible and selectable in OHT Village Mapping screen | UAT | Data | High | 2025-03-07 | Tapan Khandelwal | Closed | UAT
BugID: 21908 | MASTER | Bulk meter–village mapping appears saved in Master module, but the same is not available in DHARA for FE task assignment. | PROD | Functional | High | 2025-03-15 | Tapan Khandelwal | Closed | PROD
Bug_01 | MASTER | "On the first attempt, the user is unable to find the OHT in the dropdown under 'Assign Task' (Dhara). However, if the user revisits the OHT Village Mapping screen and updates the details without making any changes, the OHT then appears in the dropdown." | Testing | Functional | Medium | 2025-03-07 | Tapan Khandelwal | Closed | Development
Bug_02 | MASTER | When opening the OHT Village Mapping screen, the OHT Name field/column is blank or not displayed for mapped OHT records. Although OHTs exist in the master and are mapped to villages, their names are not shown on the mapping screen — making it difficult to identify which OHTs are mapped to which villages. | Testing | Functional | Medium | 2025-03-26 | Tapan Khandelwal | Closed | Requirement Analysis
Bug_03 | MASTER | After updatating the master schema, facing issue while uploading the date | Testing | Functional | Medium | 2025-03-26 | Tapan Khandelwal | Closed | Development
Bug_04 | MASTER | After editing village master data (PIU/GP change), the updated linkage is not reflected in reports or mapping screens. | Testing | Data | Medium | 2025-03-27 | Tapan Khandelwal | Closed | Development
Bug_05 | MASTER | After mapping OHT components in Master, the components are not available in DHARA under Assign Task for FE. | UAT | Functional | High | 2025-03-27 | Tapan Khandelwal | Closed | UAT
Bug_06 | MASTER | WTP meters mapped successfully in Master do not appear in Scheme Covered Villages report. | UAT | Functional | High | 2025-03-29 | Tapan Khandelwal | Closed | UAT
Bug_07 | MASTER | Pipeline data updated and approved by GM is not refreshed in CWPM/RWPM reports and shows old values. | UAT | Functional | Medium | 2025-03-30 | Tapan Khandelwal | Closed | UAT
Bug_08 | MASTER | Contractor uploads pipeline component data as per defined schema, but upload fails without clear validation message. | UAT | Functional | Low | 2025-03-07 | Tapan Khandelwal | Closed | UAT
Bug_09 | MASTER | Even after GM approves pipeline master data on web, the updated details are not visible in Anusharan mobile RFI flow. | PROD | Functional | High | 2025-03-20 | Tapan Khandelwal | Closed | PROD
Bug_10 | MASTER | After adding OHT name in Master/Anusharan configuration, it does not appear in “Generate RFI” screen on mobile. | PROD | Functional | Medium | 2025-04-05 | Tapan Khandelwal | Closed | PROD
Bug_11 | MASTER | After modifying master schema, mobile Anusharan module continues to use old schema until app is reinstalled or cache cleared. | PROD | Functional | Medium | 2025-04-11 | Tapan Khandelwal | Closed | PROD
Bug_12 | MASTER | Scheme village master mapping implemented without complete data validation documentation | Development | Code Review | Medium | 2025-06-03 | Tapan Khandelwal | Closed | Development
Bug_13 | MASTER | OHT/WTP mapping and component data flow implemented without integration testing evidence | Development | Code Review | Medium | 2025-07-03 | Tapan Khandelwal | Closed | Development
Bug_14 | MASTER | CWGM/CWPM/RWPM/Distribution Pipe reports developed without documented query optimization review | Development | Code Review | Medium | 20/03/2025 | Tapan Khandelwal | Closed | Development
Bug_15 | MASTER | Scheme Covered Villages report implemented without requirement traceability update | Development | Code Review | Medium | 27/03/2025 | Tapan Khandelwal | Closed | Development
Bug_16 | MASTER | Pipeline master upload functionality implemented without schema validation checklist | Development | Code Review | Medium | 15/03/2025 | Tapan Khandelwal | Closed | Development
Bug_17 | MASTER | GM approval/edit workflow implemented without documented approval matrix | Development | Code Review | Medium | 25-03-2026 | Tapan Khandelwal | Closed | Development
Bug_18 | MASTER | RFI request generation from mobile implemented without field-level validation documentation | Development | Code Review | Medium | 2025-11-04 | Tapan Khandelwal | Closed | Development
Bug_20 | MASTER | Schema modification and mobile anusharan changes implemented without structured impact analysis | Development | Code Review | Medium | 24/04/2025 | Tapan Khandelwal | Closed | Development
Bug_21 | MASTER | Linking Scheme, PIU, GP, Village, Bulk Meter, and O&M details is not visually grouped or structured in a step-wise layout. | UAT | UI/UX | Medium | 30/04/2025 | Vijay singh | Closed | UI/UX
Bug_22 | MASTER | Tables are data-heavy with limited spacing and weak visual hierarchy. | UAT | UI/UX | high | 2025-02-05 | Vijay singh | Closed | UI/UX
Bug_23 | MASTER | Mobile view may not clearly highlight mandatory fields. | UAT | UI/UX | high | 20/05/2025 | Vijay singh | Closed | UI/UX

## NIRMAL
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21909 | NIRMAL | Nirmal-FE- Field Engineer is not able to submit the FRC Test | Testing | Functional | High | 2025-04-06 | Amreen | Closed | Development
BugID: 21910 | NIRMAL | Nirmal-FE- Field Engineer is not able to submit photo | Testing | Functional | High | 2025-04-06 | Amreen | Closed | Development
BugID: 21912 | NIRMAL | Nirmal-FE- Field Engineer is not able to submit the sample report from field | UAT | Functional | High | 2025-04-11 | Amreen | Closed | UAT
BugID: 21913 | NIRMAL | FE is able to collect and submit water samples even when the device location is outside the defined geofence area. | PROD | Functional | Critical | 2025-04-20 | Amreen | Closed | PROD
Bug_001 | NIRMAL | Nirmal-FE- Field Engineer is not able to submit WTP sample | Testing | Functional | Medium | 2025-04-07 | Amreen | Closed | Development
Bug_002 | NIRMAL | Nirmal-Contractort- Few samples are not getting visible to contractor receivede from Field Engineer | Testing | Functional | Medium | 2025-04-20 | Amreen | Closed | Development
Bug_003 | NIRMAL | Nirmal-GM- While the submitting the contractor report GM is unable see total number of pass/fail parameter | Testing | Functional | High | 2025-05-24 | Amreen | Closed | Development
Bug_004 | NIRMAL | While FE is physically inside the allowed geofence, the app shows “Outside Location” error and blocks sample collection. | UAT | Functional | Medium | 2025-04-24 | Amreen | Closed | UAT
Bug_005 | NIRMAL | Samples collected and saved offline are not auto-synced after network restoration; FE must re-login or re-submit. | UAT | Functional | Medium | 2025-04-20 | Amreen | Closed | UAT
Bug_006 | NIRMAL | During photo upload, the mobile app becomes unresponsive and sample submission fails without error message. | UAT | Functional | Medium | 2025-04-20 | Amreen | Closed | UAT
Bug_007 | NIRMAL | After contractor updates lab test results, the same data is not visible in GM reports until cache clear or re-login. | UAT | Functional | Medium | 2025-04-21 | Amreen | Closed | UAT
Bug_008 | NIRMAL | System blocks entire lab report submission instead of showing parameter-level validation message. | PROD | Functional | High | 2025-04-25 | Amreen | Closed | PROD
Bug_009 | NIRMAL | When contractor re-submits corrected sample after defect, GM still sees old defect status. | PROD | Functional | High | 2025-04-29 | Amreen | Closed | PROD
Bug_010 | NIRMAL | When GM applies report filters and navigates back, selected filters reset automatically. | PROD | Functional | Medium | 2025-05-03 | Amreen | Closed | PROD
Bug_011 | NIRMAL | Sample counts displayed on FE mobile app do not match counts shown on GM dashboard reports. | PROD | Functional | Medium | 2025-05-03 | Amreen | Closed | PROD
Bug_012 | NIRMAL | Water sample parameter range: Few of the parameters are not getting change as per CR | PROD | Functional | High | 2025-05-07 | Amreen | Closed | PROD
Bug_013 | NIRMAL | Geofence API and sample collection implemented without location validation documentation | Development | Code Review | Medium | 2025-12-04 | Tapan Khandelwal | Closed | Development
Bug_014 | NIRMAL | Offline sample submission and sync process implemented without data integrity testing documentation | Development | Code Review | Medium | 13/04/2025 | Tapan Khandelwal | Closed | Development
Bug_015 | NIRMAL | Sample verification module implemented without documented role-based access validation | Development | Code Review | Medium | 18/04/2025 | Tapan Khandelwal | Closed | Development
Bug_016 | NIRMAL | Lab test update functionality implemented without audit trail logging documentation | Development | Code Review | Medium | 20/04/2025 | Tapan Khandelwal | Closed | Development
Bug_017 | NIRMAL | Report submission workflow implemented without regression testing documentation | Development | Code Review | Medium | 25/04/2025 | Tapan Khandelwal | Closed | Development
Bug_018 | NIRMAL | GM report review functionality implemented without validation checklist documentation | Development | Code Review | Medium | 18/04/2025 | Tapan Khandelwal | Closed | Development
Bug_019 | NIRMAL | Defect tracking visibility implemented without traceability matrix update | Development | Code Review | Medium | 20/04/2025 | Tapan Khandelwal | Closed | Development
Bug_020 | NIRMAL | Report parameter changes implemented without structured impact analysis | Development | Code Review | Medium | 15/05/2025 | Tapan Khandelwal | Closed | Development
Bug_021 | NIRMAL | Cross-module functionality changes (Nirmal & Dhara contractor/user management) implemented without integration testing documentation | Development | Code Review | Medium | 25/05/2025 | Tapan Khandelwal | Closed | Development
Bug_022 | NIRMAL | No clear visual indicator showing whether the FE is inside or outside the geofenced area. | Testing | UI/UX | High | 27/05/2025 | Vijay singh | Closed | Development
Bug_023 | NIRMAL | Water Quality parameters table is tightly spaced with limited row height. | UAT | UI/UX | Medium | 30/05/2025 | Vijay singh | Closed | UAT
Bug_024 | NIRMAL | The eye icon used under the table are similar from each other | Testing | UI/UX | High | 2025-05-05 | Vijay singh | Closed | Development

## SAHBHAGITA
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21914 | SAHBHAGITA | In the Sahbhagita module under GM → PM → ISA workflow, the ISA list is not displaying correctly as per the selected scheme. The system fails to filter or show ISA entries scheme-wise, resulting in either missing data or displaying all ISAs irrespective of the chosen scheme. This issue impacts scheme-level monitoring and assignment validation. | Testing | Functional | High | 2025-06-23 | Sunil | Closed | Development
BugID: 21915 | SAHBHAGITA | Field Engineers report that data submission intermittently fails in the Sahbhagita module. During certain attempts, clicking on the Submit button does not save data to the server. The app or web page shows no error, but the record is not reflected in the system. This appears to be a backend or sync-related issue causing data loss. | Testing | Data | Medium | 2025-06-26 | Sunil | Closed | Development
BugID: 21916 | SAHBHAGITA | The Sahbhagita activity report is not visible or accessible to the Project Manager (PM) in the UAT environment. Even though the activities have been submitted by lower roles (ISA/GM), the report section remains blank or fails to load data. This prevents PMs from reviewing progress and verifying submitted Sahbhagita activities. | UAT | Functional | Medium | 2025-06-27 | Sunil | Closed | UAT
BugID: 21917 | SAHBHAGITA | Field Engineers (FEs) are unable to upload PDF files in the Sahbhagita module on the production environment. The upload action either fails silently or shows a generic error message. This prevents submission of mandatory supporting documents such as activity proofs and reports. | PROD | Functional | High | 2025-06-28 | Sunil | Closed | PROD
Bug_01 | SAHBHAGITA | In the production environment, the Sahbhagita Activity (SA) count displayed under village-wise reports is not matching with the actual activities recorded at the field level. Some activities are either over-counted or missing, causing data inconsistency between the activity entry and the summarized report. | PROD | Functional | Medium | 2025-07-01 | Sunil | Closed | PROD
Bug_02 | SAHBHAGITA | When Field Engineer fills the Sahbhagita activity form and uploads activity data (photos/remarks) and clicks Submit, the system shows a success message but the updated activity details are not saved. After page refresh or re-login, the previously entered activity data and uploaded files are missing or reverted to old values. | PROD | Functional | High | 2025-07-06 | Sunil | Closed | PROD
Bug_03 | SAHBHAGITA | Sahbhagita report view implemented without documented requirement traceability update | Development | Code Review | Medium | 23/06/2025 | Tapan Khandelwal | Closed | Development
Bug_04 | SAHBHAGITA | Sahbhagita activity data entry and upload functionality implemented without validation and audit trail documentation | Development | Code Review | Medium | 25/06/2025 | Tapan Khandelwal | Closed | Development
Bug_05 | SAHBHAGITA | The Sahbhagita activity module allows users to fill activity details, upload activity-related data, and update changes. However, the UI does not clearly differentiate between the stages of data entry, upload, and update workflows. | UAT | UI/UX | Medium | 28/06/2025 | Vijay singh | Closed | UAT

## SOPAN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21918 | SOPAN | The Work Monitoring form allows the PIU GM to submit the form even when the Actual End Date field is left blank. This validation gap allows incomplete or inaccurate work progress records to be submitted, affecting data accuracy and reporting integrity. | Testing | Functional | High | 2025-04-23 | Sunil | Closed | Requirement Analysis
Bug ID: 21919 | SOPAN | When submitting the Work Monitoring form, an error pop-up appears with the message “Please select Status” even after the Status field has already been selected from the dropdown. This prevents successful form submission and causes confusion for the user. | Testing | Functional | High | 2025-04-23 | Sunil | Closed | Requirement Analysis
BugID: 21920 | SOPAN | Only recent chat messages are visible; earlier messages are missing when scrolling. | UAT | Medium | Low | 2025-04-28 | Sunil | Closed | UAT
Bug ID: 21921 | SOPAN | After updating OHT mapping, Monitoring view continues to show old mapping data. | PROD | Medium | High | 31-04-2025 | Sunil | Closed | PROD
Bug_01 | SOPAN | When submitting the Work Monitoring form, an error pop-up appears with the message “Please select Status” even after the Status field has already been selected from the dropdown. This prevents successful form submission and causes confusion for the user. | Testing | Validation | High | 2025-05-04 | Sunil | Closed | Development
Bug_02 | SOPAN | The Work Monitoring form allows the PIU GM to submit the form even when the Actual End Date field is left blank. This validation gap allows incomplete or inaccurate work progress records to be submitted, affecting data accuracy and reporting integrity. | Testing | Functional | High | 2025-05-05 | Sunil | Closed | Development
Bug_03 | SOPAN | Once the GM enters the actual end date, if it is later than the planned date, the number of delay days is not appearing on the UI. | Testing | UI/UX | High | 2025-05-07 | Sunil | Closed | Development
Bug_04 | SOPAN | Even after GM freezes actual start/end dates, contractor is still able to edit the work plan. | Testing | Validation | High | 2025-05-13 | Sunil | Closed | Development
Bug_05 | SOPAN | After successful upload, Panchanama document does not appear in the document list until page reload. | Testing | Functional | Medium | 2025-06-23 | Sunil | Closed | Development
Bug_06 | SOPAN | System allows duplicate WTP component mapping under the same scheme. | UAT | Functional | High | 2025-04-29 | Sunil | Closed | UAT
Bug_07 | SOPAN | Intake progress percentage shown does not match completed vs total stages. | UAT | Functional | High | 2025-05-08 | Sunil | Closed | UAT
Bug_08 | SOPAN | Stages approved by GM continue to display “In Progress” instead of “Completed”. | UAT | Functional | High | 2025-05-09 | Sunil | Closed | UAT
Bug_09 | SOPAN | OHT reports do not display stage-level planned start and end dates even though data exists. | UAT | Functional | Medium | 2025-05-15 | Sunil | Closed | UAT
Bug_10 | SOPAN | Actual duration calculation in WTP report is incorrect when start and end dates span multiple months. | UAT | Functional | Medium | 2025-06-27 | Sunil | Closed | UAT
Bug_11 | SOPAN | Freeze status applied by GM is not visible in Intake monitoring and reports. | PROD | Functional | High | 2025-05-02 | Sunil | Closed | PROD
Bug_12 | SOPAN | Applied filters in Mapping/Monitoring screens reset automatically when navigating back. | PROD | Functional | High | 2025-05-15 | Sunil | Closed | PROD
Bug_13 | SOPAN | Monitoring screen takes more than 30 seconds to load for schemes with multiple components. | PROD | Functional | Medium | 2025-05-25 | Sunil | Closed | PROD
Bug_14 | SOPAN | System does not maintain audit trail for contractor or GM edits on work plan dates. | PROD | Functional | Medium | 2025-06-30 | Sunil | Closed | PROD
Bug_15 | SOPAN | OHT/WTP/Intake/IPS work plan submission implemented without documented stage validation and workflow approval matrix | Development | Code Review | Medium | 29/03/2025 | Tapan Khandelwal | Closed | Development
Bug_16 | SOPAN | Plan start/end date submission implemented without impact analysis on project timeline tracking | Development | Code Review | Medium | 30/04/2025 | Tapan Khandelwal | Closed | Development
Bug_17 | SOPAN | Freeze actual plan date functionality implemented without audit trail logging documentation | Development | Code Review | Medium | 13/4/2025 | Tapan Khandelwal | Closed | Development
Bug_18 | SOPAN | Actual work start/end date update implemented without validation and traceability documentation | Development | Code Review | Medium | 2025-10-05 | Tapan Khandelwal | Closed | Development
Bug_19 | SOPAN | Document upload functionality implemented without file validation and security testing documentation | Development | Code Review | Medium | 2025-04-05 | Tapan Khandelwal | Closed | Development
Bug_20 | SOPAN | Chat functionality implemented without documented message logging and access control validation | Development | Code Review | Medium | 16/05/2025 | Tapan Khandelwal | Closed | Development
Bug_21 | SOPAN | Component mapping and monitoring reports implemented without performance testing documentation | Development | Code Review | Medium | 28/06/2025 | Tapan Khandelwal | Closed | Development
Bug_22 | SOPAN | The SOPAN module work plan screens lack structured stage visualization, validation controls, and workflow status indicators. | UAT | UI/UX | Medium | 30/06/2025 | Vijay Singh | Closed | UAT
Bug_23 | SOPAN | The Document and Remark logs are densely structured without strong section separation, impacting readability and usability. | UAT | UI/UX | High | 20/06/2025 | Vijay Singh | Closed | UAT
Bug_24 | SOPAN | The Document Upload section lacks clear visual hierarchy and grouping, with the upload area, document | UAT | UI/UX | Medium | 15/06/2025 | Vijay Singh | Closed | UAT