## Anushravan
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21781 | Anushravan | MBR Check Option Removed from CWGM Dropdown and Also Missing in Stages--The MBR Check option has been removed from the dropdown in the CWGM module. However, the corresponding MBR Check stage has also been removed from the workflow stages. | Testing | Functional | Critical | 19-11-2025 | Sunil Thakur | Closed | Requirement
BugID:21783 | Anushravan | Range Filter Not Working for Few Schemes in Anushravan Report--In the Anushravan report, the range filter is not functioning correctly for certain schemes. When users apply a range filter (e.g., financial/physical progress range), the report does not return accurate or filtered results for some schemes. | Testing | Validation | High | 25-11-2025 | Sunil Thakur | Closed | Development
RR‑01 | Anusharavaan | RFI Stage report does not distinguish Pending vs In‑Progress schemes as required in signed CR. | Requirement Analysis | Functional | Critical | 19-11-2025 | Dheeraj | Closed | Requirement Analysis | Incomplete capture of reporting rules during requirement workshop.
BugID:21784 |  | UI redesign of Jal Rekha inner pages implemented without usability validation and requirement traceability update | Development | Code Review | Medium | 2025-11-11 | Tapan Khandelwal | Closed | Development
BugID:21785 |  | RFI (MBR changes & status-based report updates) implemented without documented workflow validation | Development | Code Review | Medium | 2025-11-14 | Tapan Khandelwal | Closed | Development
BugID:21786 |  | Inline query and function changes done without impact analysis | Development | Code Review | Medium | 2025-11-19 | Tapan Khandelwal | Closed | Development
BugID:21787 |  | Database-level activity approval workflow designed without formal process documentation | Development | Code Review | Medium | 2025-11-20 | Tapan Khandelwal | Closed | Development

## BharosaCR NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID:17832 | Bharosa | System Allows Adding More Than the Maximum Allowed Number of Inspectors The application permits adding more than four inspectors, exceeding the defined business rule and lacking proper validation controls. | Testing | Validation | Medium | 22-12-2025 | Susheel Kumar Patel | Closed | Requirement Analysis
BugID:17833 | Bharosa | Inspection Data Not Reflected in History After Successful Upload Inspection records are not appearing in the History section after data upload, indicating a possible issue with data persistence or report synchronization. | Testing | Functional | Medium | 22-12-2025 | Susheel Kumar Patel | Closed | Development
BugID:17834 | Bharosa | Factory Testing Report Not Accessible on Web Portal The Factory Testing report is not visible or accessible on the web application despite successful submission of inspection data. | Testing | Functional | High | 22-12-2025 | Neha Soni | Closed | Development
BugID:17835 | Bharosa | Inspector Images Incorrectly Grouped Under Inspector Image Column All inspector-related images are displayed collectively under the Inspector Image column instead of being mapped to their respective inspection records. | Testing | UI/UX | Medium | 22-12-2025 | Neha Soni | Closed | Requirement Analysis
BugID:17836 | Bharosa | Inspection Images Incorrectly Displayed Under a Single Column All uploaded inspection images are displayed under the Inspection Image column without proper segregation or contextual labeling as per the design specification. | Testing | UI/UX | Medium | 22-12-2025 | Neha Soni | Closed | Development
BugID:17837 | Bharosa | Missing Rotate Functionality for Uploaded Images and Documents The image/document viewer does not provide a rotate option, impacting the ability to view uploaded inspection files in the correct orientation. | Testing | UI/UX | Low | 22-12-2025 | Neha Soni | Closed | Development
RR‑02 | Bharosa CR | Factory Testing Web requirements missed “Quantity Failed” and “Images” as mandatory fields. | Requirement Analysis | Functional | High | 20-11-2025 | Dheeraj | Closed | Requirement Analysis | Data fields requested by QC team not updated in BRD version control.
RR‑03 | Bharosa CR | Factory Testing Mobile CR does not cover offline‑sync behaviour for FE at remote plants. | Requirement Analysis | Functional | Medium | 20-11-2025 | Dheeraj | Closed | Requirement Analysis | Non‑functional offline scenarios not discussed in requirement checklist.
RR‑04 | Bharosa CR | Report View CR lacks column‑level sorting requirement for inspector‑wise view. | Requirement Analysis | Validation | Low | 21-11-2025 | Dheeraj | Closed | Requirement Analysis | Review focused on fields only, not on usability/report behaviour.
RR‑05 | Bharosa CR | FE / Reports CR lacks validation rule for duplicate family IDs across villages. | Requirement Analysis | Validation | Medium | 21-11-2025 | Dheeraj | Closed | Requirement Analysis | Cross‑village duplication scenario not considered in requirement scenarios.
BugID:17838 | Bharosa | Missing usability and responsive design validation in UI redesign may impact user experience. | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17839 | Bharosa | Incomplete field-level validation in survey inspection page may cause inconsistent data entry. | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17840 | Bharosa | Improper normalization in component and quantity mapping may lead to data redundancy | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17841 | Bharosa | Missing referential integrity checks in subcomponent mapping may create orphan records | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17842 | Bharosa | Lack of indexing and query optimization in database objects may degrade performance. | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17843 | Bharosa | Insufficient regression test coverage for bug fixes may introduce new defects. | Development | Code Review | High | 20-11-2025 | Sunil Thakur | Closed | Development
BugID:17844 | Bharosa | Factory testing UI design and draft workflow lack proper usability and state validation, leading to inconsistent user actions and data entry. | Development | Code Review | High | 30-11-2025 | Anand Gour | Closed | Development
BugID:17845 | Bharosa | Scheme addition and API integration lack input validation and duplicate checks, causing incorrect mapping and data inconsistency | Development | Code Review | High | 30-11-2025 | Anand Gour | Closed | Development
BugID:17846 | Bharosa | Mobile Insert and Get APIs lack secure authentication, payload validation, and standardized responses, increasing security and data integrity risks. | Development | Code Review | High | 2025-01-12 | Anand Gour | Closed | Development
BugID:17847 | Bharosa | Production deployment and history API integration lack performance optimization, monitoring, and rollback mechanisms, impacting system stability and reliability. | Development | Code Review | High | 2025-01-12 | Anand Gour | Closed | Development
BugID:17848 | Bharosa CR | Change requests across mobile reports, web reports, TPIA component assignment, and database functions lack comprehensive impact analysis and regression testing, increasing the risk of data inconsistency and functional breakage. | Development | Code Review | High | 14-12-2025 | Sunil Thakur | Closed | Development

## Material Testing
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21610 | Material Testing | RFI Approval Status Not Synced Between Contractor and GM-After GM approves or rejects a Material Testing RFI, the updated status is not reflected immediately on the contractor side. | Testing | Functional | High | 2025-12-27 | Neha | Closed | Development
BugID: 21613 | Material Testing | FE Receives RFI Without Complete Assignment Chain-In some cases, FE is able to see RFIs even when SQC assignment details are missing or incomplete. | Testing | Functional | High | 2025-12-28 | Neha | Closed | Development
Bug ID: 21614 | Material Testing | Pending at PIU Report Shows Incorrect Records-RFIs that are already assigned to SQC/FE or submitted by FE are still visible in the Pending at PIU report. | Testing | Functional | Medium | 2025-12-29 | Neha | Closed | Development
BugID: 21616 | Material Testing | Material Testing Insert API allows saving records even when some mandatory fields are missing, resulting in incomplete data in database tables. | UAT | Functional | High | 2025-12-30 | Neha | Closed | UAT
BugID: 21617 | Material Testing | The validation control was not incorporated in the API design specification, indicating a design-level gap rather than an implementation-only defect. | UAT | UI/UX | High | 2025-12-25 | Vijay | Closed | UAT
BugID: 21618 | Material Testing | UI allows submission of the Material Testing form even when mandatory fields are left blank, without displaying any validation message or error highlight. | UAT | UI/UX | Medium | 2025-12-31 | Vijay | Closed | UAT
BugID: 21620 | Material Testing | FE Geofencing Validation Missing at API Level-Geofencing validation for FE inspection is handled only at UI level and is not validated at API level, allowing inspection submission from outside the site location. | PROD | Functional | Medium | 10--1-2026 | Neha | Closed | PROD
RR‑07 | Material Testing | GM/Contractor login workflow does not specify SLA for GM → SQC → FE transitions in requirement note. | Requirement Analysis | Functional | High | 2025-12-25 | Dheeraj | Closed | Requirement Analysis | Business rules for SLAs captured in email but not migrated into requirement document.
RR‑08 | Material Testing | FE Login geofencing tolerance (meters) missing from requirement specification. | Requirement Analysis | Functional | Medium | 2025-12-25 | Dheeraj | Closed | Requirement Analysis | Non‑functional configuration values not part of standard template.
RR‑09 | Material Testing | Inner page navigation flow for RFI updates missing back‑link to scheme dashboard. | Requirement Analysis | UI/UX | Medium | 2025-12-27 | Dheeraj | Closed | Requirement Analysis | Wireframes were not reviewed with end users before freeze.
BugID: 21621 | Material Testing | Missing Input Validation in Contractor Request API | Development | Code Review | High | 25-12-2025 | Sunil Thakur | Closed | Development
BugID: 21622 | Material Testing | Inconsistent Error Handling in GM Approval/Rejection APIs | Development | Code Review | High | 25-12-2025 | Sunil Thakur | Closed | Development
BugID: 21623 | Material Testing | Hard-coded Status Values in Material Testing Workflow | Development | Code Review | High | 25-12-2025 | Sunil Thakur | Closed | Development
BugID: 21624 | Material Testing | Inadequate Test Coverage for FE Inspection Submission | Development | Code Review | High | 25-12-2025 | Sunil Thakur | Closed | Development
BugID: 21625 | Material Testing | Missing Data Consistency Checks in Insert API for Material Testing | Development | Code Review | High | 25-12-2025 | Sunil Thakur | Closed | Development
BugID: 21626 | Material Testing | Missing Server-Side Geofence Validation | Development | Code Review | High | 28-12-2025 | Anand Gour | Closed | Development
BugID: 21627 | Material Testing | Unsynchronized Dropdown Data Risk | Development | Code Review | High | 28-12-2025 | Anand Gour | Closed | Development
BugID: 21628 | Material Testing | DOM XSS in Jal Rekha Report Generation | Development | Code Review | High | 28-12-2025 | Anand Gour | Closed | Development

## FHTC NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21621 | FHTC | HSC Report: Photo Mandatory but Generated PDF/Excel Shows Blank Image Placeholders and Does Not Validate Missing Photos--HSC report (used by GM/PIU) requires photo as mandatory. Generated reports (PDF/Excel) photo field or produce blank image placeholders for many records; report generation does not fail when photo missing. | Testing | Functional | Medium | 2025-11-13 | Sunil | Closed | Development
BugID: 21622 | FHTC | Data Mapping Issue After NIC to Samagra API Replacement – Photo Flag, Beneficiary ID, and Tap Status Stored as Null--After replacing NIC APIs with Samagra, certain fields (photo presence flag, beneficiary identifier, tap-status field) are not mapped correctly; records on server show null for those fields though they were provided by the client. | Testing | Functional | Medium | 2025-12-08 | Sunil | Closed | Development
BugID: 21623 | FHTC | After replacing NIC APIs with Samagra APIs, the field mapping design was not properly updated, resulting in Photo Flag, Beneficiary ID, and Tap Status being stored as NULL in the database. | Testing | UI/UX | High | 2025-12-10 | Vijay | Closed | Development
BugID: 21624
BugID: 21625 | FHTC | GM/Contractor Reports do not define expected aggregation (household vs family ID) for Samagra data. | Requirement Analysis | Data | High | 2025-11-13 | Dheeraj | Closed | Requirement Analysis | Data‑mapping review between Jal Rekha and Samagra skipped in early stage.
BugID: 21626
BugID: 21627 |  | Report updates and FETCH module changes (FE/GM login) implemented without updated requirement traceability and regression testing evidence | Development | Code Review | Medium | 2025-11-10 | Tapan Khandelwal | Closed | Development
BugID: 21628 |  | SQL query fixes, database table/function updates, and PostgreSQL optimization performed without formal impact analysis and version-controlled DB change management | Development | Code Review | Medium | 2025-11-12 | Tapan Khandelwal | Closed | Development
BugID: 21629 |  | FHTC village scheme mapping bug fixes and Samagra multiple family ID issue handled without formal root cause analysis and integration validation | Development | Code Review | Medium | 2025-12-09 | Tapan Khandelwal | Closed | Development

## O&M NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21623 | O&M Billing | GM PIU Data Not Visible to Admin After Save and Submit - submitted data for all 24 PIUs not consistently visible to Kapil admin user | Testing | Validation | Medium | 2025-11-20 | Awinash | Closed | Requirement Analysis
BugID: 21624 | O&M Billing | Incorrect Data Refresh - scheme data persists after change; Additional Facilities tab data resets after logout/login | Testing | Data | Medium | 2025-11-21 | Awinash | Closed | Requirement Analysis
BugID: 21625 | O&M Billing | Incorrect Mapping and Display of GM PIU and Contractor Names in Reports - incorrect values, blanks, or stale data | Testing | Data | Medium | 2025-11-21 | Awinash | Closed | Development
BugID: 21626 | O&M Billing | Incorrect Field Labels in Contractor Billing Reports - "No of HSC" instead of "Additional Affected HSCs", "Resolved" instead of date, incorrect complaint text | Testing | Functional | Medium | 2025-12-27 | Awinash | Closed | Development
BugID: 21627 | O&M Billing | Bulk Upload and New Functionality Pages Not Integrated with Database - bulk uploads fail/process partial data | UAT | Functional | High | 2025-12-28 | Awinash | Closed | UAT
BugID: 21628 | O&M Billing | Contractor Billing module contains multiple design-level gaps related to field validations, report column structure, business rule enforcement, data visibility, and integration controls | UAT | UI/UX | Medium | 2025-11-20 | Vijay | Closed | UAT
BugID: 21629 | O&M Billing | All business rules (validation, freeze logic, conditional mandatory fields, time-based restrictions) must be clearly defined in FDD | UAT | UI/UX | Medium | 2025-11-19 | Vijay | Closed | UAT | UX copy review not part of requirement sign-off checklist.
RR-11 | O&M Billing | Change Request GM – requirement does not clearly define handling for multiple mappings of same village in old data | Requirement Analysis | Functional | High | 2025-11-15 | Dheeraj | Closed | Requirement Analysis | Legacy data exceptions not discussed with finance team during requirement review.
RR-12 | O&M Billing | Change Request GM – label text for "Additional affected HSCs" inconsistent across screen and report specification | Requirement Analysis | UI/UX | Low | 2025-11-18 | Dheeraj | Closed | Requirement Analysis | UX copy review not part of requirement sign-off checklist.
RR-13 | O&M Billing | Change Request Contractor – CPI base year/month change impact on historical bills not described in requirement document | Requirement Analysis | Functional | Critical | 2025-11-22 | Dheeraj | Closed | Requirement Analysis | Impact analysis for financial calculations not documented before approval.
CR-OMB-GM-001 | O&M Billing | GM 24 PIUs data not visible to Kapil admin after save and submit (only draft/in-progress visible, submitted bills hidden) | Code Review | Functional | High | 2025-11-26 | Awinash | Closed | Development
CR-OMB-GM-002 | O&M Billing | Kapil ID rename to "GM PIU O&M" not consistent across all screens, reports, API responses, and database comments | Code Review | UI/UX | Medium | 2025-11-25 | Awinash | Closed | Development
CR-OMB-GM-003 | O&M Billing | Village multiple time mapping validation only at UI level, allowing duplicate mappings through direct API calls | Code Review | Functional | High | 2025-11-28 | Awinash | Closed | Development
CR-OMB-GM-004 | O&M Billing | GM PIU and contractor name not coming correctly in cascading dropdown; stale data persists when parent selection changes rapidly | Code Review | Functional | High | 2025-11-28 | Awinash | Closed | Development
CR-OMB-GM-005 | O&M Billing | Agreement value data source mapping references incorrect contract table column, resulting in null or wrong values in billing calculations | Code Review | Functional | High | 2025-11-29 | Awinash | Closed | Development
CR-OMB-GM-006 | O&M Billing | Session storage uses browser localStorage which clears on logout, causing complete data loss for Additional Facilities and critical fields | Code Review | Functional | High | 2025-11-30 | Awinash | Closed | Development
CR-OMB-004 | O&M Billing | GST calculation logic does not handle reverse charge scenarios and exempt services correctly, leading to incorrect tax amounts | Code Review | Functional | High | 2025-12-02 | Awinash | Closed | Development
CR-OMB-C2-08 | O&M Billing | Document freeze mechanism not working for bulk uploads; users can add new documents after freeze in some edge cases | Code Review | Functional | Medium | 2025-12-05 | Awinash | Closed | Development
CR-OMB-C2-05 | O&M Billing | Yearly increment calculation for CPI shows off-by-one error for contracts starting mid-year | Code Review | Functional | High | 2025-12-08 | Awinash | Closed | Development
CR-OM-SEC-001 | O&M Billing | SQL injection vulnerabilities in database queries; improper query parameterization | Code Review | Security | Critical | 2025-12-10 | Awinash | Closed | Development
CR-OM-SEC-002 | O&M Billing | PostgreSQL query optimization issues; missing indexes causing performance degradation | Code Review | Security | High | 2025-12-10 | Awinash | Closed | Development
CR-OM-SEC-003 | O&M Billing | Cross-Site Scripting (XSS) DOM bugs in JavaScript files; script tags not properly escaped | Code Review | Security | High | 2025-12-10 | Awinash | Closed | Development

## Dhara CR NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21628 | DHARA | Water Supply Reports Data Mismatch-Updated DHARA reports (DWSR, MWSR, Scheme-wise, Village-wise, Bulk User, UFW) display inconsistent or outdated data after page redesign and meter-mapping updates, indicating misalignment between UI and backend queries | Testing | Functional | Medium | 2025-11-12 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 21628 | DHARA | Meter Mapping Between WTP and Village Not Reflected Correctly-The updated meter mapping between WTP and Village in the DHARA module does not reflect accurately in meter reading screens and related reports. As a result, meter readings appear under incorrect villages or are missing from village-wise and scheme-wise reports. | Testing | Functional | Medium | 2025-12-17 | Tapan Khandelwal | Closed | Develpomemt
RR‑14 | Dhara CR | Dhara Reports CR does not specify drill‑down path from DWSR/MWSR to meter‑level records. | Requirement Analysis | Functional | Medium | 2025-11-10 | Dheeraj | Closed | Requirement Analysis | Stakeholder assumed default drill‑down; not captured explicitly in BRD.
RR‑15 | Dhara CR | Security Vulnerability CR – password policy parameters (length, complexity) missing from requirements. | Requirement Analysis | Security | High | 2025-11-12 | Dheeraj | Closed | Requirement Analysis | Security requirements gathered from audit report but not itemized in requirement artefact.
BugID: 21629 | Dhara CR | Jal Rekha page redesign and multiple water supply report updates implemented without documented requirement traceability and regression validation | Development | Code Review | High | 2025-11-10 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21630 | Dhara CR | Meter mapping updates and Dhara module (WTP to Village meter reading) changes performed without formal impact analysis and workflow validation | Development | Code Review | High | 2025-11-12 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21631 | Dhara CR | Password encryption, Crashlytics vulnerability handling, and live deployment changes implemented without documented security review and penetration testing evidence | Development | Code Review | High | 2025-12-12 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21632 | Dhara CR | PostgreSQL query updates, Function/SP modifications, and Dhara report optimization performed without structured impact analysis and DB version control | Development | Code Review | High | 2025-12-17 | Tapan Khandelwal | Closed | Develpomemt

## Nirmal CR NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21634 | NIRMAL | WTP Report Not Showing Updated Parameters-Updated WTP parameters (new columns/labels/units) are not appearing in the WTP report after CR deployment. | Testing | Functional | High | 2025-11-23 | Neha | Closed | Development
BugID: 21635 | NIRMAL | WTP Raw Water Quality Parameters Not Displaying Correct Units-Some updated WTP raw water parameters (e.g., Turbidity, pH, Iron) appear in the report without units or with incorrect units (e.g., mg/l instead of NTU). This leads to misinterpretation of values and incorrect compliance evaluation. | Testing | Functional | Medium | 2025-11-24 | Neha | Closed | Development
BugID: 21637 | NIRMAL | OHT-Date Range Filter Not Working in Web Report-Date range filter on the NIRMAL web report does not return correct filtered results. | Testing | Functional | Medium | 2025-11-25 | Neha | Closed | Development
BugID: 21640 | NIRMAL | Drill Down & New Query Mapping Issue- Drill-down reports display incorrect or mismatched data after new query implementation | UAT | Functional | High | 2025-12-12 | Neha | Closed | UAT
BugID: 21641 | NIRMAL | Raw Water Data Mapping and Drill-Down Records Incorrect or Incomplete-The mapping of Nirmal Raw Water testing data using the table RawWater_Samples_Tested_Detail is incorrect or incomplete. As a result, testing details of raw water samples (before treatment) are missing or mismatched in reports. Additionally, newly added columns for Passed/Failed status and their corresponding drill-down views do not consistently display correct record-level details. | UAT | Functional | High | 2025-12-12 | Neha | Closed | UAT
BugID: 21644 | NIRMAL | UI Enhancements and 200m Buffer Rule Not Applied Consistently Across NIRMAL Reports and FE Login- Multiple approved Change Requests in the NIRMAL module are not implemented consistently across all report views and login roles (Contractor/FE). 1.Bell icon missing in comments pop-ups in certain reports. 2.Label “Remarks” not updated to “FE Remarks” across all reports and pop-ups. 3.Search options missing in some reports. 4.Comments box not available in all drill-down views. 5.Popup UI inconsistent between Contractor and GM login. | PROD | Functional | High | 2025-12-13 | Neha | Closed | PROD
RR‑16 | Nirmal | WTP/OHT/Beneficiary report CR lacks clear definition of new drill‑down combinations for test results. | Requirement Analysis | Functional | High | 19-11-2025 | Dheeraj | Closed | Requirement Analysis | Complex report hierarchy not prototyped before requirement sign‑off.
RR‑17 | Nirmal | Raw Water Report CR – range search requirement for sample date not aligned between UI spec and report spec. | Requirement Analysis | Validation | Medium | 19-11-2025 | Dheeraj | Closed | Requirement Analysis | Parallel documents (UI spec vs report spec) not cross‑reviewed.
RR‑18 | Nirmal | Raw Water Report CR – buffer distance of 200 m for sample collection not specified as configurable. | Requirement Analysis | Functional | Low | 19-11-2025 | Dheeraj | Closed | Requirement Analysis | Configuration vs hard‑coding decision not captured during requirement walkthrough.
RR‑19 | Nirmal | Multiple CRs use inconsistent terminology for “Scheme”, “Project” and “Programme” in requirements. | Requirement Analysis | Documentation | Medium | 19-11-2025 | Dheeraj | Closed | Requirement Analysis | No central terminology baseline; reviews focused module‑wise instead of portfolio‑wise.
BugID: 01 | NIRMAL | Drill-Down Data Mismatch in WTP/OHT/Beneficiary Reports- Newly added drill-down levels are not consistently filtering data based on selected Scheme ID, PIU ID, or Sample ID. Summary data does not match drill-down records in some cases. | Development | Code Review | High | 19-11-2025 | Sunil | Closed | Development
BugID: 02 | NIRMAL | Action Remarks Not Saving / Overwriting Between Roles - Action Remarks added by Contractor/GM are either not saving properly or overwriting existing remarks due to improper update conditions and missing role-based validation. | Development | Code Review | High | 19-11-2025 | Sunil | Closed | Development
BugID: 03 | NIRMAL | OHT Village Mapping Not Displayed Correctly in Reports - OHT reports are showing missing or duplicate village mapping records due to incorrect join conditions or improper data mapping logic. | Development | Code Review | High | 19-11-2025 | Sunil | Closed | Development
BugID: 04 | NIRMAL | Search & Enhanced Filters Not Applied Consistently Across Reports - Newly added search options and enhanced component filters are not working consistently across all report views, resulting in incorrect or incomplete report data. | Development | Code Review | High | 19-11-2025 | Sunil | Closed | Development
BugID: 05 | NIRMAL | Date Range & Sample ID Filter Not Working Correctly in Raw Water Report - The newly added Date Range filter and Water Sample ID search option are not filtering records correctly. Reports may return incorrect, partial, or unfiltered data due to improper parameter handling. | Development | Code Review | High | 2025-10-12 | Sunil | Closed | Development
BugID: 06 | NIRMAL | RawWater_Samples_Tested_Detail Data Mapping Mismatch- The new query for RawWater_Samples_Tested_Detail is displaying incorrect or duplicate testing records. Passed and Failed status drill-down data does not match summary counts due to improper mapping or join conditions. | Development | Code Review | High | 2025-10-12 | Sunil | Closed | Development
BugID: 07 | NIRMAL | UI Changes Not Applied Consistently in Raw Water & WTP Reports - Bell icon missing in some comment popups, label not updated from “Remarks” to “FE Remarks” in all reports, and search/comment box not available across all views, indicating incomplete UI implementation. | Development | Code Review | High | 2025-10-12 | Sunil | Closed | Development
BugID: 08 | NIRMAL | 200 Meter Intake Buffer Rule Not Applied Properly for Contractor/FE Login - The increased 200m intake buffer rule for raw water sample collection is not enforced consistently for Contractor/FE login, allowing sample entries outside the defined buffer range. | Development | Code Review | High | 2025-10-12 | Sunil | Closed | Development
BugID: 09 | NIRMAL | Report parameters and filter components not clearly defined in report design specification. | UAT | Testing | High | 2025-10-12 | Vijay | Closed | UI/UX

## Sahbhagita CR NtoJ
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 21645 | Sahbhagita | GM Report Export Not Matching On-Screen Village Data-When GM exports the village-wise Sahbhagita report (Excel/PDF), the exported data does not match what is shown on the screen. | Testing | Functional | High | 2025-11-29 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21647 | Sahbhagita | Village-wise Approval and ISA Dependency Not Functioning Correctly in Sahbhagita Module-In the Sahbhagita module, village-wise approval is not working correctly. The Get_VillageForApproval service does not consistently load village data, the Village dropdown on the Frm_Ngo_Survey_Approval page is missing or not populated, and the PIU → Scheme → ISA → Village dependency is not enforced, resulting in incorrect or unfiltered data in the Sahbhagita ISA Bill Form. | Testing | Functional | High | 2025-12-10 | Tapan Khandelwal | Closed | Develpomemt
RR‑19 | Sahbhagita | Sahbhagita Reports – requirement does not define status definitions for “No Action” vs “Pending Approval”. | Requirement Analysis | Functional | Medium | 2025-11-28 | Dheeraj | Closed | Requirement Analysis | Glossary of status values missing from requirement template.
RR‑20 | Sahbhagita | GM/PM CR – dependency flow (PIU → Scheme → ISA → Village) not documented for all pages where village dropdown appears. | Requirement Analysis | Functional | High | 2025-11-28 | Dheeraj | Closed | Requirement Analysis | Impacted screens list was not updated when dependency rule was introduced.
BugID: 21648 | Sahbhagita CR | NGO Summary report count logic (Approved/Rejected/No Action) added without data consistency validation | Development | Code Review | High | 2025-11-28 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21649 | Sahbhagita CR | Lack of role-based access validation for approval pages | Development | Code Review | High | 2025-12-08 | Tapan Khandelwal | Closed | Develpomemt
BugID: 21650 | Sahbhagita CR | Village-wise trigger change (Get_VillageForApproval) implemented without documented API validation & regression testing | Development | Code Review | High | 2025-12-10 | Tapan Khandelwal | Closed | Develpomemt