## Sheet1
Ticket Number | Subject | Description | Sub Help Topic | Help Topic | Application | Office | Department | District | Priority | Role | Reference Number | Assigned To | Ticket Due Date | Ticket Created On | Last Updated On | Time to Open/Close | Ticket Creator Mobile | Ticket Creator Email | Status | Attachment 1 | Attachment 2 | Attachment 3 | Attachment 4 | Attachment 5
14081765438276 | Issue: Manpur Bulk Meters Not Displaying in “Bulk Meter Survey” and “Bulk User MWSR” | Under the Manpur MVS, a total of 09 bulk meters have been installed. Out of these 09 bulk meters, only 01 bulk meter (Rijhaunha CWGM Meter) is visible in the Jal Rekha functions “Bulk Meter Survey” and “Bulk User MWSR.” The remaining 08 bulk meters are not appearing. Therefore, kindly resolve this issue so that all bulk meters of the Manpur Scheme become visible in the Jal Rekha functions “Bulk Meter Survey” and “Bulk User MWSR.” | Other | Dhara - Technical | Jal Rekha | Madhya Pradesh Jal Nigam Maryadit | Public Health Engineering Department | Shahdol | High | Vertical | ADITYA SHUKLA - 626340651 | Tapan Khandelwal | 14-12-2025 | 11-12-2025 13:01 | 11-12-2025 13:10 | 2 Months 14 Days 23 Hours 23 Minutes | 9826638523 | rcbcrjg@mapit.gov.in | In progress(Over Due) | Document 1 | Document 2 | NA | NA | NA
14001758110445 | TPIA PIU JHABUA - we are unable to generate the invoice August 2025 | Subject: Request for Resolution of Issue in E-Prabandha for RA Bill of August 2025 Dear Sir, On E-Prabandha, for the RA Bill of August 2025, the TL has already approved the Travel Data, Timesheet, and Office Expense Data. However, we are unable to generate the invoice as the system continues to display the message: “Submit Data, Timesheet, and Office Expense Data.” LOA No.: 5671/716/Proc./MPJNM/2023-2024 Agency: Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. in Association with AIM Consultant PIU: Jhabua Kindly look into the matter and resolve the issue at the earliest. | Other | User Management - Technical | Jal Rekha | Madhya Pradesh Jal Nigam Maryadit | Public Health Engineering Department | Jhabua | High | Vertical |  | Tapan Khandelwal | 20-09-2025 | 17-09-2025 17:30 | 19-09-2025 10:13 | 5 Months 8 Days 18 Hours 54 Minutes | 9755489488 | gmjhabua.jalnigam@mp.gov.in | In progress(Over Due) | NA | NA | NA | NA | NA
14141758097723 | Regarding work plan entry in sopan module | The two OHSRs (1. Jhali and 2. Tidunimutwa) under the Singhaura-2 MVS in Satna district, and one OHT at Pali in Panna district, have been surveyed by the site engineer. However, they are not reflecting on the mapped OHT due to which the contractor is unable to enter the work plan for these structures. | Other | Sopan - Technical | Jal Rekha | Madhya Pradesh Jal Nigam Maryadit | Public Health Engineering Department | Panna | Normal | Vertical |  | Tapan Khandelwal | 20-09-2025 | 17-09-2025 13:58 | 25-09-2025 16:11 | 5 Months 8 Days 22 Hours 26 Minutes | 9165257349 | skrafique@yahoo.co.in | In progress(Over Due) | Document 1 | NA | NA | NA | NA
14061753939137 | Issue in RFI Generation for Hydro Testing in Distribution Network | Dear sir There is an issue while generating RFI (Rewa PIU) for hydro testing in the Distribution Network module. The system currently allows the selection of not more than one pipes, which is not practical for actual site conditions. For example, if we are conducting hydro testing for a stretch of 1,000 meters, the system still restricts us to selecting only a single pipe number, rather than allowing multiple pipe numbers or a continuous length. This limitation creates difficulties in accurately documenting the hydro testing activity over longer stretches and results in the need to generate multiple RFIs for a single hydro testing operation. Request you to kindly look into this issue and make necessary modifications to allow multiple pipe numbers or continuous length selection during RFI generation for hydro testing in the distribution network. | Other | Anushravan - Technical | Jal Rekha | Madhya Pradesh Jal Nigam Maryadit | Public Health Engineering Department | Rewa | Normal | Primary | 1 | Tapan Khandelwal | 03-08-2025 | 31-07-2025 10:48 | 31-07-2025 10:48 | 6 Months 26 Days 1 Hour 35 Minutes | 7974945484 | omgtm@hotmail.com | Assigned(Over Due) | Document 1 | Document 2 | Document 3 | NA | NA