## Status All Module
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Anushravan/Cube/Material | 1. Remove Mandatory in Intake, WTP, MBR, RWPM, & CWPM in dropdown Village and GP | Done ( to be updated in Play store)
|  | 2. Give Save as Draft functionality & Provide option to upload photo later on | In Progress
|  | 3. OHT Search option during RFI | Done
2 | Anusharavan | 1. Include multiple date in report - FE RFI Submission date & Block name also added | Done
3 | Cube | 1. Structure components to be added against each Component | Done
|  | 2. Date of costing for RFI loop 7th and 28th day added | Done ( Mobile to be updated in Play store)
4 | Bharosa | 1. Factory Testing WEB - Add QAP 3rd Party & upload multiple images | Web Done ( Mobile to be updated in Play store)
5 | UI/UX | 1. Change Module sequence on portal | In Progress
6 | Aakalan | 1 Dhara Report complete and release to O&M billing | Done
7 | Asset Mapping | 1. SQC TPIA Contractor Data and Report on Web | Done
8 | User Manual | 1. Send in the group | Done
9 | Dhara | 1. New Dhara Report to be shown on all Jal Rekha logins | Testing Phase

## O&M
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | O&M Billing - Dhara Reports | Dhara report integration in O&M Billing module | Done
2 | GM Side Login | Census population addition in Scheme Master (GM side report) | Done
3 | O&M Billing - Bill | Bill generation for total 64 Schemes
4 | Contractor Side login | Check final summary report | Some Changes Required
5 | Master | scheme village master.. scheme piu village DONE | Done
6 | Master | oht village master | Done
7 | Bulk Consumer | scheme bulk consumer | Done
8 | Bulk Consumer Mapping | Bulk consumer mapping - oht wtp | Done
9 | Mapped Report Status | Of all above 4 reports Mapped in Mapped status report . summary report - vidhan sabha district wise | Done
10 | DWSR Reports | DWSR report development (basic) | Done
11 | Data Validation | Duplicate Village Mapping validation across schemes | Done
12 | Open Platform | Restrict reports: Show only Dhara & DWSR | Done
13 | Open Platform | DWSR column clickable (Hyperlink integration) | Done
14 | Report Optimization | Remove extra reports (Date-wise DWSR, MWSR, UFW, Scheme-wise WSR, Village-wise MWSR, Bulk User MWSR) | Done