## OM Billing
Internal Code Review - O&M Billing
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Recommendation of Review | compliance status | date
1 | CR-OMB-001 | Jal Rekha | O&M Billing | GM O&M Billing - Login & Basic Details | Sunil Thakur | Awinash Khare | 1. Ensure GM login authentication is secure with proper JWT token validation and role-based access control. 2. Verify basic details form captures all required fields (scheme, contractor, agreement value, LOA number) with mandatory validations. 3. Review SLBM parameter configuration and ensure calculations are accurate for billing. 4. Confirm document upload functionality integrates correctly with Dhara and Nirmal modules for fetching scheme data. 5. Validate multi-level review workflow (PIU GM/SQC → O&M GM → PMC → Deputy Manager) with proper status transitions. 6. Test bill generation logic for correctness and ensure all financial calculations follow approved formulas. | Closed | 2025-09-15
2 | CR-OMB-002 | Jal Rekha | O&M Billing | Contractor O&M Billing - CPI Calculations | Sunil Thakur | Awinash Khare | 1. Validate contractor basic and advance details forms with comprehensive field-level validations. 2. Review CPI-based financial calculation engine for accuracy in CPIW increments and yearly adjustments. 3. Confirm PIU/SQC page integration and data flow between contractor and GM workflows. 4. Verify manpower and residual pressure detail capture with proper validation rules. 5. Test bulk user mapping functionality and ensure correct village-to-scheme associations. 6. Review gross bill deduction logic and net payable calculations for compliance with department norms. 7. Validate Dhara water supply data import integration and error handling. 8. Ensure O&M billing for RM and village with management norms is implemented correctly. | Closed | 2025-09-28
3 | CR-OMB-003 | Jal Rekha | O&M Billing | Workflow - GM & Higher Officials | Sunil Thakur | Awinash Khare | 1. Implement complete approval workflow chain: GM → Contractor → CGM → PD → CFO → CA → MD with proper role-based permissions. 2. Verify RA bill data retrieval logic and test data preparation in om_ra_bill table. 3. Review RA bill month progression logic based on scheme and contractor with proper date validations. 4. Test edit and resend functionality allowing PIU GM and Contractor to revise submissions. 5. Ensure approval status tracking is accurate with audit trail for each approval/rejection. 6. Validate notification system for each approval stage and email/SMS alerts to stakeholders. 7. Review database transactions for consistency during workflow state changes. | Closed | 2025-10-05
4 | CR-OMB-004 | Jal Rekha | O&M Billing | Change Request - Enhancements | Sunil Thakur | Awinash Khare | 1. Implement "Save as Draft" functionality for GM with proper data persistence and recovery. 2. Correct census population hierarchy and provide ability to open/edit population data with proper validation. 3. Add "Other" option in SLBM norms and penalty sections with free-text input capability. 4. Update penalty labels as per revised department terminology. 5. Implement CPIW increment calculation changes and yearly computation updates. 6. Review scheme status view enhancements: document eligibility, increment tracking, year-month updates. 7. Add GST service option with proper tax calculation logic. 8. Implement document upload Yes/No toggle with freeze mechanism to prevent unauthorized changes. | Closed | 2025-11-10
5 | CR-OMB-GM-001 | Jal Rekha | O&M Billing | GM Access Control - Kapil Admin | Sunil Thakur | Awinash Khare | 1. Configure Kapil admin user access to view GM 24 PIUs billing data after save and submit. 2. Implement proper role-based access control with read-only permissions for Kapil admin. 3. Ensure data visibility is restricted to submitted bills only, not draft or in-progress records. 4. Test consolidated view of all 24 PIUs with proper filtering and search capabilities. 5. Validate data security and ensure Kapil admin cannot modify or delete GM billing records. | Closed | 2025-11-25
6 | CR-OMB-GM-002 | Jal Rekha | O&M Billing | Role Label Updates | Sunil Thakur | Awinash Khare | 1. Rename all instances of "Kapil ID" label to "GM PIU O&M" across screens and reports. 2. Update database column comments and documentation to reflect new terminology. 3. Review all user interface elements for consistency in role naming. 4. Update API responses and error messages with correct role labels. 5. Ensure reporting modules use updated role terminology in headers and filters. | Closed | 2025-11-25
7 | CR-OMB-GM-003 | Jal Rekha | O&M Billing | Village Mapping Validation | Sunil Thakur | Awinash Khare | 1. Implement unique constraint to prevent duplicate village mappings in GM O&M billing workflow. 2. Add validation at both UI and API levels to check for existing village mappings before save. 3. Provide clear error messages when duplicate mapping attempts are detected. 4. Review existing data for duplicate mappings and provide data cleanup script if needed. 5. Test edge cases including concurrent mapping attempts by different users. | Closed | 2025-11-26
8 | CR-OMB-GM-004 | Jal Rekha | O&M Billing | Master Data Binding | Sunil Thakur | Awinash Khare | 1. Correct GM PIU dropdown binding to show accurate PIU names and codes. 2. Fix contractor name dropdown to display correct contractor details linked to selected scheme. 3. Verify foreign key relationships in database for GM PIU and contractor tables. 4. Test cascading dropdowns and ensure dependent data loads correctly. 5. Review API endpoints for master data retrieval and optimize query performance. | Closed | 2025-11-26
9 | CR-OMB-GM-005 | Jal Rekha | O&M Billing | Financial Data Accuracy | Sunil Thakur | Awinash Khare | 1. Correct Agreement value column label to match department terminology. 2. Fix data source mapping for Agreement value to pull from correct contract table. 3. Verify financial calculations use Agreement value correctly in billing formulas. 4. Test agreement value display across all GM billing forms and reports. 5. Ensure Agreement value is properly validated during data entry and updates. | Closed | 2025-11-27
10 | CR-OMB-GM-006 | Jal Rekha | O&M Billing | Session Management | Sunil Thakur | Awinash Khare | 1. Implement session state persistence for Additional Facilities and critical form fields. 2. Review session storage mechanism and ensure data is preserved across logout/re-login cycles. 3. Test form field recovery after session timeout and automatic re-login. 4. Verify no data loss occurs during network interruptions or browser refresh. 5. Implement client-side caching with server-side validation for data consistency. | Closed | 2025-11-27

## OM Billing Code Review Defect
Internal Code Defects Review - O&M Billing
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Defects | Recommendation of Review | Compliance Status | Date
CYCLE - 2
1 | CR-OM-C2-01 | JAL REKHA | O&M BILLING | Data Entry Module - Save as Draft | SUNIL THAKUR | AWINASH KHARE | Auto-save every 5 minutes is not working consistently; draft data sometimes fails to persist when browser is closed unexpectedly. | Implement localStorage backup with server sync; add recovery mechanism with toast notifications; ensure IndexedDB fallback for large forms. | Closed | 2025-08-15
2 | CR-OM-C2-02 | JAL REKHA | O&M BILLING | Master Data - Census Population | SUNIL THAKUR | AWINASH KHARE | Census population hierarchy shows incorrect village-to-block mapping; editing population data doesn't validate against previous census records. | Correct the hierarchy mapping in database; add validation rules for population editing; implement audit log for population changes. | Closed | 2025-09-05
3 | CR-OM-C2-03 | JAL REKHA | O&M BILLING | Configuration - SLBM Section | SUNIL THAKUR | AWINASH KHARE | "Other" option in Norms and Penalty dropdowns does not allow custom text input; database schema missing custom_value field. | Add custom text field with character limit; update database schema; implement validation for custom entries; add max length validation. | Closed | 2025-09-10
4 | CR-OM-C2-04 | JAL REKHA | O&M BILLING | UI/UX - Penalty Labels | SUNIL THAKUR | AWINASH KHARE | Penalty label changes not reflected consistently across all screens; radio buttons for penalty type not working in mobile view. | Update all UI components with new labels; fix responsive design for radio buttons; ensure consistent terminology across platform. | Closed | 2025-09-12
5 | CR-OM-C2-05 | JAL REKHA | O&M BILLING | Calculation Engine - CPI & Yearly | SUNIL THAKUR | AWINASH KHARE | CPI-W factor dropdown shows incorrect values; yearly calculation formula not applying correctly for leap years. | Fix CPI-W master data; update calculation logic for leap year handling; add test cases for year-end calculations. | Closed | 2025-09-18
6 | CR-OM-C2-06 | JAL REKHA | O&M BILLING | Scheme Master - Status Section | SUNIL THAKUR | AWINASH KHARE | View Document button not opening PDFs in new tab; Eligibility Increment calculation off by 1 month. | Fix document viewer integration; correct increment calculation logic; add date validation for O&M start/end dates. | Closed | 2025-09-20
7 | CR-OM-C2-07 | JAL REKHA | O&M BILLING | Tax Module - GST Services | SUNIL THAKUR | AWINASH KHARE | GST rate dropdown not populating with latest rates; GST amount calculation not handling reverse charge scenarios. | Update GST master data with current rates; implement reverse charge logic; add GST invoice template updates. | Closed | 2025-09-25
8 | CR-OM-C2-08 | JAL REKHA | O&M BILLING | Document Management - Upload Freeze | SUNIL THAKUR | AWINASH KHARE | Screen freeze after document upload not working; users can still edit frozen forms; unfreeze option not visible to admins only. | Implement proper screen freeze logic with disabled fields; add role-based unfreeze permission; improve status indicator visibility. | Closed | 2025-11-05
CYCLE - 3
1 | CR-OMB-GM-001 | JAL REKHA | O&M BILLING | GM Access Control - Kapil Admin | SUNIL THAKUR | AWINASH KHARE | Kapil admin visibility control lacks proper data filtering, exposing draft and in-progress billing records that should only be visible after submission. | Implement strict query-level filtering to restrict Kapil admin access to only submitted billing records with approved status. | Closed | 2025-11-26
2 | CR-OMB-GM-002 | JAL REKHA | O&M BILLING | Role Label Updates | SUNIL THAKUR | AWINASH KHARE | Role label "Kapil ID" still appears in some reports and API responses after rename to "GM PIU O&M". | Update all instances including database comments, API responses, error messages, and report headers with new terminology. | Closed | 2025-11-25
3 | CR-OMB-GM-003 | JAL REKHA | O&M BILLING | Village Mapping Validation | SUNIL THAKUR | AWINASH KHARE | Village mapping validation is only implemented at UI level, allowing duplicate mappings through direct API calls bypassing frontend checks. | Add database-level unique constraint and API-level validation middleware to enforce village mapping uniqueness across all entry points. | Closed | 2025-11-28
4 | CR-OMB-GM-004 | JAL REKHA | O&M BILLING | Master Data Binding | SUNIL THAKUR | AWINASH KHARE | Cascading dropdown dependencies fail when parent selection changes rapidly, causing stale data to persist in child dropdowns and incorrect form submissions. | Implement debounced dropdown loading with proper state management and validation to ensure child dropdowns always reflect current parent selection. | Closed | 2025-11-28
5 | CR-OMB-GM-005 | JAL REKHA | O&M BILLING | Financial Data Accuracy | SUNIL THAKUR | AWINASH KHARE | Agreement value data source mapping references incorrect contract table column, resulting in null or wrong values displayed in billing calculations. | Correct database query to reference proper contract agreement value column and add validation to ensure non-null agreement values before billing. | Closed | 2025-11-29
6 | CR-OMB-GM-006 | JAL REKHA | O&M BILLING | Session Management | SUNIL THAKUR | AWINASH KHARE | Session storage implementation uses browser localStorage which clears on logout, causing complete data loss for Additional Facilities and other critical fields. | Implement server-side session persistence with database-backed storage and implement auto-recovery mechanism for form fields after re-login. | Closed | 2025-11-30
7 | CR-OMB-004 | JAL REKHA | O&M BILLING | GST Calculation | SUNIL THAKUR | AWINASH KHARE | GST calculation logic does not handle reverse charge scenarios and exempt services correctly, leading to incorrect tax amounts in contractor bills. | Enhance GST calculation module to support multiple tax scenarios including reverse charge, exemptions, and nil-rated services with proper configuration. | Closed | 2025-12-02
8 | CR-OMB-C2-08 | JAL REKHA | O&M BILLING | Document Freeze Enhancement | SUNIL THAKUR | AWINASH KHARE | Document freeze mechanism not working for bulk uploads; users can add new documents after freeze in some edge cases. | Enhance freeze logic to lock entire document section; add server-side validation to reject post-freeze uploads. | Closed | 2025-12-05
9 | CR-OMB-C2-05 | JAL REKHA | O&M BILLING | CPI Yearly Calculation | SUNIL THAKUR | AWINASH KHARE | Yearly increment calculation for CPI shows off-by-one error for contracts starting mid-year. | Fix pro-rated calculation logic for partial year; add test cases for mid-year contract starts. | Closed | 2025-12-08
10 | CR-OMB-C2-02 | JAL REKHA | O&M BILLING | Census Hierarchy Performance | SUNIL THAKUR | AWINASH KHARE | Census hierarchy loading slow (8+ seconds) for districts with 5000+ villages. | Implement caching and lazy loading; optimize database queries with indexes; add pagination. | Closed | 2025-12-10