## Sheet1
Data Collection Sheet
Date & Time: May 27, 2026 at 12:53:42 PM
Sr No | Department | Project Name | Module | Name of Sub Modules | CR | Size USP_FP | Planned Effort (Person Hours) | Actual Effort (Person Hours) | Planned Start Date (module) | Planned End Date (module) | Actual Start Date (module) | Actual End Date (module) | Requirement Analysis Start Date (module) | Requirement Analysis End Date (module) | Design Start Date (module) | Design End Date (module) | Coding Start Date (module) | Coding End Date (module) | Testing Start Date (module) | Testing End Date (module) | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Testing Review Efforts | Requirement Review Efforts | Design Review Effort | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Productivity | DRE | Requirement Rate | Design Rate | Code Rate | Testing Rate
1 | Public Health Engineering Department | Jal Rekha | AI Module - FHTC Tap Connection |  | No | 9 | 96 | 69 | 06/05/2026 | 23/05/2026 | 08/05/2026 | 23/05/2026 | 08/05/2026 | 11/05/2026 | 09/05/2026 | 11/05/2026 | 11/05/2026 | 19/05/2026 | 18/05/2026 | 23/05/2026 | 4 | 0 | 60 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 2.25 | 0 | 0.15 | 1.8
2 | Public Health Engineering Department | Jal Rekha | All Public Reports on Dashboard |  | No | 6 | 4 | 4 | 13/05/2026 |  | 13/05/2026 |  | 13/05/2026 | 18/05/2026 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
3 | Public Health Engineering Department | Jal Rekha | Anusharavan |  | No | 0 | 630 | 0 | 01/02/2024 | 15/03/2024 | 01/02/2024 | 19/03/2024 | 01/02/2024 | 09/02/2024 | 10/02/2026 | 11/02/2026 | 12/02/2024 | 08/03/2024 | 11/03/2024 | 19/03/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
4 | Public Health Engineering Department | Jal Rekha | Anusharavan CR |  | Yes | 0 | 39 | 20 | 08/11/2025 | 20/11/2025 | 11/11/2025 | 20/11/2025 | 11/11/2025 | 12/11/2025 | 12/11/2025 | 13/11/2025 | 14/11/2025 | 17/11/2025 | 18/11/2025 | 20/11/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Public Health Engineering Department | Jal Rekha | Asset Mapping |  | No | 0 | 987 | 0 | 01/01/2024 | 26/01/2024 | 01/01/2024 | 26/01/2024 | 01/01/2024 | 02/01/2024 | 02/01/2024 | 03/01/2024 | 03/01/2024 | 19/01/2024 | 22/01/2024 | 26/01/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Mobile |  | Yes | 8 | 25 | 25 | 18/11/2025 | 05/12/2025 | 19/11/2025 | 05/12/2025 | 19/11/2025 | 20/11/2025 | 21/11/2025 | 23/11/2025 | 24/11/2025 | 30/11/2025 | 01/12/2025 | 05/12/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0 | 0 | 0 | 0.33 | 0
7 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Web |  | Yes | 3 | 28 | 24 | 01/11/2025 | 25/11/2025 | 03/11/2025 | 25/11/2025 | 03/11/2025 | 06/11/2025 | 06/11/2025 | 09/11/2025 | 10/11/2025 | 20/11/2025 | 21/11/2025 | 25/11/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
8 | Public Health Engineering Department | Jal Rekha | Bharosa CR Report View |  | Yes | 0 | 0 | 0 | 07/12/2025 | 14/12/2025 | 10/12/2025 | 14/12/2025 | 10/12/2025 | 11/12/2025 | 11/12/2025 | 12/12/2025 | 12/12/2025 | 13/12/2025 | 13/12/2025 | 14/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web |  | No | 5 | 637 | 9 | 09/10/2025 | 16/10/2025 | 10/10/2025 | 16/10/2025 | 10/10/2025 | 11/10/2025 | 11/10/2025 | 12/10/2025 | 13/10/2025 | 15/10/2025 | 15/10/2025 | 16/10/2025 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0 | 0.56 | 1 | 1.25 | 0 | 0 | 0
10 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing Mobile |  | No | 0 | 0 | 0 | 20/10/2025 | 30/10/2025 | 22/10/2025 | 30/10/2025 | 22/10/2025 | 23/10/2025 | 24/10/2025 | 25/10/2025 | 25/10/2025 | 28/10/2025 | 28/10/2025 | 30/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Public Health Engineering Department | Jal Rekha | CMMI Documents |  | No | 5 | 845 | 121 | 02/12/2025 |  | 04/12/2025 |  | 04/12/2025 | 06/12/2025 | 07/12/2025 | 09/12/2025 |  |  |  |  | 107 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0.05 | 0 | 0.36 | 0
12 | Public Health Engineering Department | Jal Rekha | CMMI Statistical Analysis |  | No | 0 | 0 | 0 | 31/01/2026 |  | 01/02/2026 |  | 01/02/2026 | 02/02/2026 | 03/02/2026 | 04/02/2026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor |  | No | 3 | 68 | 52 | 23/03/2026 | 05/04/2026 | 23/03/2026 | 04/04/2026 | 23/03/2026 | 25/03/2026 | 26/03/2026 | 28/03/2026 | 29/03/2026 | 01/04/2026 | 02/04/2026 | 04/04/2026 | 8 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0.06 | 0 | 0.38 | 0 | 0.07 | 0
14 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE |  | No | 8 | 132 | 102 | 09/03/2026 | [11 empty] | 8 | 0 | 62 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.08 | 0 | 1 | 0 | 0.12 | 0
15 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM |  | No | 0 | 54 | 40 | 30/03/2026 | 10/04/2026 | 31/03/2026 | 09/04/2026 | 31/03/2026 | 03/04/2026 | 03/04/2026 | 05/04/2026 | 06/04/2026 | 09/04/2026 | 08/04/2026 | 09/04/2026 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA |  | No | 3 | 47 | 12 | 31/03/2026 | 07/04/2026 | 02/04/2026 | 07/04/2026 | 02/04/2026 | 03/04/2026 | 03/04/2026 | 04/04/2026 | 04/04/2026 | 06/04/2026 | 06/04/2026 | 07/04/2026 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0
17 | Public Health Engineering Department | Jal Rekha | Cube Testing CR |  | Yes | 6 | 70 | 66 | 27/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 2 | 0 | 56 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09 | 0 | 3 | 0 | 0.11 | 0.75
18 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement |  | No | 0 | 200 | 34 | 23/12/2025 |  | 24/12/2025 |  | 24/12/2025 | 25/12/2025 | 26/12/2025 | 27/12/2025 | 28/12/2025 |  |  |  | 12 | 0 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Public Health Engineering Department | Jal Rekha | Daily Inspection |  | No | 0 | 104 | 0 | 25/12/2023 | 16/02/2024 | 25/12/2023 | 16/02/2024 | 25/12/2023 | 05/01/2024 |  |  | 08/02/2024 | 13/02/2024 | 14/02/2024 | 16/02/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Public Health Engineering Department | Jal Rekha | Dashboard |  | No | 3 | 327 | 24 | 28/03/2024 | 08/04/2024 | 01/04/2024 | 08/04/2024 | 01/04/2024 | 01/04/2024 |  |  | 02/04/2024 | 06/04/2024 | 08/04/2024 | 08/04/2024 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0.38 | 0 | 0.19 | 0
21 | Public Health Engineering Department | Jal Rekha | Data Visualization |  | No | 0 | 0 | 0 | 05/01/2024 | 31/01/2024 | 06/01/2024 | 31/01/2024 | 06/01/2024 | 07/01/2024 | 09/01/2024 | 12/01/2024 | 15/01/2024 | 25/01/2024 | 26/01/2024 | 31/01/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Public Health Engineering Department | Jal Rekha | Department Meetings |  | No | 13 | 78 | 58 | [12 empty] | 38 | 0 | 16 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22 | 0 | 0.31 | 0 | 0.65 | 0
23 | Public Health Engineering Department | Jal Rekha | Dhara |  | No | 0 | 2633 | 0 | 20/09/2024 | 16/10/2024 | 20/09/2024 | 16/10/2024 | 20/09/2024 | 22/09/2024 | 22/09/2024 | 24/09/2024 | 25/09/2024 | 11/10/2024 | 14/10/2024 | 16/10/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 6 | 0 | 0.4 | 0 | 0 | 0 | 0
24 | Public Health Engineering Department | Jal Rekha | Dhara Admin |  | No | 0 | 0 | 0 | 11/02/2025 | 03/03/2025 | 11/02/2025 | 03/03/2025 | 11/02/2025 | 15/02/2025 | 18/02/2025 | 18/02/2025 | 19/02/2025 | 26/02/2025 | 27/02/2025 | 03/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - Admin / Contractor Report View |  | Yes | 0 | 0 | 0 | 01/09/2025 | 25/09/2025 | 01/09/2025 | 25/09/2025 | 01/09/2025 | 03/09/2025 | 04/09/2025 | 06/09/2025 | 09/09/2025 | 18/09/2025 | 20/09/2025 | 25/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - FE / Mobile User |  | Yes | 0 | 0 | 0 | 12/08/2025 | 24/08/2025 | 13/08/2025 | 24/08/2025 | 13/08/2025 | 16/08/2025 | 15/08/2025 | 18/08/2025 | 18/08/2025 | 24/08/2025 | 24/08/2025 | 24/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - GM PIU User/ TL |  | Yes | 6 | 73 | 73 | 01/07/2025 | 12/08/2025 | 03/07/2025 | 12/08/2025 | 03/07/2025 | 11/07/2025 | 12/07/2025 | 18/07/2025 | 22/07/2025 | 04/08/2025 | 01/08/2025 | 12/08/2025 | 17 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0.35 | 0 | 0.11 | 0
28 | Public Health Engineering Department | Jal Rekha | Dhara Change Request Reports |  | Yes | 3 | 22 | 22 | 08/11/2025 | 14/11/2025 | 08/11/2025 | 13/11/2025 | 08/11/2025 | 09/11/2025 | 09/11/2025 | 10/11/2025 | 10/11/2025 | 12/11/2025 | 12/11/2025 | 13/11/2025 | 6 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 0 | 0.5 | 0 | 0.19 | 0
29 | Public Health Engineering Department | Jal Rekha | Dhara Contractor Report View |  | No | 0 | 0 | 0 | 06/03/2025 | 08/06/2025 | 04/06/2025 | 08/06/2025 | 04/06/2025 | 04/06/2025 | 04/06/2025 | 04/06/2025 | 05/06/2025 | 06/06/2025 | 07/06/2025 | 08/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Public Health Engineering Department | Jal Rekha | Dhara CR - Reports (MWSR,DWSR, UFW) |  | Yes | 6 | 157 | 133 | 12/03/2026 | 26/03/2026 | 13/03/2026 | 24/03/2026 | 13/03/2026 | 16/03/2026 | 16/03/2026 | 19/03/2026 | 19/03/2026 | 22/03/2026 | 22/03/2026 | 24/03/2026 | 18 | 0 | 107 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0.33 | 0 | 0.05 | 0
31 | Public Health Engineering Department | Jal Rekha | Dhara FE / Mobile User |  | No | 0 | 0 | 0 | 15/02/2025 | 15/04/2025 | 16/02/2025 | 15/04/2025 | 16/02/2025 | 23/02/2025 | 27/02/2025 | 03/03/2025 | 04/03/2025 | 05/04/2025 | 06/04/2025 | 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Public Health Engineering Department | Jal Rekha | Dhara GM PIU User |  | No | 0 | 0 | 0 | 15/02/2025 | 15/04/2025 | 16/02/2025 | 15/04/2025 | 16/02/2025 | 23/02/2025 | 27/02/2025 | 03/03/2025 | 04/03/2025 | 05/04/2025 | 06/04/2025 | 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Public Health Engineering Department | Jal Rekha | Dhara GM PIU User Change request |  | Yes | 6 | 26 | 18 | 08/05/2025 | 27/05/2025 | 10/05/2025 | 27/05/2025 | 10/05/2025 | 11/05/2025 | 11/05/2025 | 13/05/2025 | 14/05/2025 | 24/05/2025 | 24/05/2025 | 27/05/2025 | 4 | 0 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 1.5 | 0 | 0.43 | 0
34 | Public Health Engineering Department | Jal Rekha | Dhara Security |  | No | 0 | 0 | 0 | 07/12/2025 | 18/12/2025 | 10/12/2025 | 18/12/2025 | 10/12/2025 | 11/12/2025 | 11/12/2025 | 12/11/2025 | 13/12/2025 | 16/12/2025 | 16/12/2025 | 18/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Public Health Engineering Department | Jal Rekha | Dhara TL |  | No | 0 | 0 | 0 | 20/03/2025 | 05/04/2025 | 21/03/2025 | 05/04/2025 | 21/03/2025 | 22/03/2025 | 23/03/2025 | 24/03/2025 | 25/03/2025 | 02/04/2025 | 03/04/2025 | 05/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Public Health Engineering Department | Jal Rekha | Dhara TL Change request |  | No | 0 | 0 | 0 | 04/06/2025 | 12/04/2025 | 07/04/2025 | 12/04/2025 | 07/04/2025 | 08/04/2025 | 08/04/2025 | 09/04/2025 | 08/04/2025 | 10/04/2025 | 11/04/2025 | 12/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports |  | No | 0 | 547 | 0 | 18/08/2025 | 27/09/2025 | 18/08/2025 | 26/09/2025 | 18/08/2025 | 22/08/2025 | 23/08/2025 | 26/08/2025 | 29/08/2025 | 13/09/2025 | 19/09/2025 | 26/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0.67 | 0 | 0 | 0 | 0
38 | Public Health Engineering Department | Jal Rekha | FHTC Change request FHTC |  | Yes | 9 | 237 | 237 | 13/10/2025 | 29/10/2025 | 14/10/2025 | 29/10/2025 | 14/10/2025 | 16/10/2025 | 16/10/2025 | 18/10/2025 | 19/10/2025 | 24/10/2025 | 26/10/2025 | 29/10/2025 | 1 | 0 | 212 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0.04 | 0 | 9 | 0 | 0.04 | 0.38
39 | Public Health Engineering Department | Jal Rekha | FHTC CR FE Reports |  | Yes | 0 | 0 | 0 | 01/12/2025 | 09/12/2025 | 03/12/2025 | 09/12/2025 | 03/12/2025 | 04/12/2025 | 04/12/2025 | 05/12/2025 | 05/12/2025 | 07/12/2025 | 07/12/2025 | 09/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Public Health Engineering Department | Jal Rekha | FHTC GM / Contractor Reports |  | Yes | 3 | 8 | 8 | 02/11/2025 | 14/11/2025 | 04/11/2025 | 14/11/2025 | 04/11/2025 | 05/11/2025 | 05/11/2025 | 06/11/2025 | 06/11/2025 | 11/11/2025 | 12/11/2025 | 14/11/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
41 | Public Health Engineering Department | Jal Rekha | Master All Web Reports |  | No | 0 | 0 | 0 | 15/03/2025 | 28/03/2025 | 15/03/2025 | 28/03/2025 | 15/03/2025 | 16/03/2025 | 16/03/2025 | 17/03/2025 | 17/03/2025 | 26/03/2025 | 26/03/2025 | 28/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Public Health Engineering Department | Jal Rekha | Master Change Request - FE Pipeline Mater |  | Yes | 0 | 0 | 0 | 04/08/2025 | 13/08/2025 | 05/08/2025 | 13/08/2025 | 05/08/2025 | 06/08/2025 | 06/08/2025 | 07/08/2025 | 08/08/2025 | 12/08/2025 | 12/08/2025 | 13/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Public Health Engineering Department | Jal Rekha | Master Change Request - GM / Contractor |  | Yes | 3 | 0 | 0 | 01/07/2025 | 19/07/2025 | 01/07/2025 | 19/07/2025 | 01/07/2025 | 04/07/2025 | 05/07/2025 | 07/07/2025 | 07/07/2025 | 15/07/2025 | 15/07/2025 | 19/07/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema |  | Yes | 6 | 74 | 73.5 | 18/03/2026 | 25/03/2026 | 18/03/2026 | 25/03/2026 | 18/03/2026 | 19/03/2026 | 18/03/2026 | 19/03/2026 | 19/03/2026 | 23/03/2026 | 24/03/2026 | 25/03/2026 | 8 | 0 | 65.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0.75 | 0 | 0.09 | 0
45 | Public Health Engineering Department | Jal Rekha | Master Contractor |  | No | 0 | 0 | 0 | 03/11/2025 | 31/03/2025 | 11/03/2025 | 31/03/2025 | 11/03/2025 | 12/03/2025 | 13/03/2025 | 14/03/2025 | 15/03/2025 | 25/03/2025 | 26/03/2025 | 31/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Public Health Engineering Department | Jal Rekha | Master CR - Scheme Village & OHT Master |  | Yes | 3 | 140 | 140 | 11/03/2026 | 19/03/2026 | 11/03/2026 | 19/03/2026 | 11/03/2026 | 12/03/2026 | 12/03/2026 | 13/03/2026 | 13/03/2026 | 16/03/2026 | 17/03/2026 | 19/03/2026 | 10 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0.3 | 0 | 0.02 | 0
47 | Public Health Engineering Department | Jal Rekha | Master FE Mobile |  | No | 0 | 0 | 0 | 04/10/2025 | 12/04/2025 | 10/04/2025 | 12/04/2025 | 10/04/2025 | 11/04/2025 | 10/04/2025 | 11/04/2025 | 11/04/2025 | 12/04/2025 | 12/04/2025 | 12/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Public Health Engineering Department | Jal Rekha | Master GM |  | No | 0 | 941 | 0 | 15/02/2025 | 08/03/2025 | 18/02/2025 | 08/03/2025 | 18/02/2025 | 20/02/2025 | 20/02/2025 | 21/02/2025 | 22/02/2025 | 05/03/2025 | 06/03/2025 | 08/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 0.67 | 0 | 0 | 0 | 0
49 | Public Health Engineering Department | Jal Rekha | Material Testing - FE Login |  | No | 0 | 30 | 0 | 17/12/2025 | 31/12/2025 | 19/12/2025 | 31/12/2025 | 19/12/2025 | 21/12/2025 | 21/12/2025 | 23/12/2025 | 23/12/2025 | 28/12/2025 | 28/12/2025 | 31/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login |  | No | 13 | 583 | 16 | 08/12/2025 | 30/12/2025 | 12/12/2025 | 30/12/2025 | 12/12/2025 | 15/12/2025 | 15/12/2025 | 17/12/2025 | 17/12/2025 | 25/12/2025 | 26/12/2025 | 30/12/2025 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0.81 | 0.5 | 0.81 | 0 | 0 | 0
51 | Public Health Engineering Department | Jal Rekha | NIrmal - Change Request - Raw water Report |  | Yes | 0 | 0 | 0 | 03/12/2025 | 14/12/2025 | 05/12/2025 | 14/12/2025 | 05/12/2025 | 06/12/2025 | 06/12/2025 | 08/12/2025 | 08/12/2025 | 12/12/2025 | 12/12/2025 | 14/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | Public Health Engineering Department | Jal Rekha | NIrmal - Change request - WTP, OHT, Beneficiary Report |  | Yes | 0 | 0 | 0 | 03/11/2025 | 27/11/2025 | 05/11/2025 | 27/11/2025 | 05/11/2025 | 07/11/2025 | 08/11/2025 | 10/11/2025 | 11/11/2025 | 22/11/2025 | 23/11/2025 | 27/11/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Public Health Engineering Department | Jal Rekha | Nirmal Change request |  | Yes | 0 | 0 | 0 | 13/05/2025 | 26/05/2025 | 13/05/2025 | 26/05/2025 | 13/05/2025 | 14/05/2025 | 15/05/2025 | 16/05/2025 | 17/05/2025 | 23/05/2025 | 24/05/2025 | 26/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Public Health Engineering Department | Jal Rekha | Nirmal Change Request - Beneficiary Report |  | Yes | 3 | 20 | 20 | 01/09/2025 | 08/09/2025 | 03/09/2025 | 08/09/2025 | 03/09/2025 | 04/09/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 07/09/2025 | 07/09/2025 | 08/09/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0
55 | Public Health Engineering Department | Jal Rekha | Nirmal Change request - WTP, OHT Report |  | Yes | 0 | 0 | 0 | 08/07/2025 | 14/07/2025 | 09/07/2025 | 14/07/2025 | 09/07/2025 | 10/07/2025 | 10/07/2025 | 11/07/2025 | 11/07/2025 | 14/07/2025 | 12/07/2025 | 14/07/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | Public Health Engineering Department | Jal Rekha | Nirmal Contractor Login |  | No | 0 | 0 | 0 | 04/02/2025 | 26/04/2025 | 02/04/2025 | 26/04/2025 | 02/04/2025 | 03/04/2025 | 04/04/2025 | 07/04/2025 | 08/04/2025 | 18/04/2025 | 19/04/2025 | 26/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile |  | No | 0 | 1243 | 0 | 28/02/2025 | 15/04/2025 | 28/02/2025 | 15/04/2025 | 28/02/2025 | 07/03/2025 | 07/03/2025 | 12/03/2025 | 14/03/2025 | 05/04/2025 | 06/04/2025 | 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5 | 0 | 0.5 | 0 | 0 | 0 | 0
58 | Public Health Engineering Department | Jal Rekha | Nirmal GM |  | No | 3 | 8 | 8 | 15/04/2025 | 21/04/2025 | 15/04/2025 | 21/04/2025 | 15/04/2025 | 15/04/2025 | 16/04/2025 | 16/04/2025 | 17/04/2025 | 19/04/2025 | 19/04/2025 | 21/04/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
59 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change request GM |  | Yes | 6 | 51 | 34 | 02/11/2025 | 22/11/2025 | 06/11/2025 | 22/11/2025 | 06/11/2025 | 08/11/2025 | 08/11/2025 | 10/11/2025 | 13/11/2025 | 19/11/2025 | 20/11/2025 | 22/11/2025 | 8 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0.75 | 0 | 0.23 | 0
60 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor |  | Yes | 28 | 259 | 249 | 27/11/2025 | 02/01/2026 | 01/12/2025 | 02/01/2026 | 01/12/2025 | 04/12/2025 | 04/12/2025 | 07/12/2025 | 10/12/2025 | 24/12/2025 | 26/12/2025 | 02/01/2026 | 18 | 16 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0 | 1.56 | 1.75 | 0.13 | 0
61 | Public Health Engineering Department | Jal Rekha | O&M Billing Change request O&M Billing |  | Yes | 0 | 0 | 0 | 29/09/2025 | 31/10/2025 | 29/09/2025 | 31/10/2025 | 29/09/2025 | 03/10/2025 | 04/10/2025 | 08/10/2025 | 09/10/2025 | 21/10/2025 | 24/10/2025 | 31/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | Public Health Engineering Department | Jal Rekha | O&M Billing Contractor |  | No | 0 | 0 | 0 | 01/09/2025 | 19/09/2025 | 01/09/2025 | 19/09/2025 | 01/09/2025 | 03/09/2025 | 04/09/2025 | 06/09/2025 | 06/09/2025 | 14/09/2025 | 14/09/2025 | 19/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | Public Health Engineering Department | Jal Rekha | O&M Billing GM |  | No | 10 | 2022 | 48 | 28/07/2025 | 29/08/2025 | 28/07/2025 | 29/08/2025 | 28/07/2025 | 03/08/2025 | 04/08/2025 | 07/08/2025 | 07/08/2025 | 21/08/2025 | 22/08/2025 | 29/08/2025 | 30 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 4 | 0 | 0.21 | 1 | 0.33 | 0 | 0.56 | 0
64 | Public Health Engineering Department | Jal Rekha | O&M Billing Security |  | No | 0 | 0 | 0 | 09/12/2025 | 14/12/2025 | 10/12/2011 | 14/12/2025 | 10/12/2011 | 11/12/2025 | 11/12/2025 | 12/12/2025 | 12/12/2025 | 13/12/2025 | 13/10/2025 | 14/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | Public Health Engineering Department | Jal Rekha | O&M Billing Workflow b/w O&M GM & Higher officials |  | No | 5 | 27 | 27 | 20/09/2025 | 29/09/2025 | 21/09/2025 | 29/09/2025 | 21/09/2025 | 22/09/2025 | 22/09/2025 | 23/09/2025 | 23/09/2025 | 26/09/2025 | 26/09/2025 | 29/09/2025 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0.19 | 0 | 0 | 0
66 | Public Health Engineering Department | Jal Rekha | Sahbhagita |  | No | 0 | 0 | 0 | 08/09/2025 | 16/09/2025 | 08/09/2025 | 16/09/2025 | 08/09/2025 | 09/09/2025 | 10/09/2025 | 11/09/2025 | 13/09/2025 | 15/09/2025 | 15/09/2025 | 16/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request |  | Yes | 3 | 23 | 23 | 11/05/2026 | 14/05/2026 | 12/05/2026 | 14/05/2026 | 12/05/2026 | 12/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
68 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request -GM / PM |  | Yes | 0 | 0 | 0 | 15/10/2025 | 22/10/2025 | 15/10/2025 | 22/10/2025 | 15/10/2025 | 16/10/2025 | 17/10/2025 | 18/10/2025 | 19/10/2025 | 21/10/2025 | 20/10/2025 | 22/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request -GM / PM / Reports |  | Yes | 3 | 22 | 22 | 02/12/2025 | 11/12/2025 | 04/12/2025 | 11/12/2025 | 04/12/2025 | 05/12/2025 | 05/12/2025 | 06/12/2025 | 06/12/2025 | 09/12/2025 | 09/12/2025 | 11/12/2025 | 2 | 0 | 16 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 0 | 1.5 | 0 | 0.19 | 0.75
70 | Public Health Engineering Department | Jal Rekha | Sahbhagita FE |  | No | 0 | 0 | 0 | 15/06/2025 | 27/06/2025 | 17/06/2025 | 27/06/2025 | 17/06/2025 | 17/06/2025 | 18/06/2025 | 19/06/2025 | 20/06/2025 | 25/06/2025 | 26/06/2025 | 27/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM |  | No | 0 | 298 | 0 | 19/06/2025 | 23/06/2025 | 17/06/2025 | 23/06/2025 | 17/06/2025 | 18/06/2025 | 18/06/2025 | 19/06/2025 | 19/06/2025 | 22/06/2025 | 23/06/2025 | 23/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 3 | 0 | 0.25 | 0 | 0 | 0 | 0
72 | Public Health Engineering Department | Jal Rekha | Sahbhagita PM |  | No | 0 | 0 | 0 | 22/06/2025 | 24/06/2025 | 22/06/2025 | 24/06/2025 | 22/06/2025 | 22/06/2025 | 22/06/2025 | 22/06/2025 | 24/06/2025 | 24/06/2025 | 24/06/2025 | 24/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Public Health Engineering Department | Jal Rekha | Sahbhagita Report |  | No | 0 | 6 | 0 | 19/11/2025 | 01/12/2025 | 22/11/2025 | 01/12/2025 | 22/11/2025 | 23/11/2025 | 23/11/2025 | 24/11/2025 | 25/11/2025 | 28/11/2025 | 28/11/2025 | 01/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | Public Health Engineering Department | Jal Rekha | Site Security Audit |  | No | 3 | 16 | 16 | 27/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0.19 | 0
75 | Public Health Engineering Department | Jal Rekha | Sopan All Web User |  | No | 0 | 0 | 0 | 28/05/2025 | 28/06/2025 | 05/06/2025 | 28/06/2025 | 05/06/2025 | 07/06/2025 | 08/06/2025 | 10/06/2025 | 11/06/2025 | 22/06/2025 | 23/06/2025 | 28/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | Public Health Engineering Department | Jal Rekha | Sopan Change Request - Contractor (Web / Mobile) |  | Yes | 0 | 0 | 0 | 01/07/2025 | 04/08/2025 | 01/07/2025 | 04/08/2025 | 01/07/2025 | 05/07/2025 | 06/07/2025 | 11/07/2025 | 12/07/2025 | 26/07/2025 | 26/07/2025 | 04/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | Public Health Engineering Department | Jal Rekha | Sopan Change Request - GM Document Upload & Reports |  | Yes | 0 | 0 | 0 | 11/08/2025 | 07/09/2025 | 12/08/2025 | 07/09/2025 | 12/08/2025 | 13/08/2025 | 12/08/2025 | 14/08/2025 | 20/08/2025 | 29/08/2025 | 03/09/2025 | 07/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Public Health Engineering Department | Jal Rekha | Sopan Contractor |  | No | 0 | 1612 | 0 | 25/03/2025 | 30/04/2025 | 28/03/2025 | 30/04/2025 | 28/03/2025 | 31/03/2025 | 01/04/2025 | 04/04/2025 | 05/04/2025 | 22/04/2025 | 23/04/2025 | 30/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 2 | 0 | 0.33 | 0 | 0 | 0 | 0
79 | Public Health Engineering Department | Jal Rekha | Sopan GM |  | No | 0 | 0 | 0 | 04/05/2025 | 10/05/2025 | 07/04/2025 | 10/05/2025 | 07/04/2025 | 10/04/2025 | 11/04/2025 | 14/04/2025 | 15/04/2025 | 03/05/2025 | 04/05/2025 | 10/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | Public Health Engineering Department | Jal Rekha | Sopan Sopan Document Upload & Chat |  | No | 0 | 0 | 0 | 05/01/2025 | 16/05/2025 | 02/05/2025 | 16/05/2025 | 02/05/2025 | 03/05/2025 | 03/05/2025 | 04/05/2025 | 04/05/2025 | 12/05/2025 | 13/05/2025 | 16/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring |  | No | 13 | 68 | 61 | 07/05/2026 |  | 11/05/2026 |  | 11/05/2026 | 14/05/2026 | 18/05/2026 | 20/05/2026 | 19/05/2026 | 22/05/2026 |  |  | 21 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0.62 | 0 | 0.33 | 0
82 | Public Health Engineering Department | Jal Rekha | User & Role Management |  | No | 0 | 10 | 0 | 20/11/2024 | 26/12/2024 | 21/11/2024 | 26/12/2024 | 21/11/2024 | 25/11/2024 | 27/11/2024 | 30/11/2024 | 02/12/2024 | 20/12/2024 | 23/12/2024 | 26/12/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0