## Sheet2
Problem Statement | Source of Problem | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Correction (immidiate Fix) | Corrective Action (Preventive actions) | Responsibility | Action Items
Productivity was impacted because FE workflow was showing only partial data of pipelin, later on we added OHT Name also. | Requirement and master data gap during FE workflow implementation | Beacause the OHT name was not available in Master Data | In pipeline data master till distribution, for each OHT was mapped under a scheme but the FE was not able to view the pipe number mapping for distribution. | Because the data of pipeline components(CWPM, CWGM, Distribution and RWPM) was not available in softcopy |  |  | An option was provided to the contractor to upload pipeline component data through the web application, and the OHT name was added to the FE workflow display. |  | Development Team, Business Team, QA/Testing Team | 1. Update master data review checklist for FE modules. 2. Review and correct similar terminology issues in other reused modules. 3. Add validation in FE UI to ensure OHT-related data is always displayed. 4. Update documentation and test cases to include OHT visibility checks.
Productivity and testing was impacted because in GM mapping of schemes to PM(ISA) is already done but just to showcase the ISA multiple scheme reportview in PM(ISA) login we have to recheck and retest. | Client | Because proper mapping of ISA was not finalized at the PIU level. | Because the ISA–scheme list was not finalized at the PIU level during initial implementation | Because in some schemes, the GM PIU was changed |  |  |  |  | Development Team, Business Team, QA/Testing Team
We have to recorrect the backdate of Sahbhagita old activity and therefore we have to change the code logic in mobile apk(FE Login). | Client | Because we received the req for only 6 months data upload for old activity FE login | Beacause The department has also received data from the past six months. So that the FE can also upload older activities. | [5 empty] | Development Team, Business Team, QA/Testing Team
Test cycle time increased for the Nirmal module during Contractor testing | Process / Functional Complexity | Because the tester had to validate the Nirmal module across multiple roles: GM, Contractor, and FE | Because each role had different workflows and validations to be tested separately | Because Contractor workflows depend on field activities, lab test updates, and final report submission | Because testing also required validation across multiple components such as Intake, WTP, OHT, and Beneficiary | Because the same scenarios had to be verified across multiple schemes with geofencing enabled | Test execution was planned role-wise and scheme-wise to reduce rework and confusion | Early test involvement during requirement finalization to identify test scope upfront | Business Analyst, QA Lead,dev | Add test-impact analysis during requirement sign-off
Code review took longer than planned because the same business logic was implemented and reviewed separately for web and mobile, with additional dependency on API integration and offline sync handling | Lack of early design standardization and reuse planning for web and mobile implementations, resulting in duplicate logic and increased review effort. | Because the reviewer had to check separate codebases for web and mobile for the same features such as login, validations, messages, API calls, and offline sync. | Because the same business logic was written independently in web and mobile instead of reusing common standards or shared logic. | Because during design and requirement discussion, cross-platform impact and reuse strategy were not planned, and delivery was prioritized over standardization. |  |  | Focused the review on critical areas first (API integration, offline sync, role-based access, exception handling) and aligned validations and messages manually to complete review on time | Define common coding standards for web and mobile Create shared API contracts and validation rules Perform design review for web + mobile together Use a single code review checklist for both platforms | Development Team, Technical Lead, | Prepare shared validation and message guideline Identify reusable components before development Add “cross-platform impact” checkpoint in design review Update code review checklist for offline sync and API dependency