## Sheet1
Problem Statement | Source of Problem | Why 1 | Why 2 | Why 3 | Correction (immidiate Fix) | Corrective Action (Preventive actions) | Responsibility | Action Items | Target Date | Actual Status | Closure Date | Remarks
Coding activities exceeded the planned timeline due to frequent change requests from the client and the additional effort required to implement SonarQube for improving code quality and structure. | Frequent change requests and previously unstructured codebase. | The billing module falls under Maintenance & Operations for multiple schemes, resulting in continuous updates from the department based on scheme-specific requirements. | Each scheme introduced multiple functional scenarios, increasing development complexity and requiring repeated modifications to the existing code. | Lack of a structured change management process and absence of predefined coding standards led to rework, refactoring efforts, and extended development time.