KEY PERFORMANCE INDICATOR

## Jal Nigam, M.P.

Version 1.0

PREPARED BY – Mr. Ankur Shrivastava

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

Revision History

| Date | Version | Description | Prepared by | Reviewed or approved by |
| --- | --- | --- | --- | --- |
|  | 1.0 | First Baseline Version | Mr. Ankur Shrivastava | Mr. Tapan Khandelwal |

Contents

1.	Introduction	4

2.	Scope	4

3.	Intent	4

4.	Value	4

5.	Glossary of terms	5

6.	Entry criteria	5

7.	Inputs	5

8.	Process	5

ESTABLISH ORGANIZATIONAL MISSION, VISION AND STRATEGIC PLANS	5

PROVISION OF NECESSARY RESOURCES AND INFRASTRUCTURE	6

DEFINE PERFORMANCE MANAGEMENT & GOVERNANCE FRAMEWORK	6

9.	COMMUNICATE RESULTS	7

10.	Exit criteria	7

11.	Output(s)	7

12.	Templates	7

# Introduction

The KPI Dashboard for the Jal Rekha Project provides a consolidated view of project performance by tracking planned versus actual progress across all phases. It enables stakeholders to measure implementation efficiency, monitor delays, identify risks, and take corrective actions to ensure timely and successful delivery. This document standardizes the monitoring and reporting process, ensuring transparency, data-driven decisions, and alignment with departmental objectives.

# Scope

This document defines, monitors, and reports Key Performance Indicators (KPIs) related to the Jal Rekha Project. It covers all critical phases, including:

- Requirement gathering and sign-off

- System design and architecture

- Module development (Dhara, Anushravan, Reports, Dashboard)

- Mobile application development

- Testing, UAT, and deployment

- Training and adoption

- Post-Go-Live performance monitoring

The KPI dashboard provides real-time, actionable insights to management and field teams, enabling faster decision-making.

# Intent

The intent of the Jal Rekha KPI Dashboard is to:

- Monitor project performance against approved baselines.

- Identify risks and variances in early stages.

- Provide transparent progress reporting to all stakeholders.

- Support evidence-based decision-making and process optimization.

# Value

- For Management → Clear visibility into project timelines, resource utilization, and overall performance.

- For Project Teams → Identification of bottlenecks, delays, and optimization opportunities.

- For Stakeholders → Assurance of accountability, transparency, and efficient governance.

Key measures

| Sr. No. | KPI | Planned | Actual | Variance | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Requirement Sign-off (FRS) | 1 Month | 1.1 Months | 0.1 | Delay due to additional data dependencies from PIUs |
| 2 | System Design & Architecture | 1 Month | 1 Month | 0 | Completed on time |
| 3 | Module Development (All Module mentioned in Scope) | 4 Months | 4.5 Months | 0.5 | Additional mapping logic caused minor delays |
| 4 | Dashboard & Reports Development | 2 Months | 2.2 Months | 0.2 | Optimization for faster data rendering |
| 5 | Mobile Application Development | 3 Months | 3.3 Months | 0.3 | Offline RFI syncing caused testing delays |
| 6 | Testing & UAT | 2 Months | 2.5 Months | 0.5 | Extended UAT due to field validation of RFI data |
| 7 | Go-Live | Month 9 | Month 9.1 | 0.1 | Minor delay in final PIU training |
| 8 | Budget Utilization | 100% | 104% | 4% | Extra resources needed for GIS integration |
| 9 | SLA Compliance (RFI Approvals) | 95% | 92% | -3% | Delay in FE report submissions |
| 10 | Training Sessions (PIUs & FEs) | 100% | 95% | -5% | Final session rescheduled |

# Glossary of terms

| Term | Description |
| --- | --- |
| KPI | Key Performance Indicator |
| PM | Project Manager |
| PIU | Project Implementation Unit |
| FE | Field Engineer |
| RFI | Request for Inspection |
| UAT | User Acceptance Testing |
| GIS | Geographic Information System |
| AMC | Annual Maintenance Contract |
| ROI | Return on Investment |
| SLA | Service Level Agreement |

# Process

## ESTABLISH ORGANIZATIONAL MISSION, VISION AND STRATEGIC PLANS

The Jal Rekha Project aligns with MP Jal Nigam’s vision to ensure safe drinking water supply and real-time monitoring of ongoing schemes. The solution integrates multiple workflows and reporting structures under a centralized platform.

## PROVISION OF NECESSARY RESOURCES AND INFRASTRUCTURE

- Dedicated project team: Business Analysts, Developers, DBAs, QA Engineers, UI/UX Designers, and Mobile App team.

- Infrastructure provisioned for hosting, secured APIs, and GIS integration.

- Dev, QA, UAT, and Production environments properly configured.

## DEFINE PERFORMANCE MANAGEMENT & GOVERNANCE FRAMEWORK

- Weekly status reviews with project teams.

- Monthly dashboard-based performance reports to management.

- Escalation matrix for dependencies involving PIUs, TPIAs, and FEs.

SPECIFY MEASURMENTS FOR ACCOUNT, PROJECT & DEPARTMENTS Level

- Account Level → SLA compliance, budget utilization.

- Project Level → Schedule variance, defect density, dashboard uptime.

- Department Level → Number of RFIs processed, pending vs accepted RFIs, re-inspections.

COLLECTION OF DATA

Data collected from:

- Project management tools (JIRA / Excel trackers).

- RFI mobile app sync logs.

- Database-level reports and API usage logs.

- UAT feedback from PIU & SQC-TPIA teams.

REVIEW & GOVERNANCE

- Weekly project team reviews.

- Bi-weekly governance committee meetings.

- Monthly status reports to management.

# COMMUNICATE RESULTS

Results are communicated through:

- Real-time KPI dashboards for ADM, DM, PIU, and FE users.

- Weekly status updates to project stakeholders.

- Monthly review meetings with management.

- Training sessions and workshops for PIU and field engineers.

# Exit criteria

The KPI Dashboard and tracking process will be considered complete when:

- All major modules (Dhara, Anushravan, Dashboard, Reports, Mobile App) are tested and deployed.

- Variance remains within acceptable limits (<5% for schedule, <10% for budget).

- Training sessions are completed for PIU officers and field engineers.

- Post-Go-Live support successfully transitioned to AMC mode.