## O&N Billing
DAR Form
Group Name |  |  |  | Project Name |  | Jal Rekha – O&M Billing Module
Decision Seeker | Project Steering Committee / Department of Water Resources / Jal Nigam |  |  | Evaluation Date |  | 2025-11-19
Problem Statement | Manual and semi-digital processes are currently used for O&M billing under Jal Rekha projects, leading to calculation errors, delays in bill generation, lack of transparency, and increased dependency on manual verification. There is a need for a centralized, automated, and auditable O&M Billing Module to handle end-to-end billing calculations and bill generation for all Jal Rekha projects.
Scope of DAR | Evaluation of available alternatives for implementing an O&M Billing Module in Jal Rekha to automate project-wise billing calculations, bill creation, approval workflow, and reporting.
DAR Team Members | Entire Project & Technical Team
Alternatives |  |  | Source of Alternatives |  |  | Remarks
A1 – Continue Existing Manual / Semi-Digital Billing O&M bills are calculated manually using spreadsheets and physical records, with manual approval and submission. |  |  | Existing Jal Rekha billing practice and field-level operations |  |  | High dependency on manual effort
A2 – Partial Digital Billing Module Basic billing calculation and bill generation done through Jal Rekha portal, but approvals, corrections, and validations remain manual. |  |  | Internal discussions and feasibility assessment |  |  | Limited automation
A3 – Full Digital O&M Billing Module End-to-end automated billing calculation, bill creation, approval workflow, audit trail, and MIS reporting through Jal Rekha system. |  |  | Digital Governance guidelines, stakeholder consultation, and Jal Rekha system capabilities |  |  | Recommended option
Criteria for Evaluation |  | Weightage (1 = Least important and 5 = Most important) |  | Rationale for Criteria and Weightage Selection
Legal & Financial Compliance |  | 5 |  | Billing must comply with financial and audit rules
Accuracy of Billing Calculations |  | 5 |  | Critical to avoid revenue loss or disputes
Process Automation & Efficiency |  | 4 |  | Faster bill generation and approvals
Data Security & Audit Trail |  | 5 |  | Financial data integrity and audit readiness
Availability of Technical & Operational Resources |  | 4 |  | Feasibility of implementation
Scalability Across Projects |  | 4 |  | Applicability for all Jal Rekha projects
Ease of Use for Field & Finance Staff |  | 3 |  | Smooth adoption
Operational Risk Reduction |  | 4 |  | Reduced manual errors and disputes
Criteria for Evaluation | A1 – Continue Existing Manual / Semi-Digital Billing O&M bills are calculated manually using spreadsheets and physical records, with manual approval and submission. |  | A2 – Partial Digital Billing Module Basic billing calculation and bill generation done through Jal Rekha portal, but approvals, corrections, and validations remain manual. |  | A3 – Full Digital O&M Billing Module End-to-end automated billing calculation, bill creation, approval workflow, audit trail, and MIS reporting through Jal Rekha system.
| Score | Weighted Score | Score | Weighted Score | Score | Weighted Score
Legal & Financial Compliance | 2 | 10 | 1 | 5 | 3 | 15
Accuracy of Billing Calculations | 5 | 25 | 4 | 20 | 4 | 20
Process Automation & Efficiency | 3 | 12 | 4 | 16 | 5 | 20
Data Security & Audit Trail | 3 | 15 | 4 | 20 | 4 | 20
Availability of Technical & Operational Resources | 1 | 4 | 4 | 16 | 4 | 16
Scalability Across Projects | 2 | 8 | 4 | 16 | 4 | 16
Ease of Use for Field & Finance Staff | 3 | 9 | 3 | 9 | 3 | 9
Operational Risk Reduction | 2 | 8 |  | 0 |  | 0
Average Weighted Score |  | 11.375 |  | 12.75 |  | 14.5
Score Range (1 - 5) : ( 1 = Minimum rating and 5 = Maximum rating)
Alternatives |  |  | Order (1 = Highest, 4 = Lowest) |  |  | Result
A1 – Continue Existing Manual / Semi-Digital Billing O&M bills are calculated manually using spreadsheets and physical records, with manual approval and submission. |  |  | 3 |  |  | Reject
A2 – Partial Digital Billing Module Basic billing calculation and bill generation done through Jal Rekha portal, but approvals, corrections, and validations remain manual. |  |  | 2 |  |  | Reject
A3 – Full Digital O&M Billing Module End-to-end automated billing calculation, bill creation, approval workflow, audit trail, and MIS reporting through Jal Rekha system. |  |  | 1 |  |  | Accept
Solution Decision (Decision Authority) |  | The decision is to implement a Full Digital O&M Billing Module for the Jal Rekha project, enabling automated billing calculations, project-wise bill generation, approval workflows, audit trails, and MIS reporting. This solution ensures accuracy, transparency, compliance, and scalability across all Jal Rekha projects.
Risk anticipated |  | Initial data migration challenges from legacy billing records Dependency on accurate project and contract master data Change management issues for field and finance users Initial increase in support requirements during rollout
Assumptions |  | Financial rules and billing formulas are clearly defined and approved Required approvals for digital billing and electronic records are in place Adequate infrastructure and connectivity are available Users will be trained prior to rollout
Remarks |  | The proposed Full Digital O&M Billing Module aligns with Digital Governance objectives and strengthens financial transparency, operational efficiency, and accountability in Jal Rekha project execution. It significantly reduces manual effort, billing errors, and audit risks while enabling real-time monitoring and reporting.
Decision Authority |  | Office of the Chief Engineer / Jal Nigam, in consultation with MPSEDC and the Project Steering Committee |  |  |  | Date | 2025-11-19