## Version Hisotry
0.12 ( According to MPSeDC GIS Entity E-Abkari Project)
Date | Version | Description | Prepared by | Reviewed & approved by
2025-08-19 | 1 | Size base Estimation Model First baseline | SEPG Team | SEPG Head

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project)
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project) | Point / per hour
|  | 1 Point | 8.3 Hours

## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project) | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 8.3 Hours | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## Estimation_DHARA
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Dhara Admin | Meter Registration | No of input fields: 10-20 , Exit scenario 1 No of screens: <10 tabular report. <10 columns. 1 data source | 4 | 0 | 0 | 4 | #N/A | #N/A | #N/A |  |  | 1*1+3*1+5*0 =4
| Admin data check for all PIU and report check | Scheme, component , From date, To date, Beneficiary,ULB No of input fields: <10 Exit scenario 1 No of Validations >5 | 2 | 1 | 0 | 5
Dhara GM | GM/PIU - Asign Work | User, Scheme, Component, Assign and Search No. of input fields- 3 No. of exit - 2 No of Prefilled - 1 No of Validations 3 | 3 | 1 | 0 | 6 | #N/A | #N/A | #N/A
| GM/PIU - GIS Mapping | PIU, Scheme, Component, Search Reset, Zoom in and Zoom out No. of input fields- 3 No. of exit scenario- 2 Map View 1 No of Validations 3 | 2 | 2 | 0 | 8
| GM/PIU - WTP Meter Linking | Search, Export to excel, Report Table, Add New, WTP Name, District, OHT Name, Meter Name and MAP Meter No. of input fields- 5 No. of exit -2 Report Column- 4 column Mobile Screen View 2-4 internal components No of Validations <5 | 3 | 2 | 0 | 9
| GM/PIU - Assign Intake Meter | Field Eng., Assistant Eng., Select Field/Assistant Engineer:, Scheme, Component, Assign, Search, Export to Excel and Tast table. No. of input field-6 No. of exit- 2 Report table 10 column Mobile Screen View 2-4 internal components No of Validations <5 | 3 | 2 | 0 | 9 |  |  |  | Value added factors
| GM/PIU -Intake Survey Report | Scheme, From Survey Date, To Survey Date, Search, Reset and Report Table No. of input fields- 3 No. of exits- 2 Report table>10 column No of Validations 3 | 1 | 2 | 0 | 7 |  |  |  | Factor | Rating
| GM/PIU -WTP Survey Report | Scheme, From Survey Date, To Survey Date, Search, Reset and Report Table No. of input fields- 3 No. of exits- 2 Report table- 14 column No of Validations 3 | 2 | 2 | 0 | 8 |  |  |  | Data Communications | 0
| GM/PIU -OHT Survey Report | Scheme, Componenet Name, Village Name, From Survey Date, To Survey Date, Search, Reset and Report Table No. of input fields- 5 No. of exit- 2 Report table- 25 column No of Validations <5 | 2 | 2 | 0 | 8 |  |  |  | Distributed Data Processing | 0
| GM/PIU -Bulk Meter Survey Report | No. of input fields- 3 No. of buttons- 2 Report table- 19 column Mobile Screen View 2-4 internal components No of Validations 3 | 2 | 3 | 0 | 11
| GM/PIU -Meter Reading Report | No. of input field- 4 Report tables with errors and cleaning- 4 Mobile Screen View 2-4 internal components No of Validations 5-10 | 1 | 2 | 1 | 12 |  |  |  | Performance | 0
Dhara Change Request GM | Change Request - Report Format & Drill down | No of input fields: 3 , Exit scenario 2 tabular report. 10 columns. 1 data source No of validations 5-10 | 2 | 2 | 0 | 8 | #N/A | #N/A | #N/A | Heavily used Configuration | 3
| Change Request - Intake WTP OHT Range functionality(MOBILE) & TL entry validation | No of input fields: 3 , Exit scenario 2 Mobile Screen view internal components No of validations 5 | 2 | 2 | 0 | 8 | #REF! | #REF! | #REF! | Transaction Rate | 4
Dhara TL | a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report | No of input fields: 3 No of validations <5 Reports Viewed: 5 | 3 | 0 | 0 | 3
Dhara Change Request TL | Change reading entry- option provided to TL | No of Input fields: 1 No of validations 5-10 | 1 | 1 | 0 | 4 | #REF! | #REF! | #REF! | Online Data Entry | 3
Field Engineer | Meter status flags (4 states) | No of input fields: 4 , Mobile Screen view internal components | 1 | 1 | 0 | 4 | #N/A | #N/A | #N/A | End-User Efficiency | 2
| Reading capture UI (numeric + date + remarks) | No of input fields: 3 , Exit scenario 1 Mobile Screen view internal components No of validations <5 | 3 | 1 | 0 | 6 | #N/A | #N/A | #N/A | Online Update | 1
| Reading validations (range/format) | No of validations 5-10 | 0 | 1 | 0 | 3 | #N/A | #N/A | #N/A | Complex Processing | 3
| Photo capture & upload workflow | Mobile Screen view internal components | 0 | 1 | 0 | 3 | #N/A | #N/A | #N/A | Reusability | 4
| Photo compression & size validation | Mobile Screen view internal components Exit scenario 1 | 1 | 1 | 0 | 4 | #N/A | #N/A | #N/A | Installation Ease | 4
| Buffer GeoCoordinate Condition for WTP and Intake(200 meter) & OHT ( 50 meter) | Mobile Screen view internal components Exit scenario 1 | 1 | 1 | 0 | 4 | #N/A | #N/A | #N/A | Operational Ease | 4
| Save readings offline and sync later (Offline-first design, local storage, and sync logic) | No of input fields: 3 , Exit scenario 2 Mobile Screen view internal components No of validations <5 1 data store | 3 | 1 | 0 | 6 | #N/A | #N/A | #N/A | Multiple Sites | 4
Contrtactor | Report View- Water supply report | Report tabular format < 10 columns Validations <5 | 2 | 0 | 0 | 2 | #N/A | #N/A | #N/A | Facilitate Change | 4
[5 empty] | Total Size | 142 | #N/A | #N/A | #N/A | Total | 36
[7 empty] | #N/A | #N/A | #N/A
|  | Productivity | 0.12 | #N/A
|  | Size | 142 | Point
|  | Effort | 1183.3333 | Man hours
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total Planned effort | 1380.4175 | Man hours
|  | Permissible Range(Man hours) | 1449.4384 | 1311.3966

## Estimation_MASTER
| Type Of work |  | New Development
Project Name
Remark
Value added factors
|  |  | Volume/Count of elements |  |  |  | Guidelines |  |  |  |  | Factor | Rating
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5 | [6 empty] | Data Communications | 0
Master - GM | Login Screen | No of input fields: 2, No of exit scenario: 1 No of validations: 2 | 3 | 0 | 0 | 3 |  | 4 |  |  |  | Distributed Data Processing | 0
Master - GM | Scheme & Village Master Data Entry | No of fields 15 on 2 screen each No of validations: 10 45 prefilled, Upto 5 APIs Upto 3 data sources | 1 | 4 | 0 | 13 |  | 13 |  |  |  | Performance | 0
Master - GM | Edit/Deactivate Master Records | No of 2 web pages 10 fields each 7 validations, 35 prefilled, 2 APIs, version control | 1 | 3 | 0 | 10 |  | 11 |  |  |  | Heavily used Configuration | 3
Master - GM | OHT Mapping & Component Data Sync | No of 2 web pages 10 fields, <5 validations, 40 prefilled, 5 APIs, 2 data sources | 2 | 2 | 0 | 8 |  | 8 |  |  |  | Transaction Rate | 4
Master - All Report User | Reports: CWGM, CWPM, RWPM, Distribution Pipe | No of 2 reports -15 columns, 4 data sources - drill-down, complex graphs | 1 | 0 | 1 | 6 |  | 10 |  |  |  | Online Data Entry | 3
Master - All Report User | Scheme Covered Villages Report | No of 1 report, 10 columns, 2 data sources, historical tracking | 2 | 0 | 0 | 2 |  | 6 |  |  |  | End-User Efficiency | 2
Master - FE Mobile | OHT Assignment via RFI | No of 1 mobile screen, 3 fields, 2 validations, 2 APIs, notification | 3 | 0 | 0 | 3 |  | 1 |  |  |  | Online Update | 1
Master - Contractor | Pipeline Master RFI Generation | No of mobile screen 1, 15 fields, <10 validations, 45 prefilled, <5 APIs, 3 data sources | 2 | 2 | 0 | 8 |  | 10 |  |  |  | Complex Processing | 3
Master - CR | Schema Modification & App Updates | No of 1 screen, 10 fields, validations 3 35 prefilled, 4 APIs, backward compatibility | 2 | 2 | 0 | 8 |  | 8 |  |  |  | Reusability | 4
[5 empty] | Total Size | 61 | [5 empty] | Installation Ease | 4
[12 empty] | Operational Ease | 4
[12 empty] | Multiple Sites | 4
[12 empty] | Facilitate Change | 4
[7 empty] | #N/A | #N/A | #N/A |  |  | Total | 36
[7 empty] | #N/A | #N/A | #N/A
[7 empty] | #N/A | #N/A | #N/A
|  | Productivity | 0.12 | #N/A | [5 empty] | 0.21 | 0.14
|  | Size | 61 | Point
|  | Effort | 508.3333 | Man hours | [5 empty] | 4.7619 | 7.1429
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total Planned effort | 592.9963 | Man hours
|  | Permissible Range(Man hours) | 622.6461 | 563.3464

## Estimation_NIRMAL
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Value added factors
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Factor | Rating
|  |  | 1 | 3 | 5
Nirmal-FE Mobile | Login Screen | No of input fields: 2, No of exit scenario: 1 No of validations on the fields: 2 | 3 | 0 | 0 | 3 | Data Communications | 0 | 1*1+3*1+5*0 =4
Nirmal-FE Mobile | Collect Water Samples | No of input fields 8 No of validations on the fields 4 Prefilled fields <30 No of API integrations 2 | 4 | 0 | 0 | 4 | Distributed Data Processing | 0
Nirmal-FE Mobile | Submit Sample Offline | no of input fields <10 Type of exit scenario: 2 (submit / cancel) No of Validation on the fields:3 No of API Integrations: 2 (sync, status) mobile App-UI: Screen with 2–4 internal components (status, cache, sync) | 4 | 1 | 0 | 7 | Performance | 0
Nirmal-FE Mobile | Multi-point Collection (Intake, WTP, OHT, Beneficiary) | No of input fields: 15 (multi-asset details) Type of exit scenario: >3 (save, save & add next, cancel, back) No of Validation on the fields: 10 No of Prefilled fields: 30-50 (asset masters, locations) No of API Integrations: 4 (GIS, master data, validation, sync) mobile App-UI: Screen with external components (GPS, Map, traverse) | 1 | 4 | 1 | 18 | Heavily used Configuration | 3
Nirmal-Contractor Login | View Collected Samples | Web Page / Screen with no of input fields: ≤10 (filters) Type of exit scenario: 1 No of Validation on the fields: 1–5 (filter validations) No of Prefilled fields: 10–30 (default dates, ULB, lab) No of API Integrations: 2–5 (dashboard, listing, counts, status) Queries or Business rules for the application: Listing + filter rules, basic dashboards, up to 3 data stores Reports: Dashboard / tabular report type 1–2 | 5 | 1 | 0 | 8 | Transaction Rate | 4
Nirmal-Contractor Login | Lab Test Input & Update | No of input fields: <10 Type of exit scenario: >3 No of Validation on the fields:3 (parameter ranges) No of API Integrations: >5 (sample, lab master, limits, report, audit) Reports: 2 lab report | 4 | 1 | 0 | 7 | Online Data Entry | 3
Nirmal-Contractor Login | Report Submit | No of input fields: 5–10 (submission meta) Type of exit scenario: >3 (submit, save draft, cancel, resend) No of Validation on the fields: 5–10 No of Prefilled fields: 10–30 No of API Integrations 5 (email, portal, audit, submission, status) Report 1 | 3 | 2 | 0 | 9 | End-User Efficiency | 2
Nirmal-GM Login | Dashboard & Defect View | No of input fields: 5–10 (filters) Type of exit scenario: 1–2 No of Validation on the fields: 1–5 No of Prefilled fields: 10–30 No of API Integrations: 2–5 (summary, defect list, charts) Queries or Business rules for the application: Aggregation logic, severity rules; up to 3 data stores Reports: Dashboard reports type 1–2 with simple charts | 4 | 2 | 0 | 10 | Online Update | 1
Nirmal-Change Request | Report Parameter Changes - OHT & WTP & User management Nirmal-Dhara | No of input fields: 10 Type of exit scenario: >3 (save, cancel, rollback, preview) No of Validation on the fields: 5–10 No of Prefilled fields: 30–50 No of API Integrations: 2–5 Reports: Impacts report definitions (3–5 types) | 3 | 2 | 0 | 9 | Complex Processing | 3
Nirmal-Web Reports | Water Supply Reports (DWSR, MWSR, Scheme, UFW, Village, Bulk) | No of input fields: 10 (filters) Type of exit scenario: 1–2 No of Validation on the fields: <5 No of API Integrations: >5 (multiple report/data APIs - DWSR, MWSR, scheme, village, bulk, export) Reports: 4 (chart, graphsTrend) | 3 | 2 | 0 | 9 | Reusability | 4
[6 empty] | 84 | Installation Ease | 4
[7 empty] | Operational Ease | 4
[5 empty] | Total Size | 84 | Multiple Sites | 4
[7 empty] | Facilitate Change | 4
[7 empty] | Total | 36
|  | Productivity | 0.12 | #N/A
|  | Size | 81 | Point
|  | Effort | 675 | Man hours
|  | VAF | 1.01 |  |  |  | 0.21 | 0.14
|  | Risk contingency | 5%
|  | Project Management | 10% |  |  |  | 4.7619 | 7.1429
|  | Total effort | 787.4212 | Man hours
|  | Permissible Range(Man hours) | 826.7923 | 748.0502

## Estimation_SOPAN
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines |  |  | Value added factors
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity | Factor | Rating
|  |  | 1 | 3 | 5
SOPAN - CONTRACTOR (Sub-Module) | OHT, Intake, WTP, IPS Work Plan Creation | Web Page / Screen with no of input fields: 10 Type of exit scenario: 2 No of Validation on the fields: 4 No of Prefilled fields: 30-50 No of API Integrations: 3 (save, validate) mobile App-UI: Screen with internal components only (Medium) | 3 | 3 | 0 | 12 | Heavily used Configuration | 3 |  | Data Communications | 0
SOPAN - GM (Sub-Module) | OHT Actual Date Management | Web Page / Screen with no of input fields: 10–15 (Medium) Type of exit scenario: 2 (Save, Cancel) No of Validation on the fields: 5 No of Prefilled fields: 10–30 (Low) No of API Integrations: 3 (fetch plan, save actual) mobile App-UI: Web GM form with 2–4 controls (Medium) | 3 | 2 | 0 | 9 | Transaction Rate | 4 |  | Distributed Data Processing | 0
SOPAN - GM (Sub-Module) | WTP Actual Date Management | Web Page / Screen with no of input fields: 10–15 (Medium) Type of exit scenario: 2 (Save, Cancel ) No of Validation on the fields: 5 No of Prefilled fields: 10–30 (Low) No of API Integrations: 3 (fetch plan, save actual, freeze flag) mobile App-UI: Web GM form with 2–4 controls (Medium) | 3 | 2 | 0 | 9 | Online Data Entry | 3 |  | Performance | 0
SOPAN - GM (Sub-Module) | Intake Actual Date Management | Web Page / Screen with no of input fields: 10–15 (Medium) Type of exit scenario: 2 (Save, Cancel ) No of Validation on the fields: 5 No of Prefilled fields: 10–30 (Low) No of API Integrations: 3 (fetch plan, save actual, freeze flag) mobile App-UI: Web GM form with 2–4 controls (Medium) | 3 | 2 | 0 | 9 | End-User Efficiency | 2 |  | Heavily used Configuration | 3
SOPAN - GM (Sub-Module) | IPS Actual Date Management | Web Page / Screen with no of input fields: 10–15 (Medium) Type of exit scenario: 2 (Save, Cancel ) No of Validation on the fields: 5–10 (Medium) No of Prefilled fields: 10–30 (Low) No of API Integrations: 3 (fetch plan, save actual, freeze flag) mobile App-UI: Web GM form with 2–4 controls (Medium) | 3 | 2 | 0 | 9 | Online Update | 1 |  | Transaction Rate | 4
SOPAN - DOCUMENT UPLOAD & CHAT (Sub-Module) | Document Upload (Panchnama & Supporting Docs) & Chat functionality contractor | No of input fields: <10 Type of exit scenario: 2 (Send, Close) No of Validation on the fields: 3 No of Prefilled fields: 10–30 No of API Integrations: 3–4 (chat, notification, upload) Data store 1 mobile App-UI: Web chat with multiple internal components (Medium) | 4 | 2 | 0 | 10 | Complex Processing | 3 |  | Online Data Entry | 3
SOPAN - ALL WEB USER (Sub-Module) | OHT Mapping, Monitoring, Report | No of input fields: 10 Type of exit scenario: 3 (Apply,Reset, Export) No of Validation on the fields 5 No of Prefilled fields: 10–30 (default filters → Low) No of API Integrations: 2 (GIS tiles, OHT status - KPI export) mobile App-UI: Web GIS with internal map component Reports: >5 map/tabular KPI outputs, multiple complex graphs (High) | 3 | 1 | 1 | 11 | Reusability | 4 |  | End-User Efficiency | 2
SOPAN - ALL WEB USER (Sub-Module) | WTP Mapping, Monitoring, Report | No of input fields: 10 Type of exit scenario: 3 (Apply,Reset, Export) No of Validation on the fields 5-10 No of Prefilled fields: 10–30 (default filters → Low) No of API Integrations: 2 (GIS tiles, OHT status - KPI export) mobile App-UI: Web GIS with internal map component Reports: >5 map/tabular KPI outputs, multiple complex graphs | 2 | 2 | 1 | 13 | Installation Ease | 4 |  | Online Update | 1
SOPAN - ALL WEB USER (Sub-Module) | Intake Mapping, Monitoring, Report | No of input fields: 10 Type of exit scenario: 3 (Apply,Reset, Export) No of Validation on the fields 5 No of Prefilled fields: 10–30 (default filters → Low) No of API Integrations: 2 (GIS tiles, OHT status - KPI export) mobile App-UI: Web GIS with internal map component Reports: >5 map/tabular KPI outputs, multiple complex graphs | 2 | 1 | 1 | 10 | Operational Ease | 4 |  | Complex Processing | 3
[7 empty] | Multiple Sites | 4 |  | Reusability | 4
[5 empty] | Total Size | 92 | Data Communications | 0 |  | Installation Ease | 4
[7 empty] | Distributed Data Processing | 0 |  | Operational Ease | 4
[7 empty] | Performance | 0 |  | Multiple Sites | 4
|  | Productivity | 0.12 | #N/A
|  | Size | 92 | Point |  |  | #N/A | #N/A | #N/A | Total | 29
|  | Effort | 766.6667 | Man hours
|  | VAF | 0.94
|  | Risk contingency | 5%
|  | Project Management | 10% | [6 empty] | 0.21 | 0.14
|  | Total effort | 832.37 | Man hours
[10 empty] | 4.7619 | 7.1429
|  | Permissible Range(Man hours) | 873.9885 | 790.7515

## Estimation_Sahbhagita
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines |  |  | Value added factors
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity | Factor | Rating
|  |  | 1 | 3 | 5
GM Admin | GM map ISA Project Managers (PMs) to Schemes | Web Page / Screen with no of input fields: 12 Type of exit scenario: 1 No of Validation on fields: 3 PM,scheme, duplicate check No of Prefilled fields: 28 mobile App‑UI: Static web screen (Low) | 5 | 0 | 0 | 5 |  |  |  | Data Communications | 0
PM Dashboard | Sahbhagita report view - PM dashboard filters | No of Prefilled fields: 25 Reports: Tabular report with <10 columns, 1 data source, 1–2 report types (Low) | 1 | 1 | 0 | 4 |  |  |  | Distributed Data Processing | 0
FE Mobile | Fill Sahbhagita activity upload - data entry with photos/GPS, version history & approval | No of input fields: 10–15 mobile App‑UI: Screen with 2–4 internal components | 1 | 1 | 0 | 4 |  |  |  | Performance | 0
[10 empty] | Heavily used Configuration | 3
[7 empty] | #N/A | #N/A | #N/A | Total | 3
[5 empty] | Total Size | 13
|  | Productivity | 0.12 | #N/A | [5 empty] | 0.21 | 0.14
|  | Size | 13 | Point
|  | Effort | 108.3333 | Man hours | [5 empty] | 4.7619 | 7.1429
|  | VAF | 0.68
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total Planned effort | 85.085 | Man hours
|  | Permissible Range(Man hours) | 89.3393 | 80.8308