## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 10 | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 3 to 5 | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## Version History
Date | Version | Description | Prepared by | Reviewed & approved by
2025-11-29 | 1.2 | Size base Estimation Model First baseline | SEPG Team | SEPG Head

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.14127 | Point / per hour
|  | 1 Point | 7.08 Hours

## FHTC Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
FHTC – FE Reports | FE login to FHTC module | No of input fields: 4 Type of exit scenario: 1 No of Validation on the fields: 3 mobile App‑UI: Static login screen | 4 | 0 | 0 | 4
FHTC – FE Reports | Visit each village household and capture data via API Capture tap status, details and upload beneficiary & tap photos | No of input fields: 10–15 (filters + 8–10 entry fields) Type of exit scenario: 2 (Save/Submit, Cancel) No of Validation on the fields: 5–10 (mandatory + GPS + status) No of Prefilled fields: 10–30 (from API) No of API Integrations: 3–4 (household list, GPS, sync, queue) mobile App‑UI: Screen with 2–4 internal components (list, form, GPS) Data Migration: Local‑to‑server sync only | 3 | 4 | 0 | 15 | #N/A | #N/A | #N/A
FHTC – FE Reports | Send rejected connections to GM & contractor. Accepted connections to GM HSC Report including mandatory beneficiary photo and complete details | No of input fields: 10 beneficiary fields Type of exit scenario: 1 No of Validation on the fields: 5–10 (form + photo rules) No of Prefilled fields: 10–30 (beneficiary defaults) No of API Integrations: 3–4 (photo upload, compression, save) 1 HSC Report with details | 5 | 1 | 0 | 8
FHTC – FE Reports | API whitelisting and security control NIC API Integration | No of input fields: 10 Type of exit scenario: 1 No of Validation on the fields: 5–10 (IP format, uniqueness) No of Prefilled fields: 10–30 (existing rules) No of API Integrations: 2–5 (auth, gateway, log) Queries or Business rules: Security/whitelisting rules across multiple stores (API gateway, security DB, logs) | 5 | 1 | 0 | 8
FHTC – Change Request | Integrate Samagra API instead of NIC Update mobile APK to integrate Samagra API Fill updated HSC Report entries with new fields | No of input fields: <10 (config) Type of exit scenario: 2 No of Validation on the fields: 5 No of API Integrations: 5 (Samagra main, auth, retries, monitoring/mapping) No of Integration: >5 (Samagra, NIC, core DB, logs, monitoring) Data Migration: One‑time mapping adjustments only 1 HSC Report details updated | 4 | 2 | 0 | 10
FHTC – Change Request | Contractor updates tap connection with photograph and sends to GM | No of input fields: <10 (config) Type of exit scenario: 2 No of Validation on the fields: 5 No of Prefilled fields: 10–30 (existing details) No of API Integrations: 2(update, notify GM) | 4 | 0 | 0 | 4 |  |  |  | Value added factors
[5 empty] | Total Count | 49 |  |  |  | Factor | Rating
[10 empty] | Data Communications | 0
[10 empty] | Distributed Data Processing | 0
|  | Productivity | 0.1413 | #N/A
|  | Size | 49 | Point |  |  | #N/A | #N/A | #N/A | Performance | 0
|  | Effort | 346.7799 | Man hours |  |  | #REF! | #REF! | #REF! | Heavily used Configuration | 3
|  | VAF | 1.01 | [6 empty] | Transaction Rate | 4
|  | Risk contingency | 5% |  |  |  | #REF! | #REF! | #REF!
|  | Project Management | 10% |  |  |  | #REF! | #REF! | #REF! | Online Data Entry | 3
|  | Total Planned effort | 404.5361 | Man hours | [5 empty] | End-User Efficiency | 2
[10 empty] | Online Update | 1
|  | Permissible Range(Man hours) | 424.7629 | 384.3093 | [5 empty] | Complex Processing | 3
[10 empty] | Reusability | 4
[10 empty] | Installation Ease | 4
[10 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
[10 empty] | Facilitate Change | 4
[10 empty] | Total | 36

## O&M Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
O&M Billing - GM | GM Login & Basic Details | Screen (18 fields): SLBM sections (Quality, Quantity, Pressure, UFW, Complaint), Norms dropdown, Penalty dropdown, Scheme status fields • Exit scenarios: 2 (Save, Draft) • Validations: 8 (SLBM rules, CPI validations, scheme-contractor mapping, UFW calculations) • Prefilled: 25 (scheme master data, last submission, contractor history) • API integrations: 3 (Scheme service, CPI lookup, Contractor service) • API save: 2 (SLBM data, Status updates) • Business rules: Complex CPI-based calculations, scheme eligibility across 3 data stores • Integration: 3 (Scheme, CPI, Contractor DBs) • Reports: None | 2 | 1 | 0 | 5
O&M Billing - GM | Advance Form with SLBM Features | Dashboard screen (4 internal components): Status widget, CPI calculator, Bill computation grid, Eligibility matrix • Exit scenarios: 2 (View, Export) • Validations: 6 (CPI factor validation, historical comparisons, month-year consistency) • Prefilled: 40 (scheme data, historical CPI, previous bills) • API integrations: 4 (Scheme, CPI history, Bill archive, Eligibility engine) • API save: 1 (Audit trail only) • Business rules: Multi-period financial logic across scheme & bill stores • Integration: 4 points • Reports: 1 financial summary report (tabular, <10 columns) | 4 | 1 | 0 | 7 | #N/A | #N/A | #N/A
O&M Billing - GM | Scheme Status & Financial Calculation & Scheme Assignment to Contractor | Screen with external components: File upload widget (accepts PDF/DOC/XLS max 10MB), Dhara integration panel, Nirmal integration panel • Exit scenarios: 2 (Upload, Sync) • Validations: 8 (file format, size, virus scan, data format consistency, relationship validation) • Prefilled: 30 (document history, previous sync data) • API integrations: 5 (Document store, Dhara portal, Nirmal portal, virus scanner, data mapper) • API save: 3 (Document store, Audit, Data reconciliation) • Business rules: Data relationship validation across Dhara & Nirmal multiple data stores • Integration: 5+ (APIs, Storage, Audit, Mapping engine) • Reports: 1 data sync audit report (2-3 columns) | 2 | 3 | 0 | 11
O&M Billing - GM | Document Upload & Data Fetch from Dhara/Nirmal | Screen with external components: File upload widget (accepts PDF/DOC/XLS max 10MB), Dhara integration panel, Nirmal integration panel • Exit scenarios: 2 (Upload, Sync) • Validations: 8 (file format, size, virus scan, data format consistency, relationship validation) • Prefilled: 30 (document history, previous sync data) • API integrations: 5 (Document store, Dhara portal, Nirmal portal, virus scanner, data mapper) • API save: 3 (Document store, Audit, Data reconciliation) • Business rules: Data relationship validation across Dhara & Nirmal multiple data stores • Integration: 5+ (APIs, Storage, Audit, Mapping engine) • Reports: 1 data sync audit report (2-3 columns) | 2 | 1 | 1 | 10
O&M Billing - GM | Contractor generate Bill. GM PIU or SQC Edit it and forward to GM of O&M then to PMC. All can check remarks then forward to Deputy Manager will only processs final bill amount with further remarks. PMC recommendations letter annexure duly verified | Screen with 4+ internal components: Bill header, PIU section (8 fields), SQC section (8 fields), Manpower grid (12 fields + residual pressure readings), Bulk user mapping grid (village-wise), PDF preview • Exit scenarios: 2 (Submit, Draft) • Validations: 12–15 (PIU completeness, SQC compliance, bill consistency, manpower format, pressure range, mapping validation, UFW deduction) • Prefilled: 40–50 (scheme details, rates, manpower history, norms, bulk user list from APIs) • API integrations: 5–6 (PIU, SQC template, Manpower service, Bulk user, Penalty calculator, PDF generator) • API save: 4–5 (Bill draft, Submission log, Manpower records, Mapping records, PDF) • Business rules: Validation & business rules across multiple data stores (scheme, rates, norms, bulk users) • Mobile App-UI: Screen with 2–4 internal components (Bill form, PIU section, SQC section, Manpower grid, User mapping) • Data Migration: Not applicable • Reports: 1 billing summary report (stacked bar chart, 2–3 data sources) Screen 2 internal components: Recommendations letter display (PDF/text viewer), Verification checklist (3–5 checkpoints: signature, format, completeness) • Exit scenarios: 2 (Verify, Reject) • Validations: 4–5 (signature validation, checklist completion, document completeness, format compliance) • Prefilled: 15–20 (letter template, previous verifications, checklist items from APIs) • API integrations: 2–3 (Letter service, Verification logger, Audit logger) • API save: 1–2 (Verification record, Audit log) • Business rules: No complex logic (single data store) • Mobile App-UI: Screen with 2–4 internal components (Letter viewer, Checklist widget, Verification buttons, History) • Data Migration: Not applicable • Reports: 1 verification summary report (tabular, <10 columns) | 2 | 2 | 0 | 8 |  |  |  | Value added factors
O&M Billing - Contractor | Contractor Basic & Advance Details Financial Calculations as per CPI | Screen (27 fields): Basic (10 fields), Advance (15 fields), Document attachments (3 docs) • Exit scenarios: 2 (Submit, Draft) • Validations: 8 (PAN format, GST validity, bank account validation, document verification) • Prefilled: 30 (contractor master, previous submissions, bank details) • API integrations: 3 (Contractor master, Document service, Validation service) • API save: 2 (Contractor profile, Document store) • Business rules: No complex validation (single data store) • Integration: 3 • Reports: None | 2 | 3 | 0 | 11 |  |  |  | Value added factors
O&M Billing - Contractor | Bill Generation with PIU & SQC Pages Manpower & Residual Pressure SP Bulk User Mapping & Net Payable Bill | Screen with 4 internal components: Bill header, PIU details section, SQC details section, PDF preview • Exit scenarios: 2 (Submit, Save draft) • Validations: 10 (PIU data completeness, SQC compliance, bill amount consistency) • Prefilled: 40 (scheme details, rates, manpower data, norms) • API integrations: 4 (PIU service, SQC template, PDF generator, Bill archive) • API save: 3 (Bill draft, Submission log, PDF storage) • Business rules: Validation & business rules across multiple data stores (scheme, rates, template) • Integration: 4 • Reports: 1 bill summary report (tabular + pie chart) | 1 | 2 | 1 | 12 |  |  |  | Factor | Rating
O&M Billing - Contractor | RA Bill Processing with RM & Village Mapping Dhara Water Supply Integration | Screen with external components: RM-Village mapping grid (20 rows), Management norms dropdown, Compliance checklist • Exit scenarios: 2 (Process, Revert) • Validations: 9 (village mapping consistency, norms applicability, compliance rules) • Prefilled: 50 (RM master, village list, norms for 147 schemes) • API integrations: 5 (RM service, Village service, Norms master, RA bill engine, Compliance checker) • API save: 2 (RA bill records, Compliance log) • Business rules: Compliance validation across multiple data stores (RM, village, norms) • Integration: 5 • Reports: 1 compliance checklist report (table) | 3 | 2 | 0 | 9 |  |  |  | Data Communications | 0
O&M Billing - GM PIU/SQC | Edit Bill & Forward Workflow | Screen with 4 internal components: Bill editor, Remarks section, Workflow status tracker, Approval buttons • Exit scenarios: 3 (Approve, Reject, Send back) • Validations: 8 (Bill amount consistency, remarks requirement, authority level) • Prefilled: 35 (current bill, previous remarks, user role) • API integrations: 4 (Bill service, Workflow engine, Notification service, Audit logger) • API save: 3 (Bill amendments, Remarks log, Status update) • Business rules: Validation & authority-based rules across multiple data stores • Integration: 4 • Reports: None |  |  |  | 0 |  |  |  | Distributed Data Processing | 0
O&M Billing - Workflow | Higher Official Approval Flow | Dashboard screen (3 internal components): Workflow queue, Remarks display, Approval controls • Exit scenarios: 3 (Approve, Reject, Escalate) • Validations: 6 (approval authority, bill completeness, MD override rules) • Prefilled: 30 (pending bills, role configuration, notification preferences) • API integrations: 3 (Workflow engine, Bill service, Email service) • API save: 2 (Approval log, Status update) • Business rules: Authority-based approval logic (single data store) • Integration: 3 • Reports: 1 approval audit report (tabular) | 3 | 0 | 0 | 3
O&M Billing - Workflow | Establish GM-Contractor-Official Flow | Workflow engine component: Status transition matrix, Role-based routing rules, Notification templates • Exit scenarios: 4 (Draft → Submit → Approve → Process) • Validations: 8 (role-based access, status transitions, mandatory fields per stage) • Prefilled: 40 (workflow templates, role definitions, notification templates) • API integrations: 5 (Bill service, User service, Notification engine, Audit logger, Status tracker) • API save: 3 (Status records, Audit trail, Notification history) • Business rules: Complex multi-stage workflow with validation across multiple data stores • Integration: 5+ • Reports: 1 workflow audit trail (line chart tracking) | 1 | 1 | 0 | 4 | #N/A | #N/A | #N/A | Performance | 0
O&M Billing - Workflow | RA Bill Data Retrieval & Test Data Preparation RA Bill Month Increment Logic | Database backend component: om_ra_bill table structure, Data retrieval queries, Test data generation scripts • Exit scenarios: 2 (Generate, Validate) • Validations: 6 (data integrity, foreign key consistency, backup validation) • Prefilled: 30 (existing test data, backup references, query templates) • API integrations: 3 (Database service, Backup service, Validation engine) • API save: 1 (Test data, Backup records) • Business rules: Data validation & relationship checks (single data store) • Integration: 3 • Reports: 1 data integrity report (tabular, <10 columns) | 2 | 1 | 0 | 5 | #REF! | #REF! | #REF! | Heavily used Configuration | 3
O&M Billing - Workflow | Edit & Resend to PIU GM then Contractor | Screen (2 internal components): Edit panel, Resend workflow controls • Exit scenarios: 2 (Resend, Cancel) • Validations: 5 (edit authority, resend path validation, version control) • Prefilled: 25 (current bill version, edit history, resend templates) • API integrations: 3 (Bill service, Workflow engine, Version control) • API save: 2 (Bill edit, Version record) • Business rules: No complex rules (single data store) • Integration: 3 • Reports: None | 3 | 0 | 0 | 3 |  |  |  | Transaction Rate | 4
O&M Billing - PMC | PMC Recommendations Letter Verification | Screen (2 internal components): Recommendations letter display, Verification checklist • Exit scenarios: 2 (Verify, Reject) • Validations: 4 (signature validation, checklist completion, document completeness) • Prefilled: 20 (letter template, previous verifications, checklist) • API integrations: 2 (Letter service, Verification logger) • API save: 1 (Verification record) • Business rules: No complex rules (single data store) • Integration: 2 • Reports: 1 verification summary report (tabular) |  |  |  | 0 | #REF! | #REF! | #REF!
O&M Billing - Change Request | Save as Draft Functionality Census Population Location Hierarchy Correction | Screen (1 main component): Form with Draft button, Auto-save timer display • Exit scenarios: 2 (Save, Auto-save) • Validations: 3 (draft data completeness, storage validation) • Prefilled: 15 (previous draft, form context) • API integrations: 2 (Draft storage, Session service) • API save: 1 (Draft data with metadata) • Business rules: Draft expiry, auto-save interval (single data store) • Integration: 2 • Reports: None | 4 | 2 | 0 | 10 |  |  |  | Online Data Entry | 3
O&M Billing - Change Request | "Other" Option in SLBM Norms & Penalty Penalty Label & Radio Button Changes | Screen (3 fields): Norms dropdown with "Other" option, Penalty dropdown with "Other" option, Custom text field (conditional display) • Exit scenarios: 2 (Submit, Cancel) • Validations: 4 (custom text validation, dropdown selection) • Prefilled: 20 (existing SLBM values, custom history) • API integrations: 2 (SLBM service, Custom value logger) • API save: 1 (SLBM records with custom values) • Business rules: No complex rules (single data store) • Integration: 2 • Reports: None | 2 | 2 | 0 | 8 |  |  |  | End-User Efficiency | 2
O&M Billing - Change Request | CPI-W Increment Type & Yearly Calculation Changes Scheme Status Section with View Document & O&M Dates | Screen (4 fields): CPI-W factor dropdown, Increment type selector (Fixed/Variable), Yearly calculation formula, Historical CPI-W data display • Exit scenarios: 2 (Calculate, Reset) • Validations: 6 (CPI-W format, formula syntax, historical data consistency) • Prefilled: 35 (CPI-W history, calculation templates, previous increments) • API integrations: 4 (CPI-W master, Calculation engine, Historical data service, Validation service) • API save: 2 (CPI-W selections, Calculation results) • Business rules: Validation & calculation across multiple data stores (CPI-W, rates, history) • Integration: 4 • Reports: 1 calculation comparison report (line chart, 2-3 data sources) | 2 | 3 | 1 | 16 |  |  |  | Online Update | 1
O&M Billing - Change Request | GST Services Option for O&M Document Upload Yes/No with Screen Freeze | Screen (3 fields): GST checkbox, GST rate dropdown (4 options: 5%, 12%, 18%, 28%), GST invoice preview • Exit scenarios: 2 (Apply, Cancel) • Validations: 4 (GST applicability rules, rate selection, invoice consistency) • Prefilled: 15 (previous GST choice, applicable rates) • API integrations: 2 (GST master, Invoice generator) • API save: 1 (GST choice) • Business rules: No complex rules (single data store) • Integration: 2-3 • Reports: 1 GST compliance report (tabular, <10 columns) | 2 | 2 | 0 | 8 |  |  |  | Complex Processing | 3
[10 empty] | Reusability | 4
[5 empty] | Total Count | 130 | #REF! | #REF! | #REF! | Installation Ease | 4
[10 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
|  | Productivity | 0.1413 | #N/A | [5 empty] | Facilitate Change | 4
|  | Size | 130 | Point | [5 empty] | Total | 36
|  | Effort | 920.0283 | Man hours
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total Planned effort | 1073.259 | Man hours
|  | Permissible Range(Man hours) | 1126.922 | 1019.5961

## Bharosa Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Bharosa - Factory Testing Web | GM Login & Basic Details & Assign Roles | Screen 6 fields (Emp Id, User Name, Password, Submit, Forgot buttons) • Exit: 2 (Login, Cancel) • Validations: 4 (format, session timeout, role-based access, password) • Prefilled: 2 (PIU, Department) • APIs: 2 (Auth, Profile) • Business rules: Session management (1 store) • UI: Static screen • Reports: 1 audit report
Bharosa - Factory Testing Web | Add New Vendor to Empanelled List | Screen 18 fields (Vendor details: 10 basic + 8 category fields) • Exit: 2 (Submit, Reject) • Validations: 8 (GST, PAN, email, phone, document type) • Prefilled: 15 (vendor categories, document templates) • APIs: 4 (Vendor service, Validation service, Document store, Approval workflow) • Business rules: Vendor approval logic (3 stores) • UI: Screen with 3 internal components (form, document upload, approval tracker) • Reports: 1 vendor compliance report |  |  |  |  | #N/A | #N/A | #N/A
Bharosa - Factory Testing Web | Create API and Service for Inspector | API insert inspector • API get inspector list • API update inspector • Service layer for business logic • Database integration • Error handling • Exit: 2 (Process, Revert) • Validations: 6 (data format, relationship integrity) • Prefilled: 20 (previous submissions, defaults) • APIs: 5 (Insert, Get, Update, Error handler, Audit logger) • Business rules: Data consistency (2 stores) • Reports: 1 API audit report
Bharosa - Factory Testing Web | View Factory Testing Summary Dashboard | Dashboard 5 fields (KPI widgets, Component summary, Vendor performance, Filter, Export) • Exit: 2 (View, Export) • Validations: 4 (date range, selection validation) • Prefilled: 25 (KPI defaults, last filters) • APIs: 3 (Dashboard service, Filter service, Summary service) • Business rules: KPI calculation logic (2 stores) • UI: Screen with 4 internal components (KPI widgets, charts, filters) • Reports: 2 summary reports (tabular & pie chart) with 2 data sources | [7 empty] | Value added factors
Bharosa - Factory Testing Web | Generate Compliance Reports | Screen 8 fields (Report template selector, batch option, signature field, retention settings) • Exit: 2 (Generate, Cancel) • Validations: 6 (template validation, batch selection, signature verification) • Prefilled: 20 (templates, signature defaults) • APIs: 5 (Report generator, Digital signature service, Archive service, Batch processor, Audit logger) • Business rules: Compliance validation & archival logic (3 stores) • UI: Screen with 3 internal components (template selector, batch grid, signature panel) • Reports: 3 compliance reports (tabular, certificate, batch summary) with 3 data sources | [7 empty] | Factor | Rating
Bharosa - Factory Testing Mobile | Inspector Login to Factory Testing | Screen 5 fields (Emp Id, Password, Remember, Sync status, Offline indicator) • Exit: 2 (Login, Cancel) • Validations: 3 (credentials, offline cache, sync) • Prefilled: 8 (last user, offline data) • APIs: 3 (Auth service, Offline cache, Sync service) • Business rules: Offline authentication (2 stores) • UI: Mobile static screen • Data Migration: Offline cache table • Reports: 1 mobile login audit report | [7 empty] | Data Communications | 0
Bharosa - Factory Testing Mobile | Fetch Component Details | Screen 6 fields (Component list, Filter by inspector, Type, Sub-type, Vendor, Test params) • Exit: 2 (View, Refresh) • Validations: 4 (inspector assignment, data availability) • Prefilled: 20 (assigned components, test parameters) • APIs: 3 (Component list service, Offline cache, Refresh service) • Business rules: Component assignment validation (2 stores) • UI: Mobile screen with 3 internal components (list, filter, details) • Reports: 1 assignment report | [7 empty] | Distributed Data Processing | 0
Bharosa - Factory Testing Mobile | Fill Details on Mobile App | Screen 20 fields (Inspector form: 10 fields + Component form: 10 fields) • Exit: 2 (Submit, Draft) • Validations: 10 (field formats, parameter ranges, form consistency) • Prefilled: 35 (inspector details, test parameters, norms) • APIs: 4 (Inspector service, Component service, Validation service, Save service) • Business rules: Test parameter validation & pass/fail logic (3 stores) • UI: Mobile screen with 3 internal components (inspector form, component form, status) • Reports: 1 test result report
Bharosa - Factory Testing Mobile | Upload Doc, Images, and Videos | Screen 8 fields (Document upload, Image multi-upload, Video upload, Compression, Progress, Storage) • Exit: 2 (Submit, Cancel) • Validations: 8 (file format, size limits, virus scan, compression status) • Prefilled: 15 (upload templates, file size limits, storage paths) • APIs: 6 (Document store, Image processor, Video processor, Compression engine, Virus scanner, Progress tracker) • Business rules: File validation & compression logic (3 stores) • UI: Mobile screen with external components (upload widget, progress bar, storage indicator) • Data Migration: File storage table with cleanup • Reports: 2 storage & upload audit reports with line charts (3 data sources) |  |  |  |  | #N/A | #N/A | #N/A | Performance | 0
Bharosa - Factory Testing Mobile | Increased Count of Inspector | Screen 15 fields (Inspector master table, Add form: 12 fields, Role assignment, Activation toggle, Count dashboard) • Exit: 3 (Add, Update, Deactivate) • Validations: 6 (inspector ID uniqueness, role validity) • Prefilled: 20 (role templates, inspector status) • APIs: 4 (Inspector master service, Role assignment service, Activation service, Count dashboard service) • Business rules: Role-based access & activation logic (2 stores) • UI: Screen with 4 internal components (master table, add form, role selector, count widget) • Reports: 1 inspector count & role report |  |  |  |  | #REF! | #REF! | #REF! | Heavily used Configuration | 3
Bharosa - System Integration | Bharosa Module Integration | API integration with Master module (Component master) • API integration with Sopan (OHT/WTP/IPS) • Data mapping logic • Error handling • Real-time sync • Exit: 2 (Sync, Validate) • Validations: 8 (data consistency, relationship integrity, format compliance) • Prefilled: 40 (mapping templates, sync rules) • APIs: 6 (Master API, Sopan API, Data mapper, Sync engine, Error handler, Audit logger) • Business rules: Complex data relationship & real-time sync logic (4 stores) • Reports: 3 integration audit reports with multiple complex charts (4 data sources) | [7 empty] | Transaction Rate | 4
[7 empty] | #REF! | #REF! | #REF!
[10 empty] | Online Data Entry | 3
[10 empty] | End-User Efficiency | 2
[10 empty] | Online Update | 1
[10 empty] | Complex Processing | 3
[10 empty] | Reusability | 4
[5 empty] | Total Count | 20 | #REF! | #REF! | #REF! | Installation Ease | 4
[10 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
|  | Productivity | 0.1413 | #N/A | [5 empty] | Facilitate Change | 4
|  | Size | 20 | Point | [5 empty] | Total | 36
|  | Effort | 141.5428 | Man hours
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total Planned effort | 165.1168 | Man hours
|  | Permissible Range(Man hours) | 173.3726 | 156.8609
[8 empty] | Yes | Yes

## DHARA CR Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Dhara - GM PIU User | Login Screen | No of input fields: <10; Exit scenario: 1; No of screens: <10; 1 data source; Static UI | 3 | 0 | 0 | 3 | #REF! | #REF! | #REF! |  |  | 1*1+3*1+5*0 =4
Dhara - GM PIU User | Habitation Mapping (OHT-wise) | User, Scheme, Component dropdown, Assign button, Search Field, Report table with 8 columns; No of input fields: <10; Exit scenario: 1; No of Validations: >5; Report Column: 8; Mobile Screen View: 2-4 internal components | 4 | 1 | 0 | 7
Dhara - GM PIU User | Component Assignment to FE | FE dropdown, Assistant Eng dropdown, FE/Assistant Eng selection, Scheme, Component, Assign button, Search functionality; No. of input fields: 6; No. of exit: 2; No of Validations: 3; Authorization rules | 2 | 1 | 0 | 5 | #N/A | #N/A | #N/A
Dhara - GM PIU User | CWGM/CWPM Mapping | Scheme dropdown, Component dropdown, Block selection, Search button, Reset button, Search input field, Report table with 10 columns, ADD NEW window (13 fields); No. of input fields: 4; No. of exit scenario: 2; No of Validations: 3; ADD NEW window (No. of input fields: 13; No. of exit scenario: 1; No of Validations: 2); Inside/Outside scheme village logic | 3 | 2 | 1 | 14
Dhara - Admin/Contractor | Month-wise Open/Close - Intake | Scheme dropdown, From Survey Date picker, To Survey Date picker, Search button, Reset button, Search input field, Export to Excel button, Report Table with 13 columns; No. of input fields: 4; No. of exit: 2; Report Column: 13; Mobile Screen View: 2-4 internal components; No of Validations: <5; Month-wise workflow; Approval rules | 1 | 1 | 0 | 4
Dhara - Admin/Contractor | Month-wise Open/Close - OHT | Scheme dropdown, Component Name dropdown, Village Name dropdown, From Survey Date picker, To Survey Date picker, Search button, Reset button, Search input, Export to Excel button, Report table with 24 columns; No. of input field: 6; No. of exit: 2; Report table: 24 column; Mobile Screen View: 2-4 internal components; No of Validations: <5; Approval/Fill workflow; Data locking rules | 0 | 2 | 1 | 11 |  |  |  | Value added factors
Dhara - Admin/Contractor | Month-wise Open/Close - WTP | Scheme dropdown, From Survey Date picker, To Survey Date picker, Search button, Reset button, Report Table with 14 columns; No. of input fields: 3; No. of exits: 2; Report table: 14 column; No of Validations: 3; Month-wise workflow; Status update rules | 0 | 1 | 1 | 8 |  |  |  | Factor | Rating
Dhara - Admin/Contractor | Month-wise Open/Close - Bulk User | Scheme dropdown, Month selector, Search button, Report Table with 8 columns; No. of input fields: 3; No. of exits: 2; Report table: 8 column; No of Validations: 3; Aggregation logic | 1 | 0 | 0 | 1 |  |  |  | Data Communications | 0
Dhara - FE Mobile | Meter Reading Modification | Mobile form with meter parameters (Meter functional, Meter not functional, Meter replace, No water supply); Default value selection; Validation rules; Offline cache support; Real-time sync; Form submission with confirmation | 0 | 1 | 1 | 8 |  |  |  | Distributed Data Processing | 0
Dhara - FE Mobile | Meter Survey Update | Survey update form for Intake, WTP, OHT, Village meters; Component-wise tracking; Historical data capture; Validation against master; Report generation; Data persistence; Mobile-first design | 0 | 1 | 1 | 8
Dhara - Admin | WTP Meter Configuration | Configuration parameters for WTP meters; Meter mapping to components; Validation rules; Range limits; API integrations (3-4); Audit trail logging; Change tracking; Multi-store data validation | 0 | 1 | 1 | 8 |  |  |  | Performance | 0
Dhara - GM PIU/TL | Village Habitation Mapping (OHT) | Village selection dropdown; Habitation assignment grid; OHT component linking; Approval workflow (2 exits); Report view with drill-down; Validation rules (>5); Data locking mechanism; Audit trail | 0 | 1 | 1 | 8 | #N/A | #N/A | #N/A | Heavily used Configuration | 3
Dhara - Admin/Contractor Report | Water Supply Reports (DWSR, MWSR, Scheme, Village, UFW) | Multi-report view (5+ report types); No of input fields: 3 (filters); Exit scenario: 1 (View); Tabular report format; >10 columns per report; 1 data source; Drill-down functionality; Export to PDF/Excel; Filter validation; Report generation engine; Historical data comparison | 3 | 0 | 1 | 8 | #REF! | #REF! | #REF! | Transaction Rate | 4
CMMI L5 Documentation | CMMI L5 Documentation & Training | VC training materials; Process documentation; User guides; Best practices; Knowledge transfer; Quality assurance procedures; Traceability matrices | 0 | 0 | 0 | 0
[5 empty] | TOTAL DHARA CR ESTIMATION | 163 | #REF! | #REF! | #REF! | Online Data Entry | 3
[7 empty] | #REF! | #REF! | #REF! | End-User Efficiency | 2
[10 empty] | Online Update | 1
|  | Productivity | 0.14127 | #N/A | [5 empty] | Complex Processing | 3
|  | Size | 163 | Point | [5 empty] | Reusability | 4
|  | Effort | 1153.7944 | Man hours | [5 empty] | Installation Ease | 4
|  | VAF | 1.01 | [6 empty] | Operational Ease | 4
|  | Risk contingency | 5% | [6 empty] | Multiple Sites | 4
|  | Project Management | 10% | [6 empty] | Facilitate Change | 4
|  | Total effort | 1345.9589 | Man hours | [5 empty] | Total | 36
|  | Permissible Range(Man hours) | 1413.2568 | 1278.6609

## MASTER CR Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Master - GM/Contractor | Login Screen | Emp Id input field, User Name input field, Password input field, Submit button, Forgot UserName button, Forgot Password link button; No of input fields: 3; Exit scenario: 1; No of Validations: 2; Static UI; Session management | 1 | 1 | 0 | 4
Master - GM/Contractor | Village Component Mapping (Other Scheme) | Data Entry fields (8-10); Multi-scheme selection dropdown; Component mapping grid; Water supply source dropdown; Validation rules (5-8); PIU-level filtering; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Up to 3 data stores; Screen with 2-4 internal components | 0 | 2 | 1 | 9
Master - Contractor | Pipeline Master Zone Numbers | Zone number input field; Contractor-level access control; Zone validation logic; Auto-increment functionality; Master data grid display; No of input fields: 8-10; Exit scenario: 2; No of Validations: 5; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Single/multiple data stores | 0 | 1 | 1 | 8
Master - Contractor | Edit Functionality Before Submission | Edit button on each row; Pre-submission validation; Change tracking log; Freeze mechanism post-submission; Rollback capability; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 2-3; Business rules: Version control, authorization across data stores; Reports: Change history log | 0 | 1 | 1 | 8 | #VALUE! | #VALUE! | #VALUE!
Master - GM/Contractor | Bulk Meter Village Mapping | Village dropdown (147 schemes); Bulk meter assignment grid; Meter ID validation; Habitation linkage; Multi-village selection; Upload functionality; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 30-50; API Integrations: 2-5; Business rules: Validation across multiple data stores; Bulk operation support | 0 | 1 | 1 | 8
Master - GM/Contractor | Habitation-OHT Mapping (Scheme Village) | Habitation dropdown by scheme; OHT selection grid (3+ OHTs per scheme); Geospatial validation; Scheme boundary checking; Multi-habitation support; No of input fields: 15-20; Exit scenario: 2-3; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 3-5; Business rules: Complex geo-spatial rules across multiple stores; Screen with external GIS components | 0 | 0 | 2 | 10 | #REF! | #REF! | #REF! | Value added factors
Master - GM/Contractor | Outside Scheme Village Mapping | Outside village search/filter; Non-scheme village grid; Component assignment for external villages; Water supply source dropdown; Approval workflow; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Non-scheme village rules across multiple stores; Workflow integration | 0 | 1 | 1 | 8 |  |  |  | Factor | Rating
Master - GM/Contractor | WTP Meter Mapping (147 Schemes) | WTP dropdown (147 schemes); Meter configuration panel; Parameter assignment (15+ parameters); Scheme-wise meter validation; Multi-meter support per WTP; No of input fields: 15+; Exit scenario: 2; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 3-5; Business rules: Complex parameter validation across multiple data stores; Advanced configuration | 0 | 1 | 1 | 8 |  |  |  | Data Communications | 0
Master - FE Pipeline | Pipeline Master-RFI Integration | API integration (RFI module); Stage-wise data sync (5 stages); Real-time update mechanism; Error handling & logging; Multi-stage validation; No of input fields: 8-10; Exit scenario: 2; No of Validations: 5-10; API Integrations: 3-5; Business rules: Stage-dependent validation across multiple stores; Sync protocols; Audit trail | 0 | 1 | 1 | 8 |  |  |  | Distributed Data Processing | 0
Master - FE Pipeline | Habitation & Data Issue Mapping (PIU) | Habitation dropdown by PIU; Issue type dropdown (5+ categories); Issue severity assignment; Photo upload with compression; GPS location tracking; PIU-level filtering; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-5 (file upload, GPS, validation); Business rules: Issue severity rules; Photo processing | 0 | 1 | 1 | 8
Master - All Users | Master Data Reports | Report type dropdown (3 types); Drill-down functionality; Export to Excel/PDF; Multi-PIU filter; Date range selection; Dashboard KPI display; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; Prefilled fields: 10-30; API Integrations: 2-3; Reports: Tabular report (3 types), <10 columns, 1 data source; KPI dashboard | 1 | 0 | 0 | 3 |  |  |  | Performance | 0
Master - Admin | User Role Management | Role creation panel; Permission matrix (10+ permissions); Audit trail logging; Cross-module access control; User activation/deactivation; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; Prefilled fields: 30-50; API Integrations: 2-3; Business rules: RBAC logic, permission matrix across multiple stores; Access control; Audit logging | 0 | 1 | 0 | 3 |  |  |  | Heavily used Configuration | 3
Master - GM | Master Data Validation & QA | Validation engine (15+ rules); Data cleansing logic; Duplicate detection; Compliance check dashboard; Error report generation; No of input fields: 5-10; Exit scenario: 1; No of Validations: 10+; Prefilled fields: Not applicable; API Integrations: 2-3; Business rules: Complex validation rules across multiple stores; QA logic; Duplicate detection; Reports: Validation error report, compliance dashboard | 1 | 0 | 0 | 1 |  |  |  | Transaction Rate | 4
TOTAL MASTER CR ESTIMATION | 13 Functionalities | All Guidelines-based estimations included | 3 | 10 | 8 | 47 | #REF! | #REF! | #REF! | Online Data Entry | 3
[10 empty] | End-User Efficiency | 2
[10 empty] | Online Update | 1
[10 empty] | Complex Processing | 3
[10 empty] | Reusability | 4
[10 empty] | Installation Ease | 4
[10 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
[10 empty] | Facilitate Change | 4
[10 empty] | Total | 36
|  | Productivity | 0.14127 | #N/A
|  | Size | 47 | Point
|  | Effort | 332.6892 | Man hours
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total effort | 388.0986 | Man hours
|  | Permissible Range(Man hours) | 407.5035 | 368.6936

## NIRMAL CR Estimation
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Nirmal - Change Request - WTP, OHT Report | WTP Report Parameter Changes | Parameter modification capability; Report template restructure; New parameter field addition; Validation rules for updated parameters; Version control; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Parameter dependency across data stores | 0 | 0 | 1 | 6
Nirmal - Change Request - WTP, OHT Report | Contractor/FE login - WTP, Intake Buffer Increase to 200m | Buffer distance configuration field; GPS range increase from default (5m) to 200m; Location validation; Mobile app parameter update; Offline sync; No of input fields: 8-10; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Buffer zone validation across location data stores | 0 | 1 | 0 | 4
Nirmal - Change Request - Beneficiary Report | Range Facility for Date Option | Date picker with range selection (from-to dates); Calendar widget integration; Date range validation; Report refresh logic; Filter application; No of input fields: 2-3; Exit scenario: 1-2; No of Validations: 3-5; Prefilled fields: <10; API Integrations: 1-2; Business rules: Date range validation | 1 | 0 | 0 | 3
Nirmal - Change Request - Beneficiary Report | Water Sample ID Search Option | Sample ID search input field; Real-time search and filter logic; Auto-suggestion from sample registry; Result display with drill-down; Metadata retrieval; No of input fields: 1; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3 (sample lookup, metadata fetch); Business rules: Sample ID validation, lookup across data stores | 0 | 1 | 0 | 5 | #VALUE! | #VALUE! | #VALUE!
Nirmal - Change Request | Report Parameter Changes | Parameter configuration panel; Field reordering functionality; Version control for changes; Field dependency management; Backward compatibility assurance; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; Prefilled fields: 30-50; API Integrations: 2-3; Business rules: Parameter dependency, version control across stores | 0 | 1 | 1 | 8
Nirmal - Change Request | Mobile App OHT/Intake/WTP Changes | OHT range calculation logic with buffer (±5m); WTP aggregation algorithm; Intake meter reading logic; Response time optimization (target <2s); API data source integration; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 3-5; Business rules: Complex calculation rules, performance optimization; Multiple data stores | 0 | 1 | 1 | 8 | #REF! | #REF! | #REF! | Value added factors
Nirmal - Change Request | User Management (Nirmal-Dhara Integration) | User role configuration interface; Permission assignment matrix (10+ permissions); Audit trail logging for access; UI accessibility compliance; Cross-module visibility rules; No of input fields: 15-20; Exit scenario: 2-3; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 2-3; Business rules: RBAC implementation, cross-module authorization; Audit logging across stores | 0 | 1 | 1 | 8 |  |  |  | Factor | Rating
CMMI | [9 empty] | Data Communications | 0
[10 empty] | Distributed Data Processing | 0
[5 empty] | Total Size | 10 |  |  |  | Performance | 0
[10 empty] | Heavily used Configuration | 3
[10 empty] | Transaction Rate | 4
[7 empty] | #REF! | #REF! | #REF! | Online Data Entry | 3
[10 empty] | End-User Efficiency | 2
[10 empty] | Online Update | 1
[10 empty] | Complex Processing | 3
[10 empty] | Reusability | 4
[10 empty] | Installation Ease | 4
[10 empty] | Operational Ease | 4
|  | Productivity | 0.14127 | #N/A | [5 empty] | Multiple Sites | 4
|  | Size | 11 | Point | [5 empty] | Facilitate Change | 4
|  | Effort | 77.8634 | Man hours | [5 empty] | Total | 36
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total effort | 90.8316 | Man hours
|  | Permissible Range(Man hours) | 95.3732 | 86.29

## Sahbhagita CR
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Sahbhagita - Contractor/GM | Login Screen | Emp Id input field, User Name input field, Password input field, Submit button, Forgot UserName button, Forgot Password link button; No of input fields: 3; Exit scenario: 1; No of Validations: 2; Static UI; Session management; Single data store | 1 | 1 | 0 | 4
Sahbhagita - GM | Report View Changes (Village-wise Triggers) | Report filtering by village; Village-wise dropdown filter; Trigger mechanism for data refresh; SQL query optimization; Dashboard integration; Report table display; No of input fields: 5-8; Exit scenario: 1-2; No of Validations: 3-5; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Village-based filtering across data stores; Screen with 2-4 internal components | 0 | 1 | 0 | 3
Sahbhagita - PM | Video Upload Option in Activity | Video file input (up to 10MB); File format validation (MP4, AVI, MOV); Upload progress indicator; Video compression logic; Storage path configuration; Thumbnail generation; No of input fields: 8-10; Exit scenario: 2; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-5 (upload service, compression, storage); Business rules: File size validation, compression rules; Screen with external video upload component | 0 | 0 | 1 | 5
[7 empty] | #N/A | #N/A | #N/A
TOTAL SAHBHAGITA CR ESTIMATION | 3 Change Request Functionalities | All Guidelines-based estimations included | 1 | 2 | 1 | 10
[7 empty] | #REF! | #REF! | #REF! | Value added factors
CMMIL5 Documentation | CMMIL5 Document creation/Meeting | [8 empty] | Factor | Rating
[5 empty] | Total Size | 10 |  |  |  | Data Communications | 0
[10 empty] | Distributed Data Processing | 0
[10 empty] | Performance | 0
[10 empty] | Heavily used Configuration | 3
[10 empty] | Transaction Rate | 4
[7 empty] | #REF! | #REF! | #REF! | Online Data Entry | 3
[10 empty] | End-User Efficiency | 2
[10 empty] | Online Update | 1
[10 empty] | Complex Processing | 3
|  | Productivity | 0.14127 | #N/A | [5 empty] | Reusability | 4
|  | Size | 10 | Point | [5 empty] | Installation Ease | 4
|  | Effort | 70.7849 | Man hours | [5 empty] | Operational Ease | 4
|  | VAF | 1.01 | [6 empty] | Multiple Sites | 4
|  | Risk contingency | 5% | [6 empty] | Facilitate Change | 4
|  | Project Management | 10% | [6 empty] | Total | 36
|  | Total effort | 82.5742 | Man hours
|  | Permissible Range(Man hours) | 86.7029 | 78.4455

## Sopan CR
| Type Of work |  | New Development
Project Name
Remark
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Sopan - Contractor Web Interface | OHT Type Selection (Conventional/Precast) | UI Form with dropdown; OHT type dropdown (Conventional/Precast); Validation rules for type selection; Database schema update with new field; Form submission workflow; No of input fields: 10-15; Exit scenario: 2 (Save, Cancel); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Type validation across data stores | 1 | 2 | 0 | 7
Sopan - Contractor Web Interface | Delete Wrongly Entered OHT/IPS/WTP Records | Delete button/function on each record; Confirmation dialog with warning; Audit trail logging (who, when, what); Permission check (role-based access); Soft delete mechanism; Rollback capability; No of input fields: Minimal (confirmation); Exit scenario: 2-3 (Delete, Cancel, Undo); No of Validations: 5-10; API Integrations: 2-3; Business rules: Authorization, audit logging across multiple stores; Screen with 2-4 internal components | 0 | 2 | 1 | 11
Sopan - Contractor Web Interface | Updated WTP Form Fields | Form layout redesign; Field addition/removal (5+ fields); Validation logic update; Database migration scripts; Data mapping; No of input fields: 10-15; Exit scenario: 2 (Save, Cancel); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Field validation across data stores; Data Migration: Schema update with validation | 1 | 2 | 0 | 7
Sopan - Contractor Web Interface | Updated IPS Form Fields | Form layout redesign; Field addition/removal (5+ fields); Validation logic update; Database migration scripts; Data mapping; No of input fields: 10-15; Exit scenario: 2 (Save, Cancel); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Field validation across data stores; Data Migration: Schema update with validation | 1 | 2 | 0 | 7 | #VALUE! | #VALUE! | #VALUE!
Sopan - Contractor Mobile App | Mobile APK with OHT Type Selection | Mobile UI with dropdown component; OHT type selection (Conventional/Precast); Offline storage capability; Sync mechanism when online; Form validation; No of input fields: 10-15; Exit scenario: 2 (Save, Sync); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 2-3; Business rules: Offline-first design, sync rules; mobile App-UI: Screen with 2-4 internal components | 0 | 2 | 1 | 11
Sopan - Contractor Mobile App | Mobile APK with Updated WTP Form | Mobile form layout; Field validation logic; Image capture functionality; GPS integration; Offline support; Photo compression; No of input fields: 10-15; Exit scenario: 2 (Submit, Draft); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-4 (photo upload, GPS, sync); Business rules: GPS validation, photo quality checks; mobile App-UI: Screen with 2-4 internal components | 1 | 2 | 0 | 7 | #REF! | #REF! | #REF! | Value added factors
Sopan - Contractor Mobile App | Mobile APK with Updated IPS Form | Mobile form layout; Field validation logic; Image capture functionality; GPS integration; Offline support; Photo compression; No of input fields: 10-15; Exit scenario: 2 (Submit, Draft); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-4 (photo upload, GPS, sync); Business rules: GPS validation, photo quality checks; mobile App-UI: Screen with 2-4 internal components | 1 | 2 | 0 | 7 |  |  |  | Factor | Rating
Sopan - Contractor Mobile App | Updated IPS Component Fields in Mobile | Mobile component form; Dynamic field rendering; Component-specific validation; Local storage for draft; Field dependency management; No of input fields: 10-15; Exit scenario: 2 (Save, Cancel); No of Validations: 5-10; Prefilled fields: 30-50; API Integrations: 2-3; Business rules: Component field validation; mobile App-UI: Screen with 2-4 internal components | 0 | 2 | 0 | 6 |  |  |  | Data Communications | 0
Sopan - GM Module | Edit Contractor Details | Edit form for contractor information; Permission control (GM-only access); Audit log for changes; Validation rules (GST, PAN, contact); Change tracking; No of input fields: 10-15; Exit scenario: 2-3 (Save, Cancel, Reset); No of Validations: 5-10; Prefilled fields: 30-50; API Integrations: 2-3; Business rules: Authorization, audit trail across multiple stores | 1 | 1 | 1 | 8 |  |  |  | Distributed Data Processing | 0
Sopan - GM Reports | Drill-down Reports (OHT/WTP/Intake) | Report interface with multi-level drill-down; Drill-down logic (District → Block → Village → Component); Data aggregation by hierarchy; Export function (Excel/PDF); Filter options (scheme, date, component type); No of input fields: 10-15; Exit scenario: 2 (View, Export); No of Validations: 5-10; API Integrations: 3-5; Business rules: Aggregation logic across multiple data stores; Reports: 3+ data sources with complex drill-down, report types 3-5 | 0 | 1 | 1 | 8
Sopan - GM Reports | Panchanama Count Reports | Report generation engine; Count logic for Panchanama documents; Filter options (scheme, date, status); PDF export functionality; Summary dashboard; No of input fields: 5-10; Exit scenario: 1-2; No of Validations: 3-5; Prefilled fields: 10-30; API Integrations: 2-3; Reports: Tabular report with <10 columns, 1 data source | 0 | 1 | 0 | 3 |  |  |  | Performance | 0
Sopan - GM Document Upload | Separate Upload for PDF and DWG Files | File upload interface (dual mode); File type validation (PDF/DWG); Storage management (separate folders); Document viewer integration; File size validation (max 10MB); Metadata capture; No of input fields: 8-10; Exit scenario: 2 (Upload, Cancel); No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-4 (file upload, storage, viewer, validation); Business rules: File type validation, storage organization across stores | 0 | 1 | 1 | 8 |  |  |  | Heavily used Configuration | 3
Sopan - System Integration | Seamless Integration with Jal Rekha Modules | API integration layer; Database sync mechanism; Error handling & logging; Rollback mechanism; Cross-module data validation; Real-time updates; Exit scenario: Not applicable; No of Validations: 10+ (cross-module); API Integrations: 5+ (Dhara, Master, Nirmal, Anusharan); Business rules: Complex integration logic, data consistency across multiple data stores; Integration: >5 modules | 0 | 0 | 1 | 5 |  |  |  | Transaction Rate | 4
Sopan - GM Reports | Plan vs Actual Timeline Report | Timeline comparison logic; Gantt chart visualization; Variance calculation (planned vs actual); Color-coded status indicators; Drill-down by stage; No of input fields: 8-10; Exit scenario: 2 (View, Export); No of Validations: 3-5; API Integrations: 2-3; Reports: Line/Bar charts with 2-3 data sources, report types 3-5 | 0 | 1 | 0 | 3
Sopan - Contractor Mobile App | OHT Completion Status Sync with Anusharan | OHT completion flag update; API sync with Anusharan/RFI module; Status change notification; Real-time integration; Error handling; No of input fields: Minimal; Exit scenario: 1; No of Validations: 3-5; API Integrations: 3-5 (Sopan, Anusharan, notification); Business rules: Status sync rules across modules | 0 | 1 | 0 | 3 | #REF! | #REF! | #REF! | Online Data Entry | 3
[10 empty] | End-User Efficiency | 2
TOTAL SOPAN CR ESTIMATION | 15 Change Request Functionalities | All Guidelines-based estimations included | 7 | 24 | 6 | 81 |  |  |  | Online Update | 1
[5 empty] | Total Size | 81 |  |  |  | Complex Processing | 3
[10 empty] | Reusability | 4
[10 empty] | Installation Ease | 4
[10 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
[10 empty] | Facilitate Change | 4
[10 empty] | Total | 36
|  | Productivity | 0.14127 | #N/A
|  | Size | 81 | Point
|  | Effort | 573.358 | Man hours
|  | VAF | 1.01
|  | Risk contingency | 5%
|  | Project Management | 10%
|  | Total effort | 668.8507 | Man hours
|  | Permissible Range(Man hours) | 702.2933 | 635.4082