## DC JultoOct
Sr No | Department | Project Name | Module | Name of Sub Modules | Features/Functionality | CR | Size USP_FP | Hours Consumed | Planned Effort (Person Hours) | Actual Effort (Person Hours) | Planned Start Date (module) | Planned End Date (module) | Actual Start Date (module) | Actual End Date (module) | Requirement Analysis Start Date (module) | Requirement Analysis End Date (module) | Design Start Date (module) | Design End Date (module) | Coding Start Date (module) | Coding End Date (module) | Testing Start Date (module) | Testing End Date (module) | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Testing Review Efforts | Requirement Review Efforts | Design Review Effort | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Productivity | DRE | Requirement Rate | Design Rate | Code Rate | Testing Rate | DRE | Productivity | Req_Rate | Des_Rate | Code_Rate | Test_Rate | Cycle Time | Req_CT | Des_CT | Code_CT | Test_CT | DRE-1 | Code Review Per Size | Total Review Defects | Internal Testing
1 | Public Health Engineering Department | Jal Rekha | FHTC | FE / Reports | 1) FE Login - Visit Each Village Household API Integration 2) FE login - Connection Tap check, Update and upload with Beneficiary & Tap Photo 3) FE login - Connection rejected (Not proper) then send it to GM & contractor 4) FE login - Connection accepted then send it to GM 5) API Whitelisting 6) NIC API Integration 7) HSC Report with all details and photo of beneficiary (mandatory) for FHTC 8) FE send rejected Tap Connection send to Contractor |  | 33 | 232 | 272 | 272 | 2025-08-18 | 2025-09-22 | 2025-08-18 | 2025-09-26 | 2025-08-18 | 2025-08-22 | 2025-08-23 | 2025-08-26 | 2025-08-29 | 2025-09-13 | 2025-09-19 | 2025-09-26 | 25 | 23 | 107 | 11 | 48 | 8 | 6 | 4 | 1 | 0 | 3 | 1 | 1 | 1 | [7 empty] | 0.14224 | 1.0645 | 1.2222 | 0.27966 | 0.58929 | 1.1818 | 0.12121 | 0.090909 | 0.45455 | 0.21212 | 0.8 | 0.090909 | 0.12121 | 0.030303
|  |  |  | Change request FHTC | 1) Earlier we used NIC services for API Integration. Now updated to Samagra API 2) Updated APK through API to integrate with Samagra 3) Updated Entries for New HSC Report 4) Contractor update the beneficiary tap connection with photograph to GM |  | 16 | 112 | 132 | 132 | 2025-10-13 | 2025-10-30 | 2025-10-14 | 2025-10-29 | 2025-10-14 | 2025-10-16 | 2025-10-16 | 2025-10-18 | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-29 | 12 | 9 | 48 | 5 | 32 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | [7 empty] | 0.14286 | 1.1429 | 1.6 | 0.30189 | 0.45714 | 0.9375 | 0.125 | 0.125 | 0.3125 | 0.1875 | 1 | 0.0625 | 0.1875 | 0
2 | Public Health Engineering Department | Jal Rekha | O&M Billing | GM | 1) GM of O&M module Login and fill basic details 2) GM Advance form details SLBM features & other additional functionalities, scheme status 3) GM Scheme status and financial calculation for billing 4) GM uploads documents and data is fetched from Dhara and Nirmal module 5) GM under a scheme assign it to a Contractor 6) Contractor generate Bill 7) GM PIU or SQC Edit it and forward to GM of O&M then to PMC 8) All can check remarks then forward to Deputy Manager will only processs final bill amount with further remarks 9) PMC recommendations letter annexure duly verified |  | 41 | 288 | 342 | 288 | 2025-07-28 | 2025-09-05 | 2025-07-28 | 2025-08-29 | 2025-07-28 | 2025-08-03 | 2025-08-04 | 2025-08-07 | 2025-08-07 | 2025-08-21 | 2025-08-22 | 2025-08-29 | 24 | 21 | 156 | 12 | 63 | 4 | 4 | 4 | 1 | 0 | 3 | 1 | 2 | 0 | [7 empty] | 0.14236 | 1.4643 | 1.64 | 0.24405 | 0.61194 | 0.78049 | 0.14634 | 0.073171 | 0.34146 | 0.17073 | 0.8 | 0.073171 | 0.097561 | 0.02439
|  |  |  | Contractor | 1) Contractor Basic details, Advance details 2) Fill Financial Calculations as per CPI 3) O&M Billing PIU and SQC page development 4) O&M Billing Manpower page development & Residual Pressure SP 5) O&M Mapping Bulk users, Gross Bill Deduction, & Net Payable Bill 6) O&M Billing Process for RM & Village & Mapping Management Norms 7) Dhara water supply entries from Portal |  | 32 | 224 | 278 | 224 | 2025-09-01 | 2025-09-22 | 2025-09-01 | 2025-09-19 | 2025-09-01 | 2025-09-03 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-14 | 2025-09-14 | 2025-09-19 | 21 | 16 | 119 | 6 | 55 | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 0 | [7 empty] | 0.14286 | 1.3913 | 1.7778 | 0.256 | 0.55172 | 0.5625 | 0.0625 | 0.0625 | 0.25 | 0.15625 | 0.8 | 0.0625 | 0.125 | 0.03125
|  |  |  | Workflow b/w O&M GM & Higher officials | 1) Establish flow between GM, Contractor 2) GM O&M, CGM, PD, CFO, CA then MD final approval of bill and status 3) Retrieve all RA bill data correctly & Prepare test data in om_ra_bill table 4) RA Bill is based on scheme id & contractor id, always choose bill month & increment after first year and next month 1 days 5) Edit option and resend to PIU GM then GM send to Contractor. |  | 16 | 112 | 102 | 112 | 2025-09-20 | 2025-09-26 | 2025-09-21 | 2025-09-29 | 2025-09-21 | 2025-09-22 | 2025-09-22 | 2025-09-23 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-29 | 9 | 10 | 55 | 3 | 29 | 2 | 2 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | [7 empty] | 0.14286 | 1.4545 | 1.3333 | 0.27586 | 0.51613 | 0.5 | 0.0625 | 0.0625 | 0.1875 | 0.1875 | 0.66667 | 0.0625 | 0.125 | 0.0625
|  |  |  | Change request O&M Billing | 1) Save as Draft at time of entry by GM 2) Census Population location hierarchy needs to be corrected and Next change to make Census population open 3) SLBM Section fields Quality, Quantity, Pressure, UFW, and Complaint, an "Other" option should be added to both the Norms and Penalty dropdowns 4) Changes for Penalty label (Name, Radio button) 5) Type of Increment for CPIW & Yearly calculation changes 6) Scheme Status section ( View Document, Eligibility Increment, Year month update for O & M start & end date) 7) GST services option open for O &M 8) Document upload Yes/No where if done then freeze the screen |  | 42 | 296 | 352 | 296 | 2025-09-29 | 2025-11-03 | 2025-09-29 | 2025-10-31 | 2025-09-29 | 2025-10-03 | 2025-10-04 | 2025-10-08 | 2025-10-09 | 2025-10-21 | 2025-10-24 | 2025-10-31 | 24 | 23 | 159 | 5 | 74 | 5 | 4 | 2 | 0 | 1 | 3 | 1 | 0 | 0 | [7 empty] | 0.14189 | 1.5 | 1.68 | 0.2561 | 0.53165 | 0.7619 | 0.095238 | 0.095238 | 0.28571 | 0.16667 | 0.8 | 0.071429 | 0.095238 | 0.02381
3 | Public Health Engineering Department | Jal Rekha | Bharosa | Factory Testing Web | 1) Assign Components to concerned Role 2) Review and visualize generated report of test samples 3) New Vendor to be added 4) Create API and Service for Bharosa insert and get Inspector Details |  | 10 | 64 | 80 | 64 | 2025-10-09 | 2025-10-19 | 2025-10-10 | 2025-10-16 | 2025-10-10 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-15 | 2025-10-15 | 2025-10-16 | 7 | 6 | 30 | 3 | 13 | 2 | 1 | 2 | 1 | 0 | 1 | 1 | 1 | 0 | [7 empty] | 0.15625 | 1.25 | 1.25 | 0.30303 | 0.66667 | 0.6 | 0.1 | 0.1 | 0.2 | 0.1 | 0.66667 | 0.1 | 0.2 | 0.1
|  |  |  | Factory Testing Mobile | 1) Bharosa Factory testing module entry 2) Fetch Components details as assigned by GM 3) Fill Details on Mobile app of inspector & Component to be tested 4) Upload Doc, Images and Videos 5) Increased count of Inspector |  | 10 | 64 | 85 | 64 | 2025-10-20 | 2025-10-31 | 2025-10-22 | 2025-10-30 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-25 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 6 | 8 | 28 | 4 | 14 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | [7 empty] | 0.15625 | 1.4286 | 1.1111 | 0.3125 | 0.625 | 0.8 | 0.1 | 0.1 | 0.3 | 0.2 | 0.66667 | 0.1 | 0.2 | 0.1
3 | Public Health Engineering Department | Jal Rekha | Dhara Rework | Change Request - GM PIU User/ TL | 1) Updated Habitation Mapping functionality to each OHT or by OHT wise and provided VC training 2) Assigned functionality to FE Mobile user 3) CWGM/CWPM (WTP) functionality added for inside and outside scheme villages mapping and provided VC training 4) Month wise open/close records - To approve/fill meter reading month wise of each component - Intake 5) Month wise open/close records - To approve/fill meter reading month wise of each component - OHT 6) Month wise open/close records - To approve/fill meter reading month wise of each component - WTP 7) Month wise open/close records - To approve/fill meter reading month wise of each component - Bulk User 8) Intake,wtp,oht and Village meter reading modification in web 9) update meter survey for Intake,wtp,oht and Village 10) For WTP added meters 11) Now all village and habitation open for OHT mapping in the scheme 12) CMMI Documentation |  | 92 | 648 | 740 | 648 | 2025-07-01 | 2025-08-20 | 2025-07-03 | 2025-08-12 | 2025-07-03 | 2025-07-11 | 2025-07-12 | 2025-07-18 | 2025-07-22 | 2025-08-04 | 2025-08-01 | 2025-08-12 | 36 | 24 | 328 | 30 | 172 | 30 | 16 | 12 | 1 | 1 | 3 | 2 | 1 | 1 | [7 empty] | 0.14198 | 1.7692 | 2.5556 | 0.25698 | 0.45545 | 0.43478 | 0.086957 | 0.065217 | 0.1413 | 0.11957 | 0.71429 | 0.032609 | 0.054348 | 0.021739
|  |  |  | Change Request - FE / Mobile User | 1) Assigned Habitation wise mapping to FE 2) Updated few changes in the parameters of meter - Meter functional, Meter not functional, Meter replace, No water supply where default value was set. 3) Assigned WTP meter where entries are repeated for OHT mapping |  | 41 | 288 | 342 | 288 | 2025-08-12 | 2025-08-30 | 2025-08-13 | 2025-08-28 | 2025-08-13 | 2025-08-16 | 2025-08-15 | 2025-08-18 | 2025-08-18 | 2025-08-24 | 2025-08-24 | 2025-08-28 | 24 | 20 | 128 | 18 | 76 | 14 | 4 | 4 | 2 | 2 | 3 | 1 | 1 | 2 | [7 empty] | 0.14236 | 1.4643 | 1.7083 | 0.28082 | 0.45556 | 0.36585 | 0.073171 | 0.073171 | 0.14634 | 0.097561 | 0.875 | 0.073171 | 0.17073 | 0.02439
|  |  |  | Change Request - Admin / Contractor Report View | 1) View Updated / Changed Water Supply Reports - a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report 2) Drill down features for all reports & correct mapping data 3) Updated changes in Reports ( DWSR, MWSR, Village wise , scheme wise, UFWR) 4) Updated Bulk user report & Dhara Report added at Home Screen of Jal Rekha Portal on public domain 5) CMMI Documentation |  | 30 | 208 | 263 | 208 | 2025-09-01 | 2025-09-30 | 2025-09-01 | 2025-09-25 | 2025-09-01 | 2025-09-03 | 2025-09-04 | 2025-09-06 | 2025-09-09 | 2025-09-18 | 2025-09-20 | 2025-09-25 | 18 | 12 | 95 | 6 | 69 | 4 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | [7 empty] | 0.14423 | 1.5 | 2.1429 | 0.29703 | 0.41096 | 0.8 | 0.066667 | 0.066667 | 0.3 | 0.16667 | 0.8 | 0.066667 | 0.13333 | 0.033333
5 | Public Health Engineering Department | Jal Rekha | Master | Change Request - GM / Contractor | 1) Mapping village and its components with Water supply through other Scheme of PIU 2) Pipeline master zone numbers are added at contractor level 3) Edit functionality provided to contractor before final submission 4) Updated Bulk Meter village mapping 5) Mapping through habitation of scheme village and OHT 6) Mapping outside scheme village also map 7) WTP meter mapping option added for all 147 schemes 8) CMMI Documentation |  | 38 | 264 | 301 | 264 | 2025-07-01 | 2025-07-22 | 2025-07-01 | 2025-07-19 | 2025-07-01 | 2025-07-04 | 2025-07-05 | 2025-07-07 | 2025-07-07 | 2025-07-15 | 2025-07-15 | 2025-07-19 | 22 | 15 | 132 | 10 | 69 | 10 | 4 | 2 | 0 | 1 | 3 | 1 | 1 | 0 | [7 empty] | 0.14394 | 1.4615 | 2.2353 | 0.26761 | 0.48101 | 0.47368 | 0.078947 | 0.052632 | 0.21053 | 0.10526 | 0.8 | 0.078947 | 0.10526 | 0.026316
|  |  |  | Change Request - FE Pipeline Mater | 1) Updated Pipeline master data integration with RFI Module at various stage 2) Mapping habitations and data issues at PIU level |  | 10 | 64 | 88 | 64 | 2025-08-04 | 2025-08-19 | 2025-08-05 | 2025-08-13 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-12 | 2025-08-12 | 2025-08-13 | 8 | 5 | 32 | 2 | 13 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | [7 empty] | 0.15625 | 1.1111 | 1.6667 | 0.29412 | 0.66667 | 0.8 | 0.1 | 0.1 | 0.4 | 0.1 | 0.75 | 0.1 | 0.3 | 0.1
6 | Public Health Engineering Department | Jal Rekha | Nirmal | Change request - WTP, OHT Report | 1) WTP Report parameter changes 2) Contractor/FE login - WTP, Intake buffer increase to 200 meter for Raw water sample collection on |  | 6 | 42 | 53 | 42 | 2025-07-08 | 2025-07-21 | 2025-07-09 | 2025-07-15 | 2025-07-09 | 2025-07-10 | 2025-07-10 | 2025-07-11 | 2025-07-11 | 2025-07-14 | 2025-07-12 | 2025-07-14 | 4 | 3 | 21 | 2 | 7 | 1 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | [7 empty] | 0.14286 | 1 | 1.2 | 0.26087 | 0.75 | 0.83333 | 0.16667 | 0.16667 | 0.5 | 0.33333 | 1 | 0.16667 | 0.33333 | 0
|  |  |  | Change Request - Beneficiary Report | 1) Range facility provided for Date option 2) According to Water sample ID provided search option in the report |  | 5 | 34 | 38 | 34 | 2025-09-01 | 2025-09-08 | 2025-09-03 | 2025-09-08 | 2025-09-03 | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-07 | 2025-09-08 | 4 | 4 | 13 | 1 | 9 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | [7 empty] | 0.14706 | 1 | 1 | 0.35714 | 0.5 | 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.5 | 0 | 0.2 | 0.2
7 | Public Health Engineering Department | Jal Rekha | Sahbhagita | Sahbhagita Reports | 1) Report Modification shown |  | 5 | 32 | 42 | 32 | 2025-09-08 | 2025-09-18 | 2025-09-08 | 2025-09-16 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-13 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2 | 2 | 16 | 1 | 6 | 1 | 2 | 2 | 0 | 2 | 1 | 2 | 0 | 1 | [7 empty] | 0.15625 | 1.25 | 1.25 | 0.29412 | 0.71429 | 1.6 | 0.2 | 0.2 | 0.4 | 0.2 | 0.6 | 0.2 | 0.6 | 0.4
|  |  |  | Change Request -GM / PM | 1) GM login - Sahbhagita report view chnages village wise triggers 2) PM - Video Upload option in sahbhagita activity |  | 5 | 32 | 40 | 32 | 2025-10-15 | 2025-10-30 | 2025-10-15 | 2025-10-29 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-21 | 2025-10-20 | 2025-10-22 | 3 | 3 | 14 | 1 | 7 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | [7 empty] | 0.15625 | 1.25 | 1.25 | 0.33333 | 0.55556 | 1.4 | 0.2 | 0.2 | 0.4 | 0.4 | 0.66667 | 0.2 | 0.4 | 0.2
8 | Public Health Engineering Department | Jal Rekha | Sopan | Change Request - Contractor (Web / Mobile) | 1) Conventional & Precast separate option provided for OHT Work plan start, plan end date on each stage 2) Delete option provided for wrong entry in conventional & then entry in precast OHT 3) Changes in WTP and IPS Forms at each stage 4) Mobile apk changed for - OHT completed in Sopan will not be shown in RFI request Anusharavan module for contractor login 5) Sopan IPS Component updated |  | 56 | 394 | 461 | 394 | 2025-07-01 | 2025-08-10 | 2025-07-01 | 2025-08-04 | 2025-07-01 | 2025-07-05 | 2025-07-06 | 2025-07-11 | 2025-07-12 | 2025-07-26 | 2025-07-26 | 2025-08-04 | 26 | 30 | 182 | 16 | 120 | 12 | 4 | 4 | 1 | 1 | 2 | 1 | 0 | 1 | [7 empty] | 0.14213 | 1.8667 | 1.6471 | 0.28283 | 0.42424 | 0.60714 | 0.071429 | 0.089286 | 0.25 | 0.16071 | 0.8 | 0.035714 | 0.071429 | 0.017857
|  |  |  | Change Request - GM Document Upload & Reports | 1) If contractor filled wrong details then GM can edit and can update actual date and freeze option at each stage 2) Drill down functionality, Plan date and actual date by each OHT wise in the reports - Mapping, Monitoring, & Report 3) Drill down functionality, Plan date and actual date by each WTP wise in the reports - Mapping, Monitoring, & Report 4) Drill down functionality, Plan date and actual date by each Intake wise in the reports - Mapping, Monitoring, & Report 5) Prepare the report with total Panchanama count and total uploaded design data 6) Changes in Panchnama and design drawing separated into pdf format with upload feature 7) CMMI Documentation |  | 25 | 177 | 167 | 177 | 2025-08-11 | 2025-09-06 | 2025-08-12 | 2025-09-07 | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-14 | 2025-08-20 | 2025-08-29 | 2025-09-03 | 2025-09-07 | 10 | 13 | 101 | 8 | 35 | 4 | 3 | 3 | 0 | 1 | 2 | 1 | 0 | 0 | [7 empty] | 0.14124 | 1.9231 | 1.5625 | 0.22936 | 0.64103 | 1.04 | 0.04 | 0.08 | 0.36 | 0.16 | 0.75 | 0.08 | 0.12 | 0.04
[31 empty] | 14 | 15 | 34 | 19 | 12

## PPM Prod Cycle 2
Productivity | Code_Rate | Test_Rate
0.14224 | 0.27966 | 0.58929
0.14286 | 0.30189 | 0.45714
0.14236 | 0.24405 | 0.61194
0.14286 | 0.256 | 0.55172
0.14286 | 0.27586 | 0.51613
0.14189 | 0.2561 | 0.53165
0.15625 | 0.30303 | 0.66667
0.15625 | 0.3125 | 0.625
0.14198 | 0.25698 | 0.45545
0.14236 | 0.28082 | 0.45556
0.14423 | 0.29703 | 0.41096
0.14394 | 0.26761 | 0.48101
0.15625 | 0.29412 | 0.66667
0.14286 | 0.26087 | 0.75
0.14706 | 0.35714 | 0.5
0.15625 | 0.29412 | 0.71429
0.15625 | 0.33333 | 0.55556
0.14213 | 0.28283 | 0.42424
0.14124 | 0.22936 | 0.64103
Regression Equation
|  |  | Productivity | = | 0.08923 + 0.1335 Code_Rate + 0.03471 Test_Rate
|  |  |  | AS-IS | Productivity | Code_Rate | Test_Rate
|  |  |  | Mean | 0.1464 | 0.2833 | 0.5581 |  | 6.8306
|  |  |  | SD | 0.0043267 | 0.03325 | 0.1034
|  |  |  | UCL | 0.15941 | 0.3831 | 0.8683 |  | 6.2731
|  |  |  | LCL | 0.13345 | 0.1836 | 0.2479 |  | 7.4934
|  |  |  | Target | Productivity
|  |  |  | Mean | 0.16104 |  | 0.01464 | mean | 6.2096
|  |  |  | SD | 0.05 |  |  | ucl | 0.172
[8 empty] | lcl | 0.138
|  |  |  | What if | Productivity | Code_Rate | Test_Rate | sd | 0.051667
|  |  |  | Mean | 0.1599 | 0.35 | 0.69 |  |  | 2.8571 | 1.4493 | 0.50725
|  |  |  | SD | 0.05 | 0.05 | 0.05
|  |  |  | USL | 0.3099 | 0.5 | 0.84
|  |  |  | LSL | 0.0099049 | 0.2 | 0.54
Action Plan
|  |  | 1 | How to Improve Code Rate
|  |  | 2 | How to Improve Test Rate
1. Outlier Analysis
2. Action Plan for Improvement

## PPM CT Cycle 2
Cycle Time | Code_CT | Test_CT
1.1818 | 0.45455 | 0.21212
0.9375 | 0.3125 | 0.1875
0.78049 | 0.34146 | 0.17073
0.5625 | 0.25 | 0.15625
0.5 | 0.1875 | 0.1875
0.7619 | 0.28571 | 0.16667
0.6 | 0.2 | 0.1
0.8 | 0.3 | 0.2
0.43478 | 0.1413 | 0.11957
0.36585 | 0.14634 | 0.097561
0.8 | 0.3 | 0.16667
0.47368 | 0.21053 | 0.10526
0.8 | 0.4 | 0.1
0.83333 | 0.5 | 0.33333 | *
1 | 0.2 | 0.2
1.6 | 0.4 | 0.2
1.4 | 0.4 | 0.4
0.60714 | 0.25 | 0.16071
1.04 | 0.36 | 0.16
Regression Equation
|  |  |  | Cycle Time | = | -0.131 + 2.166 Code_CT + 1.899 Test_CT
[5 empty] | AS-IS | Cycle time | Code_CT | Test_CT
[5 empty] | Mean | 0.815 | 0.2968 | 0.1717
[5 empty] | SD | 0.24883 | 0.10172 | 0.0528
[5 empty] | UCL | 1.561 | 0.602 | 0.3301
[5 empty] | LCL | 0.068 | -0.0083 | 0.0133
[5 empty] | Target | Cycle time
[5 empty] | Mean | 0.7335 |  | 0.0815
[5 empty] | SD | 0.25 |  |  | 0.90671
[5 empty] | What if | Cycle time | Code_CT | Test_CT
[5 empty] | Mean | 0.73897 | 0.2 | 0.23
[5 empty] | SD | 0.25 | 0.1 | 0.5
[5 empty] | USL | 1.489 | 0.5 | 1.73
[5 empty] | LSL | -0.01103 | -0.1 | -1.27

## PPM DRE Cycle 2
DRE-1 | Code Review Per Size | DRE-1 | Code Review Per Size
0.8 | 0.090909 | 0.8 | 0.090909
1 | 0.0625 | 1 | 0.0625
0.8 | 0.073171 | 0.8 | 0.073171
0.8 | 0.0625 | 0.8 | 0.0625
0.66667 | 0.0625 | 0.66667 | 0.0625
0.8 | 0.071429 | 0.8 | 0.071429
0.66667 | 0.1 | 0.66667 | 0.1
0.66667 | 0.1 | 0.66667 | 0.1
0.71429 | 0.032609 | 0.71429 | 0.032609
0.875 | 0.073171 | 0.875 | 0.073171
0.8 | 0.066667 | 0.8 | 0.066667
0.8 | 0.078947 | 0.8 | 0.078947
0.75 | 0.1 | 0.75 | 0.1
1 | 0.16667 | 1 | 0.16667
0.5 | 0 | 0.5 | 0
0.6 | 0.2 | 0.6 | 0.2
0.66667 | 0.2 | 0.66667 | 0.2
0.8 | 0.035714 | 0.8 | 0.035
0.75 | 0.08 | 0.75 | 0.08
Regression Equation
|  |  |  | DRE-1 | = | 0.6449 + 1.834 Code Review Per Size
[6 empty] | AS-IS | DRE | Code Review Per Size
[6 empty] | Mean | 0.776 | 0.0723
[6 empty] | SD | 0.11425 | 0.029017
[6 empty] | UCL | 1.1186 | 0.1593
[6 empty] | LCL | 0.4331 | -0.0148
[6 empty] | Target | DRE
[6 empty] | Mean | 0.8148 |  | 0.0388
[6 empty] | SD | 0.1
[6 empty] | What if | DRE | Code Review Per Size
[6 empty] | Mean | 0.80996 | 0.09
[6 empty] | SD | 0.1 | 0.05
[6 empty] | USL | 1.11 | 0.24
[6 empty] | LSL | 0.50996 | -0.06