## Lessons Learned Log
S.N | Project - Phases / Release | What Went Right? | What Went Wrong | Lessons Learned
1 | Jal Rekha Project Web – 2025 | • Successful implementation of GIS-based data visualization for schemes, pipelines, OHT, WTP, and assets • Transparent dashboards and role-based access improved monitoring for GM, PIU, and Contractors • Design vs Actual comparison feature improved quality control • Dhara & Nirmal modules enabled effective water quantity and quality monitoring • Factory testing and inspection reports streamlined GM approvals | • Requirements were not fully frozen initially, leading to frequent change requests • GIS data handling and visualization workflows required multiple iterations • Dependency on external systems (e-Nagar Palika, master data) caused delays • Performance tuning was required for complex GIS queries and reports | • Requirement finalization workshops are essential before development • GIS-heavy modules need early prototyping and stakeholder validation • External dependency risks must be identified during planning • Early performance benchmarking avoids late-stage optimizations
2 | Jal Rekha Project Mobile – 2025 | • Offline/online data capture worked effectively for asset mapping and inspections • Geo-tagged photos and GPS-based validations improved data authenticity • Mobile traverse functionality enabled accurate field mapping • Real-time sync after connectivity restoration reduced data loss • Standardized inspection formats improved data consistency | • Initial lack of GIS concept understanding within mobile team increased defects • Offline sync conflicts occurred during high-volume data entry • Frequent change requests during UAT increased regression cycles • Field conditions (network, device constraints) impacted usability | • Mobile teams need early GIS and domain training • Offline-first design must include robust conflict resolution mechanisms • Change requests during UAT significantly impact timelines • Field usability testing is critical before statewide rollout