## SIGN-OFF cycle 1
Sign-Off: CYCLE 1 |  | I confirm that I have reviewed and approved the Test Cases in this document and that they cover the agreed project scope and business requirements. Any item not mentioned here is considered out of scope. After sign-off, any changes will be taken up only through the change request process.
| MODULE NAME | DHARA, MASTER, NIRMAL, SAHBHAGITA and SOPAN
For Department
Name
Approved By
Designation
| Organization | Madhya Pradesh Jal Nigam Maryadit, Bhopal, M.P.
Signature with Seal
| Date | 2025-05-20

## SIGN-OFF cycle 2
Sign-Off: CYCLE 2 |  | I confirm that I have reviewed and approved the Test Cases in this document and that they cover the agreed project scope and business requirements. Any item not mentioned here is considered out of scope. After sign-off, any changes will be taken up only through the change request process.
| MODULE NAME | FHTC, O&M Billing, BHAROSA and CR's(Dhara,Nirmal,Master,Sahbhagita and Sopan)
For Department
Name
Approved By
Designation
| Organization | Madhya Pradesh Jal Nigam Maryadit, Bhopal, M.P.
Signature with Seal
| Date | 2025-09-15

## SIGN-OFF cycle 3
Sign-Off: CYCLE 3 |  | I confirm that I have reviewed and approved the Test Cases in this document and that they cover the agreed project scope and business requirements. Any item not mentioned here is considered out of scope. After sign-off, any changes will be taken up only through the change request process.
| MODULE NAME | CR's(Anushravan,Bharosa,Material Testing, FHTC,O&M Billing,Dhara,Nirmal and Sahbhagita)
For Department
Name
Approved By
Designation
| Organization | Madhya Pradesh Jal Nigam Maryadit, Bhopal, M.P.
Signature with Seal
| Date | 2025-12-10

## Cycle1 TC
Phase | Test Script ID | Test Script Name | Test Description | Scenario ID | Prerequisite | Test Data | Action | Expected Result | Date of Execution | Actual Results | Pass/Fail | Bug No. | Input Data | Comments | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11
Phase 1 | TC001 | Validate User Management-(User Access Mapping) | Verify that "User Access Mapping" screen is visible to the logged-in user after clicking on User registration tab under User Management | TS001 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Login page is reachable 4.CAPTCHA service is enabled | 1.https://gisuat.mp.gov.in/Jalnigam/web/Login 2.User/password-admin/abc@123 3.Valid CAPTCHA | 1.Nevigate to the url: https://gisuat.mp.gov.in/Jalnigam/web/Login 2.Enter Valid Username and Password 3.Enter Valid 6-digit CAPTCHA 4.Click on Terms&Conditions checkbox 5.Click on Login button 5.User redirected to Jal Rekha screen 6.Click on User Access Mapping tab under User Management | User should be able to see below mentions fields/tabs on User Access Mapping screen: 1..Select User Type dropdown(Type:Web User, Mobile User and Contractor) 2.Search Field 3.Table column with headers:(S.No, Login ID, Name, Mobile Number, Email id, Role, Designation, Access Module, Login Access, Sarthak User ID, Active and Action) | 2024-12-24 | User should be able to see below mentions fields/tabs on User Access Mapping screen: 1..Select User Type dropdown(Type:Web User, Mobile User and Contractor) 2.Search Field 3.Table column with headers:(S.No, Login ID, Name, Mobile Number, Email id, Role, Designation, Access Module, Login Access, Sarthak User ID, Active and Action) | PASS
Phase 1 | TC002 | Validate User Management-(User Access Mapping) | To verify the functionality of "Select User Type" dropdown field | TS002 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Login page is reachable 4.CAPTCHA service is enabled | 1.https://gisuat.mp.gov.in/Jalnigam/web/Login 2.User/password-admin/abc@123 3.Valid CAPTCHA | 1.Nevigate to the url: https://gisuat.mp.gov.in/Jalnigam/web/Login 2.Enter Valid Username and Password 3.Enter Valid 6-digit CAPTCHA 4.Click on Terms&Conditions checkbox 5.Click on Login button 5.User redirected to Jal Rekha screen 6.Click on User Access Mapping tab under User Management 7.Now click on Select User Type dropdown | User should be able to select any one user type from the below mentioned dropdown list: 1.Web User 2.Mobile User 3.Contractor | 2024-12-25 | User should be able to select any one user type from the below mentioned dropdown list: 1.Web User 2.Mobile User 3.Contractor | PASS
Phase 1 | TC003 | Validate User Management-(User Access Mapping) | To verify that the list of registered user is visible for the logged in user as per selected User Type(Web User) | TS003 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Login page is reachable 4.CAPTCHA service is enabled | 1.https://gisuat.mp.gov.in/Jalnigam/web/Login 2.User/password-admin/abc@123 3.Valid CAPTCHA | 1.Nevigate to the url: https://gisuat.mp.gov.in/Jalnigam/web/Login 2.Enter Valid Username and Password 3.Enter Valid 6-digit CAPTCHA 4.Click on Terms&Conditions checkbox 5.Click on Login button 5.User redirected to Jal Rekha screen 6.Click on User Access Mapping tab under User Management 7.Now click on Select User Type dropdown and select "Web User" 8.Once user type selection is done click on "Search Tab" | User should be able to see the records of all the registered Web Users with the below mentioned details in Table Form: 1.S.No 2.Login ID 3.Name 4.Mobile Number 5.Email id, 6.Role 7.Designation 8.Access Module 9.Login Access, 10.Sarthak User ID, 11.Active 12.Action | 2024-12-25 | User should be able to see the records of all the registered Web Users with the below mentioned details in Table Form: 1.S.No 2.Login ID 3.Name 4.Mobile Number 5.Email id, 6.Role 7.Designation 8.Access Module 9.Login Access, 10.Sarthak User ID, 11.Active 12.Action | PASS
Phase 1 | TC004 | Validate User Management-(User Access Mapping) | To verify that the list of registered user is visible for the logged in user as per selected User Type(Mobile User) | TS004 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Login page is reachable 4.CAPTCHA service is enabled | 1.https://gisuat.mp.gov.in/Jalnigam/web/Login 2.User/password-admin/abc@123 3.Valid CAPTCHA | 1.Nevigate to the url: https://gisuat.mp.gov.in/Jalnigam/web/Login 2.Enter Valid Username and Password 3.Enter Valid 6-digit CAPTCHA 4.Click on Terms&Conditions checkbox 5.Click on Login button 5.User redirected to Jal Rekha screen 6.Click on User Access Mapping tab under User Management 7.Now click on Select User Type dropdown and select "Mobile User" 8.Once user type selection is done click on "Search Tab" | User should be able to see the records of all the registered Mobile Users with the below mentioned details in Table form: 1.S.No 2.Login ID 3.Name 4.Mobile Number 5.Email id, 6.Role 7.Designation 8.Access Module 9.Login Access, 10.Sarthak User ID, 11.Active 12.Action | 2024-12-25 | User should be able to see the records of all the registered Mobile Users with the below mentioned details in Table form: 1.S.No 2.Login ID 3.Name 4.Mobile Number 5.Email id, 6.Role 7.Designation 8.Access Module 9.Login Access, 10.Sarthak User ID, 11.Active 12.Action | PASS
Phase 1 | TC005 | Validate Assign Task | Verify Assign button is disabled until all required selections are made | TS005 | Test environment up; user account exists; app/web accessible. | Valid credentials; sample image file (JPG ≤5MB); valid GPS coords; sample readings. | Open app/web → navigate to relevant module → perform described action steps. | Component successfully assigned to the selected engineer; assignment visible in Assign Task List. | 2024-10-15 | Approval should be blocked with message | PASS
Phase 1 | TC006 | Validate Assign Task | Verify duplicate task assignment prevention (same user, same component) | TS006 | Test environment up; user account exists; app/web accessible. | Valid credentials; sample image file (JPG ≤5MB); valid GPS coords; sample readings. | Open app/web → navigate to relevant module → perform described action steps. | System detects duplicates and prevents duplicate records or marks them, providing a clear message to the uploader. | 2024-10-15 | Edit option should be disabled | PASS
Phase 1 | TC007 | Validate Assign Task | Verify that exporting without any data does not crash the system | TS007 | User logged in; network available for sync/export; backend available. | Assigned schemes/components; sample data for export. | Trigger Sync/Export → confirm popup → observe progress and results. | System performs the described action successfully; changes are persisted and visible in UI/lists. Validation errors shown for invalid inputs. | 2024-10-15 | Image should be visible | PASS
Phase 1 | TC008 | Validate Assign Task | Verify that GM can see deactivated tasks if filter/view is applied | TS008 | GM account exists; web portal accessible; relevant data synced. | GM credentials; existing FE submissions or mapping data as applicable. | Login as GM → navigate to relevant dashboard/screen → perform review/edit/approve/export. | Task is deactivated and no longer appears in active list; can be viewed when 'Show Deactivated' filter enabled. | 2024-10-15 | Remarks should save correctly | PASS
Phase 1 | TC009 | Validate Mobile App Dhara Module | Verify login with valid credentials. | TS009 | GM account exists; web portal accessible; relevant data synced. | GM credentials; existing FE submissions or mapping data as applicable. | Login as GM → navigate to relevant dashboard/screen → perform review/edit/approve/export. | User authenticates successfully and is redirected to the Home/Dashboard; relevant modules visible. | 2024-10-15 | Correct data should appear in each | PASS
Phase 1 | TC010 | Validate Mobile App Dhara Module | Verify login fails with invalid credentials. | TS010 | Test environment up; user account exists; app/web accessible. | Valid credentials; sample image file (JPG ≤5MB); valid GPS coords; sample readings. | Open app/web → navigate to relevant module → perform described action steps. | User authenticates successfully and is redirected to the Home/Dashboard; relevant modules visible. | 2024-10-15 | Validation message should appear | PASS
Phase 1 | TC011 | Validate NIRMAL Mobile APP | To verify that FE can log in with valid credentials. | TS011 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Nirmal app installed; FE account active; Internet available | Username: fe_user1 Password: ValidPass@123 | Open app. | Mobile app opened successfully | 2025-03-17 | Mobile app opened successfully | PASS
[7 empty] | Enter valid username. | User should be able to enter Valid username | 2025-03-17 | User should be able to enter Valid username
[7 empty] | Enter valid password | User should be able to enter Valid Password | 2025-03-17 | User should be able to enter Valid Password
[7 empty] | Tap Login | User logged in successfully; redirected to Home Screen. | 2025-03-17 | User logged in successfully; redirected to Home Screen.
Phase 1 | TC012 | Validate NIRMAL Mobile APP | Verify that login fails with invalid credentials. | TS012 | 1.Test Environment is set up and accessible 2.Valid test credentials are available 3.Nirmal app installed; Internet available | Username: fe_user1 Password: wrongpass | Open app. | Mobile app opened successfully | 2025-03-17 | Mobile app opened successfully | PASS
[7 empty] | Enter invalid username. | User should be able to enter Valid username | 2025-03-17 | User should be able to enter Valid username
[7 empty] | Enter invalid password | User should be able to enter Valid Password | 2025-03-17 | User should be able to enter Valid Password
[7 empty] | Tap Login | Error message 'Invalid Username or Password' displayed; login fails. | 2025-03-17 | Error message 'Invalid Username or Password' displayed; login fails.
Phase 1 | TC013 | Validate NIRMAL Mobile APP | Verify that FE is redirected to home screen after successful login | TS013 | 1.Test Environment is set up and accessible 2.Valid FE credentials are available 3.Nirmal app installed; FE account active; Internet available | Username: fe_user1 Password: ValidPass@123 | Login into Mobile App | FE Login should be done Successfully | 2025-03-17 | FE Login should be done Successfully | PASS
[7 empty] | Observe Nevigation | Home screen should be displayed | 2025-03-17 | Home screen should be displayed
Phase 1 | TC014 | Validate NIRMAL Mobile APP | Verify Nirmal module icon is visible after login | TS014 | 1.Test Environment is set up and accessible 2.Valid FE credentials are available 3.Nirmal app installed; FE account active; Internet available 4.Successful Login | Username: fe_user1 Password: ValidPass@123 | Login into Mobile App | FE Login should be done Successfully | 2025-03-17 | FE Login should be done Successfully | PASS
[7 empty] | Check Home screen for Nirmal Module | Nirmal Icon should be displayed on Home screen | 2025-03-17 | Nirmal Icon should be displayed on Home screen
Phase 1 | TC015 | Validate NIRMAL Mobile APP | Verify Nirmal data sync occurs successfully after login | TS015 | 1.Test Environment is set up and accessible 2.Valid FE credentials are available 3.Nirmal app installed; FE account active; Internet available 4.Successful Login | Username: fe_user1 Password: ValidPass@123 | Login into Mobile App | FE Login should be done Successfully | 2025-03-17 | FE Login should be done Successfully | PASS
[7 empty] | Check Home screen for Nirmal Module | Nirmal Icon should be displayed on Home screen | 2025-03-17 | Nirmal Icon should be displayed on Home screen
[7 empty] | Select Nirmal Icon and click on Sync button | Sync should be completed and updated component list should be available. | 2025-03-17 | Sync should be completed and updated component list should be available.
Phase 1 | TC016 | Validate NIRMAL Mobile APP | Verify only components assigned in Dhara module are displayed in NIRMAL | TS016 | 1.Test Environment is set up and accessible 2.Valid FE credentials are available 3.Nirmal app installed; FE account active; Internet available 4.Successful Login 5.Components assigned in Dhara | Username: fe_user1 Password: ValidPass@123 | Login into Mobile App | FE Login should be done Successfully | 2025-03-17 | FE Login should be done Successfully | PASS
[7 empty] | Open Nirmal Module and Sync | User should be able to open and synce NIRMAL | 2025-03-17 | User should be able to open and synce NIRMAL
[7 empty] | Check displayed componenets | Only assigned component should be visible in Nirmal | 2025-03-17 | Only assigned component should be visible in Nirmal
Phase 1 | TS.017 | Validate MASTER | Verify open Scheme Village Master page | TS017 | User logged in with Master-module access |  | Navigate: Master → Scheme Village Master | Page opens; table lists existing mappings | 2025-02-20 | Page opens; table lists existing mappings | PASS
Phase 1 | TS.018 | Validate MASTER | Verify columns in mapping table | TS018 | Page open |  | Inspect table columns | Columns include Scheme Name, Village Code, District, Block, GP and flags (O&M, Water Supply Started, Bulk) | 2025-02-20 | Columns include Scheme Name, Village Code, District, Block, GP and flags (O&M, Water Supply Started, Bulk) | PASS
Phase 1 | TS.019 | Validate MASTER | Verify add new village mapping — positive | TS019 | User has valid Scheme/District/Block/GP/Village values |  | Click +Add Village → select Scheme, District, Block, GP, Village → set flags → Save (Mapped Village) | New mapping saved; confirmation message; row appears in table with correct values; PIU auto-filled | 2025-02-20 | New mapping saved; confirmation message; row appears in table with correct values; PIU auto-filled | PASS
Phase 1 | TS.020 | Validate MASTER | Verify mandatory field validation on Add | TS020 | Add form open |  | Leave one or more required fields blank → Click Mapped Village | UI validation prevents save; shows appropriate error messages | 2025-02-20 | UI validation prevents save; shows appropriate error messages | PASS
Phase 1 | TS.021 | Validate MASTER | Verify Duplicate mapping prevention | TS021 | Mapping for Scheme+Village already exists |  | Try to add same mapping again | System shows duplicate warning / prevents duplicate insert | 2025-02-20 | System shows duplicate warning / prevents duplicate insert | PASS
Phase 1 | TS.022 | Validate MASTER | Verify PIU auto-fill verification | TS022 | Add form open, selected Scheme belongs to PIU |  | Select Scheme → observe PIU field | PIU auto-populated and non-editable (if per spec) | 2025-02-20 | PIU auto-populated and non-editable (if per spec) | PASS
Phase 1 | TS.023 | Validate MASTER | Verify Flag toggle behaviour | TS023 | Add form open |  | Toggle Is O&M / Water Supply Started / Bulk Village between Yes/No → Save | Flags saved as selected and reflected in table | 2025-02-20 | Flags saved as selected and reflected in table | PASS
Phase 1 | TS.024 | Validate MASTER | Verify Edit existing mapping | TS024 | Existing mapping present |  | Click edit on mapping row → change flags or village → Save | Changes saved; confirmation shown; table updated | 2025-02-20 | Changes saved; confirmation shown; table updated | PASS
Phase 1 | TS.025 | Validate MASTER | Verify Delete mapping | TS025 | Existing mapping present |  | Click Delete → Confirm | Mapping removed; success message; row removed from table | 2025-02-20 | Mapping removed; success message; row removed from table | PASS
Phase 1 | TS.026 | Validate MASTER | Verify Filtering/searching mappings | TS026 | Table with many rows |  | Use filters (Scheme, District, Block, GP, Village) or search | Table shows filtered rows only | 2025-02-20 | Table shows filtered rows only | PASS
Phase 1 | TS.027 | Validate MASTER | Verify Pagination and sorting | TS027 | Table has many entries |  | Sort by Scheme / Village Code; navigate pages | Sorting works; pagination accurate | 2025-02-20 | Sorting works; pagination accurate | PASS

## Cycle2 TC
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify that FE can login with valid credentials and is redirected to the Jal Rekha profile page successfully. | System should allow the FE to log in successfully and redirect to the Jal Rekha profile page, ensuring smooth workflow and expected functionality. | System should allow the FE to log in successfully and redirect to the Jal Rekha profile page, ensuring smooth workflow and expected functionality. | 2025-09-19 | Pass | Major
TC.002 | Verify that the HSC module is visible and clickable on the Jal Rekha profile page after login. | System should display the HSC module, which must be visible and clickable, ensuring smooth workflow and expected functionality. | System should display the HSC module, which must be visible and clickable, ensuring smooth workflow and expected functionality. | 2025-09-19 | Pass | Major
TC.003 | Verify that all five tabs namely DOWNLOAD, HSC Verification, SYNC Offline data, View/Delete Draft, and History appear on the HSC Survey page. | System should display all five tabs (Download, Verification, SYNC, Draft, and History) on the HSC Survey page, ensuring smooth workflow and expected functionality. | System should display all five tabs (Download, Verification, SYNC, Draft, and History) on the HSC Survey page, ensuring smooth workflow and expected functionality. | 2025-09-19 | Pass | Major
TC.004 | Verify that the dropdowns for Scheme, District, Block, Panchayat, and Village populate with correct data fetched from the server. | System should populate dropdowns with correct data fetched from the server, ensuring smooth workflow and expected functionality. | System should populate dropdowns with correct data fetched from the server, ensuring smooth workflow and expected functionality. | 2025-09-20 | Pass | Major
TC.005 | Verify that Fetch Village Survey Data returns the expected list of households for the selected village. | System should display the list of households for the selected village, ensuring smooth workflow and expected functionality. | System should display the list of households for the selected village, ensuring smooth workflow and expected functionality. | 2025-09-20 | Pass | Major
TC.006 | Verify Type of Increment radio is present and one option must be selected. | Radio control with options CPI-W and Yearly Factor is present. One option is pre-selected per spec or UI shows validation if none (i.e., Save/Next blocked until selection). | Radio control with options CPI-W and Yearly Factor is present. One option is pre-selected per spec or UI shows validation if none (i.e., Save/Next blocked until selection). | 2025-08-22 | Pass | Minor
TC.007 | Verify penalty numeric validation (>0) and rejects invalid input. | System rejects negative value; shows validation error like “Penalty must be greater than 0”. Add should be blocked. | System rejects negative value; shows validation error like “Penalty must be greater than 0”. Add should be blocked. | 24-082025 | Pass | Minor
TC.008 | Verify Supply of Portable Water option dropdown (55 LPCD / 70 LPCD) is present and selectable. | LPCD control should be present with options 55 LPCD, 70 LPCD | LPCD control should be present with options 55 LPCD, 70 LPCD | 24-082025 | Pass | Major
TC.009 | Verify Add saves Quantity entry including selected LPCD option. | Row added to Quantity list/grid. Row shows Norm name, Penalty=50, LPCD=55 LPCD. Success message displayed (e.g., “Quantity entry added”). | Row added to Quantity list/grid. Row shows Norm name, Penalty=50, LPCD=55 LPCD. Success message displayed (e.g., “Quantity entry added”). | 24-082025 | Pass | Minor
TC.010 | Verify Quantity entry row shows Norm, Penalty, LPCD value. | The newly added row displays: Quantity Norm, Penalty value, LPCD column showing 55 or 70 as selected. | The newly added row displays: Quantity Norm, Penalty value, LPCD column showing 55 or 70 as selected. | 24-082025 | Pass | Major
TC.011 | Verify removing or editing Quantity row works correctly. | Row should removed from grid and success message shown; total list updates. | Row should removed from grid and success message shown; total list updates. | 24-082025 | Pass | Minor
TC.012 | Verify error handling when LPCD not selected and Add clicked (if LPCD is required). | System shows validation error like “Please select LPCD” and prevents Add. | System shows validation error like “Please select LPCD” and prevents Add. | 24-082025 | Pass | Low
TC.013 | Verify combination permutations (same Quantity norm with different LPCD) — duplicate handling as per spec. | If spec forbids duplicates: system prevents and shows “Duplicate entry” error. If spec allows different LPCD per same norm: system blocks exact duplicate only. | If spec forbids duplicates: system prevents and shows “Duplicate entry” error. If spec allows different LPCD per same norm: system blocks exact duplicate only. | 24-082025 | Fail | Low | 25-082025
TC.014 | Verify that user must select either 'Yes' or 'No' before proceeding. | System blocks and shows inline validation: 'Please select Yes or No' | System blocks and shows inline validation: 'Please select Yes or No' | 2025-08-27 | Pass | Major
TC.015 | Verify that when 'Yes' is selected, 'Trial Run' and 'O&M' related fields display. | Trial Run, O&M and CPI fields become visible/enabled | Trial Run, O&M and CPI fields become visible/enabled | 2025-08-27 | Pass | Major
TC.016 | Verify that when 'No' is selected, 'Trial Run' and 'O&M' fields remain hidden. | Trial Run, O&M, CPI fields hidden/disabled | Trial Run, O&M, CPI fields hidden/disabled | 2025-08-27 | Pass | Major
TC.017 | Verify screen behavior on toggling between 'Yes' and 'No'. | Fields appear/disappear correctly; no JS errors; data preserved per rules | Fields appear/disappear correctly; no JS errors; data preserved per rules | 2025-08-27 | Pass | Minor
TC.018 | Verify that user cannot select a future date. | Validation: 'Trial Run Date cannot be future'; value rejected | Validation: 'Trial Run Date cannot be future'; value rejected | 2025-08-27 | Pass | Minor
TC.019 | Verify that field cannot be left blank. | Final submit blocked; shows 'Trial Run Date is required' | Final submit blocked; shows 'Trial Run Date is required' | 2025-08-27 | Pass | Minor
TC.020 | Verify valid date entry (today or past date). | Accepted, no validation error | Accepted, no validation error | 2025-08-28 | Pass | Minor
TC.021 | Verify that field hides when ‘Is Full Scheme Under O&M’ = No. | Upload succeeds; file listed with name and delete option | Upload succeeds; file listed with name and delete option | 2025-08-28 | Pass | Minor
TC.022 | Verify upload functionality for valid PDF/DOC file. | Rejected; inline error 'Invalid file type. Only PDF/DOC allowed' | Rejected; inline error 'Invalid file type. Only PDF/DOC allowed' | 2025-08-28 | Pass | Minor
TC.023 | Verify invalid file format rejection. | Final submit blocked; 'Trial Run Letter required when Trial Run Date is entered' | Final submit blocked; 'Trial Run Letter required when Trial Run Date is entered' | 2025-08-28 | Pass | Minor
TC.024 | Verify that upload is mandatory when Trial Run date is entered. | Control hidden/disabled | Control hidden/disabled | 2025-08-28 | Pass | Minor
TC.025 | Verify that upload field hides when ‘Is Full Scheme Under O&M’ = No. | Error shown: 'Start Date of O&M cannot be future' | Error shown: 'Start Date of O&M cannot be future' | 2025-08-28 | Pass | Minor
TC.026 | Verify that user cannot enter a future date. | Error: 'Start Date must be on/after Trial Run Date' | Error: 'Start Date must be on/after Trial Run Date' | 2025-08-28 | Pass | Minor
TC.027 | Verify that entered date must be ≥ Trial Run Date. | Final submit blocked; 'Start Date of O&M is required' | Final submit blocked; 'Start Date of O&M is required' | 2025-08-28 | Pass | Major
TC.028 | Verify that field is mandatory. | Upload shown in list; download/delete options present | Upload shown in list; download/delete options present | 2025-08-28 | Pass | Major

## Cycle3 TC
Test Case No. | Test Description | Expected Result | Actual Result | Date when Test Case Performed | Status (Pass / Fail / Cannot Be Tested/ Blocked/Invalid) | Severity (Major Minor, Low) | Date Closed for Failed Status | Remarks (Resolution for Failed Test Cases)
TC.001 | Verify Contractor can create Material Testing RFI | Request Inspection screen opens | Request Inspection screen opens
|  | RFI created successfully | RFI created successfully
TC.002 | Verify PIU and Scheme are auto-populated | PIU and Scheme auto-populated and read-only | PIU and Scheme auto-populated and read-only
TC.003 | Verify Component dropdown loads correctly | All components displayed | All components displayed
TC.004 | Verify Material Type dropdown displays all configured values | All configured material types displayed | All configured material types displayed
TC.005 | Verify RFI submission with all valid inputs | No validation error | No validation error
|  | RFI submitted successfully | RFI submitted successfully
TC.006 | Verify photo capture from camera only | Camera opens | Camera opens
|  | Gallery option not allowed | Gallery option not allowed
TC.007 | Verify RFI is submitted successfully to GM | Submitted RFI visible | Submitted RFI visible
TC.008 | Verify Sub-component hidden for Distribution Pipeline | Field not displayed | Field not displayed
TC.009 | Verify Stage, Stretch No, Application Type hidden for Distribution | Fields hidden | Fields hidden
TC.010 | Verify OHT selection enables Pipeline dropdown | Pipeline dropdown enabled | Pipeline dropdown enabled
TC.011 | Verify only pipelines mapped to selected OHT are displayed | Only mapped pipelines displayed | Only mapped pipelines displayed
TC.012 | Verify same-day inspection date is blocked | Error displayed | Error displayed
TC.013 | Verify past date is blocked | Error displayed | Error displayed
TC.014 | Verify next-day inspection date is accepted | Date accepted | Date accepted
TC.015 | Verify future inspection date is accepted | Date accepted | Date accepted
TC.016 | Verify GM can assign RFI to SQC | RFI assigned | RFI assigned
TC.017 | Verify GM can assign RFI to TPIA | RFI assigned | RFI assigned
TC.018 | Verify GM can assign RFI to both SQC & TPIA | RFI assigned to both | RFI assigned to both
TC.019 | Verify assigned users receive notification | Notification received | Notification received
TC.020 | Verify FE can view assigned RFI | Assigned RFI visible | Assigned RFI visible
TC.021 | Verify FE can submit Accept recommendation | Recommendation submitted | Recommendation submitted
TC.022 | Verify FE can submit Reject recommendation | Recommendation submitted | Recommendation submitted
TC.023 | Verify FE recommendation reaches GM | Recommendation visible | Recommendation visible
TC.024 | Verify GM can accept RFI | RFI closed as Accepted | RFI closed as Accepted
TC.025 | Verify RFI status changes to Closed on acceptance | Status Closed | Status Closed
TC.026 | Verify GM can reject RFI | RFI closed as Rejected | RFI closed as Rejected
TC.027 | Verify rejected RFI is returned to Contractor | Rejected RFI visible | Rejected RFI visible
TC.028 | Verify submit RFI without Material Type | Error shown | Error shown
TC.029 | Verify submit RFI without photo | Submission blocked | Submission blocked
TC.030 | Verify select same-day inspection date | Error shown | Error shown