## Revision History
Version | Date | Description | Prepared by | Reviewed by
0.1
1
1.1
Revision History is meant to be updated when there is a revision to the template.

## Legend
Legend
Column Header | Description of the field
ID# | Risk Number
Risk Description | Detailed Description of the Risk
Probability | Probability of the Risk Occurring. More details are in the worksheet titled "Reference"
Impact | Impact of the Risk. More details are in the worksheet titled "Reference"
Risk Level Value | Multiplication of Risk Probability and Impact. More details are in the worksheet titled "Reference"
Risk Level | If value is <=2 then Low If value is <=4 and >=3 then Medium If value is <=6 then High
Risk Category | The Risk management process must categorize the different types of Risk so that controlling and Mitigation plan can handle the same category of Risk. The list of Categories is as follows:
Scope
Requirements
Estimation
Design
Planning
Technology
Resources
Quality Control
Coordination
Support
Management
Environment
Contractual
Legislation
Site/facilities
Regulatory
Risk Source | Source of Risk is basically considering all the factors which are responsible for any kind of Risk. The list of sources of risks is as follows:
INTERNAL - Complex Design
INTERNAL - Incompatible development tools
INTERNAL - Lack of technical support
INTERNAL - Unreliable Connectivity
INTERNAL - Lack or delay in Staffing
INTERNAL - Lack of experience
INTERNAL - Lack or delay in hardware & software
INTERNAL - Lack of contingency plans
EXTERNAL - Unclear Requirements
EXTERNAL - Volatile Requirements
EXTERNAL - Delayed response from Client
EXTERNAL - Unrealistic or Aggressive Requirements
EXTERNAL - Third Party Dependency
Trigger Event /Indicator | The event that will trigger the risk
Risk Strategy | The approach to be adopted for risk mitigation - 4T's of Risk.
Treat
Tolerate
Terminate
Transfer
Risk Response | Action to be taken based to address the risk mitigation
Contingency Plan | The Plan to be used in case the risk materialized
Owner | The person Owning the Risk and its mitigation
Date Identified | Date when the risk was identified
Date of Expected Closure | Proposed date by when the mitigation action will be completed
Date of Actual Closure | Actual date by when the mitigation action was completed
Date of Last Review | Date when the risk was last reviewed
Status | Status of the Risk whether Open or Closed
Probability (after risk mitigation action) | Probability of the Risk occurring after mitigation action completed. More details are in the worksheet titled "Reference"
Impact (after risk mitigation action) | Impact of the Risk after mitigation action completed. More details are in the worksheet titled "Reference"
Residual Risk description | Detailed Description of the Risk remaining after mitigation action
Residual Risk Level Value | Multiplication of Risk Probability and Impact. More details are in the worksheet titled "Reference"
Residual Risk Level | If value is <=2 then Low If value is <=4 and >=3 then Medium If value is <=6 then High

## Reference
Reference
Risk Probability Guidelines
Rating | Description | Score
High | Event that has a greater than 75% chance of occurring | 3
Medium | Event that has between a 51 – 75% chance of occurring | 2
Low | Event that has a 0 – 50% chance of occurring | 1
Risk Impact Guidelines
Rating | Description | Score
High | Impact is more than 25% of the annual project budget or amount of $250,000, whichever is lower | 3
Medium | Impact between 10 – 25% of the project budget or amount between $100,000 and $250,000, whichever is lower | 2
Low | Impact less than 10% of the project budget or less than $100,000 | 1
Risk Level:
Risk Level = Probability of event X Impact of event
Probability
|  | Low | Medium | High
Impact | High | 3 | 6 | 9
| Medium | 2 | 4 | 6
| Low | 1 | 2 | 3
Opportunity Priority
Opportunity Priority=CBA*Probability
CBA=Cost*Benefit
| COST BENEFIT ANALYSIS (CBA) |  | POTENTIAL BENEFIT
|  |  | Low | Medium | High
| POTENTIAL COST | Low | Medium | High | High
|  | Medium | Low | Medium | High
|  | High | Low | Low | Medium
| OPPORTUNITY ANALYSIS |  | PROBABILITY
|  |  | Low | Medium | High
| CBA | Low | Low | Low | Medium
|  | Medium | Low | Medium | High
|  | High | Medium | High | High

## Pivot Status
Pivot Status
| Count of Risk Level | Column Labels
| Row Labels | Closed | Open | Grand Total
| Low | 2 |  | 2
| Medium | 18 | 2 | 20
| High | 2 |  | 2
| Grand Total | 22 | 2 | 24

## Risk Log
ID# | Risk Description | Probability | Impact | Risk Level Value | Risk Level | Risk Category | Risk Source | Trigger Event /Indicator | Risk Strategy | Risk Response | Contingency Plan | Owner | Date Identified | Date of Expected Closure | Date of Actual Closure | Date of Last Review | Status | Probability (after risk mitigation action) | Impact (after risk mitigation action) | Residual Risk description | Residual Risk Level Value | Residual Risk Level
101 | Form/report formats may get delayed from client users | 1 | 1 | 1 | Low | Regulatory | EXTERNAL - Delayed response from Client | Requirement Gathering | Tolerate | PM/BA visits client site to collect required formats and approvals from users | Prepare initial report formats internally and only seek client confirmation/changes to reduce dependency | PM/BA | 2025-01-30 | 2025-02-10 | 2025-02-10 | 2025-02-10 | Closed | 1 | 1 | Few delays due to dependency on MD approval | 2 | Low
102 | Development speed may slow due to shared resources moving to other projects | 2 | 2 | 4 | Medium | Resources | INTERNAL - Lack or delay in staffing | Development Phase | Tolerate | Use weekend work and shared GIS division resources to meet schedule | Inform HR and management early and arrange backup developers from other projects | PM | 2025-02-27 | 2025-03-15 | 2025-03-15 | 2025-03-15 | Closed | 2 | 1 | Occasional delays in edge cases | 2 | Low
103 | Late findings in service integration due to parameter changes from Web Portal to application | 2 | 1 | 2 | Medium | Technology | EXTERNAL - Third Party Dependency | Time of Integration | Treat | Monitor integration closely on regular basis | Keep services parameterized and plan joint review sessions with client team when issues are triggered | Developer | 2025-03-20 | 2025-04-10 | 2025-04-10 | 2025-04-15 | Closed | 2 | 1 | Minimal impact due to fallback design | 2 | Low
104 | Slow performance of DisplayAllUser list because all user records are fetched in one go | 2 | 2 | 4 | Medium | Technology | INTERNAL - Incompatible development tools | Time of Integration | Treat | Monitor list performance during tests | Tune queries and use filtered/paginated user list if slowness occurs | Developer | 2025-03-28 | 2025-04-26 | 2025-04-26 | 2025-04-30 | Closed | 2 | 1 | Delay in DB fetch causes temporary blank screen | 2 | Low
105 | Non‑availability of shared System Test environment for Jal Rekha modules | 1 | 2 | 2 | Medium | Environment | INTERNAL - Lack or delay in hardware & software | Testing | Treat | Monitor environment booking and conflicts | Reserve environment in advance; deploy build to DEV environment as fallback for system testing | PM | 2025-04-04 | 2025-04-24 | 2025-04-24 | 2025-05-02 | Closed | 1 | 1 | Resolved through advance booking and DEV fallback | 1 | Low
106 | Non‑availability of Android developer due to planned leave during mobile build - Need to take assistance from Intern | 1 | 2 | 2 | Medium | Resources | INTERNAL - Lack or delay in staffing | Operation and Maintenance | Tolerate | Share Android resources from other projects for critical builds | Maintain pool of cross‑skilled developers who can be onboarded when primary resource is unavailable | PM | 2025-06-05 | 2025-07-25 | 2025-07-25 | 2025-08-03 | Closed | 1 | 1 | Resolved using shared Android resources | 1 | Low
107 | In Anusharavan module, component dropdown and village dropdown do not load for some schemes, limiting GM/FE ability to select correct assets during data entry. | 1 | 2 | 2 | Medium | Functional | Application configuration / data mapping gaps | User unable to see component or village in dropdown for selected scheme. | Tolerate | Accept current behaviour for low‑usage schemes and guided contractor to inform GM | If dropdown fails for critical scheme master mapping offline and update records later after fix deployment. | TL – Anusharavan | 27/02/2025 | 31/03/2025 | 31/04/2025 | 2025-10-05 | Closed | Medium | Low | Occasional non‑critical dropdown issues may still occur on newly added schemes until mapping is refreshed. | 2 | Low
201 | Data sync issues between Jal Rekha execution modules and database ( also between web and mobile app) | 2 | 2 | 4 | Medium | Technical | Internal | Inconsistent fulfilment reports | Transfer | Use escalation mechanism and predefined SLA with infra/vendor team to resolve sync failures | Execute manual intervention protocol to correct mismatched | Infra Team | 2025-07-07 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Closed | 1 | 1 | Minor delivery delays may persist during exceptional sync issues | 2 | Low
202 | Delays in receiving timely approvals on CR deployments may impact delivery schedule | 2 | 2 | 4 | Medium | Security | Internal | Missed deadlines while approvals are pending from senior officials | Treat | Implement cross‑training and backup approver assignment for key roles | Use bypass route through secondary approval chain when primary approver is unavailable | Security Team | 2025-08-07 | 2025-08-20 | 2025-08-25 | 2025-08-26 | Closed | 1 | 1 | Occasional delays in edge approval cases | 2 | Low
203 | Key Jal Rekha module owner or developer becomes unavailable during cycle‑2, project continuity suffer | 2 | 2 | 4 | Medium | Operational | Internal | Sudden unavailability of key personnel for critical releases | Tolerate | Define SLA timelines for processing and distribute module knowledge among team members | Arrange temporary replacement resource from District Excise or other departments as backup | Internal Team | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-04 | Closed | 1 | 1 | Slight productivity dip during transition and knowledge handover | 2 | Low
R‑NIR‑205 | In Nirmal module, there is a risk that FE may collect water sample from outside defined OHT/WTP/Intake boundary, leading to inaccurate quality reporting. | 2 | 2 | 4 | Medium | Data Quality / Operational | Field operations, GPS inaccuracy | Sample location captured more than configured distance from mapped OHT/WTP/Intake coordinates. | Treat (Mitigate) | Implement geofence using asset‑mapping data; enforce sampling only within 50‑meter buffer of mapped components; show warning and block submission if outside buffer. | For genuine cases where access is not possible within geofence, allow supervised override by GM with reason and attach photograph as evidence. | TL – Nirmal / QA | 27/10/2025 | 30/10/2025 | 15/11/2025 | 15/12/2025 | Closed | Low | Medium | Some samples may still be taken near boundary where GPS error exists, but risk of wrong location is significantly reduced. | 2 | Medium
R‑FHTC‑206 | In Parinam FHTC module, Samagra API integration may return incorrect or incomplete village‑wise Samagra data, causing wrong beneficiary mapping. | 6 | 6 | 6 | High | Integration / External Dependency | External Samagra system | Frequent mismatches between Samagra data and local master (village/household counts) detected during reconciliation. | Transfer | Contractually assign responsibility of data accuracy to Samagra Department. | Maintain periodic reports to correct beneficiary data in some cases to Samagra department | TL – FHTC / Integration SPOC | 27/07/2025 | 31/08/2025 | 2025-05-09 | 20/09/2025 | Closed | Medium | Medium | Residual risk of occasional mismatches remains due to external source; handled via reconciliation and manual verification for high‑impact cases. | 3 | Medium
301 | Anusharavaan RFI stage updations and report modifications may cause incorrect approval status or missing RFI records across schemes. | 2 | 2 | 4 | Medium | Technical | Internal | Defects in new inner pages, function‑based queries, or activity approval workflow during testing. | Treat | Perform peer review of all query changes, validate RFI reports (Pending/In‑Progress/Approved) with sample schemes. | Maintain rollback script to previous RFI logic and keep manual tracking sheet for critical RFIs. | Anusharavaan Module Lead | 2025-11-11 | 22-11-2025 | 20-11-2025 | 22-11-2025 | Closed | 1 | 1 | Minor mismatches in RFI report filters may appear for few schemes. | 2 | Low
302 | Bharosa Factory Testing Web CR may lead to incomplete or wrongly mapped factory test details (components, quantities, failures, documents). | 2 | 2 | 4 | Medium | Functional | Internal | UAT defects in new web pages, tables, or mapping of factory testing masters. | Treat | Use comprehensive test scenarios for all component/sub‑component combinations; review DB design and mappings. | Allow interim capture of inspection results in controlled Excel template for critical factories. | Bharosa Web Lead | 2025-03-11 | 26-11-2025 | 25-11-2025 | 26-11-2025 | Closed | 1 | 1 | Occasional correction of master mapping may be required. | 2 | Low
303 | Bharosa Factory Testing Mobile changes (draft, APIs, history) may fail in production causing interruption in on‑site inspections. | 2 | 2 | 4 | Medium | Technical | Internal | Errors in new insert/get APIs or sync logic observed during mobile testing. | Treat | Conduct end‑to‑end testing on staging, pilot rollout with limited FEs, and monitoring via logs. | Provide fallback to web entry at PIU office if mobile submission fails. | Bharosa Mobile Lead | 19-11-2025 | 2025-05-12 | 2025-05-12 | 2025-05-12 | Closed | 1 | 1 | Some field inspectors may need to re‑sync drafts or re‑enter few inspections. | 2 | Low
304 | Bharosa report view CR (web and mobile) may produce inconsistent summary counts or wrong TPIA assignment visibility. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Discrepancies between mobile and web factory testing reports in UAT. | Treat | Cross‑verify report outputs with DB queries; align functions used by both channels. | Share reconciled “official” factory testing summary from DB for audit until reports stabilize. | Reporting SPOC | 2025-10-12 | 17-12-2025 | 14-12-2025 | 17-12-2025 | Closed | 1 | 1 | Edge‑case mismatches in few component‑level summaries. | 2 | Low
305 | New Material Testing GM/Contractor workflow may cause approval bottlenecks or mis‑routing of material inspections. | 2 | 2 | 4 | Medium | Operational | Internal | UAT comments on contractor→GM→SQC→FE workflow or “Pending at PIU” report. | Treat | Validate workflow with end‑to‑end test cases; review routing functions and master configuration. | Provide manual override facility at PIU to reassign or force‑close stuck inspections. | Material Testing PM | 2025-12-12 | 2026-02-01 | 30-12-2025 | Need implementation | Open | 1 | 1 | Small number of inspections may need manual reassignment. | 2 | Low
306 | Material Testing FE mobile login and security fixes may affect geofence validations or data sync leading to missed tests. | 2 | 2 | 4 | Medium | Security | Internal | Issues found in FE geofencing, sync APIs, or DOM XSS fixes in mobile JS files. | Treat | Perform security and field testing with sample sites; monitor crashlytics and API logs. | Allow FE to capture readings offline and submit later via supervised web interface if app fails. | Security / Mobile Lead | 19-12-2025 | 2026-02-01 | 31-12-2025 | Need implementation | Open | 1 | 1 | Few FE users may face retry of sync after token refresh. | 2 | Low
307 | FHTC GM/Contractor and FE report CRs may result in wrong scheme–village mapping or Samagra linkage impacting beneficiary decisions. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Defects in updated SQL queries or mapping logic identified during report testing. | Treat | Peer‑review SQL, reconcile outputs with earlier reports, and validate Samagra multiple‑family cases. | Maintain cross‑checked beneficiary list for critical schemes until new reports are stable. | FHTC Module Lead | 2025-04-11 | 13-12-2025 | 2025-09-12 | 13-12-2025 | Closed | 1 | 1 | Some exceptional Samagra records may still require manual override. | 2 | Low
308 | O&M Billing GM and Contractor CRs may introduce new billing, CPI, or penalty calculation errors across PIUs. | 6 | 6 | 6 | High | Financial | Internal | Differences between system‑generated bills and manual calculations in UAT. | Treat | Create detailed test matrix for all billing scenarios; run parallel calculation with prior version. | Option to revert to previous formula set for one cycle if major defect arises. | O&M Billing Lead | 2025-06-11 | 2026-07-01 | 2026-02-01 | 2026-07-01 | Closed | 1 | 1 | Minor manual adjustments required for few bills. | 2 | Low
309 | Security vulnerability fixes (SonarCube/SVN, encryption, XSS) in O&M and Dhara may cause regression or performance issues. | 2 | 1 | 2 | Low | Security | Internal | New security code leading to failures in heavy pages or login flows. | Treat | Batch deployment with regression pack; monitor DB and app performance post‑release. | Ability to toggle specific security rule or rollback DB package in coordination with security team. | Security Team | 2025-10-12 | 24-12-2025 | 18-12-2025 | 24-12-2025 | Closed | 1 | 1 | Minimal impact such as slight latency on some reports. | 2 | Low
310 | Dhara CR reports and meter‑mapping changes may produce inconsistent water‑supply analytics for some schemes. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Validation issues in redesigned Dhara reports or updated mapping logic. | Treat | Validate reports (DWSR, MWSR, UFW etc.) against sampled ground data; run peer review on queries. | Provide access to legacy report version for cross‑verification during first month. | Dhara CR Owner | 2025-08-11 | 24-12-2025 | 18-12-2025 | 24-12-2025 | Closed | 1 | 1 | Few scheme‑level variances requiring manual correction. | 2 | Low
311 | Nirmal WTP/OHT/Beneficiary and Raw‑water report CRs may impact report performance and correctness across multiple drill‑downs. | 2 | 2 | 4 | Medium | Technical | Internal | Timeouts or incorrect counts discovered during multi‑level drill‑down testing. | Treat | Optimize and index heavy queries; stage‑wise rollout of complex reports with monitoring. | Offer CSV export and offline analysis if on‑screen report fails for very large datasets. | Nirmal Module Lead | 2025-05-11 | 17-12-2025 | 14-12-2025 | 17-12-2025 | Closed | 1 | 1 | Occasional delay or partial load of deepest drill‑down levels. | 2 | Low
312 | Sahbhagita report and approval‑flow CRs may misrepresent NGO performance or cause video upload/approval failures. | 2 | 2 | 4 | Medium | Operational | Internal | UAT comments on new approval pages, triggers, and ISA‑wise filters. | Treat | Run end‑to‑end NGO workflow scenarios; verify Approved/Rejected/No‑Action counts with sample data. | Use temporary manual consolidation of NGO progress if report discrepancies are found. | Sahbhagita PM | 22-11-2025 | 14-12-2025 | 2025-11-12 | 14-12-2025 | Closed | 1 | 1 | Some NGO records may need manual status correction in rare cases. | 2 | Low

## Risk Log 01
Risk Log 01 for -GIS/JALREKHA/MP/25/07/01 – Jal Rekha Execution Phase Modules
ID# | Risk Description | Probability | Impact | Risk Level Value | Risk Level | Risk Category | Risk Source | Trigger Event /Indicator | Risk Strategy | Risk Response | Contingency Plan | Owner | Date Identified | Date of Expected Closure | Date of Actual Closure | Date of Last Review | Status | Probability (after risk mitigation action) | Impact (after risk mitigation action) | Residual Risk description | Residual Risk Level Value | Residual Risk Level
101 | Form/report formats may get delayed from client users | 1 | 1 | 1 | Low | Regulatory | EXTERNAL - Delayed response from Client | Requirement Gathering | Tolerate | PM/BA visits client site to collect required formats and approvals from users | Prepare initial report formats internally and only seek client confirmation/changes to reduce dependency | PM/BA | 2025-01-30 | 2025-02-10 | 2025-02-10 | 2025-02-10 | Closed | 1 | 1 | Few delays due to dependency on MD approval | 2 | Low
102 | Development speed may slow due to shared resources moving to other projects | 2 | 2 | 4 | Medium | Resources | INTERNAL - Lack or delay in staffing | Development Phase | Tolerate | Use weekend work and shared GIS division resources to meet schedule | Inform HR and management early and arrange backup developers from other projects | PM | 2025-02-27 | 2025-03-15 | 2025-03-15 | 2025-03-15 | Closed | 2 | 1 | Occasional delays in edge cases | 2 | Low
103 | Late findings in service integration due to parameter changes from Web Portal to application | 2 | 1 | 2 | Medium | Technology | EXTERNAL - Third Party Dependency | Time of Integration | Treat | Monitor integration closely on regular basis | Keep services parameterized and plan joint review sessions with client team when issues are triggered | Developer | 2025-03-20 | 2025-04-10 | 2025-04-10 | 2025-04-15 | Closed | 2 | 1 | Minimal impact due to fallback design | 2 | Low
104 | Slow performance of DisplayAllUser list because all user records are fetched in one go | 2 | 2 | 4 | Medium | Technology | INTERNAL - Incompatible development tools | Time of Integration | Treat | Monitor list performance during tests | Tune queries and use filtered/paginated user list if slowness occurs | Developer | 2025-03-28 | 2025-04-26 | 2025-04-26 | 2025-04-30 | Closed | 2 | 1 | Delay in DB fetch causes temporary blank screen | 2 | Low
105 | Non‑availability of shared System Test environment for Jal Rekha modules | 1 | 2 | 2 | Medium | Environment | INTERNAL - Lack or delay in hardware & software | Testing | Treat | Monitor environment booking and conflicts | Reserve environment in advance; deploy build to DEV environment as fallback for system testing | PM | 2025-04-04 | 2025-04-24 | 2025-04-24 | 2025-05-02 | Closed | 1 | 1 | Resolved through advance booking and DEV fallback | 1 | Low
106 | Non‑availability of Android developer due to planned leave during mobile build - Need to take assistance from Intern | 1 | 2 | 2 | Medium | Resources | INTERNAL - Lack or delay in staffing | Operation and Maintenance | Tolerate | Share Android resources from other projects for critical builds | Maintain pool of cross‑skilled developers who can be onboarded when primary resource is unavailable | PM | 2025-06-05 | 2025-07-25 | 2025-07-25 | 2025-08-03 | Closed | 1 | 1 | Resolved using shared Android resources | 1 | Low
107 | In Anusharavan module, component dropdown and village dropdown do not load for some schemes, limiting GM/FE ability to select correct assets during data entry. | 1 | 2 | 2 | Medium | Functional | Application configuration / data mapping gaps | User unable to see component or village in dropdown for selected scheme. | Tolerate | Accept current behaviour for low‑usage schemes and guided contractor to inform GM | If dropdown fails for critical scheme master mapping offline and update records later after fix deployment. | TL – Anusharavan | 27/02/2025 | 31/03/2025 | 31/04/2025 | 2025-10-05 | Closed | Medium | Low | Occasional non‑critical dropdown issues may still occur on newly added schemes until mapping is refreshed. | 2 | Low

## Risk Log 02
Risk Log for GIS/Jal Rekha/MP/25/10/31 – Jal Rekha Execution Modules
ID# | Risk Description | Probability | Impact | Risk Level Value | Risk Level | Risk Category | Risk Source | Trigger Event /Indicator | Risk Strategy | Risk Response | Contingency Plan | Owner | Date Identified | Date of Expected Closure | Date of Actual Closure | Date of Last Review | Status | Probability (after risk mitigation action) | Impact (after risk mitigation action) | Residual Risk description | Residual Risk Level Value | Residual Risk Level
201 | Data sync issues between Jal Rekha execution modules and database ( also between web and mobile app) | 2 | 2 | 4 | Medium | Technical | Internal | Inconsistent fulfilment reports | Transfer | Use escalation mechanism and predefined SLA with infra/vendor team to resolve sync failures | Execute manual intervention protocol to correct mismatched | Infra Team | 2025-07-07 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Closed | 1 | 1 | Minor delivery delays may persist during exceptional sync issues | 2 | Low
202 | Delays in receiving timely approvals on CR deployments may impact delivery schedule | 2 | 2 | 4 | Medium | Security | Internal | Missed deadlines while approvals are pending from senior officials | Treat | Implement cross‑training and backup approver assignment for key roles | Use bypass route through secondary approval chain when primary approver is unavailable | Security Team | 2025-08-07 | 2025-08-20 | 2025-08-25 | 2025-08-26 | Closed | 1 | 1 | Occasional delays in edge approval cases | 2 | Low
203 | Key Jal Rekha module owner or developer becomes unavailable during cycle‑2, project continuity suffer | 2 | 2 | 4 | Medium | Operational | Internal | Sudden unavailability of key personnel for critical releases | Tolerate | Define SLA timelines for processing and distribute module knowledge among team members | Arrange temporary replacement resource from District Excise or other departments as backup | Internal Team | 2025-09-15 | 2025-09-30 | 2025-10-01 | 2025-10-04 | Closed | 1 | 1 | Slight productivity dip during transition and knowledge handover | 2 | Low
R‑NIR‑205 | In Nirmal module, there is a risk that FE may collect water sample from outside defined OHT/WTP/Intake boundary, leading to inaccurate quality reporting. | 2 | 2 | 4 | Medium | Data Quality / Operational | Field operations, GPS inaccuracy | Sample location captured more than configured distance from mapped OHT/WTP/Intake coordinates. | Treat (Mitigate) | Implement geofence using asset‑mapping data; enforce sampling only within 50‑meter buffer of mapped components; show warning and block submission if outside buffer. | For genuine cases where access is not possible within geofence, allow supervised override by GM with reason and attach photograph as evidence. | TL – Nirmal / QA | 27/10/2025 | 30/10/2025 | 15/11/2025 | 15/12/2025 | Closed | Low | Medium | Some samples may still be taken near boundary where GPS error exists, but risk of wrong location is significantly reduced. | 2 | Medium
R‑FHTC‑206 | In Parinam FHTC module, Samagra API integration may return incorrect or incomplete village‑wise Samagra data, causing wrong beneficiary mapping. | 6 | 6 | 6 | High | Integration / External Dependency | External Samagra system | Frequent mismatches between Samagra data and local master (village/household counts) detected during reconciliation. | Transfer | Contractually assign responsibility of data accuracy to Samagra Department. | Maintain periodic reports to correct beneficiary data in some cases to Samagra department | TL – FHTC / Integration SPOC | 27/07/2025 | 31/08/2025 | 2025-05-09 | 20/09/2025 | Closed | Medium | Medium | Residual risk of occasional mismatches remains due to external source; handled via reconciliation and manual verification for high‑impact cases. | 3 | Medium

## Risk Log 03
Risk Log for GIS/Jal Rekha/MP/26/01/02 – Jal Rekha Exceution CR, Operation & Maintenance Modules
ID# | Risk Description | Probability | Impact | Risk Level Value | Risk Level | Risk Category | Risk Source | Trigger Event /Indicator | Risk Strategy | Risk Response | Contingency Plan | Owner | Date Identified | Date of Expected Closure | Date of Actual Closure | Date of Last Review | Status | Probability (after risk mitigation action) | Impact (after risk mitigation action) | Residual Risk description | Residual Risk Level Value | Residual Risk Level
401 | Anusharavaan RFI stage updations and report modifications may cause incorrect approval status or missing RFI records across schemes. | 2 | 2 | 4 | Medium | Technical | Internal | Defects in new inner pages, function‑based queries, or activity approval workflow during testing. | Treat | Perform peer review of all query changes, validate RFI reports (Pending/In‑Progress/Approved) with sample schemes. | Maintain rollback script to previous RFI logic and keep manual tracking sheet for critical RFIs. | Anusharavaan Module Lead | 2025-11-11 | 22-11-2025 | 20-11-2025 | 22-11-2025 | Closed | 1 | 1 | Minor mismatches in RFI report filters may appear for few schemes. | 2 | Low
402 | Bharosa Factory Testing Web CR may lead to incomplete or wrongly mapped factory test details (components, quantities, failures, documents). | 2 | 2 | 4 | Medium | Functional | Internal | UAT defects in new web pages, tables, or mapping of factory testing masters. | Treat | Use comprehensive test scenarios for all component/sub‑component combinations; review DB design and mappings. | Allow interim capture of inspection results in controlled Excel template for critical factories. | Bharosa Web Lead | 2025-03-11 | 26-11-2025 | 25-11-2025 | 26-11-2025 | Closed | 1 | 1 | Occasional correction of master mapping may be required. | 2 | Low
403 | Bharosa Factory Testing Mobile changes (draft, APIs, history) may fail in production causing interruption in on‑site inspections. | 2 | 2 | 4 | Medium | Technical | Internal | Errors in new insert/get APIs or sync logic observed during mobile testing. | Treat | Conduct end‑to‑end testing on staging, pilot rollout with limited FEs, and monitoring via logs. | Provide fallback to web entry at PIU office if mobile submission fails. | Bharosa Mobile Lead | 19-11-2025 | 2025-05-12 | 2025-05-12 | 2025-05-12 | Closed | 1 | 1 | Some field inspectors may need to re‑sync drafts or re‑enter few inspections. | 2 | Low
404 | Bharosa report view CR (web and mobile) may produce inconsistent summary counts or wrong TPIA assignment visibility. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Discrepancies between mobile and web factory testing reports in UAT. | Treat | Cross‑verify report outputs with DB queries; align functions used by both channels. | Share reconciled “official” factory testing summary from DB for audit until reports stabilize. | Reporting SPOC | 2025-10-12 | 17-12-2025 | 14-12-2025 | 17-12-2025 | Closed | 1 | 1 | Edge‑case mismatches in few component‑level summaries. | 2 | Low
405 | New Material Testing GM/Contractor workflow may cause approval bottlenecks or mis‑routing of material inspections. | 2 | 2 | 4 | Medium | Operational | Internal | UAT comments on contractor→GM→SQC→FE workflow or “Pending at PIU” report. | Treat | Validate workflow with end‑to‑end test cases; review routing functions and master configuration. | Provide manual override facility at PIU to reassign or force‑close stuck inspections. | Material Testing PM | 2025-12-12 | 2026-02-01 | 30-12-2025 | 2026-02-01 | Closed | 1 | 1 | Small number of inspections may need manual reassignment. | 2 | Low
406 | Material Testing FE mobile login and security fixes may affect geofence validations or data sync leading to missed tests. | 2 | 2 | 4 | Medium | Security | Internal | Issues found in FE geofencing, sync APIs, or DOM XSS fixes in mobile JS files. | Treat | Perform security and field testing with sample sites; monitor crashlytics and API logs. | Allow FE to capture readings offline and submit later via supervised web interface if app fails. | Security / Mobile Lead | 19-12-2025 | 2026-02-01 | 31-12-2025 | 2026-02-01 | Closed | 1 | 1 | Few FE users may face retry of sync after token refresh. | 2 | Low
407 | FHTC GM/Contractor and FE report CRs may result in wrong scheme–village mapping or Samagra linkage impacting beneficiary decisions. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Defects in updated SQL queries or mapping logic identified during report testing. | Treat | Peer‑review SQL, reconcile outputs with earlier reports, and validate Samagra multiple‑family cases. | Maintain cross‑checked beneficiary list for critical schemes until new reports are stable. | FHTC Module Lead | 2025-04-11 | 13-12-2025 | 2025-09-12 | 13-12-2025 | Closed | 1 | 1 | Some exceptional Samagra records may still require manual override. | 2 | Low
408 | O&M Billing GM and Contractor CRs may introduce new billing, CPI, or penalty calculation errors across PIUs. | 2 | 2 | 4 | Medium | Financial | Internal | Differences between system‑generated bills and manual calculations in UAT. | Treat | Create detailed test matrix for all billing scenarios; run parallel calculation with prior version. | Option to revert to previous formula set for one cycle if major defect arises. | O&M Billing Lead | 2025-06-11 | 2026-07-01 | 2026-02-01 | 2026-07-01 | Closed | 1 | 1 | Minor manual adjustments required for few bills. | 2 | Low
409 | Security vulnerability fixes (SonarCube/SVN, encryption, XSS) in O&M and Dhara may cause regression or performance issues. | 2 | 1 | 2 | Low | Security | Internal | New security code leading to failures in heavy pages or login flows. | Treat | Batch deployment with regression pack; monitor DB and app performance post‑release. | Ability to toggle specific security rule or rollback DB package in coordination with security team. | Security Team | 2025-10-12 | 24-12-2025 | 18-12-2025 | 24-12-2025 | Closed | 1 | 1 | Minimal impact such as slight latency on some reports. | 2 | Low
410 | Dhara CR reports and meter‑mapping changes may produce inconsistent water‑supply analytics for some schemes. | 2 | 2 | 4 | Medium | Data Accuracy | Internal | Validation issues in redesigned Dhara reports or updated mapping logic. | Treat | Validate reports (DWSR, MWSR, UFW etc.) against sampled ground data; run peer review on queries. | Provide access to legacy report version for cross‑verification during first month. | Dhara CR Owner | 2025-08-11 | 24-12-2025 | 18-12-2025 | 24-12-2025 | Closed | 1 | 1 | Few scheme‑level variances requiring manual correction. | 2 | Low
411 | Nirmal WTP/OHT/Beneficiary and Raw‑water report CRs may impact report performance and correctness across multiple drill‑downs. | 2 | 2 | 4 | Medium | Technical | Internal | Timeouts or incorrect counts discovered during multi‑level drill‑down testing. | Treat | Optimize and index heavy queries; stage‑wise rollout of complex reports with monitoring. | Offer CSV export and offline analysis if on‑screen report fails for very large datasets. | Nirmal Module Lead | 2025-05-11 | 17-12-2025 | 14-12-2025 | 17-12-2025 | Closed | 1 | 1 | Occasional delay or partial load of deepest drill‑down levels. | 2 | Low
412 | Sahbhagita report and approval‑flow CRs may misrepresent NGO performance or cause video upload/approval failures. | 2 | 2 | 4 | Medium | Operational | Internal | UAT comments on new approval pages, triggers, and ISA‑wise filters. | Treat | Run end‑to‑end NGO workflow scenarios; verify Approved/Rejected/No‑Action counts with sample data. | Use temporary manual consolidation of NGO progress if report discrepancies are found. | Sahbhagita PM | 22-11-2025 | 14-12-2025 | 2025-11-12 | 14-12-2025 | Closed | 1 | 1 | Some NGO records may need manual status correction in rare cases. | 2 | Low

## Opportunity
Opportunity Register | [15 empty] | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register | Opportunity Register
Opp. ID | Date Identified (dd-mm-yyyy) | Description | Category | Potential Benefits | Cost | Benefit | CBA Priority (Cost*Benefit) | Probability | Opportunity Priority (CBA*Probability) | Opportunity Leverage Strategy | Action | Ownership | Target Closure Date (dd-mm-yyyy) | Status | Remark (If any)
OP01 | 24/04/2025 | Reuse of existing modules | Technical | Opportunity to reuse existing modules to save time. | Low | High | High | Medium | High | Enhance | Identify reusable modules and integrate them into the current solution | TL/Developer | 22/05/2025 | Closed | –
OP02 | 29/05/2025 | GIS Data Enrichment using Jal Rekha execution data | Other | Increase/enhance MPSSDI data repository with detailed water‑supply network and execution status layers. | Medium | High | High | High | High | Enhance | Prepare and periodically update GIS layers of schemes, components, and execution progress from Jal Rekha. | PM | 28/06/2025 | Closed | Base for future analytics and planning.
OP03 | 21/05/2025 | Pilot Jal Rekha execution modules to Jal Nigam | Client | Exposure to other states/countries and possibility of replicating Jal Rekha solution. | Medium | High | High | High | High | Enhance | Deliver pilot project to Jal Nigam using stable Jal Rekha CR releases. | PM | 30/06/2025 | Closed | Depends on UK counterpart confirmation.
OP04 | 2025-01-06 | Extend Jal Rekha solution to other departments (Urban, MPUDC, UADD) | Performance | May receive more varied requirements and larger adoption of Jal Rekha execution framework. | Medium | Medium | Medium | Medium | Medium | Enhance | Present execution‑module capabilities and propose adaptation for Urban water‑supply projects. | PM | 2025-07-07 | Closed | Implementing in MPUDC and UADD.
OP05 | 22/07/2025 | Use risk insights from Cycle‑1 Jal Rekha Execution modules | Process | Improve future CR estimation, test coverage, and DRE by analysing closed risks and defects. | Low | Medium | Medium | Medium | Medium | Enhance | Conduct post‑implementation review of Cycle‑1 risks and update checklists/standards. | QA / PM | 30/09/2025 | Closed | To be aligned with CMMI audit.
OP06 | 15/10/2025 | Standardize mobile‑first patterns from Bharosa, FHTC and Material Testing | Technical | Faster rollout of future FE‑oriented modules with reusable APIs, offline patterns, and security fixes. | Medium | High | High | Medium | High | Enhance | Create common mobile framework (auth, sync, geofence, media upload) reused across Jal Rekha apps. | Mobile Lead | 31/01/2026 | Closed | Leverages fixes from Cycles 2 and 3.
OP07 | 2025-01-11 | Leverage Nirmal/Dhara reporting CR work for enterprise water‑quality analytics | Business | Create consolidated analytics for raw water, WTP, OHT, and beneficiary quality for decision‑making. | Medium | High | High | Medium | High | Enhance | Build cross‑module data mart using optimized queries from Nirmal and Dhara CRs. | Data Analytics Team | 30/12/2025 | Closed | Can feed dashboards for PHED and other agencies.
OP08 | 2025-10-12 | Institutionalize security hardening (SonarCube, encryption, XSS fixes) from Jal Rekha | Security | Reduce future security vulnerabilities and audit findings across MPSeDC applications. | Low | High | High | Medium | High | Enhance | Convert Jal Rekha security fixes and rules into reusable secure‑coding guidelines and CI checks. | Security Team | 28/12/2025 | Closed | To be rolled out to other departmental projects.

## Legends (hidden)
Risk Category | Risk & Opportunities Parameters | Risk Status | Risk Handling | Opportunity Leveraging | RISK ANALYSIS |  | IMPACT
Select | Select | Select | Avoid | Exploit |  |  | Low | Medium | High
Client | Low | Open | Accept | Monitor | PROBABILITY | Low | Low | Low | Medium
Cost | Medium | In-Action | Reduce | Enhance |  | Medium | Low | Medium | High
Data Privacy | High | Closed | Transfer | Share |  | High | Medium | High | High
Management
Performance |  |  |  |  | COST BENEFIT ANALYSIS (CBA) |  | POTENTIAL BENEFIT
Quality | [6 empty] | Low | Medium | High
Resource |  |  |  |  | POTENTIAL COST | Low | Medium | High | High
Schedule | [5 empty] | Medium | Low | Medium | High
Security | [5 empty] | High | Low | Low | Medium
Skills
Technical |  |  |  |  | OPPORTUNITY ANALYSIS |  | PROBABILITY
Other | [6 empty] | Low | Medium | High
[5 empty] | CBA | Low | Low | Low | Medium
[6 empty] | Medium | Low | Medium | High
[6 empty] | High | Medium | High | High