## JAL Rekha_NFR_TestScenarios
Non-Functional Requirements | Req ID | Requirement Description | Scenario ID | Is Unit Test Case? | Is Integration Test Case? | Is Regression Test Case? | Scenario Description | Test Condition Description | Testcase Severity | Date of Execution | Test Result (Pass/Fail) | Retest Status | Bug Reference | Comments
10.1 Performance • The system shall respond to user actions within 2–3 seconds under normal load. • The system shall handle up to 500 concurrent users without degradation. • The system shall allow simultaneous file uploads/downloads without affecting other operations. | NFR-01 | The system shall respond to user actions within 2–3 seconds under normal load | 01.TS.001 | No | Yes | Yes | Verify system response time under normal load | Simulate average user operations and measure response time | Critical |  | FAILED | PASSED | JAL_NFR_01
| NFR-02 | The system shall handle up to 500 concurrent users without degradation | 01.TS.002 | No | Yes | Yes | Verify system performance under 500 concurrent users | Use load testing tools to simulate 500 concurrent users | Critical |  | PASSED
| NFR-03 | Allow simultaneous file uploads/downloads without affecting other ops | 01.TS.003 | No | Yes | Yes | Verify simultaneous file uploads/downloads without performance impact | Concurrently upload/download files with other system operations ongoing | High |  | PASSED
10.2 Scalability • The system shall support horizontal scaling to accommodate increased user load or additional modules. • The architecture shall allow integration of future modules without major redesign. | NFR-04 | Support horizontal scaling for increased user load or modules | 02.TS.004 | No | Yes | Yes | Verify system scales horizontally by adding nodes | Add nodes to cluster and validate system load distribution | High |  | FAILED |  | JAL_NFR_05
| NFR-05 | Architecture shall allow integration of future modules without major redesign | 02.TS.005 | No | Yes | No | Verify new module integration without system downtime or redesign | Add a test module and validate integration | Medium |  | PASSED
10.3 Availability and Reliability • The system shall maintain 99.5% uptime, excluding scheduled maintenance. • The system shall implement automatic recovery in case of failures. • The system shall provide daily data backups and support point-in-time recovery. | NFR-06 | Maintain 99.5% uptime excluding scheduled maintenance | 03.TS.006 | No | Yes | Yes | Monitor system uptime over 1 month | Use monitoring tools to track downtime and uptime metrics | Critical
| NFR-07 | Implement automatic recovery in case of failures | 03.TS.007 | No | Yes | Yes | Simulate system failure and verify automatic recovery | Manually cause failure and check system restart/recovery | Critical |  | FAILED | PASSED | JAL_NFR_04
| NFR-08 | Provide daily data backups and support point-in-time recovery | 03.TS.008 | No | Yes | Yes | Verify daily backups and point-in-time database recovery | Restore database to different points in time | Critical |  | PASSED
10.4 Security • The system shall enforce role-based access control (RBAC) for all users. • The system shall require strong passwords and enforce password policies. • The system shall support SSO login for department users and secure authentication for external users. • All sensitive data shall be encrypted at rest and in transit using industry-standard protocols. • The system shall log all user actions for audit purposes. • The system shall automatically log out users after 15 minutes of inactivity. | NFR-09 | Enforce role-based access control (RBAC) for all users | 04.TS.009 | Yes | Yes | Yes | Verify RBAC enforced for various user roles | Attempt actions with different roles and verify access rights | Critical |  | PASSED
| NFR-10 | Require strong passwords and enforce password policies | 04.TS.010 | Yes | No | Yes | Verify password strength enforcement during user creation | Enter weak and strong passwords and check acceptance | High |  | FAILED | PASSED | JAL_NFR_03
| NFR-11 | Support SSO login for department users and secure auth for external users | 04.TS.011 | No | Yes | Yes | Verify SSO login and secure external authentication | Test login flows with SSO and standard credentials | Critical |  | PASSED
| NFR-12 | Encrypt all sensitive data at rest and in transit | 04.TS.012 | No | Yes | Yes | Verify encryption of data in storage and during network transit | Inspect data storage and network traffic for proper encryption | Critical
| NFR-13 | Log all user actions for audit purposes | 04.TS.013 | No | Yes | Yes | Verify logging of user actions with timestamps and user ids | Perform user operations and check audit logs | High |  | PASSED
| NFR-14 | Auto logout users after 15 minutes inactivity | 04.TS.014 | Yes | Yes | Yes | Verify user is logged out automatically after 15 mins idle | Leave session idle for 15 minutes and verify logout | Medium |  | PASSED
10.5 Usability • The system shall provide a user-friendly interface with intuitive navigation. • The system shall provide dashboards and widgets for quick monitoring. • The system shall provide help tooltips and context-sensitive guidance for all major operations. | NFR-15 | Provide user-friendly interface with intuitive navigation | 05.TS.015 | Yes | No | No | Verify UI usability and intuitive navigation | Walkthrough core screens and evaluate UI ease | Medium |  | FAILED | PASSED | JAL_NFR_02
| NFR-16 | Provide dashboards and widgets for quick monitoring | 05.TS.016 | No | Yes | Yes | Verify dashboards show correct monitoring data | Check dashboard data with backend data | High |  | PASSED
| NFR-17 | Provide help tooltips and context-sensitive guidance for major ops | 05.TS.017 | Yes | No | No | Verify help tooltips appear for major operations | Navigate operational screens and check tooltip availability | Low |  | FAILED | PASSED | JAL_NFR_06
10.6 Maintainability • The system shall follow modular architecture for easier maintenance and future enhancements. • The system shall allow configuration changes (e.g., fee updates, module addition) without downtime. • The system shall generate audit logs and reports to help administrators monitor usage and troubleshoot issues. | NFR-18 | Follow modular architecture for easier maintenance and future enhancements | 06.TS.018 | No | Yes | No | Verify modular architecture by adding configuration changes | Modify config and verify no system downtime required | Medium |  | PASSED
| NFR-19 | Allow config changes without downtime (fee updates, module additions) | 06.TS.019 | No | Yes | Yes | Verify dynamic configuration updates without downtime | Update fees/config and monitor system availability | High |  | PASSED
| NFR-20 | Generate audit logs and reports to help admin monitor usage and troubleshoot | 06.TS.020 | No | Yes | Yes | Verify audit logs and reports generation | Access audit reports and verify accuracy | High |  | PASSED
10.7 Interoperability • The system shall integrate with government systems such as TNCP, PWD, PHE, and MPEB. • The system shall support import/export of reports in Excel and PDF formats. • The system shall provide APIs for future integration with mobile apps or GIS platforms. | NFR-21 | Integrate with government systems like TNCP, PWD, PHE, and MPEB | 07.TS.021 | No | Yes | Yes | Verify integration with external government systems | Exchange data and verify sync with external services | Critical |  | PASSED
| NFR-22 | Support import/export of reports in Excel and PDF formats | 07.TS.022 | Yes | Yes | Yes | Verify import/export functionality for Excel and PDF | Import/export sample reports and validate data | High
| NFR-23 | Provide APIs for future integration with mobile apps or GIS platforms | 07.TS.023 | No | Yes | Yes | Verify API endpoints for external integrations | Test APIs with sample requests | Critical |  | PASSED
10.8 Mobile Access • The system shall allow RIs to access modules via mobile applications. • The mobile app shall support offline data capture and automatic synchronization when connectivity is restored. | NFR-24 | Allow RIs to access modules via mobile applications | 08.TS.024 | No | Yes | Yes | Verify mobile app access to required modules | Login via mobile and validate module availability | High |  | PASSED
| NFR-25 | Mobile app shall support offline data capture and auto-sync on connectivity | 08.TS.025 | No | Yes | Yes | Verify offline data capture and automatic sync | Capture data offline and verify sync when online | High |  | PASSED
10.9 Audit and Compliance • The system shall maintain complete audit trails for all operations. • The system shall comply with state IT policies and data privacy regulations. • The system shall maintain versioning of all uploaded documents for traceability. | NFR-26 | Maintain complete audit trails for all operations | 09.TS.026 | No | Yes | Yes | Verify audit trails cover all operations | Perform operations and verify audit trail completeness | Critical |  | PASSED
| NFR-27 | Comply with state IT policies and data privacy regulations | 09.TS.027 | No | Yes | Yes | Verify compliance with applicable IT policies and regulations | Review system policies and data handling practices | Critical
| NFR-28 | Maintain versioning of all uploaded documents for traceability | 09.TS.028 | No | Yes | Yes | Verify document versioning on uploads and edits | Upload docs multiple times and validate version history | High |  | PASSED
10.10 Backup and Disaster Recovery • The system shall perform daily backups to a secure location. • The system shall support disaster recovery procedures, restoring critical operations within 4 hours. • The system shall allow restoration of database and file system in case of failure. | NFR-29 | Perform daily backups to a secure location | 10.TS.029 | No | Yes | Yes | Verify backups scheduled daily and stored securely | Check backup logs and storage location | Critical |  | PASSED
| NFR-30 | Support disaster recovery restoring critical operations in 4 hours | 10.TS.030 | No | Yes | Yes | Test disaster recovery restoring system within SLA | Simulate failure and measure recovery time | Critical |  | PASSED
| NFR-31 | Allow restoration of database and file system on failure | 10.TS.031 | No | Yes | Yes | Verify restore procedures for DB and file system | Perform restore from backups and validate | Critical |  | PASSED

## JAL Rekha_NFR_TestCases
Test Case ID | Test Case Description | Scenario ID | Prerequisite | Step No. | Action / Description | Expected Result | Date of Execution | Actual Results | Pass/Fail | Bug No. | Input Data | Comments
TS.001 | Verify system response time under normal load | 01.TS.001 | System deployed | 1 | Login to system | Login successful |  | Not As Expected | FAILED | JAL_NFR_01 | Valid credentials
|  |  |  | 2 | Perform common user actions | Response time ≤ 3 seconds |  | As Expected | PASSED |  | User actions
|  |  |  | 3 | Measure response time | Time measured within expected range |  | As Expected | PASSED
TS.002 | Verify system performance with 500 concurrent users | 01.TS.002 | Load testing tool setup | 1 | Simulate 500 concurrent users | System stable, no crash or slow response |  | As Expected | PASSED |  | Load tool config
|  |  |  | 2 | Monitor CPU, memory, network | Metrics within acceptable limits |  | As Expected | PASSED
TS.003 | Verify simultaneous uploads/downloads without impact | 01.TS.003 | Multiple logged in users | 1 | Concurrent file uploads/downloads | All files transfer successfully on time |  | As Expected | PASSED |  | Sample files
|  |  |  | 2 | Run other system operations concurrently | Other operations unaffected |  | As Expected | PASSED
TS.004 | Verify horizontal scaling by adding nodes. Slowness issue. | 02.TS.004 | System cluster in place | 1 | Add nodes to system cluster | Load distributed, system performance steady |  | As Expected | FAILED | JAL_NFR_05
TS.005 | Verify future module integration without redesign | 02.TS.005 | Existing modules working | 1 | Add test module | Module integrated without downtime |  | As Expected | PASSED |  | Test module assets
TS.006 | Monitor system uptime over 1 month | 03.TS.006 | Monitoring tools enabled | 1 | Track uptime over time | Uptime ≥ 99.5% excluding scheduled maintenance |  | As Expected | PASSED
TS.007 | Verify automatic recovery after failure | 03.TS.007 | System failure simulation enabled | 1 | Simulate system failure | System automatically recovers fully |  | As Expected | FAILED | JAL_NFR_04
TS.008 | Verify daily backups and point-in-time recovery | 03.TS.008 | Backup system operational | 1 | Verify daily backups | Backup files created successfully |  | As Expected | PASSED |  | Backup data
|  |  |  | 2 | Perform point-in-time database recovery | Database recovered accurately |  | As Expected | PASSED |  | Backup files
TS.009 | Verify RBAC enforcement for various roles | 04.TS.009 | Users with roles registered | 1 | Login as user with limited role | Access only allowed features |  | As Expected | PASSED |  | Role credentials
|  |  |  | 2 | Attempt restricted actions | Access denied, proper error message |  | As Expected
TS.010 | Verify password strength policy | 04.TS.010 | User creation or password change | 1 | Try weak password | System rejects weak password |  | As Expected | PASSED |  | Weak password
|  |  |  | 2 | Try strong password | System accepts strong password |  | As Expected | FAILED | JAL_NFR_03 | Strong password
TS.011 | Verify SSO login and secure auth | 04.TS.011 | SSO configured | 1 | Login with department SSO credentials | Login successful |  | As Expected | PASSED |  | SSO credentials
|  |  |  | 2 | Login external user using secure auth | Login successful |  | As Expected | PASSED |  | External creds
TS.012 | Verify encryption of sensitive data | 04.TS.012 | Encryption enabled | 1 | Inspect data at rest | Data encrypted |  | As Expected | PASSED
|  |  |  | 2 | Inspect data in transit | Data transmitted encrypted |  | As Expected
TS.013 | Verify user action logging with timestamps | 04.TS.013 | Audit logging enabled | 1 | Perform typical user operations | Operations logged with correct timestamps |  | As Expected | PASSED |  | User operations
TS.014 | Verify auto logout after inactivity | 04.TS.014 | User logged in | 1 | Leave session idle for 15 minutes | User automatically logged out |  | As Expected | PASSED
TS.015 | Verify user-friendly UI with proper alignment | 05.TS.015 | UI deployed | 1 | Navigate core screens | Navigation intuitive, no confusion |  | As Expected | FAILED | JAL_NFR_02
TS.016 | Verify dashboards and widgets show correct data | 05.TS.016 | Dashboards configured | 1 | View dashboards | Data matches backend |  | As Expected | PASSED
TS.017 | Verify error message user friendly | 05.TS.017 | Help system enabled | 1 | Access major operations | Context-sensitive help tooltip appears |  | As Expected | FAILED | JAL_NFR_06
TS.018 | Verify modular architecture and config changes | 06.TS.018 | Modular setup enabled | 1 | Modify config parameter | No system downtime, change effective |  | As Expected | PASSED |  | Config parameters
TS.019 | Verify config changes allowed without downtime | 06.TS.019 | System live | 1 | Change fee or add module dynamically | System remains available, changes effective |  | As Expected | PASSED |  | Config changes
TS.020 | Verify audit logs and report generation | 06.TS.020 | Audit system enabled | 1 | Generate audit logs | Logs accurate and complete |  | As Expected | PASSED
TS.021 | Verify integration with government systems | 07.TS.021 | External systems accessible | 1 | Exchange data with TNCP, PWD etc | Data sync verified |  | As Expected | PASSED
TS.022 | Verify import/export of reports in Excel & PDF | 07.TS.022 | Reporting module enabled | 1 | Export report to Excel | File exports correctly |  | As Expected | PASSED |  | Sample reports
|  |  |  | 2 | Export report to PDF | File exports correctly |  | As Expected |  |  | Sample reports
TS.023 | Verify API endpoints for future integration | 07.TS.023 | APIs deployed | 1 | Make sample API call | API responds successfully |  | As Expected | PASSED |  | API request data
TS.024 | Verify mobile app access to modules | 08.TS.024 | Mobile app deployed | 1 | Login through mobile app | Modules visible and accessible |  | As Expected | PASSED |  | Mobile user creds
TS.025 | Verify mobile app offline data capture and sync | 08.TS.025 | Mobile app deployed | 1 | Capture data offline | Data stored locally |  | As Expected | PASSED |  | Offline data
|  |  |  | 2 | Restore connectivity and sync data | Data synced to server |  | As Expected | PASSED
TS.026 | Verify complete audit trails | 09.TS.026 | Audit system enabled | 1 | Perform diverse operations | All operations logged |  | As Expected | PASSED
TS.027 | Verify compliance with IT policies and privacy regulations | 09.TS.027 | Policies defined | 1 | Review system design and policies | Compliance assured |  | As Expected | PASSED |  | Documentation
TS.028 | Verify document versioning for traceability | 09.TS.028 | Document management enabled | 1 | Upload document versions | Version history maintained |  | As Expected | PASSED |  | Multiple document versions
TS.029 | Verify daily backups to secure location | 10.TS.029 | Backup system live | 1 | Check backup logs | Daily backups completed successfully |  | As Expected | PASSED |  | Backup logs
TS.030 | Verify disaster recovery restores critical ops within 4h | 10.TS.030 | Recovery procedures defined | 1 | Simulate critical failure | Restored within 4 hours |  | As Expected | PASSED
TS.031 | Verify restore DB and file system on failure | 10.TS.031 | Backup data available | 1 | Restore DB from backup | Data restored successfully |  | As Expected | PASSED |  | Backup files
|  |  |  | 2 | Restore file system | Files restored without corruption |  | As Expected | PASSED |  | Backup files

## JAL Rekha_NFR_Bugs
S.No. | Bug ID | Project | Application Area/Path/Module | Test Case Reference | Build No. | Severity | Priority | Assigned to | Reported by | Reported on | Status | Bug Summary | Phase Detected | Phase Injection | Screenshot1's URL | Screenshot2's URL | Bug Description | Steps to Reproduce | Expected Result | Retesting Build Version | Retested On | Retest Status | Retest Screenshot1 | Retest Screenshot2 | Comments
1 | JALRekha_NFR_01 | JAL Rekha Web App | Performance & Load Related | 01.TS.001 |  | High | High | Sunil Thakur | Ranjana Yadav |  | Closed | Slow dashboard loading when GM logs in and large amounts of activity data are fetched | System Testing | Requirement Analysis | N/A | N/A | Slow dashboard loading when GM logs in and large amounts of activity data are fetched | 1.Login as GM with valid credentials. 2.Ensure database has thousands of activity records (from multiple PIUs/ISAs). 3.Navigate to the GM dashboard. | Dashboard should load within acceptable performance benchmark (e.g., <3–5 seconds), even with large datasets. |  |  | PASSED | N/A | N/A
2 | JALRekha_NFR_02 | JAL Rekha Web App | Usability & UI/UX | 05.TS.015 |  | Medium | High | Sunil Thakur | Ranjana Yadav |  | Closed | Inconsistent font sizes and alignment in tabular form data | Usability Testing | UI Design | N/A | N/A | Inconsistent font sizes and alignment in tabular form data | 1. Login as any valid user (GM/PIU/CM). 2Navigate to Sahbhagita Activity reports page. 3.View tabular report data across multiple columns. | Font sizes and alignment should be consistent across all rows/columns, ensuring readability. |  |  | PASSED | N/A | N/A
3 | JALRekha_NFR_03 | JAL Rekha Web App | Security | 04.TS.010 |  | Critical | High | Sunil Thakur | Ranjana Yadav |  | Closed | Password update error messages too detailed, exposing system behavior. | Security Testing | Requirement Analysis | N/A | N/A | Session not auto-terminated after long inactivity, leaving portal open. | 1.Login as GM. 2.Leave the portal idle for 1+ hour (simulate inactivity). 3.Without re-login, try to access protected page (e.g., Work Monitoring). | System should auto-terminate inactive sessions (e.g., 15–20 min) and redirect to login screen with message “Session Expired. Please login again.” |  |  | PASSED | N/A | N/A
4 | JALRekha_NFR_04 | JAL Rekha Web App | Reliability & Availability | 03.TS.007 |  | Critical | High | Sunil Thakur | Ranjana Yadav |  | Closed | Data inconsistency between mobile uploads and web reports after sync | Compliance Audit | Policy Definition | N/A | N/A | Data inconsistency between mobile uploads and web reports after sync | 1.On mobile app, submit OHT meter reading and Sahbhagita activity. 2.Sync the data with server. 3.Login to GM portal and open Activity reports | Uploaded mobile data should be consistently reflected in web reports without missing or mismatched entries. |  |  | PASSED | N/A | N/A
5 | JALRekha_NFR_05 | JAL Rekha Web App | Scalability | 02.TS.004 |  | Critical | High | Sunil Thakur | Ranjana Yadav |  | Closed | System slows down significantly when user count exceeds 500 concurrent logins | Security Testing | Requirement Analysis | N/A | N/A | System slows down significantly when user count exceeds 500 concurrent logins | 1. Perform load testing with 500+ concurrent user logins. 2.Monitor response times while users generate reports or update mappings. | System should remain stable and responsive under high load (response times within acceptable SLA). |  |  | PASSED | N/A | N/A
6 | JALRekha_NFR_06 | JAL Rekha Web App | Usability & UI/UX | 05.TS.017 |  | High | High | Sunil Thakur | Ranjana Yadav |  | Closed | Error messages not user-friendly (e.g., “500 Server Error” instead of “Session Expired. Please login again”). | Functional Testing | Requirement Specification | N/A | N/A | Error messages not user-friendly (e.g., “500 Server Error” instead of “Session Expired. Please login again”). | 1. Login as GM. 2.Keep session idle until token expires. 3.Try to navigate to Sahbhagita Activity screen | System should show clear, user-friendly message like: “Session expired. Please login again.” instead of technical error. |  |  | PASSED | N/A | N/A