## FHTC JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19770 | FHTC (Functional Household Tap Connection) | Tap Photo Upload Not Persisted / Corrupt on Server--FE attaches a tap/beneficiary photo in Household Survey and submits. On web (GM/Contractor) the image is missing or corrupted (broken thumbnail). Sometimes the mobile preview shows the image but server-side record lacks image link. | Testing | Fucntional | High | 2025-09-19 | Tapan Khandelwal | Closed | Development
BugID: 19785 | FHTC (Functional Household Tap Connection) | Reject Routing Not Delivered to Contractor--When FE marks a connection as Rejected (Not Proper) and submits, GM receives the record but contractor does not receive notification or record in contractor portal. | UAT | Fucntional | High | 2025-09-19 | Tapan Khandelwal | Closed | UAT
BugID: 19787 | FHTC (Functional Household Tap Connection) | Accept Routing Misrouted / Duplicate Notifications--When FE marks connection as Accepted, sometimes the GM web shows pending or duplicate entries; notifications are duplicated or the record status remains unupdated. | UAT | Fucntional | Medium | 2025-09-20 | Tapan Khandelwal | Closed | UAT
BugID: 19789 | FHTC (Functional Household Tap Connection) | HSC Report Missing Mandatory Photo Flag / Export Incomplete--HSC report (used by GM/PIU) requires photo as mandatory. Generated reports (PDF/Excel) omit photo field or produce blank image placeholders for many records; report generation does not fail when photo missing. | PROD | Fucntional | Medium | 2025-09-21 | Tapan Khandelwal | Closed | PROD
BugID: 19790 | FHTC (Functional Household Tap Connection) | Mandatory geo-coordinates not enforced--Requirement states geo-coordinates (Lat/Long) are mandatory for FHTC completion, but UI allows saving without capturing location. | Requirement Analysis | UI/UX | High | 2025-08-23 | BA/UI Team | Closed | Requirement
BugID: 19791 | FHTC (Functional Household Tap Connection) | Date validation rules not clearly defined--System allows future dates or dates older than scheme sanction date during FHTC entry. | Requirement Analysis | Validation | High | 2025-10-18 | BA/UI Team | Closed | Requirement
BugID: 19792 | FHTC | Corrected the input field of login page | UAT | UI/UX | Medium | 2025-08-23 | Vijay | Closed | UAT
BugID: 19793 | FHTC | Missing Backend Role Validation (FE/GM/Contractor workflow controlled only at UI level) | Development | Code Review | Medium | 2025-08-22 | Tapan Khandelwal | Closed | Development
BugID: 19794 | FHTC | Mandatory Beneficiary Photo validation not enforced at backend | Development | Code Review | Medium | 2025-08-28 | Tapan Khandelwal | Closed | Development
BugID: 19795 | FHTC | No Proper API Logging & Change Control | Development | Code Review | Medium | 2025-09-11 | Tapan Khandelwal | Closed | Development
BugID: 19796 | FHTC | Requirement documents, RTM, and design documents may not be updated; integration risks not formally tested or approved | Development | Code Review | Medium | 2025-10-23 | Tapan Khandelwal | Closed | Development

## Bharosa JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19800 | BHAROSA | When GM adds a new vendor using “Add New Vendor,” the vendor is saved but does not appear in the vendor dropdown. This prevents factory testing entries from being submitted for new or unlisted vendors. | Testing | Fucntional | High | 2025-10-15 | Neha | Closed | Requirement Analysis
BugID: 19801 | BHAROSA | When GM selects a Component, the Sub-Component dropdown does not refresh and still displays all sub-components, including unrelated ones. This allows invalid combinations to be saved | Testing | Fucntional | High | 2025-10-28 | Neha | Closed | Development
BugID: 19804 | BHAROSA | Inspectors attempting to upload short test videos receive an “Unsupported Format” error even for allowed formats (MP4/MOV). Backend MIME validation is incorrect. | UAT | Fucntional | High | 2025-10-29 | Neha | Closed | UAT
BugID: 19806 | BHAROSA | The exported Excel/PDF report does not include new CR fields such as Inspector Name, Vendor Category, or updated Samagra-linked metadata. Users rely on incomplete data for audit. | UAT | Fucntional | Medium | 2025-10-29 | Neha | Closed | UAT
RR‑BHA‑C2‑02 | Bharosa | Component–Sub‑Component dependency rules were not fully defined in requirements, allowing design to permit all sub‑components irrespective of selected component in Factory Testing Web. | Requirement Analysis | Requirement | High | 2025-10-12 | Dheeraj | Closed | Requirement Analysis | Requirement document listed components and sub‑components but did not capture mapping matrix or invalid combinations, so validation logic was left to developer assumptions.
BugID: 19807 | BHAROSA | Role-based validation is missing at both UI and API levels, allowing unauthorized role mapping and leading to potential security and access control issues. | Development | Code Review | High | 2025-10-15 | Sunil Thakur | Closed | Develpomemt
BugID: 19808 | BHAROSA | Proper input validation, data synchronization, and media upload error handling are missing across the Factory Testing workflow, which may lead to inconsistent inspector entries, incorrect component mapping, and failed or incomplete document, image, and video uploads. | Development | Code Review | High | 2025-10-28 | Anand Gour | Closed | Development
BugID: 17836 | BHAROSA | Inspection Images Incorrectly Displayed Under a Single Column | UAT | UI/UX | Medium | 2025-10-25 | Vijay | Closed | UAT

## O&M JtoN
Defect ID | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects | RCA for Major Defects
RR-OMB-C2-01 | Requirements for GM and Contractor flows do not define a single master source for contractor "Firm Name" | Requirement Analysis | Functional | Critical | 2025-08-06 | Ankur | Closed | Requirement Analysis | Field list was finalized screen-wise instead of using a common contract data model; cross-screen mandatory attributes like Firm Name were not validated during requirement review.
RR-OMB-C2-02 | Residual Pressure entry requirements do not specify accepted value range, data type | Requirement Analysis | Functional | Critical | 2025-09-04 | Ankur | Closed | Requirement Analysis | Detailed validation rules for engineering parameters were assumed to match Dhara norms but never copied into O&M Billing requirements or checked with domain experts.
RR-OMB-C2-03 | RA Bill requirements do not clearly state details after save/submit and audit trail | Requirement Analysis | Functional | High | 2025-09-25 | Ankur | Closed | Requirement Analysis | Life-cycle of create, edit, delete, lock after RA bill specific parameters was not modelled in, so delete behaviour was left to default CRUD assumptions.
CR-OM-C2-04 | Penalty label changes not reflected consistently across screens | Code Review | UI/UX | Medium | 2025-09-12 | Awinash Khare | Closed | Design
BugID: 19796 | Incorrect pop-up message after adding Census data | UAT | UI/UX | High | 2025-09-19 | Sunil | Closed | Design
BugID: 13216 | "Previous" tab at bottom should be removed | UAT | UI/UX | Medium | 2025-09-15 | Vijay | Closed | Design
BugID: 13375 | Alignment issue with date fields | UAT | UI/UX | Medium | 2025-09-09 | Vijay | Closed | Design
CR-OM-C2-01 | Auto-save every 5 minutes not working consistently | Code Review | Functional | High | 2025-08-15 | Awinash Khare | Closed | Development
CR-OM-C2-02 | Census population hierarchy shows incorrect village-to-block mapping | Code Review | Functional | High | 2025-09-05 | Awinash Khare | Closed | Development
CR-OM-C2-03 | "Other" option in Norms and Penalty dropdowns missing custom text input | Code Review | Functional | High | 2025-09-10 | Awinash Khare | Closed | Development
CR-OM-C2-05 | CPI-W factor dropdown shows incorrect values; leap year calculation issue | Code Review | Functional | High | 2025-09-18 | Awinash Khare | Closed | Development
CR-OM-C2-06 | View Document button not opening PDFs; Eligibility Increment calculation off | Code Review | Functional | Medium | 2025-09-20 | Awinash Khare | Closed | Development
CR-OM-C2-07 | GST rate dropdown not populating with latest rates | Code Review | Functional | High | 2025-09-25 | Awinash Khare | Closed | Development |  | Field list was finalized screen-wise instead of using a common contract data model; cross-screen mandatory attributes like Firm Name were not validated during requirement review.
CR-OM-C2-08 | Screen freeze after document upload not working | Code Review | Functional | High | 2025-11-05 | Awinash Khare | Closed | Development |  | Life-cycle of create, edit, delete, lock after RA bill specific parameters was not modelled in, so delete behaviour was left to default CRUD assumptions.
BUDID:001 | Auto-save every 5 minutes not working consistently | Code Review | Functional | High | 2025-08-15 | Awinash Khare | Closed | Development
BugID: 19791 | Contract details > Advance details > correct spelling "precentage" to "percentage" | Testing | Functional | High | 2025-10-15 | Rahul | Closed | Development
BugID: 19792 | Firm Name missing from Advance Details, Document Upload, Scheme Status | Testing | Functional | High | 2025-10-15 | Rahul | Closed | Requirement Analysis
BugID: 19793 | Measured Pressure field not accepting values | Testing | Functional | High | 2025-10-16 | Rahul | Closed | Development
BugID: 19794 | Unexpected validation pop-up in O&M Bill | Testing | Functional | Medium | 2025-10-16 | Rahul | Closed | Development
BugID: 19797 | User able to delete census population record after save and next | UAT | Validation | Medium | 2025-09-20 | Sunil | Closed | UAT
BugID: 19798 | Incorrect pop-up message after save and next from basic details | UAT | Data | Medium | 2025-09-21 | Sunil | Closed | UAT

## Dhara CR JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19813 | DHARA CR | When the user maps habitation with an OHT and clicks Save, the system does not store the mapping. The record disappears after refresh, leading to incomplete scheme-level linkage. | Testing | Fucntional | High | 2025-08-01 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 19815 | DHARA CR | Habitation mapping assignments created by GM/TL are not pushed to the FE mobile application, so field executives don't receive the tasks. | Testing | Fucntional | High | 2025-08-01 | Tapan Khandelwal | Closed | Requirement Analysis
Bug ID: 19816 | DHARA CR | Updates made to Intake meter survey fields (functional status, parameters) are not persisted after Save. | Testing | Fucntional | High | 2025-08-20 | Tapan Khandelwal | Closed | Develpomemt
Bug ID: 19817 | DHARA CR | Modified OHT meter readings do not sync to DWSR, MWSR, or village-level reports, causing discrepancies in reporting. | Testing | Fucntional | Medium | 2025-08-10 | Tapan Khandelwal | Closed | Develpomemt
Bug ID: 19818 | DHARA CR | When modifying an existing Intake meter reading, the updated values are not saved and revert back to the previous values after refresh. | UAT | Fucntional | High | 2025-08-08 | Tapan Khandelwal | Closed | UAT
Bug ID: 19819 | DHARA CR | Drill-down view shows an incorrect count of OHTs (e.g., displays 10 when only 7 exist in the database). | UAT | Fucntional | Medium | 2025-09-05 | Tapan Khandelwal | Closed | UAT
BugID: 19820 | DHARA CR | Valid WTP meter reading values trigger validation errors such as 'Invalid Reading', blocking the update/save operation. | UAT | Fucntional | Medium | 2025-08-08 | Tapan Khandelwal | Closed | UAT
Bug ID: 19821 | DHARA CR | Tasks assigned from GM/TL to FE via the portal do not sync to the FE mobile app, leaving FE with an empty task list. | PROD | Fucntional | Medium | 2025-08-24 | Tapan Khandelwal | Closed | PROD
BugID: 19822 | DHARA CR | When mapping OHTs, the dropdown for villages/habitations does not load the complete list; many active villages are missing. | PROD | Fucntional | Medium | 2025-08-24 | Tapan Khandelwal | Closed | PROD
BugID: 19823 | DHARA CR | Updates to meter status performed by FE or GM are not saved and revert after page refresh. | PROD | Fucntional | Medium | 2025-08-24 | Tapan Khandelwal | Closed | PROD
BugID: 19824 | DHARA CR | Bulk meter supporting document upload (e.g., Agreement PDF) fails with an error despite valid file type and size. | PROD | Fucntional | Medium | 2025-09-05 | Tapan Khandelwal | Closed | PROD
RR‑DHA‑C2‑01 | Dhara CR | Requirements for habitation–OHT mapping did not clearly state persistence rules and success criteria, allowing save‑without‑commit behaviour to pass design review. | Requirement Analysis | Requirement | High | 2025-09-06 | Ankur | Closed | Requirement Analysis | BRD mentioned “mapping” generically but lacked detailed CRUD behaviour and post‑save validation scenarios, so analysts and developers assumed default framework behaviour.
RR‑DHA‑C2‑02 | Dhara CR | GM/TL‑to‑FE task assignment requirements did not specify guaranteed sync to mobile app with status tracking, causing ambiguity on whether FE tasks are mandatory or optional to receive on device. | Requirement Analysis | Requirement | High | 2025-08-16 | Ankur | Closed | Requirement Analysis | Cross‑channel sync (web to mobile) was treated as technical detail and not captured as explicit functional requirement with SLA and error‑handling use cases.
RR‑DHA‑C2‑03 | Dhara CR | Meter survey and reading update requirements (Intake, OHT, WTP) did not define update vs. insert behaviour, validations, and how corrected readings should cascade into DWSR/MWSR and village‑level reports. | Requirement Analysis | Requirement | High | 2025-07-11 | Ankur | Closed | Requirement Analysis | Impact of changed readings on downstream aggregates and reports was not modelled in data‑flow diagrams, leading to partial implementation assumptions.
RR‑DHA‑C2‑04 | Dhara CR | Requirements for dropdowns and drill‑down reports did not mandate completeness of village/habitation lists or consistency between UI counts and database records, enabling under‑specified behaviour in mapping and reporting screens. | Requirement Analysis | Requirement | Medium | 2025-09-09 | Ankur | Closed | Requirement Analysis | Stakeholders assumed “all active records will appear” but this was never written as an acceptance criterion, so pagination/filter rules were left open to interpretation.
BugID: 19825 | Dhara CR | Data mapping errors or unauthorized mapping changes | Development | Code Review | High | 2025-07-16 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19826 | Dhara CR | Incorrect approvals, backdated entries, lack of approval tracking | Development | Code Review | High | 2025-07-24 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19827 | Dhara CR | Unauthorized data modification and data integrity issues | Development | Code Review | High | 2025-08-01 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19828 | Dhara CR | Habitation-wise mapping to FE was not properly assigned or missing in the system. | Development | Code Review | High | 2025-08-13 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19829 | Dhara CR | Meter parameter values (Meter Functional, Meter Not Functional, Meter Replace, No Water Supply) were incorrectly configured with default values. | Development | Code Review | High | 2025-08-18 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19830 | Dhara CR | Incorrect default settings may cause wrong reporting and data inconsistency | Development | Code Review | High | 2025-08-27 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19831 | Dhara CR | Water Supply Reports (DWSR, MWSR, Scheme Wise, Village Wise, Bulk User, UFW) were not reflecting updated/changed data properly. | Development | Code Review | High | 2025-09-02 | Tapan Khandelwal | Closed | Develpomemt
BugID: 19832 | Dhara CR | Drill-down functionality was not working correctly or mapping data was inconsistent. | Development | Code Review | High | 2025-09-15 | Tapan Khandelwal | Closed | Develpomemt
Bug_01 | Dhara CR | Fixed the input fields and alignment of the Add New User Modal popup | UAT | UI/UX | Medium | 2025-07-19 | Vijay | Closed | UAT
Bug_02 | Dhara CR | No error message displayed when clicking "Mapped" without selecting any RFI | UAT | UI/UX | Medium | 2025-08-18 | Vijay | Closed | UAT
Bug_03 | Dhara CR | icon shown despite no image captured in Pending RFI View Detail | UAT | UI/UX | Medium | 2025-08-18 | Vijay | Closed | UAT
BugID: 21902 | Dhara CR | Login Page-->Forgot Password--> Mobile field-->Enter unregistered mobile Number-->Send OTP-->Enter here OTP -->Enter OTP-->Password-->Enter new password-->Update password-->Page disappears after clic | UAT | UI/UX | Medium | 2025-08-19 | Vijay | Closed | UAT

## Master CR JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID:19830 | MASTER CR | In Master → OHT Mapping screen, habitation dropdown does not expand or loads empty | Testing | Fucntional | High | 2025-07-16 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 19832 | MASTER CR | When an RFI stage is approved/rejected, the Pipeline Master table does not update its stage status. The RFI workflow works correctly, but Pipeline Master remains stuck at previous stage. | Testing | Fucntional | High | 2025-08-12 | Tapan Khandelwal | Closed | Development
BugID: 19833 | MASTER CR | When mapping WTP to Intake source, the system generates duplicate relationship entries even when mapping already exists. This results in redundant records and incorrect report totals. | UAT | Fucntional | Medium | 2025-07-19 | Tapan Khandelwal | Closed | UAT
BugID: 19835 | MASTER CR | Daily WTP water readings are recorded successfully but do not roll up into the month-wise summary totals. Monthly dashboard shows zero/blank consumption despite daily entries being present. | PROD | Fucntional | Medium | 2025-08-26 | Tapan Khandelwal | Closed | PROD
BugID: 19836 | Master | Master CR requirements for GM/Contractor and FE Pipeline changes do not explicitly define one‑to‑one rules between WTP, Intake, OHT, and village mappings, allowing duplicate relationships and missing roll‑up logic in month‑wise summaries. | Requirement Analysis | Requirement | High | 2025-08-06 | Ankur | Closed | Requirement Analysis | Mapping and aggregation rules for updated Pipeline Master were discussed at high level but not translated into detailed requirement scenarios or data‑flow diagrams before sign‑off.
BugID: 19837 | Master | OHT Name is not reflecting on OHT Village mapping screen | UAT | UI/UX | Medium | 2025-07-15 | Vijay | Closed | UAT
BugID: 19838 | Master | Duplicate date picker popup shown for single date field | UAT | UI/UX | Medium | 2025-08-08 | Vijay | Closed | UAT
BugID: 19839 | Master | Contractor edit functionality before final submission | Development | Code Review | Medium | 2025-07-04 | Tapan Khandelwal | Closed | Development
BugID: 19840 | Master | Village / Habitation / OHT / Outside Scheme mapping without strict control | Development | Code Review | Medium | 2025-07-09 | Tapan Khandelwal | Closed | Development
BugID: 19841 | Master | WTP meter mapping added for all 147 schemes without controlled validation | Development | Code Review | Medium | 2025-07-15 | Tapan Khandelwal | Closed | Development

## Nirmal CR JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19844 | NIRMAL CR | Even after increasing buffer to 200m, mobile app still blocks sample collection beyond 100m or old lower limit | Testing | Fucntional | Medium | 2025-07-12 | Aamreen | Closed | Development
BugID: 19847 | NIRMAL CR | If FE records Intake or WTP readings offline, the data does not sync automatically once the device reconnects to the internet. Users must manually re-enter the reading, leading to data loss and duplication risk. | UAT | Fucntional | High | 2025-09-08 | Aamreen | Closed | UAT
BugID: 21607 | NIRMAL CR | WTP Report Parameter Change--WTP report shows incorrect parameter mapping after CR deployment After parameter changes in WTP report: Old parameters still visible in some schemes. New parameters not mapped properly for certain PIUs. Report export (PDF/Excel) does not reflect updated parameter sequence. Some calculated fields show incorrect values. | PROD | Fucntional | High | 2025-09-25 | Aamreen | Closed | PROD
BugID_01 | NIRMAL CR | Date range filter & Water Sample ID search-Filters/search may return incomplete or wrong records if logic not updated. Intake buffer increased to 200m for raw water sample collection- System may not reflect the updated buffer, causing missing or incorrect sample data. | Development | Code Review | High | 14-07-2025 | Sunil | Closed | Development
RR‑NIR‑C2‑01 | Nirmal | WTP/OHT Report CR does not clearly specify that the increased 200 m buffer must fully replace any earlier distance limit in mobile validations, leading to conflicting rules interpreted differently by app and report designers. | Requirement Analysis | Requirement | Medium | 2025-09-04 | Ankur | Closed | Requirement Analysis | Change request mentioned buffer increase informally; requirement document did not update existing validation rules or define single source of truth for distance configuration.
BugID_01 | Nirmal | Default value missing in Block, Gram Panchayat, and Village dropdowns | UAT | UI/UX | Medium | 2025-07-14 | Vijay | Closed | UAT
BugID_02 | Nirmal | Inspection Images Incorrectly Displayed Under a Single Column | UAT | UI/UX | Medium | 2025-07-09 | Vijay | Closed | UAT

## Sahbhagita CR JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19855 | Sahbhagita CR | The system accepts video files in unsupported formats (e.g., .mkv, .mov), but fails during upload or corrupts attachment. | Testing | Fucntional | Low | 2025-09-16 | Tapan Khandelwal | Closed | Requirement Analysis
BugID: 19858 | Sahbhagita CR | Activities uploaded by FE (photos, remarks, timestamps) are visible in FE mobile, but do not appear on GM’s Sahbhagita dashboard. Sync delay leads to incomplete field monitoring and incorrect daily activity status. | Testing | Fucntional | High | 2025-09-16 | Tapan Khandelwal | Closed | Development
BugID:19859 | Sahbhagita CR | FE is able to submit Sahbhagita activity without uploading a mandatory Gram Sabha photo. System accepts blank photo field and marks activity as “Completed”, violating workflow rules. | Testing | Fucntional | High | 2025-10-21 | Tapan Khandelwal | Closed | Development
BugID: 19861 | Sahbhagita CR | Village dropdown in Sahbhagita report only displays partial list. Some active villages mapped to the scheme are hidden or missing, preventing GM/PM from reviewing full activity coverage. | PROD | Fucntional | Medium | 2025-09-29 | Tapan Khandelwal | Closed | PROD
Bug ID: 19862 | Sahbhagita CR | Excel/PDF export of Sahbhagita report does not include FE Name, Submission Time, or Activity Type. Exported file provides incomplete information compared to UI report. | PROD | Fucntional | Medium | 2025-11-05 | Tapan Khandelwal | Closed | PROD
RR‑SAH‑C2‑06 | Sahbhagita CR | Requirement for “Report Modification shown” did not define detailed use cases (filters, sorting, drill‑down) for Sahbhagita Reports, causing varying interpretations among designers and testers. | Requirement Analysis | Requirement | Medium | 2025-10-16 | Dheeraj | Closed | Requirement Analysis | High‑level CR description accepted without decomposing into concrete scenarios and acceptance criteria during review.
Bug ID: 19863 | Sahbhagita | Report modification implemented without updated requirement documentation and testing evidence | Development | Code Review | High | 2025-09-16 | Tapan Khandelwal | Closed | Develpomemt
Bug ID: 19864 | Sahbhagita CR | GM Sahbhagita report view changes and PM video upload functionality implemented without documented validation, storage policy, and access control review | Development | Code Review | High | 2025-10-28 | Tapan Khandelwal | Closed | Develpomemt
BugID_01 | Sahbhagita | The alignment was going up and down when the Gram Sabha photo was uploaded. | UAT | UI/UX | Medium | 2025-09-15 | Vijay | Closed | UAT
BugID_02 | Sahbhagita | Alignment issue with the input fields in top bar search block | UAT | UI/UX | Medium | 2025-09-19 | Vijay | Closed | UAT

## Sopan CR JtoN
Defect ID | Modul Name | Defect Description | Phase Detected | Defect Type | Defect Severity | Date Logged | Assigned to | Status | Phase Injected | RCA for Major Defects
BugID: 19864 | SOPAN CR | The “Panchanama PDF Upload” feature is not functioning. Users are unable to upload the Panchanama PDF file, and no validation message is displayed | Testing | Fucntional | Medium | 2025-07-27 | Leena | Closed | Development
BugID: 19865 | SOPAN CR | GM edits actual start/end dates in SOPAN, but RFI module still displays the old dates. This causes mismatch during inspection validation. | Testing | Fucntional | Medium | 2025-08-02 | Leena | Closed | Development
BugID: 19869 | SOPAN CR | Refreshing during stage save creates duplicate records. GM sees multiple identical rows under the same stage. | PROD | Fucntional | High | 2025-08-01 | Leena | Closed | PROD
BugID: 19870 | SOPAN CR | The requirement does not clearly define: Mandatory stage sequence (e.g., Civil → Electromechanical) Whether later stages can be entered without completing earlier stages Auto-enable behavior for the next stage after completion | Requirement Analysis | Requirement | Medium | 2025-07-05 | Ankur | Closed | Requirement
BugID: 19871 | SOPAN CR | The GM Edit icon is not visible in the table | UAT | UI/UX | Medium | 2025-07-13 | Vijay | Closed | UAT
BugID: 19872 | SOPAN CR | Alignment Issue in select dropdown input field | UAT | UI/UX | Medium | 2025-08-20 | Vijay | Closed | UAT
BugID: 19873 | SOPAN CR | OHT (Conventional & Precast), WTP, IPS form changes and delete functionality implemented without strict workflow control and impact analysis | Development | Code Review | Medium | 2025-07-15 | Tapan Khandelwal | Closed | Development
BugID: 19874 | SOPAN CR | Mobile APK logic change (Sopan OHT completion not shown in RFI module) implemented without documented integration validation | Development | Code Review | Medium | 2025-08-01 | Tapan Khandelwal | Closed | Development
BugID: 19875 | SOPAN CR | GM edit & freeze functionality at each stage implemented without strict approval workflow and audit tracking | Development | Code Review | Medium | 2025-08-12 | Tapan Khandelwal | Closed | Development
BugID: 19876 | SOPAN CR | Drill-down reports (OHT/WTP/Intake) and Panchnama/design PDF upload changes implemented without documented validation & data consistency checks | Development | Code Review | Medium | 2025-09-07 | Tapan Khandelwal | Closed | Development