## Sheet1
Sr No | Sr No | Department | Project Name | Module | Name of Sub Modules | CR | Size USP FP | Planned Effort (Person Hours) | Actual Effort (Person Hours) | Planned Start Date (module) | Planned End Date (module) | Actual Start Date (module) | Actual End Date (module) | Requirement Analysis Start Date (module) | Requirement Analysis End Date (module) | Design Start Date (module) | Design End Date (module) | Coding Start Date (module) | Coding End Date (module) | Testing Start Date (module) | Testing End Date (module) | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Testing Review Efforts | Requirement Review Efforts | Design Review Effort | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Productivity | DRE | Requirement Rate | Design Rate | Code Rate | Testing Rate
1 | 1 | Public Health Engineering Department | Jal Rekha | AI Module - FHTC Tap Connection |  | No | 9 | 112 | 85 | 08/05/2026 | 24/05/2026 | 08/05/2026 | 23/05/2026 | 08/05/2026 | 11/05/2026 | 09/05/2026 | 11/05/2026 | 11/05/2026 | 19/05/2026 | 18/05/2026 | 23/05/2026 | 4 | 0 | 76 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0 | 2.25 | 0 | 0.12 | 1.8
2 | 2 | Public Health Engineering Department | Jal Rekha | AI Module - FHTC Tap Connection | ML model implementation on the tap connection monitoring buffer region, and other validations | No | 3 | 32 | 28 | [12 empty] | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0 | 0 | 0 | 0.11 | 0
3 | 3 | Public Health Engineering Department | Jal Rekha | AI Module - FHTC Tap Connection | Data Processing of FHTC Tap connections using AI models | No | 3 | 80 | 57 | [12 empty] | 4 | 0 | 48 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0.75 | 0 | 0.06 | 0.6
4 | 4 | Public Health Engineering Department | Jal Rekha | AI Module - FHTC Tap Connection | Machine Learning Predictive Model Implementation | No | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 5 | Public Health Engineering Department | Jal Rekha | All Public Reports on Dashboard |  | No | 6 | 4 | 4 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 13/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
6 | 6 | Public Health Engineering Department | Jal Rekha | All Public Reports on Dashboard | CR/Prod/UAT Bug testing | No | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 7 | Public Health Engineering Department | Jal Rekha | All Public Reports on Dashboard | Internal Testing | No | 3 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
8 | 8 | Public Health Engineering Department | Jal Rekha | Anusharavan |  | No | 0 | 630 | 527 | 01/02/2024 | 15/03/2024 | 01/02/2024 | 19/03/2024 | 01/02/2024 | 09/02/2024 | 10/02/2026 | 11/02/2026 | 12/02/2024 | 08/03/2024 | 11/03/2024 | 19/03/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
9 | 9 | Public Health Engineering Department | Jal Rekha | Anusharavan | NEW Stage changes | No | 0 | 145 | 143 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 10 | Public Health Engineering Department | Jal Rekha | Anusharavan | Report creation/ Modification | No | 0 | 273 | 236 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 11 | Public Health Engineering Department | Jal Rekha | Anusharavan | Stage Updation | No | 0 | 68 | 68 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 12 | Public Health Engineering Department | Jal Rekha | Anusharavan | Testing | No | 0 | 128 | 64 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
13 | 13 | Public Health Engineering Department | Jal Rekha | Anusharavan | Video Creation | No | 0 | 16 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 14 | Public Health Engineering Department | Jal Rekha | Anusharavan CR |  | Yes | 0 | 31 | 21 | 08/11/2025 | 20/11/2025 | 11/11/2025 | 20/11/2025 | 11/11/2025 | 12/11/2025 | 12/11/2025 | 13/11/2025 | 14/11/2025 | 17/11/2025 | 18/11/2025 | 20/11/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 15 | Public Health Engineering Department | Jal Rekha | Anusharavan CR | Addition of FE inspection details (PIU) & Customize Report | Yes | 0 | 30 | 20 | [12 empty] | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 16 | Public Health Engineering Department | Jal Rekha | Anusharavan CR | Internal Testing | Yes | 0 | 1 | 1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 17 | Public Health Engineering Department | Jal Rekha | Asset Mapping |  | No | 0 | 987 | 928 | 01/01/2024 | 26/01/2024 | 01/01/2024 | 26/01/2024 | 01/01/2024 | 02/01/2024 | 02/01/2024 | 03/01/2024 | 03/01/2024 | 19/01/2024 | 22/01/2024 | 26/01/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 18 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Bug Fixing from Frontend | No | 0 | 80 | 72 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 19 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Data Access Methods (GET/SET) creation/ updation | No | 0 | 104 | 101 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 20 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Download D&D and Survey Data | No | 0 | 24 | 24 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 21 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Field Survey Data Correction | No | 0 | 744 | 696 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 22 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Internal Testing | No | 0 | 3 | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 23 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Move OHTs | No | 0 | 24 | 24 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 24 | Public Health Engineering Department | Jal Rekha | Asset Mapping | Video Creation | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 25 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Mobile |  | Yes | 8 | 25 | 25 | 18/11/2025 | 05/12/2025 | 19/11/2025 | 05/12/2025 | 19/11/2025 | 20/11/2025 | 21/11/2025 | 23/11/2025 | 24/11/2025 | 30/11/2025 | 01/12/2025 | 05/12/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0 | 0 | 0 | 0.33 | 0
26 | 26 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Mobile | Internal Testing | Yes | 5 | 1 | 1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
27 | 27 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Mobile | QAP Document Download Functionality | Yes | 3 | 24 | 24 | [12 empty] | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
28 | 28 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Web |  | Yes | 3 | 28 | 24 | 01/11/2025 | 25/11/2025 | 03/11/2025 | 25/11/2025 | 03/11/2025 | 06/11/2025 | 06/11/2025 | 09/11/2025 | 10/11/2025 | 20/11/2025 | 21/11/2025 | 25/11/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
29 | 29 | Public Health Engineering Department | Jal Rekha | Bharosa CR Factory Testing Web | Functionality to Upload Multiple Documents on Web | Yes | 3 | 28 | 24 | [12 empty] | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
30 | 30 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web |  | No | 5 | 627 | 565.5 | 09/10/2025 | 16/10/2025 | 10/10/2025 | 16/10/2025 | 10/10/2025 | 11/10/2025 | 11/10/2025 | 12/10/2025 | 13/10/2025 | 15/10/2025 | 15/10/2025 | 16/10/2025 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0.01 | 0 | 1.25 | 0 | 0 | 0
31 | 31 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Bug Fixing- API | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 32 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Bug Fixing from Database | No | 0 | 53 | 28 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 33 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Bug Fixing from Frontend | No | 0 | 40 | 40 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 34 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Bug Fixing-Mobile App | No | 0 | 22 | 22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 35 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Data Access Methods (GET/SET) creation/ updation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 36 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Database Architecture Design & Function Creation(For Master Check) | No | 0 | 201 | 183.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 37 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Factory Testing Contractor Login Mobile Page Creation | No | 5 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 38 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Material & Cube testing Requirement Gathering | No | 0 | 8 | 4 | [12 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 39 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Mobile APP development | No | 0 | 68 | 68 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 40 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | New web page creation/ Modification | No | 0 | 113 | 101 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 41 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Production deployment | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 42 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Requirement Gathering | No | 0 | 3 | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 43 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Service or API Creation | No | 0 | 50 | 50 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 44 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | SIT Testing | No | 0 | 15 | 15 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 45 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Test Case Creation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 46 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Test Scenario Creation | No | 0 | 5 | 5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 47 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | UAT/Prod/CR Testing | No | 0 | 1 | 1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 48 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | UI update in existing page | No | 0 | 36 | 33 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 49 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Unit Testing for module | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 50 | Public Health Engineering Department | Jal Rekha | Bharosa Factory Testing - Web | Wireframe of Bharosa Factory testing | No | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 51 | Public Health Engineering Department | Jal Rekha | CMMI Documents |  | No | 8 | 884 | 796.5 | 02/12/2025 |  | 04/12/2025 |  | 04/12/2025 | 06/12/2025 | 07/12/2025 | 09/12/2025 |  |  |  |  | 113 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0.07 | 0 | 0.57 | 0
52 | 52 | Public Health Engineering Department | Jal Rekha | CMMI Documents | CMMI Documentation | No | 0 | 322 | 287.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 53 | Public Health Engineering Department | Jal Rekha | CMMI Documents | CMMI documents Creation | No | 0 | 350 | 315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 54 | Public Health Engineering Department | Jal Rekha | CMMI Documents | Data collection for July to Noember Cycle | No | 0 | 54 | 46 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 55 | Public Health Engineering Department | Jal Rekha | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | No | 3 | 16 | 6 | [12 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0
56 | 56 | Public Health Engineering Department | Jal Rekha | CMMI Documents | Induction Training Attended | No | 5 | 12 | 12 | [12 empty] | 8 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42 | 0 | 0.63 | 0 | 1.25 | 0
57 | 57 | Public Health Engineering Department | Jal Rekha | CMMI Documents | Promot activity- CMMIL5 Audit | No | 0 | 21 | 21 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 58 | Public Health Engineering Department | Jal Rekha | CMMI Documents | Streamline Documentation of O&M Billing , Bharosa module, Material | No | 0 | 109 | 109 | [12 empty] | 99 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 59 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor |  | No | 3 | 68 | 64 | 23/03/2026 | 05/04/2026 | 23/03/2026 | 04/04/2026 | 23/03/2026 | 24/03/2026 | 26/03/2026 | 28/03/2026 | 29/03/2026 | 01/04/2026 | 02/04/2026 | 04/04/2026 | 8 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0.05 | 0 | 0.38 | 0 | 0.07 | 0
60 | 60 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor | Creation of Cube Inspection by Contractor | No | 3 | 56 | 52 | [12 empty] | 8 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 0.38 | 0 | 0.07 | 0
61 | 61 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor | Internal Testing | No | 0 | 3 | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 62 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor | Prod/CR/UAT Testing (Including prod issue validation) | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 63 | Public Health Engineering Department | Jal Rekha | Cube Testing - Contractor | Test Case Creation | No | 0 | 9 | 9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 64 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE |  | No | 8 | 132 | 120 | 09/03/2026 | 10/04/2026 | 09/03/2026 | 09/04/2026 | 09/03/2026 | 12/03/2026 | 12/03/2026 | 19/03/2026 | 20/03/2026 | 30/03/2026 | 31/03/2026 | 09/04/2026 | 8 | 0 | 62 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.07 | 0 | 1 | 0 | 0.12 | 0
65 | 65 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE | Cube inspection carried out by FE | No | 3 | 82 | 70 | [12 empty] | 8 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0.38 | 0 | 0.05 | 0
66 | 66 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE | Internal Testing | No | 0 | 10 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 67 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE | Prod/CR/UAT Testing (Including prod issue validation) | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 68 | Public Health Engineering Department | Jal Rekha | Cube Testing - FE | Test Case and Test Scenario Creation | No | 5 | 32 | 32 | [12 empty] | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 0 | 0 | 1.25 | 0
69 | 69 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM |  | No | 0 | 57 | 51 | 31/03/2026 | 10/04/2026 | 31/03/2026 | 09/04/2026 | 31/03/2026 | 03/04/2026 | 03/04/2026 | 05/04/2026 | 06/04/2026 | 09/04/2026 | 08/04/2026 | 09/04/2026 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 70 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM | Bug Fixing from Frontend | No | 0 | 5 | 5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 71 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM | Internal Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 72 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM | Prod/CR/UAT Testing (Including prod issue validation) | No | 0 | 6 | 6 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 73 | Public Health Engineering Department | Jal Rekha | Cube Testing - GM | RFI request status update and see the list | No | 0 | 46 | 40 | [12 empty] | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 74 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA |  | No | 3 | 47 | 47 | 02/04/2026 | 07/04/2026 | 02/04/2026 | 07/04/2026 | 02/04/2026 | 03/04/2026 | 03/04/2026 | 04/04/2026 | 04/04/2026 | 06/04/2026 | 06/04/2026 | 07/04/2026 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.06 | 0 | 0 | 0 | 0.25 | 0
75 | 75 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA | Bug Fixing from Frontend | No | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 76 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA | Internal Testing | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 77 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA | Prod/CR/UAT Testing (Including prod issue validation) | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 78 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA | SQC TPIA Web pages & API creation | No | 3 | 12 | 12 | [12 empty] | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0
79 | 79 | Public Health Engineering Department | Jal Rekha | Cube Testing - SQC/TPIA | Test case/Test scenario creation | No | 0 | 23 | 23 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 80 | Public Health Engineering Department | Jal Rekha | Cube Testing CR |  | Yes | 6 | 70 | 70 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 2 | 0 | 56 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09 | 0 | 3 | 0 | 0.11 | 0.75
81 | 81 | Public Health Engineering Department | Jal Rekha | Cube Testing CR | Mandatory Mulitple Image Upload functionality | Yes | 3 | 50 | 50 | [12 empty] | 2 | 0 | 40 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0 | 1.5 | 0 | 0.08 | 0.38
82 | 82 | Public Health Engineering Department | Jal Rekha | Cube Testing CR | New web page creation/ Modification | Yes | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 83 | Public Health Engineering Department | Jal Rekha | Cube Testing CR | Option for manual entry for Components | Yes | 3 | 16 | 16 | [12 empty] | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0.19 | 0
84 | 84 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement |  | No | 0 | 200 | 180 | 23/12/2025 |  | 24/12/2025 |  | 24/12/2025 | 25/12/2025 | 26/12/2025 | 27/12/2025 | 28/12/2025 |  |  |  | 12 | 0 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 85 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Business Logic APIs creation/Changes | No | 0 | 15 | 15 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 86 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Cude Testing understanding and WIreframing | No | 0 | 34 | 34 | [12 empty] | 12 | 0 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 87 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Data Access Methods (GET/SET) creation/ updation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 88 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Data Validation & Integrity | No | 0 | 24 | 24 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 89 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | DB schema, Master and Design Table | No | 0 | 32 | 17 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 90 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Function/SP Development and Modification | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 91 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Internal Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 92 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | New web page creation/ Modification | No | 0 | 20 | 20 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 93 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Production deployment | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 94 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Query Optimization | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 95 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Query/SP creation/Modification | No | 0 | 32 | 28 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 96 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Report creation/ Modification | No | 0 | 8 | 7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 97 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Requirement Gathering | No | 0 | 14 | 14 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 98 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Test Case Creation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 99 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Test Plan Document | No | 0 | 5 | 5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 100 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Test Scenario Creation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 101 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | UI update in existing page | No | 0 | 16 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 102 | Public Health Engineering Department | Jal Rekha | Cube Testing Requirement | Unit Testing for module | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 103 | Public Health Engineering Department | Jal Rekha | Daily Inspection |  | No | 0 | 104 | 88 | 25/12/2023 | 16/02/2024 | 25/12/2023 | 16/02/2024 | 25/12/2023 | 05/01/2024 |  |  | 08/02/2024 | 13/02/2024 | 14/02/2024 | 16/02/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 104 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Bug Fixing- API | No | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 105 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Bug Fixing from Database | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 106 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Bug Fixing from Frontend | No | 0 | 16 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 107 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Bug Fixing Mobile APP | No | 0 | 12 | 12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 108 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Data Access Methods (GET/SET) creation/ updation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 109 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Database Architecture Design & Function Creation(For Master Check) | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 110 | Public Health Engineering Department | Jal Rekha | Daily Inspection | New web page creation/ Modification | No | 0 | 56 | 40 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 111 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Production deployment | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 112 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Requirement Gathering | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 113 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Service or API Creation | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 114 | Public Health Engineering Department | Jal Rekha | Daily Inspection | Unit Testing for module | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 115 | Public Health Engineering Department | Jal Rekha | Dashboard |  | No | 3 | 327 | 281.5 | 28/03/2024 | 08/04/2024 | 01/04/2024 | 08/04/2024 | 01/04/2024 | 01/04/2024 |  |  | 02/04/2024 | 06/04/2024 | 08/04/2024 | 08/04/2024 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0.38 | 0 | 0.19 | 0
116 | 116 | Public Health Engineering Department | Jal Rekha | Dashboard | Data Verification | No | 0 | 65 | 43.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 117 | Public Health Engineering Department | Jal Rekha | Dashboard | Modified Excel Reports in all Jal Rekha Modules | No | 3 | 24 | 24 | [12 empty] | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0.38 | 0 | 0.19 | 0
118 | 118 | Public Health Engineering Department | Jal Rekha | Dashboard | Requirement Gathering | No | 0 | 40 | 40 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 119 | Public Health Engineering Department | Jal Rekha | Dashboard | Wireframing | No | 0 | 198 | 174 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 120 | Public Health Engineering Department | Jal Rekha | Department Meetings |  | No | 13 | 78 | 72.5 | [12 empty] | 38 | 0 | 16 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0.31 | 0 | 0.81 | 0
121 | 121 | Public Health Engineering Department | Jal Rekha | Department Meetings | Addition & Updation in Nirmal, Bharosa, O&M Billing and other modules | No | 5 | 35 | 32 | [12 empty] | 12 | 0 | 16 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16 | 0 | 0.31 | 0 | 0.31 | 0
122 | 122 | Public Health Engineering Department | Jal Rekha | Department Meetings | Department meeting on All modules requirements and changes | No | 3 | 4 | 4 | [12 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 0 | 0 | 0
123 | 123 | Public Health Engineering Department | Jal Rekha | Department Meetings | Discussion on new material , cube testing modules & changes in Dhara, Nirmal, O&M billing & Bharosa Factory testing | No | 5 | 22 | 22 | [12 empty] | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23 | 0 | 0.23 | 0 | 0 | 0
124 | 124 | Public Health Engineering Department | Jal Rekha | Department Meetings | Requirement Gathering for Changes & Updations | No | 0 | 17 | 14.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 125 | Public Health Engineering Department | Jal Rekha | Dhara |  | No | 0 | 2665 | 2330 | 20/09/2024 | 16/10/2024 | 20/09/2024 | 16/10/2024 | 20/09/2024 | 22/09/2024 | 22/09/2024 | 24/09/2024 | 25/09/2024 | 11/10/2024 | 14/10/2024 | 16/10/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 6 | 0 | 0.6 | 0 | 0 | 0 | 0
126 | 126 | Public Health Engineering Department | Jal Rekha | Dhara | Knowledge trasfer sessions | No | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 127 | Public Health Engineering Department | Jal Rekha | Dhara | Billing Module | No | 0 | 40 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 128 | Public Health Engineering Department | Jal Rekha | Dhara | Bug Fixing from Database | No | 0 | 561 | 516.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 129 | Public Health Engineering Department | Jal Rekha | Dhara | Bug fixing from Dhara Report | No | 0 | 400 | 307.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 130 | Public Health Engineering Department | Jal Rekha | Dhara | Dashboard | No | 0 | 28 | 28 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 131 | Public Health Engineering Department | Jal Rekha | Dhara | Development of Mobile Application for Dhara Module | No | 0 | 224 | 212 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 132 | Public Health Engineering Department | Jal Rekha | Dhara | New web page creation/ Modification | No | 0 | 984 | 912.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 133 | Public Health Engineering Department | Jal Rekha | Dhara | SIT Testing | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 134 | Public Health Engineering Department | Jal Rekha | Dhara | Testing of Changes Done | No | 0 | 232 | 190 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 135 | Public Health Engineering Department | Jal Rekha | Dhara | UAT/Prod/CR Testing | No | 0 | 16 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0.6 | 0 | 0 | 0 | 0
136 | 136 | Public Health Engineering Department | Jal Rekha | Dhara | UI update in existing page | No | 0 | 136 | 87.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 137 | Public Health Engineering Department | Jal Rekha | Dhara | Updating Meter as per Department | No | 0 | 32 | 32 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 138 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - GM PIU User/ TL |  | Yes | 6 | 73 | 73 | 01/07/2025 | 12/08/2025 | 03/07/2025 | 12/08/2025 | 03/07/2025 | 11/07/2025 | 12/07/2025 | 18/07/2025 | 22/07/2025 | 04/08/2025 | 01/08/2025 | 12/08/2025 | 17 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0.35 | 0 | 0.11 | 0
139 | 139 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - GM PIU User/ TL | Intake Meter reading survey changes | Yes | 3 | 3 | 3 | [12 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
140 | 140 | Public Health Engineering Department | Jal Rekha | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | Yes | 3 | 70 | 70 | [12 empty] | 14 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0.21 | 0 | 0.05 | 0
141 | 141 | Public Health Engineering Department | Jal Rekha | Dhara Change Request Reports |  | Yes | 3 | 22 | 22 | 08/11/2025 | 14/11/2025 | 08/11/2025 | 13/11/2025 | 08/11/2025 | 09/11/2025 | 09/11/2025 | 10/11/2025 | 10/11/2025 | 12/11/2025 | 12/11/2025 | 13/11/2025 | 6 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 0 | 0.5 | 0 | 0.19 | 0
142 | 142 | Public Health Engineering Department | Jal Rekha | Dhara Change Request Reports | Bulk metter consumer reading survey form | Yes | 3 | 22 | 22 | [12 empty] | 6 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 0 | 0.5 | 0 | 0.19 | 0
143 | 143 | Public Health Engineering Department | Jal Rekha | Dhara CR - Reports (MWSR,DWSR, UFW) |  | Yes | 6 | 157 | 141 | 13/03/2026 | 26/03/2026 | 13/03/2026 | 24/03/2026 | 13/03/2026 | 13/03/2026 | 16/03/2026 | 19/03/2026 | 19/03/2026 | 22/03/2026 | 22/03/2026 | 24/03/2026 | 18 | 0 | 107 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0.33 | 0 | 0.05 | 0
144 | 144 | Public Health Engineering Department | Jal Rekha | Dhara CR - Reports (MWSR,DWSR, UFW) | Internal Testing | Yes | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 145 | Public Health Engineering Department | Jal Rekha | Dhara CR - Reports (MWSR,DWSR, UFW) | Requirement gathering of Report changes in Dhara reports | Yes | 3 | 34 | 26 | [12 empty] | 18 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0.17 | 0 | 0.38 | 0
146 | 146 | Public Health Engineering Department | Jal Rekha | Dhara CR - Reports (MWSR,DWSR, UFW) | Updation and recreate fetch - DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW | Yes | 3 | 115 | 107 | [12 empty] | 0 | 0 | 99 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0.03 | 0
147 | 147 | Public Health Engineering Department | Jal Rekha | Dhara GM PIU User Change request |  | Yes | 6 | 30 | 22 | 08/05/2025 | 27/05/2025 | 10/05/2025 | 27/05/2025 | 10/05/2025 | 11/05/2025 | 11/05/2025 | 13/05/2025 | 14/05/2025 | 24/05/2025 | 24/05/2025 | 27/05/2025 | 4 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 0 | 1.5 | 0 | 0.33 | 0
148 | 148 | Public Health Engineering Department | Jal Rekha | Dhara GM PIU User Change request | Dhara WTP Meter Reading Issue Resolution | Yes | 3 | 22 | 14 | [12 empty] | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0.75 | 0 | 0.3 | 0
149 | 149 | Public Health Engineering Department | Jal Rekha | Dhara GM PIU User Change request | Test Case/Scenario Creation | Yes | 3 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
150 | 150 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports |  | No | 0 | 547 | 475 | 18/08/2025 | 27/09/2025 | 18/08/2025 | 26/09/2025 | 18/08/2025 | 22/08/2025 | 23/08/2025 | 26/08/2025 | 29/08/2025 | 13/09/2025 | 19/09/2025 | 26/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0.33 | 0 | 0 | 0 | 0
151 | 151 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | Mobile Application API Integration | No | 0 | 108 | 108 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 152 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | New web page creation/ Modification | No | 0 | 238 | 230 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 153 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | Query/SP creation/Modification | No | 0 | 156 | 92 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 154 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | Requirement Gathering | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 155 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | SIT Testing | No | 0 | 13 | 13 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 156 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | Test Case Creation | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 157 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | Test Scenario Creation | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 158 | Public Health Engineering Department | Jal Rekha | FHTC (Functional Household Tap Connection) FE Reports | UAT/Prod/CR Testing | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0
159 | 159 | Public Health Engineering Department | Jal Rekha | FHTC Change request FHTC |  | Yes | 9 | 247 | 247 | 13/10/2025 | 29/10/2025 | 14/10/2025 | 29/10/2025 | 14/10/2025 | 16/10/2025 | 16/10/2025 | 18/10/2025 | 19/10/2025 | 24/10/2025 | 26/10/2025 | 29/10/2025 | 1 | 0 | 220 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0.04 | 0 | 9 | 0 | 0.04 | 0.35
160 | 160 | Public Health Engineering Department | Jal Rekha | FHTC Change request FHTC | Add Search Functionality to FE and Contractor login | Yes | 3 | 26 | 26 | [12 empty] | 0 | 0 | 24 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0.13 | 1.5
161 | 161 | Public Health Engineering Department | Jal Rekha | FHTC Change request FHTC | Customized and Summary report changes | Yes | 3 | 5 | 5 | [12 empty] | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 3 | 0 | 0.75 | 0
162 | 162 | Public Health Engineering Department | Jal Rekha | FHTC Change request FHTC | FHTC Loop functionality implementation | Yes | 3 | 216 | 216 | [12 empty] | 0 | 0 | 192 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0.02 | 0.13
163 | 163 | Public Health Engineering Department | Jal Rekha | FHTC GM / Contractor Reports |  | Yes | 3 | 8 | 8 | 02/11/2025 | 14/11/2025 | 04/11/2025 | 14/11/2025 | 04/11/2025 | 05/11/2025 | 05/11/2025 | 06/11/2025 | 06/11/2025 | 11/11/2025 | 12/11/2025 | 14/11/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
164 | 164 | Public Health Engineering Department | Jal Rekha | FHTC GM / Contractor Reports | Report Filter issues at column level | Yes | 3 | 8 | 8 | [12 empty] | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
165 | 165 | Public Health Engineering Department | Jal Rekha | Master Change Request - GM / Contractor |  | Yes | 3 | 0 | 0 | 01/07/2025 | 19/07/2025 | 01/07/2025 | 19/07/2025 | 01/07/2025 | 04/07/2025 | 05/07/2025 | 07/07/2025 | 07/07/2025 | 15/07/2025 | 15/07/2025 | 19/07/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 166 | Public Health Engineering Department | Jal Rekha | Master Change Request - GM / Contractor | Option for manual entry for Components | Yes | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 167 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema |  | Yes | 6 | 74 | 73.5 | 18/03/2026 | 25/03/2026 | 18/03/2026 | 24/03/2026 | 18/03/2026 | 19/03/2026 | 18/03/2026 | 19/03/2026 | 19/03/2026 | 19/03/2026 | 24/03/2026 | 24/03/2026 | 8 | 0 | 65.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0.75 | 0 | 0.09 | 0
168 | 168 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema | Bulk Consumer Master (Add-Update-Get) | Yes | 0 | 16 | 16 | [12 empty] | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 169 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema | Dhara Mapped Summary report - Changes in Abstract report | Yes | 0 | 32 | 32 | [12 empty] | 8 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 170 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema | Dhara Master DWSR Updations | Yes | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 171 | Public Health Engineering Department | Jal Rekha | Master Change request - Schema | In Bulk Consumer Master - add delete functionality | Yes | 3 | 26 | 25.5 | [12 empty] | 0 | 0 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0 | 0 | 0.12 | 0
172 | 172 | Public Health Engineering Department | Jal Rekha | Master CR - Scheme Village & OHT Master |  | Yes | 3 | 140 | 140 | 11/03/2026 | 19/03/2026 | 11/03/2026 | 19/03/2026 | 11/03/2026 | 12/03/2026 | 12/03/2026 | 13/03/2026 | 13/03/2026 | 16/03/2026 | 17/03/2026 | 19/03/2026 | 10 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0.3 | 0 | 0.02 | 0
173 | 173 | Public Health Engineering Department | Jal Rekha | Master CR - Scheme Village & OHT Master | Internal Testing | Yes | 3 | 3 | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
174 | 174 | Public Health Engineering Department | Jal Rekha | Master CR - Scheme Village & OHT Master | Scheme Village OHT Mapping & Report Updations | Yes | 0 | 137 | 137 | [12 empty] | 10 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 175 | Public Health Engineering Department | Jal Rekha | Master GM |  | No | 0 | 941 | 778.5 | 15/02/2025 | 08/03/2025 | 18/02/2025 | 08/03/2025 | 18/02/2025 | 20/02/2025 | 20/02/2025 | 21/02/2025 | 22/02/2025 | 05/03/2025 | 06/03/2025 | 08/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 1 | 0 | 0.33 | 0 | 0 | 0 | 0
176 | 176 | Public Health Engineering Department | Jal Rekha | Master GM | Data Access Methods (GET/SET) creation/ updation | No | 0 | 101 | 99.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 177 | Public Health Engineering Department | Jal Rekha | Master GM | New web page creation/ Modification | No | 0 | 344 | 243 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 178 | Public Health Engineering Department | Jal Rekha | Master GM | New Wireframes Suggested by Department | No | 0 | 60 | 60 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 179 | Public Health Engineering Department | Jal Rekha | Master GM | Pipeline Master | No | 0 | 416 | 360 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 180 | Public Health Engineering Department | Jal Rekha | Master GM | SIT Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 181 | Public Health Engineering Department | Jal Rekha | Master GM | UAT/Prod/CR Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0.33 | 0 | 0 | 0 | 0
182 | 182 | Public Health Engineering Department | Jal Rekha | Master GM | Wireframe of Pipeline master data | No | 0 | 20 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 183 | Public Health Engineering Department | Jal Rekha | Material Testing - FE Login |  | No | 0 | 30 | 30 | 17/12/2025 | 31/12/2025 | 19/12/2025 | 31/12/2025 | 19/12/2025 | 21/12/2025 | 21/12/2025 | 23/12/2025 | 23/12/2025 | 28/12/2025 | 28/12/2025 | 31/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 184 | Public Health Engineering Department | Jal Rekha | Material Testing - FE Login | Internal Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 185 | Public Health Engineering Department | Jal Rekha | Material Testing - FE Login | UAT/Prod/CR Testing | No | 0 | 30 | 30 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 186 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login |  | No | 13 | 584 | 471 | 08/12/2025 | 30/12/2025 | 12/12/2025 | 30/12/2025 | 12/12/2025 | 15/12/2025 | 15/12/2025 | 17/12/2025 | 17/12/2025 | 25/12/2025 | 26/12/2025 | 30/12/2025 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0.03 | 0.5 | 0.81 | 0 | 0 | 0
187 | 187 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Bug Fixing from Database | No | 0 | 32 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 188 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Bug Fixing from Frontend | No | 0 | 25 | 25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 189 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Business Logic APIs creation/Changes | No | 0 | 43 | 37 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 190 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Data Access Methods (GET/SET) creation/ updation | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 191 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Data Validation & Integrity | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 192 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | DB Schema, Master & Design Table | No | 0 | 16 | 7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 193 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Function/SP development and modification | No | 0 | 120 | 71 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 194 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Internal Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 195 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Mobile Development | No | 0 | 170 | 166 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 196 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | New web page creation/ Modification | No | 0 | 30 | 30 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 197 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Production deployment | No | 0 | 2 | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 198 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Query optimization | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 199 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Requirement Gathering | No | 0 | 24 | 17 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 200 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Requirement gathering and Analysis | No | 5 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 201 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | SQC TPIA Login | No | 3 | 8 | 8 | [12 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0.38 | 0 | 0 | 0
202 | 202 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Staging deployment | No | 0 | 5 | 5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 203 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Test Case Creation | No | 0 | 16 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 204 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Test Scenario Creation | No | 0 | 20 | 20 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 205 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | UAT/PROD/CR Testing | No | 0 | 41 | 31 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0
206 | 206 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | UI update in existing page | No | 0 | 16 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 207 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Unit Testing for module | No | 0 | 4 | 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 208 | Public Health Engineering Department | Jal Rekha | Material Testing - GM/Contractor Login | Wireframing & workflow | No | 5 | 12 | 8 | [12 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63 | 0 | 0.63 | 0 | 0 | 0
209 | 209 | Public Health Engineering Department | Jal Rekha | Nirmal Change Request - Beneficiary Report |  | Yes | 3 | 20 | 20 | 01/09/2025 | 08/09/2025 | 03/09/2025 | 08/09/2025 | 03/09/2025 | 04/09/2025 | 04/09/2025 | 05/09/2025 | 06/09/2025 | 07/09/2025 | 07/09/2025 | 08/09/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0
210 | 210 | Public Health Engineering Department | Jal Rekha | Nirmal Change Request - Beneficiary Report | Report Issue | Yes | 3 | 20 | 20 | [12 empty] | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0
211 | 211 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile |  | No | 0 | 1243 | 1058.5 | 28/02/2025 | 15/04/2025 | 28/02/2025 | 15/04/2025 | 28/02/2025 | 07/03/2025 | 07/03/2025 | 12/03/2025 | 14/03/2025 | 05/04/2025 | 06/04/2025 | 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5 | 0 | 0.5 | 0 | 0 | 0 | 0
212 | 212 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Water Sampling Collection by Contractor | No | 0 | 62 | 58 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 213 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | API creation | No | 0 | 52 | 52 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 214 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Geofencing | No | 0 | 224 | 208 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 215 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | New Module in Mobile Application | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 216 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | New web page creation/ Modification | No | 0 | 264 | 221 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 217 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Nirmal Reports | No | 0 | 341 | 274.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 218 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Requirement Gathering & Wireframe | No | 0 | 40 | 24 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 219 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | SIT Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 220 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Testing of Nirmal Module | No | 0 | 105 | 81 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 221 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | UAT/Prod/CR Testing | No | 0 | 2 | 2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0.5 | 0 | 0 | 0 | 0
222 | 222 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | UI update in existing page | No | 0 | 101 | 86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 223 | Public Health Engineering Department | Jal Rekha | Nirmal FE Mobile | Unit Testing for module | No | 0 | 52 | 52 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 224 | Public Health Engineering Department | Jal Rekha | Nirmal GM |  | No | 3 | 8 | 8 | 15/04/2025 | 21/04/2025 | 15/04/2025 | 21/04/2025 | 15/04/2025 | 15/04/2025 | 16/04/2025 | 16/04/2025 | 17/04/2025 | 19/04/2025 | 19/04/2025 | 21/04/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
225 | 225 | Public Health Engineering Department | Jal Rekha | Nirmal GM | Report Creation/Modification | No | 3 | 8 | 8 | [12 empty] | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 | 0 | 0.38 | 0
226 | 226 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change request GM |  | Yes | 6 | 51 | 50 | 02/11/2025 | 22/11/2025 | 06/11/2025 | 22/11/2025 | 06/11/2025 | 08/11/2025 | 08/11/2025 | 10/11/2025 | 13/11/2025 | 19/11/2025 | 20/11/2025 | 22/11/2025 | 8 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 0 | 0.75 | 0 | 0.14 | 0
227 | 227 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change request GM | Census Population get from Scheme Village Master | Yes | 3 | 24 | 23 | [12 empty] | 8 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0.38 | 0 | 0.2 | 0
228 | 228 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change request GM | GM HSC Change | Yes | 3 | 11 | 11 | [12 empty] | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27 | 0 | 0 | 0 | 0.27 | 0
229 | 229 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change request GM | GM Side Power Consumption and Water Supply COnstruction Phase Changes | Yes | 0 | 16 | 16 | [12 empty] | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 230 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor |  | Yes | 28 | 259 | 249 | 27/11/2025 | 02/01/2026 | 01/12/2025 | 02/01/2026 | 01/12/2025 | 04/12/2025 | 04/12/2025 | 07/12/2025 | 10/12/2025 | 24/12/2025 | 26/12/2025 | 02/01/2026 | 18 | 16 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0 | 1.56 | 1.75 | 0.13 | 0
231 | 231 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | "Generate Abstract Page(Pressure Redressal Sheet)" After Save & Submit – Contractor Side | Yes | 3 | 24 | 24 | [12 empty] | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
232 | 232 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Complaint Date column modification | Yes | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 233 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Contractor Bill generation flow and update Approved Reports | Yes | 3 | 64 | 57 | [12 empty] | 5 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0.6 | 0 | 0.06 | 0
234 | 234 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | CR in Contractor - Summary page Abstract Report | Yes | 3 | 5 | 5 | [12 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0
235 | 235 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Enable "Generate Abstract Page(Complaint Redressal Sheet )" After Save & Submit – Contractor Side | Yes | 3 | 10 | 10 | [12 empty] | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0.3 | 0
236 | 236 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Enable "Generate Abstract Page(Pressure Redressal Sheet)" After Save & Submit – Contractor Side | Yes | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 237 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Generate Summary Page – Contractor Side | Yes | 5 | 28 | 28 | [12 empty] | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0 | 0 | 0.18 | 0
238 | 238 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | O&M Billing Contractor Summary Page changes | Yes | 5 | 96 | 96 | [12 empty] | 0 | 16 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.31 | 0.06 | 0
239 | 239 | Public Health Engineering Department | Jal Rekha | O&M Billing - Change Request Contractor | Updation & Validation addition in Dhara Reports | Yes | 0 | 32 | 29 | [12 empty] | 8 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 240 | Public Health Engineering Department | Jal Rekha | O&M Billing GM |  | No | 10 | 2038 | 1789 | 28/07/2025 | 29/08/2025 | 28/07/2025 | 29/08/2025 | 28/07/2025 | 03/08/2025 | 04/08/2025 | 07/08/2025 | 07/08/2025 | 21/08/2025 | 22/08/2025 | 29/08/2025 | 30 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 4 | 0 | 0.01 | 0 | 0.33 | 0 | 0.56 | 0
241 | 241 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Bug Fixing from Database | No | 0 | 40 | 36 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 242 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Bug Fixing from Frontend | No | 0 | 11 | 11 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 243 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Data Access Methods (GET/SET) creation/ updation | No | 0 | 138 | 122 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 244 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Database Architecture Design & Function Creation(For Master Check) | No | 0 | 410 | 315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 245 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Internal Meeting with Team to implement changes from Department for O&M Billing Module | No | 5 | 8 | 8 | [12 empty] | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63 | 0 | 0.83 | 0 | 2.5 | 0
246 | 246 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | New web page creation/ Modification | No | 0 | 696 | 640 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 247 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Partial O&M Bills | No | 0 | 188 | 172 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 248 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Requirement Analysis | No | 0 | 12 | 12 | [12 empty] | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 249 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Requirement Analysis on GM Contractor Flow & Reports discussion | No | 0 | 22 | 6 | [12 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 250 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Requirement Gathering | No | 0 | 344 | 316 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 251 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Requirement Gathering & Monitoring changes | No | 5 | 28 | 22 | [12 empty] | 6 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23 | 0 | 0.83 | 0 | 0.31 | 0
252 | 252 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Service or API Creation | No | 0 | 9 | 9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 253 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | SIT Testing | No | 0 | 20 | 20 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 254 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | Test cases | No | 0 | 8 | 8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 255 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | UAT/Prod/CR Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 256 | Public Health Engineering Department | Jal Rekha | O&M Billing GM | UI update in existing page | No | 0 | 104 | 92 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 257 | Public Health Engineering Department | Jal Rekha | O&M Billing Workflow b/w O&M GM & Higher officials |  | No | 5 | 27 | 27 | 20/09/2025 | 29/09/2025 | 21/09/2025 | 29/09/2025 | 21/09/2025 | 22/09/2025 | 22/09/2025 | 23/09/2025 | 23/09/2025 | 26/09/2025 | 26/09/2025 | 29/09/2025 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0.19 | 0 | 0 | 0
258 | 258 | Public Health Engineering Department | Jal Rekha | O&M Billing Workflow b/w O&M GM & Higher officials | O&M Billing Workflow preparation & requirement gathering | No | 5 | 27 | 27 | [12 empty] | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0.19 | 0 | 0 | 0
259 | 259 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request |  | Yes | 3 | 39 | 39 | 12/05/2026 | 14/05/2026 | 12/05/2026 | 14/05/2026 | 12/05/2026 | 12/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 13/05/2026 | 14/05/2026 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0 | 0 | 0.08 | 0
260 | 260 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request | RA Bill Functionlaity on CP Manager | Yes | 3 | 39 | 39 | [12 empty] | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0 | 0 | 0.08 | 0
261 | 261 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request -GM / PM / Reports |  | Yes | 3 | 36 | 36 | 02/12/2025 | 11/12/2025 | 04/12/2025 | 11/12/2025 | 04/12/2025 | 05/12/2025 | 05/12/2025 | 06/12/2025 | 06/12/2025 | 09/12/2025 | 09/12/2025 | 11/12/2025 | 2 | 0 | 24 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 1.5 | 0 | 0.13 | 0.3
262 | 262 | Public Health Engineering Department | Jal Rekha | Sahbhagita Change Request -GM / PM / Reports | Add Save as Draft Functionality | Yes | 3 | 36 | 36 | [12 empty] | 2 | 0 | 24 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 1.5 | 0 | 0.13 | 0.3
263 | 263 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM |  | No | 0 | 115 | 83 | 19/06/2025 | 23/06/2025 | 17/06/2025 | 23/06/2025 | 17/06/2025 | 18/06/2025 | 18/06/2025 | 19/06/2025 | 19/06/2025 | 22/06/2025 | 23/06/2025 | 23/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 3 | 0 | 0.75 | 0 | 0 | 0 | 0
264 | 264 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM | Bug Fixing from Frontend | No | 0 | 19 | 11 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 265 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM | Bug Fixing from Frontend | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 266 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM | SIT Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 267 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM | UAT/Prod/CR Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0.75 | 0 | 0 | 0 | 0
268 | 268 | Public Health Engineering Department | Jal Rekha | Sahbhagita GM | Upload Activities through Web Portal | No | 0 | 96 | 72 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 269 | Public Health Engineering Department | Jal Rekha | Sahbhagita Report |  | No | 0 | 10 | 10 | 19/11/2025 | 01/12/2025 | 22/11/2025 | 01/12/2025 | 22/11/2025 | 23/11/2025 | 23/11/2025 | 24/11/2025 | 25/11/2025 | 28/11/2025 | 28/11/2025 | 01/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 270 | Public Health Engineering Department | Jal Rekha | Sahbhagita Report | New web page creation/ Modification | No | 0 | 10 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 271 | Public Health Engineering Department | Jal Rekha | Site Security Audit |  | No | 3 | 16 | 16 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 28/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 28/04/2026 | 29/04/2026 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0.19 | 0
272 | 272 | Public Health Engineering Department | Jal Rekha | Site Security Audit | Jal rekha Site Fortify Security Audit | No | 3 | 16 | 16 | [12 empty] | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0.19 | 0
273 | 273 | Public Health Engineering Department | Jal Rekha | Sopan Contractor |  | No | 0 | 1612 | 1387.5 | 25/03/2025 | 30/04/2025 | 28/03/2025 | 30/04/2025 | 28/03/2025 | 31/03/2025 | 01/04/2025 | 04/04/2025 | 05/04/2025 | 22/04/2025 | 23/04/2025 | 30/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 2 | 0 | 0.67 | 0 | 0 | 0 | 0
274 | 274 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Bug Fixing from Database | No | 0 | 96 | 88 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 275 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Correct OHT Data | No | 0 | 154 | 146 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 276 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Dashboard | No | 0 | 36 | 16 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 277 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Dashboard Creation | No | 0 | 40 | 40 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 278 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Data Access Methods (GET/SET) creation/ updation | No | 0 | 304 | 266.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 279 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | New web page creation/ Modification | No | 0 | 732 | 603 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 280 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Requirement Gathering | No | 0 | 96 | 80 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 281 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | SIT Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 282 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Testing of New Functionality added in Sopan | No | 0 | 80 | 80 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 283 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | UAT/Prod/CR Testing | No | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0.67 | 0 | 0 | 0 | 0
284 | 284 | Public Health Engineering Department | Jal Rekha | Sopan Contractor | Upload Activities Through Web Portal | No | 0 | 74 | 68 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 285 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring |  | No | 22 | 70 | 69 | 12/05/2026 | 21/05/2026 | 12/05/2026 | 20/05/2026 | 12/05/2026 | 12/05/2026 | 13/05/2026 | 14/05/2026 | 14/05/2026 | 17/05/2026 | 18/05/2026 | 20/05/2026 | 27 | 0 | 40 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0 | 0.81 | 0 | 0.55 | 11
286 | 286 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Database functionality to add specific fields into the required tables | No | 1 | 8 | 8 | [12 empty] | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
287 | 287 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Development of Web pages and Database functions | No | 3 | 24 | 24 | [12 empty] | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0
288 | 288 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Internal meeting to finalize API from NIC Panchayat Darpan & Village Master data | No | 3 | 18 | 17 | [12 empty] | 9 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0.33 | 0 | 0.38 | 0
289 | 289 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Internal Testing | No | 3 | 2 | 2 | [12 empty] | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 1.5
290 | 290 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Project Module Initiation Meeting and Requirement gathering | No | 3 | 12 | 12 | [12 empty] | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0 | 0 | 0
291 | 291 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | SVS Daily Water Supply Wireframe | No | 3 | 6 | 6 | [12 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0
292 | 292 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Test Case/Scenario Creation | No | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 293 | Public Health Engineering Department | Jal Rekha | SVS Water Supply Monitoring | Test Plan Document | No | 3 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 294 | Public Health Engineering Department | Jal Rekha | User & Role Management |  | No | 0 | 10 | 10 | 20/11/2024 | 26/12/2024 | 21/11/2024 | 26/12/2024 | 21/11/2024 | 25/11/2024 | 27/11/2024 | 30/11/2024 | 02/12/2024 | 20/12/2024 | 23/12/2024 | 26/12/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 295 | Public Health Engineering Department | Jal Rekha | User & Role Management | Functional/SIT Testing | No | 0 | 10 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0