## Version
Version | Date | Description | Prepared by | Reviewed by
1 | 2025-07-01 | Initial CR Draft | Mr. Ankur | Mr. Tapan K

## Dhara
Dhara CHANGE REQUEST LOG
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-DH-01 | DH-CR-ADM-01 | Dhara Business User / GM PIU | BA / TL | 2025-10-05 | Report format change and drill-down functionality, additional reading-entry options to GM after TL & FE, and Intake/WTP/OHT range functionality for mobile development. | Dhara | Change request (GM / PIU User & Reports) | Functional / Usability | Enhances accuracy of meter-reading approvals and provides better analytical drill-down for GM decisions; medium effort, no architectural change. | Implemented | 27-05-2025 | Approved | High | Medium
CR-DH-02 | DH-CR-TL-01 | Dhara TL | BA / TL | 2025-06-04 | Change in reading-entry options so that all edit options available to TL also after FE submission. | Dhara | Change request (TL flow) | Process / Usability | Streamlines correction workflow, reduces back-and-forth with FE; small change but affects daily operations. | Implemented | 2025-12-04 | Approved | Medium | Low

## Master
Master CHANGE REQUEST LOG
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-MST-01 | MST-CR-MOB-01 | Master Module – Product Owner / TL | BA / TL | 18/04/2025 | Modify the existing master‑data schema and implement Anusharvan mobile app changes inside Master (schema update plus corresponding app adjustments). | Master | Change request | Technical / Data Model | Schema change in Master and Anusharvan mobile will improve flexibility for future pipeline and OHT data but needs careful migration and testing to avoid data inconsistency. | Implemented | 25/04/2025 | Approved | Medium | Medium
CR-MST-02 | MST-CR-GOV-01 | PHED HQ / Data Governance Cell | Enterprise Architect / BA | 2025-05-07 | Introduce central master‑data governance for Scheme–PIU–Village hierarchy with audit trail (created/modified by, effective‑from/to) and maker–checker approval for critical master changes. | Master | GM & Contractor Masters | Governance / Compliance | Strengthens control over master changes, improves traceability for audits, but increases complexity of update workflows and requires changes in integration jobs consuming master data. | Under Analysis | 2025-05-12 | Approved | High | High

## Nirmal
Nirmal CHANGE REQUEST LOG
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-NM-01 | NM-CR-REP-01 | Nirmal Product Owner / PM | BA / TL | 13/05/2025 | Report parameter changes, mobile app functionality changes for OHT/Intake/WTP, and Nirmal & Dhara contractor functionality and user‑management enhancements. | Nirmal | Change request | Functional / Usability | Improves correctness and usability of sampling reports and contractor workflows across Nirmal and Dhara; moderate change touching web reports and mobile flows but no core architecture impact. | Implemented | 26/05/2025 | Approved | High | Medium
CR-NM-02 | NM-CR-QA-01 | QA / District Lab Team | BA / QA | 20/06/2025 | Introduce additional validation rules on sample collection (minimum mandatory parameters, duplicate‑sample checks) and enhance Nirmal contractor screens to highlight overdue lab tests. | Nirmal | Contractor Login & Reports | Quality / Data Accuracy | Expected to reduce invalid or duplicate water‑quality samples and improve timeliness of lab result entry; minimal architectural impact, moderate UI and rule‑engine changes. | Implemented | 28/06/2025 | Approved | High | Medium