## Version
Version | Date | Description | Prepared by | Reviewed by
1.2 | 2025-09-01 | Initial CR Draft | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal
1.2.1 | 2025-09-30 | CR | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal

## FHTC
CHANGE REQUEST LOG
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
1 | CR-FHTC-001 | FE | FHTC Sector Admin | 2025-10-05 | FHTC Tap Connection Status Capture – FE to visit each household, capture tap connection status, update and upload with beneficiary & tap photos, and send accepted/rejected connections to GM/Contractor. | FHTC | Tap Connection Module | Data Entry | New FE tap‑connection workflow and data capture on mobile. | Completed | 30-05-2025 | Approved | High | Low
2 | CR-FHTC-002 | FE | FHTC Sector Admin | 2025-10-05 | Beneficiary Photo Mandatory Validation – enforce mandatory beneficiary photo in FHTC forms before submission. | FHTC | Photo Module | Validation Engine | Strengthens photo validation rules in FHTC capture screens. | Completed | 30-05-2025 | Approved | High | Low
3 | CR-FHTC-003 | FE | GM Admin / FHTC Admin | 18-08-2025 | FHTC FE / Reports – FE login with API integration, village household visit, tap‑check update with photos, rejected/accepted connection routing to GM and contractor, NIC API whitelisting & integration, HSC report with beneficiary photo, rejected tap connections sent back to contractor. | Jal Rekha | FHTC – FE / Reports | Mobile App + Integration + Reports | Introduces full FE reporting flow and NIC integration for FHTC including HSC report generation. | Completed | 26-09-2025 | Approved | High | Medium
4 | CR-FHTC-004 | FE / Contractor | GM Admin / FHTC Admin | 14-10-2025 | Change request FHTC – replace NIC services with Samagra API, update APK to use Samagra, update HSC report entries, and enable contractor to update beneficiary tap connection with photograph to GM. | Jal Rekha | FHTC – Change request FHTC | Integration + Reports | Migrates integration to Samagra APIs and aligns HSC reporting and contractor workflow. | Completed | 29-10-2025 | Approved | High | Medium

## O&M Billing
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
1 | CR-OMB-001 | GM | O&M PM / GM Admin | 28-07-2025 | GM O&M Billing – GM login and basic details, SLBM and scheme status fields, financial calculation for billing, document upload with data fetched from Dhara and Nirmal, scheme‑wise contractor assignment, bill generation, multi‑level review (PIU GM/SQC → O&M GM → PMC → Deputy Manager). | Jal Rekha | O&M Billing – GM | Workflow Engine + Calculation Engine | New GM‑side O&M billing workflow, SLBM‑based billing parameters and integration with Dhara/Nirmal data. | Completed | 29-08-2025 | Approved | High | Medium
2 | CR-OMB-002 | Contractor | O&M PM / GM Admin | 2025-01-09 | Contractor O&M Billing – contractor basic and advance details, CPI‑based financial calculations, PIU/SQC pages, manpower and residual pressure details, bulk user mapping, gross bill deduction and net payable, O&M billing for RM and village with management norms, Dhara water‑supply data import. | Jal Rekha | O&M Billing – Contractor | Data Entry + Calculation Logic | Introduces contractor‑side billing forms and CPI‑driven bill computation, including bulk user and Dhara‑based inputs. | Completed | 19-09-2025 | Approved | High | Medium
3 | CR-OMB-003 | GM | O&M PM / GM Admin | 21-09-2025 | Workflow between O&M GM and higher officials – establish approval flow between GM, Contractor, CGM, PD, CFO, CA and MD; retrieve RA bill data and prepare test data in om_ra_bill; RA bill logic based on scheme and contractor with month progression; edit and resend options back to PIU GM and Contractor. | Jal Rekha | O&M Billing – Workflow b/w O&M GM & Higher Officials | Workflow Engine | Defines RA bill approval hierarchy and RA bill month logic, ensuring traceable review and re‑submission mechanism. | Completed | 29-09-2025 | Approved | High | Medium
4 | CR-OMB-004 | GM | O&M PM / GM Admin | 29-09-2025 | Change request O&M Billing – Save as Draft for GM, census population hierarchy correction and ability to open population; SLBM section enhancements with “Other” option in norms and penalty; penalty label changes; CPIW increment and yearly calculation updates; scheme status view document/eligibility increment/year‑month updates; GST service option; document upload Yes/No with freeze. | Jal Rekha | O&M Billing – Change request O&M Billing | UI/UX + Calculation + Data Validation | Enhances existing O&M billing screens with draft capability, refined CPI/GST calculations and stricter scheme‑status/document controls. | Completed | 31-10-2025 | Approved | High | Medium
5 | CR-OMB-011 | GM | O&M PM / GM Admin | 25-07-2025 | O&M Master Data Locking – option for GM to freeze scheme‑wise O&M master data (SLBM norms, census figures, start/end date) before first RA bill generation, with change‑request trail for any later modifications. | Jal Rekha | O&M Billing – Master Locking | Data Integrity & Governance | Prevents ad‑hoc master changes that impact historical RA/Final bills and ensures audit‑ready configuration control. | Planned | TBD | Pending | High | Medium
6 | CR-OMB-012 | Contractor | O&M PM | 2025-10-08 | Contractor Self‑Service Statement – screen for contractors to view scheme‑wise outstanding RA bills, paid bills, deductions, and GST summary, with month and scheme filters. | Jal Rekha | O&M Billing – Contractor Statement | BI / MIS Reporting | Improves transparency for contractors and reduces manual queries to GM and finance section. | Planned | TBD | Pending | Medium | Medium
7 | CR-OMB-013 | PIU GM | O&M PM / Finance Team | 2025-05-09 | Advance Adjustment Register – functionality to capture O&M advances released to contractors and auto‑adjust them across subsequent RA bills with clear narration and balance tracking. | Jal Rekha | O&M Billing – Advance Management | Calculation Engine | Ensures systematic advance recovery and clear visibility of advance balances at scheme and contractor level. | Planned | TBD | Pending | High | High
8 | CR-OMB-014 | Auditor / PMC | O&M PM | 22-09-2025 | Penalty Justification Notes – provision to record detailed justification, documents, and references for each SLBM penalty imposed in the bill and include them in an annexure for audit. | Jal Rekha | O&M Billing – Penalty Documentation | Compliance & File Management | Strengthens defensibility of penalties during audits and dispute resolution. | Planned | TBD | Pending | Medium | Medium
9 | CR-OMB-015 | Finance (CFO) | O&M PM / Finance Team | 2025-06-10 | TDS & GST Reconciliation Utility – automated comparison of billed amounts with TDS and GST ledgers, showing differences by contractor and scheme, with exportable reconciliation report. | Jal Rekha | O&M Billing – Tax Reconciliation | Reports Module + Calculation | Reduces manual reconciliation effort and helps ensure statutory tax compliance. | Planned | TBD | Pending | High | High
10 | CR-OMB-016 | MD Office | O&M PM | 20-10-2025 | Exception Monitoring Report – dashboard highlighting exceptional cases such as repeated zero‑billing months, frequent penalties, unusually high deductions or GST values per scheme. | Jal Rekha | O&M Billing – Exception Dashboard | BI / MIS Reporting | Enables top management to quickly identify outliers and initiate corrective action in O&M operations. | Planned | TBD | Pending | High | Medium
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
41 | CR-OMB-001 | GM Admin | O&M Billing PM | 29-09-2025 | Draft Saving Functionality – Enable GM to save billing entries as draft at any point during data entry, with ability to retrieve and continue editing at a later stage without submission. | Jal Rekha | O&M Billing – GM Module | Workflow Engine | Improves user experience by allowing incomplete entries to be saved temporarily and prevents data loss during entry. | Planned | TBD | Pending | High | Medium
42 | CR-OMB-002 | PIU Admin | O&M Billing PM | 29-09-2025 | Census Population Location Hierarchy Correction – Rectify and restructure census population hierarchy data model; provide expanded visibility and open-access view for authorized users across all hierarchy levels. | Jal Rekha | O&M Billing – GM Module | Data Model & Hierarchy | Ensures accurate population-based calculations and enables better scheme-wise analysis and compliance reporting. | Planned | TBD | Pending | High | High
43 | CR-OMB-003 | QA/Testing | O&M Billing PM | 2025-02-10 | SLBM Section Field Enhancement – Add "Other" option to Quality, Quantity, Pressure, UFW, and Complaint fields in SLBM (Scheme Level Billing Management) section; update both Norms and Penalty dropdowns to include this new category. | Jal Rekha | O&M Billing – SLBM Module | UI Enhancement & Data Validation | Increases flexibility in billing criteria entry and accommodates non-standard or exceptional scenarios during billing cycle. | Planned | TBD | Pending | Medium | Medium
44 | CR-OMB-004 | GM | O&M Billing PM | 2025-04-10 | Penalty Label & Control Enhancement – Modify penalty label naming and convert from text field to radio button controls for standardized selection; ensure consistent penalty classification across billing entries. | Jal Rekha | O&M Billing – SLBM Module | UI/UX | Improves data consistency and ensures uniform penalty application across all billing records. | Planned | TBD | Pending | Medium | Low
45 | CR-OMB-005 | Finance Team | O&M Billing PM | 2025-06-10 | Increment Calculation Logic Update – Modify CPIW (Consumer Price Index Weighted) increment calculation and yearly increment computation logic; ensure compliance with revised financial policies and CPI indices. | Jal Rekha | O&M Billing – Contractor Module | Calculation Engine | Ensures accurate financial calculations per updated government norms and reduces billing disputes and reconciliation issues. | Planned | TBD | Pending | High | Medium
46 | CR-OMB-006 | GM PIU | O&M Billing PM | 2025-08-10 | Scheme Status Module Enhancement – Implement view documents functionality, eligibility increment tracking, and year-month update capability for O&M start and end dates; link with scheme reference data. | Jal Rekha | O&M Billing – Scheme Status Module | Workflow & Data Entry | Provides comprehensive scheme lifecycle tracking and improves billing period accuracy and scheme management visibility. | Planned | TBD | Pending | High | High
47 | CR-OMB-007 | Billing Officer | O&M Billing PM | 2025-09-10 | GST Services Integration – Unlock and open GST services option for O&M module; configure GST calculation, tax slabs, and exemption rules per government notification; enable GST inclusion in final bill amounts. | Jal Rekha | O&M Billing – Contractor Module | Business Logic & Integration | Ensures tax-compliant billing and incorporates latest GST regulations into billing computation. | Planned | TBD | Pending | High | Medium
48 | CR-OMB-008 | GM Admin | O&M Billing PM | 15-10-2025 | Document Upload Freeze Control – Implement Yes/No document upload option; when "Yes" is selected and documents are uploaded, freeze (lock) the screen to prevent accidental modifications to uploaded documentation; enable unlock via authorized personnel only. | Jal Rekha | O&M Billing – Document Management Module | Validation & Authorization | Enhances data integrity and prevents unauthorized changes to finalized billing documentation post-upload. | Planned | TBD | Pending | Medium | Low

## Dhara CR
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
1 | CR-DHRW-001 | PIU GM / TL | Dhara Rework BA Team | 2025-03-07 | Habitation and Component Mapping Revamp – enhance habitation mapping for each OHT (OHT-wise and individual) with VC training, extend CWGM/CWPM (WTP) functionality for inside/outside scheme villages, and open all villages/habitations for OHT mapping; includes CMMI documentation. | Jal Rekha | Dhara Rework – GM PIU User / TL | Workflow & Master Data | Provides accurate habitation-to-asset mapping and supports correct meter reading approval across Intake, OHT, WTP, and Bulk User components. | Completed | 2025-12-08 | Approved | High | Medium
50 | CR-DHRW-002 | GM PIU | Dhara Rework BA Team | 2025-11-07 | Month-wise Meter Reading Approval – implement month-wise open/close records for approving/filling meter readings for Intake, OHT, WTP, and Bulk User components; enable web modification of Intake/WTP/OHT/Village meter readings and update meter survey including new WTP meters. | Jal Rekha | Dhara Rework – GM PIU User / TL | Workflow Engine & Data Entry | Ensures consistent monthly billing data, improves control over meter reading approvals, and enhances data accuracy for Dhara consumption reports. | Completed | 2025-04-08 | Approved | High | High
51 | CR-DHRW-003 | GM PIU | Dhara Rework BA Team | 22-07-2025 | Meter Survey and WTP Meter Addition – streamline update of meter survey for Intake/WTP/OHT/Village, add new WTP meters in the system, and align with revised field survey; includes necessary web form changes. | Jal Rekha | Dhara Rework – GM PIU User / TL | Data Model & UI | Improves coverage of metered locations and supports better validation of water supply and UFW analysis. | Completed | 2025-12-08 | Approved | Medium | Medium
52 | CR-DHRW-004 | FE / Mobile User | Dhara Rework BA Team | 13-08-2025 | FE Habitation-wise Mapping – assign habitation-wise mapping capability to FE mobile users for Dhara components (Intake, OHT, WTP, Village). | Jal Rekha | Dhara Rework – FE / Mobile User | Mobile Workflow | Enables FE users to capture and correct habitation mappings on-site, reducing dependency on back-office GM users. | Completed | 28-08-2025 | Approved | High | Medium
53 | CR-DHRW-005 | FE / Mobile User | Dhara Rework BA Team | 16-08-2025 | Meter Status Parameter Update – modify meter status parameters on mobile: Meter functional, Meter not functional, Meter replace, No water supply; set appropriate default values to avoid wrong selections. | Jal Rekha | Dhara Rework – FE / Mobile User | Validation & UX | Reduces incorrect meter status entries and improves quality of field data for Dhara analytics. | Completed | 24-08-2025 | Approved | Medium | Low
54 | CR-DHRW-006 | FE / Mobile User | Dhara Rework BA Team | 18-08-2025 | WTP Meter Assignment Optimization – assign WTP meters where entries are repeated for OHT mapping so that correct component is selected during FE entry. | Jal Rekha | Dhara Rework – FE / Mobile User | Data Integrity | Eliminates duplicate/incorrect WTP-OHT mappings and improves correctness of component-wise readings. | Completed | 28-08-2025 | Approved | Medium | Medium
55 | CR-DHRW-007 | Admin / Contractor | Dhara Rework BA Team | 2025-01-09 | Water Supply Report Layout Changes – update DWSR, MWSR, Scheme-wise, Village-wise, Bulk user and UFW reports to reflect new mapping and meter logic; publish Dhara report on Jal Rekha public home page. | Jal Rekha | Dhara Rework – Admin / Contractor Report View | Reports & UI/UX | Aligns all Dhara reports with revised data structure and provides transparency on public portal. | Completed | 25-09-2025 | Approved | High | Medium
56 | CR-DHRW-008 | Admin / Contractor | Dhara Rework BA Team | 2025-03-09 | Drill-down and Mapping Correction – enable drill-down for all Dhara water supply reports (DWSR, MWSR, Scheme, Village, Bulk User, UFW) and correct underlying mapping data to ensure consistency between summary and detail levels. | Jal Rekha | Dhara Rework – Admin / Contractor Report View | Backend API & Reporting | Improves traceability of reported figures to component-level data, supporting audit and performance review. | Completed | 25-09-2025 | Approved | High | High
57 | CR-DHRW-009 | Admin / Contractor | Dhara Rework BA Team | 2025-09-09 | CMMI-aligned Reporting Enhancements – finalize CMMI documentation, stabilize report filters, and standardize export formats for Dhara water-supply reports. | Jal Rekha | Dhara Rework – Admin / Contractor Report View | Process Compliance | Ensures process documentation and reporting are compliant with CMMI requirements and internal QA guidelines. | Completed | 25-09-2025 | Approved | Medium | Low

## Master CR
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
58 | CR-MST-006A | GM / Contractor | Master BA Team | 2025-01-07 | Cross-Scheme Village–Component Mapping – enable mapping of a village and its components with water supply through other PIU schemes. | Jal Rekha | Master – GM / Contractor | Master Data | Allows reuse of schemes across villages and improves correctness of supply source mapping. | Completed | 19-07-2025 | Approved | High | Medium
59 | CR-MST-006B | GM / Contractor | Master BA Team | 2025-01-07 | Pipeline Zone Number at Contractor Level – add pipeline master zone numbers configurable by contractor for better segmentation. | Jal Rekha | Master – GM / Contractor | Data Model | Supports zone-wise monitoring and billing calculations. | Completed | 19-07-2025 | Approved | Medium | Medium
60 | CR-MST-006C | GM / Contractor | Master BA Team | 2025-04-07 | Contractor Edit Before Final Submission – provide edit functionality to contractors on master screens prior to final submit/lock. | Jal Rekha | Master – GM / Contractor | Workflow | Reduces rework requests to PIU and improves data accuracy before lock. | Completed | 19-07-2025 | Approved | High | Low
61 | CR-MST-006D | GM / Contractor | Master BA Team | 2025-05-07 | Bulk Meter–Village Mapping Update – revise bulk meter mapping logic to correctly associate bulk meters with served villages. | Jal Rekha | Master – GM / Contractor | Data Quality | Ensures correct consumption and UFW computation for bulk consumers. | Completed | 19-07-2025 | Approved | High | Medium
62 | CR-MST-006E | GM / Contractor | Master BA Team | 2025-07-07 | Habitation-Based Mapping for Scheme Villages and OHT – enable mapping through habitation for scheme villages to respective OHTs. | Jal Rekha | Master – GM / Contractor | Master Data | Provides finer granularity for supply planning and reporting. | Completed | 19-07-2025 | Approved | High | Medium
63 | CR-MST-006F | GM / Contractor | Master BA Team | 2025-07-07 | Outside-Scheme Village Mapping – allow mapping of outside-scheme villages to appropriate components where water is supplied. | Jal Rekha | Master – GM / Contractor | Master Data & Policy | Captures actual coverage and supports exception reporting for non-scheme villages. | Completed | 19-07-2025 | Approved | Medium | Medium
64 | CR-MST-006G | GM / Contractor | Master BA Team | 2025-11-07 | WTP Meter Mapping for 147 Schemes – add and map WTP meters for all 147 schemes in master. | Jal Rekha | Master – GM / Contractor | Asset Master | Improves tracking of production and losses at WTP level. | Completed | 19-07-2025 | Approved | High | Medium
65 | CR-MST-006H | GM / Contractor | Master BA Team | 15-07-2025 | CMMI Documentation for Master Changes – prepare/update CMMI-compliant documents for new Master mappings and workflows. | Jal Rekha | Master – GM / Contractor | Process Compliance | Aligns Master module changes with organizational quality standards. | Completed | 19-07-2025 | Approved | Medium | Low
66 | CR-MST-007A | FE / PIU | Master BA Team | 2025-05-08 | Pipeline Master–RFI Integration – integrate pipeline master data with RFI module at all required stages (planning, execution, closure). | Jal Rekha | Master – FE Pipeline Master | Integration | Ensures that RFI processing always uses latest pipeline master data. | Completed | 13-08-2025 | Approved | Medium | Medium
67 | CR-MST-007B | FE / PIU | Master BA Team | 2025-06-08 | Habitation Mapping at PIU Level – provide facility to map habitations and resolve data issues from PIU interface. | Jal Rekha | Master – FE Pipeline Master | Data Quality | Speeds up correction of field data issues without code changes. | Completed | 13-08-2025 | Approved | Medium | Low

## Sahbhagita C
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
68 | CR-SHB-002A | GM | Sahbhagita Admin / PM | 15-10-2025 | GM Sahbhagita Report View Enhancement – modify GM login report view to support village-wise triggers and updated filters for Sahbhagita activities. | Jal Rekha | Sahbhagita – GM Reports | Reports & UI/UX | Gives GM granular visibility at village level, helping to monitor scheme-wise participation and trigger follow-up actions. | Completed | 29-10-2025 | Approved | Medium | Medium
69 | CR-SHB-002B | PM | Sahbhagita Admin / PM | 16-10-2025 | PM Video Upload in Sahbhagita Activity – provide PM role the option to upload and manage activity-related videos within Sahbhagita module. | Jal Rekha | Sahbhagita – PM Activity Management | Document & Media Management | Enables richer evidence capture for activities, improving transparency and audit readiness. | Completed | 22-10-2025 | Approved | Medium | Low

## Nirmal CR
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
70 | CR-NRM-007A | GM | Nirmal Admin | 2025-09-07 | WTP Report Parameter Changes – modify existing WTP report parameters (columns, filters, and summary metrics) as per revised monitoring format. | Jal Rekha | Nirmal – WTP, OHT Report | Reports & UI/UX | Provides clearer visibility of WTP performance and aligns reporting with updated departmental format. | Completed | 14-07-2025 | Approved | Medium | Low
71 | CR-NRM-007B | Contractor / FE | Nirmal Admin | 2025-10-07 | Intake/WTP Buffer Distance Enhancement – update Contractor/FE login logic so that WTP and Intake buffer distance for raw water sample collection is increased to 200 meters. | Jal Rekha | Nirmal – WTP, OHT Report | Calculation & Business Rules | Ensures correct validation of sampling locations and compliance with new buffer-distance norms. | Completed | 14-07-2025 | Approved | High | Medium
72 | CR-NRM-008A | GM | Nirmal Admin | 2025-03-09 | Beneficiary Report – Date Range Filter – provide “From Date / To Date” range filter to restrict beneficiary report results to a specific period. | Jal Rekha | Nirmal – Beneficiary Report | Reporting & Filter Logic | Speeds up report generation and analysis for defined review periods (monthly, quarterly, etc.). | Completed | 2025-08-09 | Approved | Medium | Low
73 | CR-NRM-008B | GM | Nirmal Admin | 2025-04-09 | Beneficiary Report – Water Sample ID Search – add direct search option using Water Sample ID to instantly locate related beneficiary and test details. | Jal Rekha | Nirmal – Beneficiary Report | Search & Traceability | Improves traceability of lab results and supports quick resolution of field queries and complaints. | Completed | 2025-08-09 | Approved | Medium | Low
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
74 | CR-NRM-007A1 | GM | Nirmal Admin | 2025-09-07 | WTP Report – Column Definition Update (add/rename parameters as per new WTP monitoring template). | Jal Rekha | Nirmal – WTP, OHT Report | Report Layout | Aligns WTP report structure with revised departmental format. | Completed | 14-07-2025 | Approved | Medium | Low
75 | CR-NRM-007A2 | GM | Nirmal Admin | 2025-09-07 | WTP Report – Filter Criteria Revision (scheme, source, and date filters to match updated business rules). | Jal Rekha | Nirmal – WTP, OHT Report | Filter Logic | Improves precision of report extraction for specific schemes and periods. | Completed | 14-07-2025 | Approved | Medium | Low
76 | CR-NRM-007A3 | GM | Nirmal Admin | 2025-10-07 | WTP Report – Summary KPI Recalculation (update formulas for key performance indicators such as count, pass/fail, and UFW-related metrics). | Jal Rekha | Nirmal – WTP, OHT Report | Calculation Engine | Ensures KPIs reflect the new sampling and evaluation methodology. | Completed | 14-07-2025 | Approved | High | Medium
77 | CR-NRM-007B1 | Contractor / FE | Nirmal Admin | 2025-10-07 | Intake Sampling Buffer Logic – increase allowed buffer radius for raw water sampling around Intake to 200 meters in Contractor/FE login. | Jal Rekha | Nirmal – WTP, OHT Report | Validation Rules | Prevents rejection of valid Intake sampling points within new permissible distance. | Completed | 14-07-2025 | Approved | High | Medium
78 | CR-NRM-007B2 | Contractor / FE | Nirmal Admin | 2025-10-07 | WTP Sampling Buffer Logic – increase allowed buffer radius for raw water sampling around WTP to 200 meters in Contractor/FE login. | Jal Rekha | Nirmal – WTP, OHT Report | Validation Rules | Standardizes WTP sampling rules with Intake and supports field practicality. | Completed | 14-07-2025 | Approved | High | Medium
79 | CR-NRM-008A1 | GM | Nirmal Admin | 2025-03-09 | Beneficiary Report – From Date Field addition with validation against data availability. | Jal Rekha | Nirmal – Beneficiary Report | UI & Validation | Allows users to restrict report start date, avoiding unnecessary large result sets. | Completed | 2025-08-09 | Approved | Medium | Low
80 | CR-NRM-008A2 | GM | Nirmal Admin | 2025-03-09 | Beneficiary Report – To Date Field addition with range check ensuring To Date ≥ From Date. | Jal Rekha | Nirmal – Beneficiary Report | UI & Validation | Prevents invalid date ranges and improves user experience. | Completed | 2025-08-09 | Approved | Medium | Low
81 | CR-NRM-008B1 | GM | Nirmal Admin | 2025-04-09 | Beneficiary Report – Water Sample ID Search Box on UI (with exact-match search). | Jal Rekha | Nirmal – Beneficiary Report | Search UI | Enables quick entry of Water Sample ID for direct lookup. | Completed | 2025-08-09 | Approved | Medium | Low
82 | CR-NRM-008B2 | GM | Nirmal Admin | 2025-04-09 | Beneficiary Report – Backend Search Logic to fetch record(s) by Water Sample ID and display associated beneficiary and test details. | Jal Rekha | Nirmal – Beneficiary Report | Backend Logic | Improves traceability of lab results from ID to beneficiary record. | Completed | 2025-08-09 | Approved | Medium | Low

## Sopan CR
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
83 | CR-SOP-011 | Sopan Contractor | Sopan Admin | 2025-01-07 | Conventional vs Precast OHT Planning – provide separate configuration for Conventional and Precast OHT work plans with start/end dates at each stage. | Jal Rekha | Sopan – Contractor (Web/Mobile) | Workflow Engine | Enables accurate tracking of timelines and status for both Conventional and Precast OHT structures. | Completed | 2025-04-08 | Approved | High | Medium
84 | CR-SOP-012 | Sopan Contractor | Sopan Admin | 2025-05-07 | OHT Entry Correction – add delete option to remove wrong Conventional entries and allow fresh entry under Precast OHT. | Jal Rekha | Sopan – Contractor (Web/Mobile) | Data Correction | Reduces erroneous records and avoids confusion between Conventional and Precast OHT data. | Completed | 2025-04-08 | Approved | Medium | Low
85 | CR-SOP-013 | Sopan Contractor | Sopan Admin | 2025-06-07 | WTP and IPS Form Changes – update WTP and IPS forms at each stage as per revised information requirements. | Jal Rekha | Sopan – Contractor (Web/Mobile) | UI & Data Model | Ensures all required technical and progress details are captured uniformly. | Completed | 26-07-2025 | Approved | High | Medium
86 | CR-SOP-014 | Sopan Contractor | Sopan Admin | 2025-11-07 | RFI Visibility Control – modify mobile APK so that OHTs completed in Sopan are not shown for RFI requests in Anusharavan contractor login. | Jal Rekha | Sopan – Contractor (Web/Mobile) | Integration & Validation | Prevents duplicate RFIs and ensures only pending OHTs appear for inspection requests. | Completed | 26-07-2025 | Approved | High | Medium
87 | CR-SOP-015 | Sopan Contractor | Sopan Admin | 2025-12-07 | Sopan IPS Component Update – revise IPS components and stage lists used in Sopan for better alignment with field requirements. | Jal Rekha | Sopan – Contractor (Web/Mobile) | Master Data | Improves accuracy of IPS progress tracking and reporting. | Completed | 26-07-2025 | Approved | Medium | Low
88 | CR-SOP-016 | GM | Sopan Admin | 2025-12-08 | GM Edit & Freeze for Actual Dates – allow GM to edit wrong contractor-filled actual dates and freeze each stage after correction. | Jal Rekha | Sopan – GM Document Upload & Reports | Workflow & Authorization | Ensures final dates are accurate while preventing further unauthorized modification. | Completed | 2025-07-09 | Approved | High | Medium
89 | CR-SOP-017 | GM | Sopan Admin | 13-08-2025 | OHT-wise Drill-down – provide drill-down reports showing plan vs actual dates for each OHT (Mapping, Monitoring & Report). | Jal Rekha | Sopan – GM Document Upload & Reports | Reporting | Helps management identify delays and bottlenecks at individual OHT level. | Completed | 2025-07-09 | Approved | High | Medium
90 | CR-SOP-018 | GM | Sopan Admin | 20-08-2025 | WTP-wise Drill-down – enable drill-down for plan vs actual dates for each WTP in Sopan reports. | Jal Rekha | Sopan – GM Document Upload & Reports | Reporting | Provides detailed visibility into WTP construction progress and delays. | Completed | 2025-07-09 | Approved | Medium | Medium
91 | CR-SOP-019 | GM | Sopan Admin | 29-08-2025 | Intake-wise Drill-down – enable drill-down for plan vs actual dates for each Intake structure in reports. | Jal Rekha | Sopan – GM Document Upload & Reports | Reporting | Completes end-to-end visibility on Intake component progress. | Completed | 2025-07-09 | Approved | Medium | Medium
92 | CR-SOP-020 | GM | Sopan Admin | 2025-03-09 | Panchanama & Design Upload Reporting – prepare report with total Panchanama count and uploaded design data for each asset. | Jal Rekha | Sopan – GM Document Upload & Reports | Document Reporting | Supports audit and verification of design documentation coverage. | Completed | 2025-07-09 | Approved | Medium | Low
93 | CR-SOP-021 | GM | Sopan Admin | 2025-03-09 | Panchanama vs Drawing File Handling – separate Panchanama and design drawing into distinct PDF uploads with appropriate UI changes. | Jal Rekha | Sopan – GM Document Upload & Reports | Document Management | Improves clarity and retrieval of legal (Panchanama) vs technical (design) documents. | Completed | 2025-07-09 | Approved | Medium | Low
94 | CR-SOP-022 | GM | Sopan Admin | 2025-03-09 | CMMI Documentation for Sopan Reporting – create/update CMMI-compliant documents for new GM document upload and drill-down report functionalities. | Jal Rekha | Sopan – GM Document Upload & Reports | Process Compliance | Aligns Sopan enhancements with organization’s quality and audit standards. | Completed | 2025-07-09 | Approved | Medium | Low

## Overall
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
1 | CR-FHTC-001 | FE | GM Admin / FHTC Admin | 18-08-2025 | FE login, village household visit, tap connection capture with photos, NIC API whitelisting & integration, HSC report generation and rejected tap routing to contractor/GM. | Jal Rekha | FHTC – FE / Reports | Data Entry + Integration | New FE mobile workflow and NIC API integration for FHTC. | Completed | 26-09-2025 | Approved | High | Medium
2 | CR-FHTC-002 | FE / Contractor | GM Admin / FHTC Admin | 14-10-2025 | Change request FHTC – migrate from NIC to Samagra APIs, APK update, new HSC report entries, contractor updates tap connection with photograph to GM. | Jal Rekha | FHTC – Change request FHTC | Integration + Reports | API migration to Samagra and HSC report change impact on FE and contractor workflows. | Completed | 29-10-2025 | Approved | High | Medium
3 | CR-OMB-001 | GM | O&M PM / GM Admin | 28-07-2025 | O&M GM billing screens – login and basic details, SLBM features, scheme status & financial calculation, document upload from Dhara/Nirmal, contractor assignment, bill generation, multi‑level review till PMC. | Jal Rekha | O&M Billing – GM | Workflow Engine + Calculation | New GM O&M billing workflow and calculation logic across Dhara/Nirmal integrations. | Completed | 29-08-2025 | Approved | High | Medium
4 | CR-OMB-002 | Contractor | O&M PM / GM Admin | 2025-01-09 | O&M contractor pages – basic and advance details, CPI‑based financial calculations, PIU/SQC pages, manpower & residual pressure, bulk user mapping, gross/net payable, Dhara water supply import. | Jal Rekha | O&M Billing – Contractor | Data Entry + Calculation | New contractor billing forms and CPI‑based billing engine. | Completed | 19-09-2025 | Approved | High | Medium
5 | CR-OMB-003 | GM | O&M PM / GM Admin | 21-09-2025 | Workflow between GM and higher officials – RA bill data retrieval, RA bill month logic, approval sequence GM–CGM–PD–CFO–CA–MD, edit/resend options. | Jal Rekha | O&M Billing – Workflow b/w O&M GM & Higher Officials | Workflow Engine | Re‑definition of RA bill approval workflow and RA bill generation logic. | Completed | 29-09-2025 | Approved | High | Medium
6 | CR-OMB-004 | GM | O&M PM / GM Admin | 29-09-2025 | Change request O&M Billing – Save as Draft, census population hierarchy correction, SLBM norms/penalty “Other” option, CPIW increment changes, scheme status enhancements, GST option, freeze on document upload. | Jal Rekha | O&M Billing – Change request O&M Billing | UI/UX + Calculation + Validation | Enhancements to O&M billing forms, CPI logic, and scheme status handling. | Completed | 31-10-2025 | Approved | High | Medium
7 | CR-BHR-001 | GM | Bharosa Admin | 2025-10-10 | Bharosa Factory Testing Web – assign components to roles, view test sample reports, add vendors, create API/service for inspector details. | Jal Rekha | Bharosa – Factory Testing Web | Backend API + UI | New factory testing web workflow and APIs. | Completed | 16-10-2025 | Approved | High | Medium
8 | CR-BHR-002 | GM / Contractor | Bharosa Admin | 22-10-2025 | Factory Testing Mobile – inspector entries, fetch assigned components, capture test details, upload docs/images/videos, support more inspectors. | Jal Rekha | Bharosa – Factory Testing Mobile | Mobile App | New Bharosa mobile data‑entry and media capture. | Completed | 30-10-2025 | Approved | High | Medium
9 | CR-DHR-REW-001 | GM PIU / TL | Dhara Admin | 2025-03-07 | Dhara Rework – GM PIU User/TL: enhanced habitation mapping per OHT, FE assignment, CWGM/CWPM mapping for inside/outside villages, month‑wise open/close meter reading (Intake/OHT/WTP/Bulk), meter survey updates, WTP meter additions, open all villages/habitations for OHT mapping, CMMI docs. | Jal Rekha | Dhara Rework – GM PIU User / TL | Workflow Engine + Component Data | Major rework of Dhara habitation/meter workflows and mappings. | Completed | 2025-12-08 | Approved | High | High
10 | CR-DHR-REW-002 | FE Mobile | Dhara Admin | 13-08-2025 | Dhara Rework – FE/Mobile: habitation mapping assignment, meter parameter updates (functional/not functional/replace/no water supply), WTP meter entries for OHT mapping. | Jal Rekha | Dhara Rework – FE / Mobile User | Mobile App | FE meter‑entry changes and habitation mapping on mobile. | Completed | 28-08-2025 | Approved | High | Medium
11 | CR-DHR-REW-003 | GM / Contractor | Dhara Admin | 2025-01-09 | Dhara Rework – Admin/Contractor Report View: updated water supply reports (DWSR, MWSR, scheme, village, bulk user, UFW), drill‑down, corrected mappings, bulk user report changes, Dhara report on portal home, CMMI docs. | Jal Rekha | Dhara Rework – Admin / Contractor Report View | Reports Module | Report redesign with drill‑down and mapping corrections. | Completed | 25-09-2025 | Approved | High | Medium
12 | CR-MST-CR-001 | GM / Contractor | Master Admin | 2025-01-07 | Master – GM/Contractor CR: village and component mapping for other schemes of PIU, pipeline zone numbers at contractor level, contractor edit before final submission, bulk meter village mapping, habitation‑based village–OHT mapping including outside villages, WTP meter mapping for all 147 schemes, CMMI docs. | Jal Rekha | Master – Change Request GM / Contractor | Component Master | Master data changes for cross‑scheme mappings and WTP meters. | Completed | 19-07-2025 | Approved | High | Medium
13 | CR-MST-CR-002 | FE | Master Admin | 2025-05-08 | Master – FE Pipeline Master: pipeline master data integration with RFI at stages and habitation mapping/data issue resolution at PIU level. | Jal Rekha | Master – Change Request FE Pipeline Master | Data Model + Integration | Pipeline master enhancements and RFI integration. | Completed | 13-08-2025 | Approved | Medium | Medium
14 | CR-NRM-CR-001 | GM | Nirmal Admin | 2025-09-07 | Nirmal – Change request WTP/OHT Report: WTP report parameter changes and raw‑water sampling buffer increased to 200m for contractor/FE logins. | Jal Rekha | Nirmal – WTP, OHT Report | Reports Module + GPS/Location | WTP parameter change and geofenced raw‑water sampling. | Completed | 14-07-2025 | Approved | High | Medium
15 | CR-NRM-CR-002 | GM | Nirmal Admin | 2025-03-09 | Nirmal – Beneficiary Report CR: date range filter, Water Sample ID search in beneficiary report. | Jal Rekha | Nirmal – Beneficiary Report | Reports Module | Search and filter enhancements for beneficiary tests. | Completed | 2025-08-09 | Approved | Medium | Low
16 | CR-SAH-001 | GM | Sahbhagita Admin | 2025-08-09 | Sahbhagita Reports – report modification shown: updated participation report layout, filters and columns. | Jal Rekha | Sahbhagita – Sahbhagita Reports | Reports Module | Community participation report redesign. | Completed | 16-09-2025 | Approved | Medium | Low
17 | CR-SAH-002 | GM / PM | Sahbhagita Admin | 15-10-2025 | Sahbhagita CR GM/PM: GM village‑wise report view triggers, PM video upload option in Sahbhagita activities. | Jal Rekha | Sahbhagita – Change Request GM / PM | Reports + Mobile App | Village‑wise approval trigger and video evidence capture. | Completed | 22-10-2025 | Approved | High | Medium
18 | CR-SOPN-CR-001 | Contractor | Sopan Admin | 2025-01-07 | Sopan Contractor (Web/Mobile) CR: conventional vs precast options for OHT stages, delete wrong entries, WTP/IPS form changes, mobile APK update so completed OHT not shown in RFI, IPS component updates. | Jal Rekha | Sopan – Contractor Web/Mobile | Workflow Engine + Mobile App | Sopan contractor planning and mobile behavior change. | Completed | 2025-04-08 | Approved | High | Medium
19 | CR-SOPN-CR-002 | GM | Sopan Admin | 2025-12-08 | Sopan GM Document Upload & Reports: GM edit & freeze actual dates, OHT/WTP/Intake drill‑down plan vs actual, Panchanama and design data reports, separate design/Panchanama PDF upload, CMMI docs. | Jal Rekha | Sopan – GM Document Upload & Reports | Reports Module + File Management | Enhanced Sopan progress reports and GM control on dates and documents. | Completed | 2025-07-09 | Approved | High | Medium

## Sheet1
CHANGE REQUEST LOG
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Imapct Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
1 | CR-DHR-001 | PIU GM | GM Admin | 2025-08-05 | Report Format Change - DWSR Layout Redesign | Dhara | Reports Module | UI/UX |  | Completed | 30-05-2025 | Approved | High | Low
2 | CR-DHR-002 | PIU GM | GM Admin | 2025-08-05 | Drill-down Functionality Implementation | Dhara | Reports Module | Backend API |  | Completed | 30-05-2025 | Approved | High | Medium
3 | CR-DHR-003 | PIU GM | GM Admin | 2025-08-05 | Change Reading Entry Workflow - GM Permissions | Dhara | Data Entry Module | Workflow Engine |  | Completed | 30-05-2025 | Approved | High | Low
4 | CR-DHR-004 | PIU GM | GM Admin | 2025-08-05 | GM Override Option for TL Entries | Dhara | Data Entry Module | Authorization |  | Completed | 30-05-2025 | Approved | Medium | Medium
5 | CR-DHR-005 | PIU GM | GM Admin | 2025-08-05 | Intake WTP OHT Range Calculation Mobile | Dhara | Mobile Module | Calculation Engine |  | Completed | 30-05-2025 | Approved | High | High
6 | CR-DHR-006 | PIU GM | GM Admin | 2025-08-05 | OHT Range Functionality Enhancement | Dhara | Mobile Module | GPS/Location |  | Completed | 30-05-2025 | Approved | Medium | Medium
7 | CR-DHR-007 | PIU GM | GM Admin | 2025-08-05 | WTP Range Calculation Logic Update | Dhara | Mobile Module | Data Validation |  | Completed | 30-05-2025 | Approved | Medium | Low
8 | CR-MST-001 | FE Mobile | Contractor | 25-04-2025 | Master Schema Modification - Field Additions | Master | Component Master | Data Model |  | In Progress | TBD | Pending | Medium | Medium
9 | CR-MST-002 | Contractor | Master Admin | 2025-11-03 | Anusharan Module Schema Update | Master | Pipeline Master | Schema Change |  | Completed | 28-05-2025 | Approved | High | Medium
10 | CR-MST-003 | FE Mobile | Contractor | 30-04-2025 | APK Update for Master Module | Master | Mobile Module | Mobile App |  | Completed | 28-05-2025 | Approved | High | High
11 | CR-MST-004 | FE Mobile | Contractor | 30-04-2025 | API Integration for Component Upload | Master | Component Master | Backend API |  | Completed | 28-05-2025 | Approved | High | Medium
12 | CR-MST-005 | Contractor | Master Admin | 2025-11-03 | OHT Component Addition in Anusharan | Master | Anusharan Module | UI Enhancement |  | Completed | 28-05-2025 | Approved | Medium | Low
13 | CR-NRM-001 | GM | Nirmal Admin | 30-05-2025 | Report Parameter Changes - UFW Calculation | Nirmal | Reports Module | Calculation Engine |  | Completed | 30-05-2025 | Approved | High | Medium
14 | CR-NRM-002 | GM | Nirmal Admin | 30-05-2025 | Mobile App OHT Functionality Enhancement | Nirmal | Mobile Module | Calculation Logic |  | Completed | 30-05-2025 | Approved | Medium | Low
15 | CR-NRM-003 | GM | Nirmal Admin | 30-05-2025 | Intake Functionality Mobile Update | Nirmal | Mobile Module | Component Data |  | Completed | 30-05-2025 | Approved | Medium | Low
16 | CR-NRM-004 | GM | Nirmal Admin | 30-05-2025 | WTP Functionality Mobile Update | Nirmal | Mobile Module | Component Data |  | Completed | 30-05-2025 | Approved | Medium | Low
17 | CR-NRM-005 | GM | Nirmal Admin | 30-05-2025 | User Management Integration with Dhara | Nirmal + Dhara | User Module | Cross-Module Integration |  | Completed | 30-05-2025 | Approved | High | High
18 | CR-NRM-006 | GM | Nirmal Admin | 30-05-2025 | Contractor Functionality Sync with Dhara | Nirmal + Dhara | Contractor Module | Cross-Module Integration |  | Completed | 30-05-2025 | Approved | High | Medium
19 | CR-SOPN-001 | Sopan GM | Sopan Admin | 15-04-2025 | OHT Work Plan Stage Definition | Sopan | Work Plan Module | Workflow Engine |  | Completed | 30-05-2025 | Approved | High | Medium
20 | CR-SOPN-002 | Sopan GM | Sopan Admin | 15-04-2025 | Intake Work Plan Stage Definition | Sopan | Work Plan Module | Workflow Engine |  | Completed | 30-05-2025 | Approved | High | Medium
21 | CR-SOPN-003 | Sopan GM | Sopan Admin | 15-04-2025 | WTP Work Plan Stage Definition | Sopan | Work Plan Module | Workflow Engine |  | Completed | 30-05-2025 | Approved | High | Medium
22 | CR-SOPN-004 | Sopan GM | Sopan Admin | 15-04-2025 | IPS Work Plan Stage Definition | Sopan | Work Plan Module | Workflow Engine |  | Completed | 30-05-2025 | Approved | High | Medium
23 | CR-SOPN-005 | Sopan GM | Sopan Admin | 25-04-2025 | OHT Actual Date Management Freeze Logic | Sopan | Actual Date Module | Date Validation |  | Completed | 30-05-2025 | Approved | Medium | Low
24 | CR-SOPN-006 | Sopan GM | Sopan Admin | 25-04-2025 | WTP Actual Date Management Variance Calculation | Sopan | Actual Date Module | Calculation Logic |  | Completed | 30-05-2025 | Approved | Medium | Medium
25 | CR-SOPN-007 | Sopan GM | Sopan Admin | 25-04-2025 | Intake Actual Date Stage-wise Tracking | Sopan | Actual Date Module | Status Management |  | Completed | 30-05-2025 | Approved | Medium | Low
26 | CR-SOPN-008 | Sopan GM | Sopan Admin | 25-04-2025 | IPS Actual Date Completion Percentage Logic | Sopan | Actual Date Module | Calculation Logic |  | Completed | 30-05-2025 | Approved | Medium | Medium
27 | CR-SOPN-009 | Sopan Contractor | Sopan Admin | 20-04-2025 | Document Upload Functionality | Sopan | Document Module | File Management |  | Completed | 30-05-2025 | Approved | High | Low
28 | CR-SOPN-010 | Sopan Contractor | Sopan Admin | 20-04-2025 | Chat Integration with Contractor | Sopan | Chat Module | Realtime Communication |  | Completed | 30-05-2025 | Approved | High | Medium
29 | CR-FHTC-001 | FE | FHTC Sector Admin | 2025-10-05 | FHTC Tap Connection Status Capture | FHTC | Tap Connection Module | Data Entry |  | Completed | 30-05-2025 | Approved | High | Low
30 | CR-FHTC-002 | FE | FHTC Sector Admin | 2025-10-05 | Beneficiary Photo Mandatory Validation | FHTC | Photo Module | Validation Engine |  | Completed | 30-05-2025 | Approved | High | Low