## Version
Version | Date | Description | Prepared by | Reviewed by
1.3 | 2025-12-28 | Initial CR Draft | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal

## Anusharavan CR
CHANGE REQUEST LOG - CHANGE REQUEST ANUSHARAVAAN MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-ANU-001 | RFI-UPDT-2025-001 | Business Analyst | Senior BA | 08-11-2025 | Redesign new inner pages of Jal Rekha RFI module with improved navigation | Jal Rekha | Anusharavaan | UI/UX Redesign | High - Affects user experience and navigation efficiency across all users | In Progress | 20-11-2025 | Approved | High | Low
CR-ANU-002 | RFI-UPDT-2025-002 | Technical Lead | Technical Architect | 11-11-2025 | Update MBR (Meter Break-up Report) changes for multiple schemes | Jal Rekha | Anusharavaan | Report Generation | Medium - Impacts billing and financial reporting accuracy for 12 schemes | Completed | 15-11-2025 | Approved | High | Low
CR-ANU-003 | RFI-UPDT-2025-003 | QA Team | QA Lead | 12-11-2025 | Update Inline Query to Function & Query Type Changes for performance optimization | Jal Rekha | Anusharavaan | Database Performance | High - Improves query performance by 40-50% across all reports | In Progress | 25-11-2025 | Approved | High | Medium
CR-ANU-004 | RFI-UPDT-2025-004 | System Administrator | Sr. System Admin | 15-11-2025 | Implement Work on RFI Report - Pending, In Progress status tracking and approval workflow | Jal Rekha | Anusharavaan | Workflow Management | High - Critical for workflow governance and audit compliance | Planned | 02-12-2025 | Pending | Medium | Medium
CR-ANU-005 | RFI-UPDT-2025-005 | Business Analyst | Senior BA | 18-11-2025 | Database-level analysis and design for activity approval workflow implementation | Jal Rekha | Anusharavaan | Database Architecture | High - Foundation for approval mechanism and process control | Planned | 05-12-2025 | Pending | Medium | Medium
CR-ANU-006 | RFI-UPDT-2025-006 | Project Manager | Program Manager | 21-11-2025 | Implement Anusharavan Report Modifications with enhanced reporting features | Jal Rekha | Anusharavaan | Reporting & Analytics | Medium - Enhances reporting capabilities and data visualization | In Progress | 22-11-2025 | Approved | Medium | Low
IMPACT AREA BREAKDOWN
Impact Area | Count | Percentage
UI/UX Redesign | 1 | 16.67%
Report Generation | 1 | 16.67%
Database Performance | 1 | 16.67%
Workflow Management | 1 | 16.67%
Database Architecture | 1 | 16.67%
Reporting & Analytics | 1 | 16.67%
PRIORITY BREAKDOWN
Priority Level | Count | Percentage
High | 3 | 50%
Medium | 3 | 50%
APPROVAL STATUS BREAKDOWN
Status | Count | Percentage
Approved | 4 | 66.67%
Pending | 2 | 33.33%
IMPLEMENTATION STATUS BREAKDOWN
Status | Count | Percentage
In Progress | 3 | 50%
Completed | 1 | 16.67%
Planned | 2 | 33.33%
IMPLEMENTATION TIMELINE - ANUSHARAVAAN MODULE
CR No. | CR Code | Logging Date | Target Implementation Date
CR-ANU-001 | RFI-UPDT-2025-001 | 08-11-2025 | 20-11-2025
CR-ANU-002 | RFI-UPDT-2025-002 | 11-11-2025 | 15-11-2025
CR-ANU-003 | RFI-UPDT-2025-003 | 12-11-2025 | 25-11-2025
CR-ANU-004 | RFI-UPDT-2025-004 | 15-11-2025 | 02-12-2025
CR-ANU-005 | RFI-UPDT-2025-005 | 18-11-2025 | 05-12-2025
CR-ANU-006 | RFI-UPDT-2025-006 | 21-11-2025 | 22-11-2025
CMMI LEVEL 5 COMPLIANCE CHECKLIST
Control Point | Status | Evidence | Comments
Change Request Formalization | Compliant | CR Registry with unique IDs | All CRs have CR codes and logging dates
Impact Assessment | Compliant | Detailed impact analysis for each CR | Impact areas and scope clearly defined
Approval Workflow | Compliant | Approval status tracked for each CR | 4 approved, 2 pending - formal workflow
Implementation Tracking | Compliant | Implementation dates and status | All CRs have target dates and status
Risk Management | Compliant | Risk levels assigned to each CR | Low/Medium risk levels documented
Configuration Management | Compliant | CR database maintained | Comprehensive CR registry established

## Bharosa CR
CHANGE REQUEST LOG - CHANGE REQUEST Bharosa MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
Bharosa – Factory Testing Web
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-BHR-FTW-001 | BHR-FTW-2025-001 | Business Analyst | Senior BA | 2025-03-11 | Redesign inner pages of Jal Rekha for Bharosa Factory Testing to improve navigation, consistency, and readability. | Jal Rekha | Bharosa – Factory Testing Web | UI/UX Redesign | High – Directly affects usability for all factory testing web users, reducing navigation errors and training effort. | Completed | 20-11-2025 | Approved | High | Medium
CR-BHR-FTW-002 | BHR-FTW-2025-002 | Business Analyst | Senior BA | 2025-04-11 | Create dedicated web pages for Bharosa Factory Testing survey/inspection with complete header, scheme, component, and inspection detail sections. | Jal Rekha | Bharosa – Factory Testing Web | Functional Enhancement | High – Enables structured capture of survey/inspection data required for audit and MIS. | Completed | 22-11-2025 | Approved | High | Medium
CR-BHR-FTW-003 | BHR-FTW-2025-003 | Business Analyst | Senior BA | 2025-05-11 | Extend factory testing detail section to capture component, sub‑component, ordered quantity, inspected quantity, failed quantity, remarks, and upload of documents and images. | Jal Rekha | Bharosa – Factory Testing Web | Data Model Enhancement | High – Improves traceability of inspection outcomes against purchase orders and QA norms. | Completed | 25-11-2025 | Approved | High | Medium
CR-BHR-FTW-004 | BHR-FTW-2025-004 | Business Analyst | Senior BA | 2025-06-11 | Add “New” option in all subcomponents and items, with mapping to master data for Bharosa Factory Testing. | Jal Rekha | Bharosa – Factory Testing Web | Master Data Management | Medium – Allows onboarding of new items without code change, reduces turnaround time. | Completed | 23-11-2025 | Approved | Medium | Medium
CR-BHR-FTW-005 | BHR-FTW-2025-005 | QA Lead | Senior BA | 2025-07-11 | Create detailed test scenarios and test cases for Bharosa Factory Testing web flows (create, edit, approve, view). | Jal Rekha | Bharosa – Factory Testing Web | Quality Assurance | Medium – Ensures coverage of critical paths and regression areas for each release. | Completed | 24-11-2025 | Approved | Medium | Low
CR-BHR-FTW-006 | BHR-FTW-2025-006 | Technical Lead | Senior BA | 2025-08-11 | Create new database tables and functions for Bharosa Factory Testing to persist inspection details and link to procurement masters. | Jal Rekha | Bharosa – Factory Testing Web | Database Design | High – Forms base schema for reporting and downstream integrations. | Completed | 25-11-2025 | Approved | High | Medium
CR-BHR-FTW-007 | BHR-FTW-2025-007 | Technical Lead | Senior BA | 2025-09-11 | Fix database‑level defects and correct mapping of new master data records used in Bharosa Factory Testing pages. | Jal Rekha | Bharosa – Factory Testing Web | Defect Fixing | Medium – Stabilizes production data and prevents inconsistent inspection records. | Completed | 25-11-2025 | Approved | Medium | Low
Bharosa – Factory Testing Mobile
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-BHR-FTM-001 | BHR-FTM-2025-001 | Business Analyst | Senior BA | 19-11-2025 | Design Bharosa factory testing mobile screens aligned with web fields and Jal Rekha design guidelines. | Jal Rekha | Bharosa – Factory Testing Mobile | Mobile UI/UX | High – Impacts FE adoption and reduces input errors in the field. | Completed | 28-11-2025 | Approved | High | Medium
CR-BHR-FTM-002 | BHR-FTM-2025-002 | Business Analyst | Senior BA | 20-11-2025 | Implement “Draft Activity” feature in mobile app to allow FE to save partially filled inspections offline/online. | Jal Rekha | Bharosa – Factory Testing Mobile | Workflow Enhancement | High – Reduces data loss in low‑network areas and improves completion rates. | Completed | 30-11-2025 | Approved | High | Medium
CR-BHR-FTM-003 | BHR-FTM-2025-003 | Business Analyst | Senior BA | 21-11-2025 | Provide scheme selection and mapping in factory testing mobile module with validations against assigned schemes. | Jal Rekha | Bharosa – Factory Testing Mobile | Functional Enhancement | Medium – Ensures inspections are tagged to correct schemes and PIUs. | Completed | 2025-01-12 | Approved | Medium | Medium
CR-BHR-FTM-004 | BHR-FTM-2025-004 | Technical Lead | Senior BA | 22-11-2025 | Integrate factory testing APIs (insert, update, fetch) with mobile application and handle error responses. | Jal Rekha | Bharosa – Factory Testing Mobile | API Integration | High – Critical for syncing field data to central server and MIS. | Completed | 2025-03-12 | Approved | High | Medium
CR-BHR-FTM-005 | BHR-FTM-2025-005 | Technical Lead | Senior BA | 23-11-2025 | Deploy Bharosa Factory Testing mobile module and services to production environment with configuration changes. | Jal Rekha | Bharosa – Factory Testing Mobile | Deployment | Medium – Enables live usage by FE teams across districts. | Completed | 2025-05-12 | Approved | Medium | Medium
CR-BHR-FTM-006 | BHR-FTM-2025-006 | Technical Lead | Senior BA | 24-11-2025 | Integrate history API in production to show previous inspections for a component/scheme in mobile app. | Jal Rekha | Bharosa – Factory Testing Mobile | Reporting on Mobile | Medium – Helps FE avoid duplicate inspections and check historical failures. | Completed | 2025-05-12 | Approved | Medium | Low
CR-BHR-FTM-007 | BHR-FTM-2025-007 | QA Lead | Senior BA | 25-11-2025 | Resolve Bharosa FE login issues and finalize new mobile insert API design for secure authentication and data posting. | Jal Rekha | Bharosa – Factory Testing Mobile | Security & Access | High – Prevents login failures and ensures secure submission of inspection data. | Completed | 2025-05-12 | Approved | High | Medium
CR-BHR-FTM-008 | BHR-FTM-2025-008 | Technical Lead | Senior BA | 26-11-2025 | Implement Bharosa mobile Insert and Get APIs for factory testing with validation, error logging, and performance tuning. | Jal Rekha | Bharosa – Factory Testing Mobile | Backend Services | High – Core service layer for mobile‑to‑server communication of test records. | Completed | 2025-05-12 | Approved | High | Medium
Bharosa – Factory Testing Reports (CR – Report View)
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-BHR-RPT-001 | BHR-RPT-2025-001 | Business Analyst | Senior BA | 2025-10-12 | Modify Bharosa Factory Testing mobile report layout and filters as per department change request. | Jal Rekha | Bharosa – Factory Testing Reports | Reporting – Mobile | Medium – Improves readability and accuracy of mobile‑side summaries for supervisors. | Completed | 13-12-2025 | Approved | Medium | Low
CR-BHR-RPT-002 | BHR-RPT-2025-002 | Business Analyst | Senior BA | 2025-11-12 | Modify Bharosa Factory Testing web report (detailed and summary) including new columns and status filters. | Jal Rekha | Bharosa – Factory Testing Reports | Reporting – Web | Medium – Gives GM/PIU better visibility into inspection coverage and failures. | Completed | 14-12-2025 | Approved | Medium | Low
CR-BHR-RPT-003 | BHR-RPT-2025-003 | Technical Lead | Senior BA | 2025-11-12 | Conduct discussion and implement function changes to support assignment of components to TPIA in reports and backend. | Jal Rekha | Bharosa – Factory Testing Reports | TPIA Monitoring | Medium – Enables third‑party inspection agencies to track assigned components and status. | Completed | 14-12-2025 | Approved | Medium | Low
CR-BHR-RPT-004 | BHR-RPT-2025-004 | Technical Lead | Senior BA | 2025-12-12 | Update existing database functions used by Bharosa Factory Testing reports to support new filters, statuses, and performance tuning. | Jal Rekha | Bharosa – Factory Testing Reports | Database Functions | Medium – Ensures report data remains accurate and performant after CR changes. | Completed | 14-12-2025 | Approved | Medium | Low

## O& M Billing CR
CHANGE REQUEST LOG - CHANGE REQUEST O&M Billing MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-OMB-GM-001 | OMB-GM-2025-001 | Business Analyst | Senior BA | 2025-06-11 | Show GM 24 PIUs data to Kapil admin user after save and submit with proper access control in O&M Billing. | Jal Rekha | O&M Billing – GM | Access & Visibility | Medium – Provides Kapil admin consolidated visibility of GM 24 PIUs billing data post submission. | Completed | 22-11-2025 | Approved | Medium | Medium
CR-OMB-GM-002 | OMB-GM-2025-002 | Business Analyst | Senior BA | 2025-06-11 | Rename Kapil ID label and role to “GM PIU O&M” across O&M Billing screens and reports. | Jal Rekha | O&M Billing – GM | Labeling & Role Clarity | Low – Avoids confusion by aligning user role naming with actual function in O&M Billing. | Completed | 22-11-2025 | Approved | Low | Low
CR-OMB-GM-003 | OMB-GM-2025-003 | Business Analyst | Senior BA | 2025-06-11 | Prevent multiple mappings for the same village in GM O&M Billing workflow. | Jal Rekha | O&M Billing – GM | Data Integrity – Mapping | High – Prevents duplicate village mappings leading to billing inconsistencies. | Completed | 22-11-2025 | Approved | High | Medium
CR-OMB-GM-004 | OMB-GM-2025-004 | Business Analyst | Senior BA | 2025-08-11 | Correct GM PIU and contractor name binding and display in GM O&M Billing forms. | Jal Rekha | O&M Billing – GM | Data Accuracy – Master Binding | High – Ensures correct identification of GM PIU and contractor in all GM billing records. | Completed | 22-11-2025 | Approved | High | Medium
CR-OMB-GM-005 | OMB-GM-2025-005 | Business Analyst | Senior BA | 2025-08-11 | Correct Agreement value column label and data source mapping in GM O&M Billing. | Jal Rekha | O&M Billing – GM | Data Accuracy – Financials | High – Avoids financial mis‑reporting due to incorrect agreement value label or source. | Completed | 22-11-2025 | Approved | High | Medium
CR-OMB-GM-006 | OMB-GM-2025-006 | Business Analyst | Senior BA | 13-11-2025 | Ensure Additional Facilities and similar fields do not change after logout and re‑login (state persistence). | Jal Rekha | O&M Billing – GM | Session & State Management | Medium – Prevents unintended data changes after re‑login, improving data reliability. | Completed | 22-11-2025 | Approved | Medium | Low
CR-OMB-GM-007 | OMB-GM-2025-007 | Business Analyst | Senior BA | 19-11-2025 | When scheme name is changed, clear old scheme data and refresh to avoid showing previously filled values. | Jal Rekha | O&M Billing – GM | Workflow Consistency | Medium – Removes stale scheme data when switching schemes, reducing user errors. | Completed | 22-11-2025 | Approved | Medium | Low
CR-OMB-CTR-001 | OMB-CTR-2025-001 | Business Analyst | Senior BA | 2025-01-12 | Implement contractor billing workflow screens and validations in O&M module. | Jal Rekha | O&M Billing – Contractor | Functional Workflow – Contractor | High – Enables complete contractor billing flow inside O&M module. | Completed | 2026-02-01 | Approved | High | Medium
CR-OMB-CTR-002 | OMB-CTR-2025-002 | Business Analyst | Senior BA | 2025-01-12 | Calculate CPI base year and month instantly for contractor billing as per defined formula. | Jal Rekha | O&M Billing – Contractor | Financial Calculation – CPI | High – Ensures CPI is calculated correctly and instantly for billing computations. | Completed | 2026-02-01 | Approved | High | Medium
CR-OMB-CTR-003 | OMB-CTR-2025-003 | Business Analyst | Senior BA | 2025-01-12 | Move Remark field to the end in specified contractor billing reports. | Jal Rekha | O&M Billing – Contractor | Reporting Layout | Low – Improves readability and standardization of contractor reports. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-004 | OMB-CTR-2025-004 | Business Analyst | Senior BA | 2025-04-12 | Rename “No of HSC” column to “Additional affected HSCs” in relevant reports. | Jal Rekha | O&M Billing – Contractor | Reporting Layout | Low – Clarifies metric meaning in reports for stakeholders. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-005 | OMB-CTR-2025-005 | Business Analyst | Senior BA | 2025-04-12 | Update Complaint resolved field to show correct status text (“Resolved”). | Jal Rekha | O&M Billing – Contractor | Field Label & Status | Low – Provides correct complaint closure terminology for audit and users. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-006 | OMB-CTR-2025-006 | Business Analyst | Senior BA | 2025-04-12 | Correct Type of Complaint text to “Demand that cannot be fulfilled as per the agreement”. | Jal Rekha | O&M Billing – Contractor | Field Label & Status | Low – Aligns complaint type text with approved legal wording. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-007 | OMB-CTR-2025-007 | Business Analyst | Senior BA | 2025-07-12 | Block edits for events before 48 hours and increase count only after 48‑hour threshold. | Jal Rekha | O&M Billing – Contractor | Business Rule – Time Restriction | High – Enforces SLA that events before 48 hours cannot be edited, preserving audit trail. | Completed | 2026-02-01 | Approved | High | Medium
CR-OMB-CTR-008 | OMB-CTR-2025-008 | Business Analyst | Senior BA | 2025-07-12 | Make Reason for relaxation mandatory only when user selects YES for relaxation. | Jal Rekha | O&M Billing – Contractor | Business Rule – Validation | Medium – Ensures relaxation reason is captured only when applicable, improving data quality. | Completed | 2026-02-01 | Approved | Medium | Low
CR-OMB-CTR-009 | OMB-CTR-2025-009 | Business Analyst | Senior BA | 2025-10-12 | Correct spelling of “Penalty Relaxation” across forms and reports. | Jal Rekha | O&M Billing – Contractor | Field Label & Spelling | Low – Fixes spelling to maintain professional presentation and reduce confusion. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-010 | OMB-CTR-2025-010 | Business Analyst | Senior BA | 2025-10-12 | Ensure all new/changed fields are visible in contractor O&M reports with document links. | Jal Rekha | O&M Billing – Contractor | Reporting Coverage | Medium – Ensures reports reflect all new fields and attached documents for review. | Completed | 2026-02-01 | Approved | Medium | Medium
CR-OMB-CTR-011 | OMB-CTR-2025-011 | Business Analyst | Senior BA | 24-12-2025 | Allow upload of a single PDF for power consumption bills (electricity bills of Intake, IPS, WTP). | Jal Rekha | O&M Billing – Contractor | Document Management | Medium – Standardizes power consumption document uploads and simplifies verification. | Completed | 2026-02-01 | Approved | Medium | Medium
CR-OMB-CTR-012 | OMB-CTR-2025-012 | Business Analyst | Senior BA | 26-12-2025 | Show CPI increments in Manpower penalty column under Additional facilities and freeze saved entries for Manpower/Vehicle/Other. | Jal Rekha | O&M Billing – Contractor | Penalty & CPI Handling | High – Correctly reflects CPI impact in penalties and prevents unintended edits after save. | Completed | 2026-02-01 | Approved | High | Medium
CR-OMB-CTR-013 | OMB-CTR-2025-013 | Business Analyst | Senior BA | 26-12-2025 | Validate that number of mobiles is ≤ number of manpower in penalty section. | Jal Rekha | O&M Billing – Contractor | Business Rule – Validation | Medium – Prevents configurations that violate manpower–mobile policy. | Completed | 2026-02-01 | Approved | Medium | Low
CR-OMB-CTR-014 | OMB-CTR-2025-014 | Business Analyst | Senior BA | 26-12-2025 | Add label “Upload supporting doc (Sub Meter Reading Proof)” to the respective upload control. | Jal Rekha | O&M Billing – Contractor | Field Label & Guidance | Low – Guides users to upload correct supporting document for sub‑meter readings. | Completed | 2026-02-01 | Approved | Low | Low
CR-OMB-CTR-015 | OMB-CTR-2025-015 | Business Analyst | Senior BA | 28-12-2025 | Implement Bulk User MWSR and Dhara report integration and new functionality/pages at database side. | Jal Rekha | O&M Billing – Contractor | Reporting & New Functionality | High – Provides additional MIS (Bulk User MWSR, Dhara) and new DB functionality for analysis. | Completed | 2026-02-01 | Approved | High | Medium
CR-OMB-SV-001 | OMB-SV-2025-001 | Technical Lead | Senior BA | 2025-10-12 | Analyze and fix O&M Billing SQL queries; update related tables and functions. | Jal Rekha | O&M Billing – Security | Database Accuracy | High – Fixes incorrect outputs in O&M Billing due to faulty SQL or schema. | Completed | 14-12-2025 | Approved | High | Medium
CR-OMB-SV-002 | OMB-SV-2025-002 | Technical Lead | Senior BA | 2025-10-12 | Develop and optimize PostgreSQL queries used by O&M Billing and reports. | Jal Rekha | O&M Billing – Security | Performance Optimization | Medium – Improves performance of billing‑related queries and reports. | Completed | 14-12-2025 | Approved | Medium | Low
CR-OMB-SV-003 | OMB-SV-2025-003 | Security Analyst | Senior BA | 2025-11-12 | Perform security sanitization (Cross‑Site Scripting DOM fixes in Jal Rekha JS files) as per SonarQube/SVN security audit. | Jal Rekha | O&M Billing – Security | Security Hardening | High – Closes XSS and related vulnerabilities to meet security audit requirements. | Completed | 14-12-2025 | Approved | High | Medium
5 | CR-OMB-005 | GM | O&M PM / GM Admin | 2025-05-11 | SLA‑based Alert & Escalation – auto alerts for pending RA/Final bills, colour‑coded status dashboard, configurable SLA matrix for each role (Contractor, PIU GM, SQC, PMC, CFO, MD). | Jal Rekha | O&M Billing – SLA & Alerts | Workflow Engine + UI/UX | Introduces proactive delay control with escalation to higher authorities on SLA breach. | Planned | TBD | Pending | High | Medium
6 | CR-OMB-006 | Finance (CFO) | O&M PM / Finance Team | 2025-12-11 | Multi‑Year CPI & GST Revision – configuration screen for yearly CPI indices, GST rate master, and automatic recomputation of variance for already‑generated bills with audit trail. | Jal Rekha | O&M Billing – Finance Configuration | Calculation Engine | Separates financial parameters from code and reduces manual CPI/GST updates. | Planned | TBD | Pending | High | High
7 | CR-OMB-007 | Auditor / PMC | O&M PM | 20-11-2025 | RA/Final Bill Audit Trail – line‑item level change history (old vs new values, user, timestamp, reason) and downloadable audit PDF attached with each bill. | Jal Rekha | O&M Billing – Audit Trail | Compliance & File Management | Strengthens traceability and supports statutory/third‑party audits. | Planned | TBD | Pending | Medium | Medium
8 | CR-OMB-008 | Contractor | O&M PM | 28-11-2025 | Bulk Bill Upload – Excel/CSV template for multiple village/scheme bills, server‑side validation with error log, and partial‑success save for correct rows. | Jal Rekha | O&M Billing – Bulk Upload | Data Entry + Validation | Reduces data‑entry time for contractors handling many schemes. | Planned | TBD | Pending | Medium | Medium
9 | CR-OMB-009 | PIU GM | O&M PM | 2025-05-12 | Interactive Reconciliation Report – compare O&M bills with Dhara supply data and Nirmal quality data, highlight mismatches in quantity/pressure/quality and allow drill‑down to component level. | Jal Rekha | O&M Billing – Reconciliation Reports | Reports Module + Cross‑Module Integration | Gives single view for technical‑financial reconciliation before approval. | Planned | TBD | Pending | High | Medium
10 | CR-OMB-010 | MD Office | O&M PM | 2025-12-12 | Bill Lifecycle Dashboard – MD‑level dashboard showing RA/Final bills by status, amount, scheme, district, and contractor, with filters and export to Excel/PDF. | Jal Rekha | O&M Billing – Management Dashboard | BI / MIS Reporting | Provides management‑level visibility and decision‑making support on O&M expenditure. | Planned | TBD | Pending | High | Medium

## FHTC CR
CHANGE REQUEST LOG - CHANGE REQUEST FHTC MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-FHTC-GM-001 | FHTC-GM-2025-001 | QA Team | QA Lead | 2025-04-11 | Create detailed test scenarios for FHTC FETCH module covering FE and GM login, report access flows, negative cases, and regression set. | Jal Rekha | FHTC – GM/Contractor Reports | Test Design & Coverage | Medium – Ensures adequate regression coverage for FETCH module before and after CR deployment. | Completed | 14-11-2025 | Approved | High | Medium
CR-FHTC-GM-002 | FHTC-GM-2025-002 | Business Analyst | Senior BA | 2025-05-11 | Apply report updates in FHTC GM and Contractor modules including new columns, filters, status indicators, and formatting changes. | Jal Rekha | FHTC – GM/Contractor Reports | Reporting – GM/Contractor | High – Directly affects correctness and usability of GM/Contractor FHTC reports used for review and approvals. | Completed | 14-11-2025 | Approved | High | Medium
CR-FHTC-GM-003 | FHTC-GM-2025-003 | Technical Lead | Senior BA | 2025-06-11 | Analyze and fix FHTC SQL queries and update related database tables/functions to correct aggregations and joins. | Jal Rekha | FHTC – GM/Contractor Reports | Database Accuracy | High – Prevents incorrect figures and missing data in FHTC GM/Contractor reports. | Completed | 14-11-2025 | Approved | High | Medium
CR-FHTC-GM-004 | FHTC-GM-2025-004 | Technical Lead | Senior BA | 2025-06-11 | Develop and optimize PostgreSQL queries used in FHTC reports to improve performance on large data sets. | Jal Rekha | FHTC – GM/Contractor Reports | Performance Optimization | Medium – Reduces report execution time and improves response for district‑level users. | Completed | 14-11-2025 | Approved | Medium | Low
CR-FHTC-FE-001 | FHTC-FE-2025-001 | Business Analyst | Senior BA | 2025-03-12 | Modify FE login‑based reports for FHTC to align with latest workflow, including new status and filter fields. | Jal Rekha | FHTC – FE/Reports | Reporting – FE | Medium – Provides accurate FE‑wise tracking of FHTC survey and testing activities. | Completed | 2025-09-12 | Approved | Medium | Low
CR-FHTC-FE-002 | FHTC-FE-2025-002 | Business Analyst | Senior BA | 2025-04-12 | Create or modify FHTC web pages for FE reports as per departmental requirements (new views, drill‑downs). | Jal Rekha | FHTC – FE/Reports | Functional Enhancement – Web | Medium – Enables FE/GM users to access revised report views without manual compilation. | Completed | 2025-09-12 | Approved | Medium | Low
CR-FHTC-FE-003 | FHTC-FE-2025-003 | Technical Lead | Senior BA | 2025-04-12 | Fix FHTC village–scheme mapping issues impacting FE/GM reporting and validations. | Jal Rekha | FHTC – FE/Reports | Data Integrity – Scheme Mapping | High – Corrects scheme attribution to villages, avoiding mis‑reported beneficiary and scheme statistics. | Completed | 2025-09-12 | Approved | High | Medium
CR-FHTC-FE-004 | FHTC-FE-2025-004 | UI/UX Designer | Senior BA | 2025-05-12 | Implement UI changes on FHTC survey page for FE based on departmental feedback (labels, layout, mandatory fields). | Jal Rekha | FHTC – FE/Reports | UI/UX – FE Survey Page | Medium – Aligns survey UI with departmental formats, reducing user confusion and data entry errors. | Completed | 2025-09-12 | Approved | Medium | Low
CR-FHTC-FE-005 | FHTC-FE-2025-005 | Technical Lead | Senior BA | 2025-05-12 | Resolve Samagra multiple family ID issues impacting FHTC validations and mapping to beneficiaries. | Jal Rekha | FHTC – FE/Reports | Integration – Samagra ID | High – Avoids duplicate or mis‑linked families and ensures correct beneficiary mapping in FHTC. | Completed | 2025-09-12 | Approved | High | Medium

## Dhara CR
CHANGE REQUEST LOG - CHANGE REQUEST Dhara MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-DHARA-RPT-001 | DHARA-RPT-2025-001 | Business Analyst | Senior BA | 2025-08-11 | Redesign Dhara pages of Jal Rekha to align with updated UI standards and navigation for water supply reports. | Jal Rekha | Dhara – Reports | UI/UX – Dhara Pages | Medium – Improves usability of Dhara pages and reduces navigation issues for stakeholders. | Completed | 13-11-2025 | Approved | Medium | Low
CR-DHARA-RPT-002 | DHARA-RPT-2025-002 | Business Analyst | Senior BA | 2025-09-11 | Provide updated/changed Dhara water supply reports – DWSR, MWSR, scheme‑wise, village‑wise, bulk user, and UFW reports. | Jal Rekha | Dhara – Reports | Reporting – Water Supply | High – Ensures all key Dhara water supply reports are aligned with revised departmental formats. | Completed | 13-11-2025 | Approved | High | Medium
CR-DHARA-RPT-003 | DHARA-RPT-2025-003 | Business Analyst | Senior BA | 2025-09-11 | Update meter mapping configuration in Dhara as per latest departmental instructions. | Jal Rekha | Dhara – Reports | Data Integrity – Meter Mapping | High – Keeps meter mapping accurate with departmental structure, avoiding mis‑reported consumptions. | Completed | 13-11-2025 | Approved | High | Medium
CR-DHARA-RPT-004 | DHARA-RPT-2025-004 | Business Analyst | Senior BA | 2025-10-11 | Implement WTP‑to‑village meter reading flow in Dhara module including data capture and processing. | Jal Rekha | Dhara – Reports | Functional Flow – WTP to Village | High – Enables end‑to‑end capture of WTP to village meter readings for Dhara analytics. | Completed | 13-11-2025 | Approved | High | Medium
CR-DHARA-SV-001 | DHARA-SV-2025-001 | Security Analyst | Senior BA | 2025-10-12 | Configure Play Console crashlytics and vulnerability monitoring for Jal Rekha mobile components used in Dhara. | Jal Rekha | Dhara – Security | Monitoring – Crashlytics | Medium – Provides early crash and vulnerability signals for mobile usage. | Completed | 18-12-2025 | Approved | Medium | Low
CR-DHARA-SV-002 | DHARA-SV-2025-002 | QA Lead | Senior BA | 2025-10-12 | Perform UI testing for all Dhara‑related modules to ensure consistency and identify defects. | Jal Rekha | Dhara – Security | Quality Assurance – UI | Medium – Detects UI issues across modules before production release. | Completed | 18-12-2025 | Approved | Medium | Low
CR-DHARA-SV-003 | DHARA-SV-2025-003 | Technical Lead | Senior BA | 2025-11-12 | Create and update PostgreSQL queries supporting Dhara reporting and processing. | Jal Rekha | Dhara – Security | Database & Reporting Queries | Medium – Supports correct data extraction and calculations for Dhara reports. | Completed | 18-12-2025 | Approved | Medium | Medium
CR-DHARA-SV-004 | DHARA-SV-2025-004 | Technical Lead | Senior BA | 2025-11-12 | Implement password encryption for all Jal Rekha users in database as per security policy. | Jal Rekha | Dhara – Security | Security – Password Management | High – Secures user credentials at rest to comply with security guidelines. | Completed | 18-12-2025 | Approved | High | Medium
CR-DHARA-SV-005 | DHARA-SV-2025-005 | Technical Lead | Senior BA | 13-12-2025 | Develop and modify Functions/SPs used by Dhara for reporting and data processing. | Jal Rekha | Dhara – Security | Database Functions & SPs | Medium – Ensures Dhara logic is maintainable and supports new requirements. | Completed | 18-12-2025 | Approved | Medium | Medium
CR-DHARA-SV-006 | DHARA-SV-2025-006 | Technical Lead | Senior BA | 16-12-2025 | Optimize and validate Dhara report queries for performance and correctness. | Jal Rekha | Dhara – Security | Performance Optimization – Reports | Medium – Reduces report latency and improves experience for district‑level users. | Completed | 18-12-2025 | Approved | Medium | Low
CR-DHARA-SV-007 | DHARA-SV-2025-007 | Technical Lead | Senior BA | 16-12-2025 | Redesign and deploy updated Dhara pages on Jal Rekha live server after security and query changes. | Jal Rekha | Dhara – Security | Deployment – Live Environment | Medium – Ensures secured and optimized Dhara changes are available on live portal. | Completed | 18-12-2025 | Approved | Medium | Medium

## Nirmal CR
CHANGE REQUEST LOG - CHANGE REQUEST Nirmal MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-NIR-WTP-001 | NIR-WTP-2025-001 | Business Analyst | Senior BA | 2025-05-11 | Apply WTP report parameter changes in Nirmal as per latest departmental requirement. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – WTP | Medium – Keeps WTP reporting aligned with current parameters used by department. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-002 | NIR-WTP-2025-002 | Business Analyst | Senior BA | 2025-05-11 | Align Nirmal Beneficiary, OHT, WTP, and RawWater reports to a consolidated structure and common filters. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – Consolidated Nirmal Reports | High – Provides unified structure for key Nirmal reports across all entities. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-003 | NIR-WTP-2025-003 | Business Analyst | Senior BA | 2025-08-11 | Add two additional drill‑down levels in all Nirmal OHT, WTP, and Raw Water reports. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – Drill‑downs | High – Enables deeper multi‑level analysis for Nirmal reporting. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-004 | NIR-WTP-2025-004 | Business Analyst | Senior BA | 2025-08-11 | Update Beneficiary water test report parameters to support additional quality metrics. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – Beneficiary Quality | High – Supports more granular assessment of beneficiary‑level water quality. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-005 | NIR-WTP-2025-005 | Business Analyst | Senior BA | 2025-08-11 | Add Action remarks field in Beneficiary report drill‑down views. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Action Tracking – Beneficiary | Medium – Captures contractor/GM decisions directly in Beneficiary reports. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-006 | NIR-WTP-2025-006 | Business Analyst | Senior BA | 2025-10-11 | Add two more drill‑downs in Beneficiary Water Test report for detailed analysis and “still pending test cases”. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – Drill‑downs | High – Provides detailed traceability for beneficiary water test status. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-007 | NIR-WTP-2025-007 | Business Analyst | Senior BA | 2025-11-11 | Increase component filters in Nirmal reports to support fine‑grained component‑wise filtering. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Filtering – Components | Medium – Improves usability for component‑level slicing. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-008 | NIR-WTP-2025-008 | Business Analyst | Senior BA | 2025-11-11 | Show OHT along with OHT–village mapping details in Nirmal reports. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Data Integrity – OHT Mapping | High – Ensures correct visibility of OHT–village relationships. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-009 | NIR-WTP-2025-009 | Business Analyst | Senior BA | 22-11-2025 | Allow contractors and GM to record Action remarks in drill‑down reports, with corresponding UI changes. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Action Tracking – Contractor/GM | Medium – Improves audit trail of actions taken at different roles. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-010 | NIR-WTP-2025-010 | Business Analyst | Senior BA | 22-11-2025 | Implement UI changes for Action Remarks link button and “still pending test cases” drill‑down. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | UI/UX – Action Remarks & Pending Cases | Medium – Provides intuitive navigation for pending cases and remarks. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-011 | NIR-WTP-2025-011 | Business Analyst | Senior BA | 23-11-2025 | Apply popup tables on action buttons for contractor and GM to show remarks/history. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Usability – Popup Views | Medium – Gives consolidated view of actions and history for each record. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-012 | NIR-WTP-2025-012 | Business Analyst | Senior BA | 23-11-2025 | Add search options and comments box on all Nirmal WTP/OHT/Beneficiary reports. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Usability – Search & Comments | Medium – Enhances findability and collaboration within reports. | Completed | 27-11-2025 | Approved | Medium | Low
CR-NIR-WTP-013 | NIR-WTP-2025-013 | Business Analyst | Senior BA | 25-11-2025 | Remove inline queries from Jal Nigam Service DB class and move to parameterized DB layer; validate through Postman and portal (≈25 queries). | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Technical Debt – Inline Query Removal | High – Reduces technical debt and improves maintainability/security. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-014 | NIR-WTP-2025-014 | Business Analyst | Senior BA | 25-11-2025 | Create new query type to fetch Component Master details based on Scheme ID and PIU ID. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Database – New Query Type | High – Enables efficient retrieval of component masters for reports. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-WTP-015 | NIR-WTP-2025-015 | Business Analyst | Senior BA | 27-11-2025 | Create new queries WTP_Samples_Tested_Detail and Beneficiary_Testing_Report_Tested_List for detailed WTP and beneficiary/OHT testing data. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Database – New Testing Detail Queries | High – Adds dedicated queries for detailed sample testing analysis. | Completed | 27-11-2025 | Approved | High | Medium
CR-NIR-RAW-001 | NIR-RAW-2025-001 | Business Analyst | Senior BA | 2025-05-12 | Provide date‑range facility in Nirmal Raw Water reports. | Jal Rekha | Nirmal – Raw Water | Reporting – Raw Water | Medium – Improves flexibility of time‑based raw water analysis. | Completed | 14-12-2025 | Approved | Medium | Low
CR-NIR-RAW-002 | NIR-RAW-2025-002 | Business Analyst | Senior BA | 2025-05-12 | Finalize Raw water testing and WTP report requirements and implement on web. | Jal Rekha | Nirmal – Raw Water | Requirements & Web Implementation | High – Delivers web‑based Raw water and WTP reports required by department. | Completed | 14-12-2025 | Approved | High | Medium
CR-NIR-RAW-003 | NIR-RAW-2025-003 | Business Analyst | Senior BA | 2025-06-12 | Add search by Water Sample ID in Raw water report. | Jal Rekha | Nirmal – Raw Water | Reporting – Raw Water | Medium – Allows direct lookup of records using Water Sample ID. | Completed | 14-12-2025 | Approved | Medium | Low
CR-NIR-RAW-004 | NIR-RAW-2025-004 | Business Analyst | Senior BA | 2025-06-12 | Implement RawWater_Samples_Tested_Detail mapping to fetch testing details for raw water samples. | Jal Rekha | Nirmal – Raw Water | Data Mapping – Raw Water Samples | High – Ensures correct mapping and retrieval of raw water testing details. | Completed | 14-12-2025 | Approved | High | Medium
CR-NIR-RAW-005 | NIR-RAW-2025-005 | Business Analyst | Senior BA | 2025-08-12 | Add two new columns and drill‑down for passed and failed raw water records. | Jal Rekha | Nirmal – Raw Water | Reporting – Raw Water | High – Separates passed/failed records, improving QA visibility. | Completed | 14-12-2025 | Approved | High | Medium
CR-NIR-RAW-006 | NIR-RAW-2025-006 | Business Analyst | Senior BA | 2025-08-12 | Add bell icon on all comments pop‑ups in Raw water reports. | Jal Rekha | Nirmal – Raw Water | Usability – Notifications | Low – Provides visual notification cue on comment presence. | Completed | 14-12-2025 | Approved | Low | Low
CR-NIR-RAW-007 | NIR-RAW-2025-007 | Business Analyst | Senior BA | 2025-10-12 | Change label text from “Remarks” to “FE Remarks” in all Raw water reports and pop‑ups. | Jal Rekha | Nirmal – Raw Water | Field Label – FE Remarks | Low – Clarifies ownership of remarks by FE. | Completed | 14-12-2025 | Approved | Low | Low
CR-NIR-RAW-008 | NIR-RAW-2025-008 | Business Analyst | Senior BA | 2025-10-12 | Add search options and comments box on all Raw water reports. | Jal Rekha | Nirmal – Raw Water | Usability – Search & Comments | Medium – Improves searchability and collaboration. | Completed | 14-12-2025 | Approved | Medium | Medium
CR-NIR-RAW-009 | NIR-RAW-2025-009 | Business Analyst | Senior BA | 2025-12-12 | Increase WTP/Intake buffer to 200 meter for Raw water sample collection in Contractor/FE login. | Jal Rekha | Nirmal – Raw Water | Business Rule – Sampling Buffer | Medium – Aligns sampling buffer distance with departmental guideline of 200 meters. | Completed | 14-12-2025 | Approved | Medium | Medium

## Sahbhagita CR
CHANGE REQUEST LOG - CHANGE REQUEST Sahbhagita MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-SHB-RPT-001 | SHB-RPT-2025-001 | Business Analyst | Senior BA | 22-11-2025 | Modify Sahbhagita survey reports as per new layout and updated data requirements. | Jal Rekha | Sahbhagita – Reports | Reporting – Layout & Data | Medium – Aligns survey report layout and contents with the latest departmental format. | Completed | 2025-03-12 | Approved | Medium | Low
CR-SHB-RPT-002 | SHB-RPT-2025-002 | Business Analyst | Senior BA | 22-11-2025 | Create new Sahbhagita page for approval of survey reports with action options. | Jal Rekha | Sahbhagita – Reports | Workflow – Survey Approval | High – Enables structured approval workflow for Sahbhagita survey reports. | Completed | 2025-03-12 | Approved | High | Medium
CR-SHB-RPT-003 | SHB-RPT-2025-003 | Business Analyst | Senior BA | 23-11-2025 | Update Sahbhagita video upload functionality to support required size and file formats. | Jal Rekha | Sahbhagita – Reports | Media Handling – Video | Medium – Ensures video uploads comply with size/format constraints and avoid failures. | Completed | 2025-01-12 | Approved | Medium | Low
CR-SHB-RPT-004 | SHB-RPT-2025-004 | Business Analyst | Senior BA | 23-11-2025 | Enhance Frm_Ngo_Summary_Reports page to show counts for Approved, Rejected, and No Action survey reports. | Jal Rekha | Sahbhagita – Reports | Reporting – NGO Summary KPIs | High – Provides management visibility into survey status across NGOs. | Completed | 2025-01-12 | Approved | High | Medium
CR-SHB-RPT-005 | SHB-RPT-2025-005 | Business Analyst | Senior BA | 24-11-2025 | Introduce new service for Village dropdown based on district code and related video enhancements. | Jal Rekha | Sahbhagita – Reports | Dropdown Service – Village & Video Enhancements | Medium – Improves usability of village selection and supports video‑related services. | Completed | 2025-01-12 | Approved | Medium | Low
CR-SHB-GM-001 | SHB-GM-2025-001 | Business Analyst | Senior BA | 2025-04-12 | Change Sahbhagita report view to support village‑wise triggers using Get_VillageForApproval. | Jal Rekha | Sahbhagita – GM/PM | Reporting – Village‑wise View | Medium – Allows GM/PM to review survey reports village‑wise. | Completed | 14-12-2025 | Approved | Medium | Low
CR-SHB-GM-002 | SHB-GM-2025-002 | Business Analyst | Senior BA | 2025-04-12 | Add an additional Village dropdown on Frm_Ngo_Survey_Approval page. | Jal Rekha | Sahbhagita – GM/PM | UI/UX – Filters | Medium – Improves usability by giving more granular village filtering while approving surveys. | Completed | 14-12-2025 | Approved | Medium | Low
CR-SHB-GM-003 | SHB-GM-2025-003 | Business Analyst | Senior BA | 2025-05-12 | Implement service and functionality to make ISA selection dependent on Scheme and District (PIU → Scheme → ISA → Village). | Jal Rekha | Sahbhagita – GM/PM | Business Rule – ISA Dependency | High – Enforces correct ISA mapping sequence and prevents wrong associations. | Completed | 2025-11-12 | Approved | High | Medium
CR-SHB-GM-004 | SHB-GM-2025-004 | Business Analyst | Senior BA | 2025-05-12 | Update Sahbhagita ISA Bill form as per revised format and financial fields. | Jal Rekha | Sahbhagita – GM/PM | Financial Form – ISA Billing | Medium – Keeps ISA billing aligned with updated financial structure and reporting. | Completed | 2025-11-12 | Approved | Medium | Low