## Bharosa Code Review Defect
Internal Code Defects Review-Bharosa
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Defects | Recommendation of Review | Compliance Status | Date
CYCLE -2
1 |  | JAL REKHA | BHAROSA | Factory Testing Web | SUNIL THAKUR | NEHA SONI | Role-based validation is missing at both UI and API levels, allowing unauthorized role mapping and leading to potential security and access control issues. | Enforce strict role-based access control with server-side authorization and UI validation to prevent unauthorized role mapping. | Closed | 2025-10-13
2 |  |  |  | Factory Testing Mobile |  |  | Proper input validation, data synchronization, and media upload error handling are missing across the Factory Testing workflow, which may lead to inconsistent inspector entries, incorrect component mapping, and failed or incomplete document, image, and video uploads. | Implement robust input validation, transactional data synchronization, and reliable media upload handling with retry, size checks, and error logging to ensure data accuracy and upload reliability. | Closed | 2025-10-27
CYCLE -3
3 |  | JAL REKHA | BHAROSA | Factory Testing Web | SUNIL THAKUR | NEHA SONI | Missing usability and responsive design validation in UI redesign may impact user experience. | Conduct usability testing and implement responsive design standards to ensure consistent user experience across devices. | Closed | 2025-11-20
4 | [6 empty] | Incomplete field-level validation in survey inspection page may cause inconsistent data entry. | Enforce mandatory field validation with proper input checks to ensure accurate and complete data entry. | Closed | 2025-11-21
5 | [6 empty] | Improper normalization in component and quantity mapping may lead to data redundancy | Normalize database design and optimize data mapping to eliminate redundancy and maintain data consistency. | Closed | 2025-11-21
6 | [6 empty] | Missing referential integrity checks in subcomponent mapping may create orphan records | Implement strict referential integrity constraints and foreign key validations to prevent orphan records. | Closed | 2025-11-20
7 | [6 empty] | Lack of indexing and query optimization in database objects may degrade performance. | Add proper indexing and optimize database queries to improve performance and scalability. | Closed | 2025-11-18
8 | [6 empty] | Insufficient regression test coverage for bug fixes may introduce new defects. | Implement comprehensive regression testing and automate test cases to prevent defect reoccurrence. | Closed | 2025-11-22
9 |  | JAL REKHA | BHAROSA | Factory Testing Mobile | SUNIL THAKUR | NEHA SONI | Factory testing UI design and draft workflow lack proper usability and state validation, leading to inconsistent user actions and data entry. | Implement usability testing and enforce strict workflow state validation to ensure consistent user actions and accurate data entry. | Closed | 2025-12-01
10 | [6 empty] | Scheme addition and API integration lack input validation and duplicate checks, causing incorrect mapping and data inconsistency | Add robust input validation and duplicate checks in scheme mapping and API integration to maintain data accuracy. | Closed | 2025-12-03
11 | [6 empty] | Mobile Insert and Get APIs lack secure authentication, payload validation, and standardized responses, increasing security and data integrity risks. | Enforce secure authentication, strict payload validation, and standardized API responses to improve security and data integrity. | Closed | 2025-12-03
12 | [6 empty] | Production deployment and history API integration lack performance optimization, monitoring, and rollback mechanisms, impacting system stability and reliability. | Implement performance tuning, real-time monitoring, and rollback mechanisms to ensure stable and reliable production deployment. | Closed | 2025-12-04
13 |  | JAL REKHA | BHAROSA | CR - Report View | SUNIL THAKUR | NEHA SONI | Change requests across mobile reports, web reports, TPIA component assignment, and database functions lack comprehensive impact analysis and regression testing, increasing the risk of data inconsistency and functional breakage. | Conduct comprehensive impact analysis and full regression testing for all change requests to prevent functional and data inconsistencies | Closed | 2025-12-13

## Bharosa
Internal Code Review-Bharosa
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Recommendation of Review | compliance status | date
1 |  | Jal Rekha | Bharosa | Factory Testing Web | Sunil Thakur | Neha Soni | 1.Ensure UI redesign and wireframe implementation follow approved standards with consistent layout and user experience. 2.Verify correct mapping and validation of factory testing data including components, quantities, remarks, documents, and images. 3.Review new database tables, functions, and APIs for correctness, performance optimization, and error handling. 4.Confirm bug fixes and new master data mappings are stable and do not cause regression issues. 5.Validate test scenarios for complete functional coverage and role-based access control. | Closed | 2025-11-17
2 |  | Jal Rekha | Bharosa | Factory Testing Mobile | Sunil Thakur | Neha Soni | 1.Designed and implemented Factory Testing screens with a consistent and user-friendly layout. 2.Developed Factory Testing draft activity workflow with proper data handling and validations. 3.Implemented Add Scheme functionality in Factory Testing module. 4.Integrated Factory Testing APIs ensuring smooth data flow between UI and backend. 5.Deployed Bharosa Factory Testing module successfully in the production environment. 6.Integrated Factory Testing history APIs for production use and data tracking. 7.Resolved Bharosa FE login issues and discussed, designed, and created new Mobile Insert APIs for the Bharosa module. 8.Developed Bharosa module Insert and Get APIs for mobile application integration. | Closed | 2025-11-29