Project Status Report

Project Status Report

Project: Jal Rekha

Govt. of Madhya Pradesh

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

Revision History

| Version | Date | Description | Prepared by | Reviewed by |
| --- | --- | --- | --- | --- |
| 1.0 | 30th January 2026 | Status report including completed activities, delays, and next steps | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal |

# Project Status Report

| Project Code: | MPSEDC/MPSSDI (GIS)/2025/00423 | Project Name: | Jal Rekha |
| --- | --- | --- | --- |

| Client: | 8, Arera Hills, Bhopal, Madhya Pradesh 462027 |
| --- | --- |

| Business Analyst: | Mr. Dheeraj Motiyani | Service Project Manager: | Mr. Tapan Khandelwal |
| --- | --- | --- | --- |

PLANNED ACTIVITIES – JANUARY 2026

| Planned Activities | Activities Completed | Schedule Variance | Effort Variance | DRE (%) |
| --- | --- | --- | --- | --- |
| O&M Billing module – CR & Contractor Login | In Progress | On Schedule | Within Effort | 78% |
| O&M Billing GM – Power Consumption, Summary & Complaint Redressal CR | Completed | On Schedule | Within Effort | 78% |
| Material Testing – GM/Contractor Login Module | Completed | On Schedule | Within Effort | 80% |
| Material Testing – FE Mobile Login & API Integration | In Progress | On Schedule | Within Effort | 83% |
| Nirmal – FE Mobile Reports (Beneficiary, OHT, WTP, Raw Water) | Completed | On Schedule | Within Effort | 75% |
| Dhara – UFW Report Correction & Meter Updation | Completed | On Schedule | Within Effort | 66% |
| Anusharavan – RFI History Screen Search & Pipeline Details Fix | Completed | On Schedule | Within Effort | 67% |
| Bharosa Factory Testing Web – Unit Field Addition & Mobile Bug Fix | Completed | On Schedule | Within Effort | 100% |
| FHTC – FE Reports Change Request | In Progress | On Schedule | Within Effort | Approx 70% |
| CMMI L5 – Documentation, Review Meetings & VC Calls | In Progress | On Schedule | Within Effort | N/A |

RISK MANAGEMENT

| Risk Description | Risk Mitigation Plan | Status |
| --- | --- | --- |
| O&M Billing GM module CR (Power Consumption, Summary, Complaint Redressal) may introduce billing calculation errors or summary mismatches across PIUs. | Created detailed test matrix for Power Consumption and Summary tab scenarios, ran parallel calculation checks against prior version, and kept the previous formula set available for rollback for one billing cycle. | Closed |
| O&M Billing Contractor Login CR (in progress) may cause approval bottlenecks if contractor-side workflow validations are incomplete before rollout. | Conducting phased UAT with sample contractors, validating each workflow stage independently, and keeping a manual override at PIU level to reassign or force-close stuck approvals until CR is fully closed. | Open – Monitoring |
| Material Testing FE Mobile login changes (API integration, OHT search, draft save) may affect offline sync or geofence validation leading to missed test entries. | Performed field-level API integration testing with sample sites, monitored sync logs for null/duplicate records, and enabled manual web-based fallback entry at PIU office if mobile submission fails. | Closed |
| Material Testing GM/Contractor module changes may cause mis-routing of inspection requests between Contractor → SQC → FE workflow stages. | Validated end-to-end routing logic with test cases for each role transition, reviewed master configuration and Anusharavan-aligned flow, and provided manual reassignment option at PIU login for stuck requests. | Closed |
| Nirmal FE Mobile report changes (Beneficiary, OHT, WTP, Raw Water) may produce incorrect failed-sample counts or mismatched data after merge to production. | Cross-verified report outputs against local/UAT test data before production merge, ran parallel validation on WTP count mismatch cases, and retained legacy report version for one cycle for cross-check. | Closed |
| Dhara UFW Report correction and meter updation may introduce inconsistent water-loss percentage values for certain schemes during the transition period. | Investigated and corrected backend calculation logic with database function review, tested updated UFW report across multiple schemes, and merged only after end-to-end validation with sample ground data. | Closed |
| Anusharavan RFI history screen search and pipeline details fix may regress existing Contractor/FE search functionality or hide previously visible RFI records. | Performed peer review of search query changes, validated fix on Play Store live build before wider rollout, and maintained manual tracking sheet for critical RFI records during transition. | Closed |
| Bharosa Factory Testing Web/Mobile CR (unit field, document upload bug fixes) may cause incomplete factory test data capture if mobile sync fails. | Conducted end-to-end testing on staging for unit field and document upload changes, monitored mobile API logs post-release, and provided fallback web entry for critical factory inspections. | Closed |
| FHTC FE Reports change request (in progress) may affect Samagra-linked beneficiary mapping accuracy if report logic changes are not fully validated. | Running peer review on SQL/report logic changes, reconciling outputs against earlier FHTC reports, and maintaining a cross-checked beneficiary list for critical schemes until CR is closed. | Open – Monitoring |
| CMMI L5 documentation activities (Phase 1-3 streamlining, review meetings) may face schedule slippage due to dependency on external MQAS agency coordination. | Maintaining structured document tracking over SVN repository, scheduling regular internal and external review meetings, and following up proactively with MQAS for interview scheduling and feedback closure. | Open – Monitoring |

DATE-WISE CHRONOLOGICAL MODULE & SUB-MODULE FUNCTIONALITY DETAIL – JANUARY 2026

| Module / Sub-Module | Date Range (January 2026) | Functionality / Activity Details | Hours Consumed |
| --- | --- | --- | --- |
| Material Testing – GM/Contractor Login | 08-Jan to 30-Jan-2026 | Mobile sync API fixes, OHT ID parameter addition, Inspection Request local DB save & insert API integration, Function/SP development and modification, FE Login UI enhancement. | 88.5 |
| O&M Billing GM | 08-Jan to 30-Jan-2026 | Power Consumption Sheet calculation modification, Summary tab (web & service) modification, Module-wide requirement changes as per department discussion. | 78.0 |
| CMMI Documents | 08-Jan to 28-Jan-2026 | CMMI L5 documentation and review meetings/VC calls; documentation of Cycle 2 & Cycle 3 models. | 154.5 |
| Nirmal – FE Mobile | 08-Jan to 30-Jan-2026 | Nirmal report failed-record highlighting, requirement gathering for Beneficiary report changes, merge to UAT/Production, Beneficiary/OHT/WTP/Raw Water report development and bug fixing. | 58.0 |
| Department Meetings | 08-Jan to 23-Jan-2026 | Discussion and review on Nirmal, Bharosa, O&M Billing module updates; planning for new Material and Cube Testing modules and Dhara/Nirmal/O&M/Bharosa changes. | 38.0 |
| Dhara | 08-Jan to 28-Jan-2026 | Module changes as per department request, meter updation, UFW report data modification and correction. | 32.0 |
| Anusharavan | 21-Jan to 29-Jan-2026 | RFI Module history screen search functionality for Contractor & FE, pipeline details fix on history detail screen (Play Store live build verification), bug fixes. | 28.0 |
| Bharosa Factory Testing – Web | 08-Jan to 27-Jan-2026 | Mobile App login API issue resolution, Unit & Quantity input field addition (Get/Insert in Mobile App), document upload enhancement and bug fixes. | 20.0 |
| Asset Mapping | 15-Jan to 16-Jan-2026 | Redesigning and deployment of live server pages for Jal Rekha & Amrut Rekha. | 16.0 |
| Dashboard | 12-Jan to 13-Jan-2026 | Redesigning the pages of Amrut Rekha MPUDC. | 16.0 |
| FHTC – FE Reports | 27-Jan-2026 | Work on FHTC Module and report changes as per change request. | 8.0 |

QUANTITATIVE INFORMATION (CYCLE 4 – CUMULATIVE THROUGH JANUARY 2026)

Productivity, Code Rate & Test Rate

| AS-IS |  |  |  |
| --- | --- | --- | --- |
|  | Productivity | Code_Rate | Test_Rate |
| Mean | 0.18452 | 0.31448 | 0.72905 |
| SD | 0.03006 | 0.01276 | 0.13391 |
| UCL | 0.20283 | 0.35277 | 1.13077 |
| LCL | 0.0225 | 0.27619 | 0.32734 |

| Target |  |
| --- | --- |
|  | Productivity |
| Mean | 0.20297 |
| SD | 0.05 |

| What If |  |  |  |
| --- | --- | --- | --- |
|  | Productivity | Code_Rate | Test_Rate |
| Mean | 0.19943 | 0.4 | 0.85 |
| SD | 0.05 | 0.05 | 0.05 |
| USL | 0.34943 | 0.55 | 1 |
| LSL | 0.04943 | 0.25 | 0.7 |

Cycle Time

| AS-IS |  |  |  |
| --- | --- | --- | --- |
|  | Cycle Time | Code_CT | Test_CT |
| Mean | 0.68252 | 0.27604 | 0.17336 |
| SD | 0.17128 | 0.09563 | 0.07439 |
| UCL | 1.19635 | 0.56292 | 0.39653 |
| LCL | 0.16869 | -0.01084 | -0.04981 |

Defect Removal Efficiency (DRE)

| AS-IS |  |  |
| --- | --- | --- |
|  | DRE | Code Review Per Size |
| Mean | 0.778 | 0.1992 |
| SD | 0.086 | 0.062 |
| UCL | 1.0368 | 0.384 |
| LCL | 0.5197 | 0.0145 |

| Target |  |
| --- | --- |
|  | DRE |
| Mean | 0.8 |
| SD | 0.1 |

| What If |  |  |
| --- | --- | --- |
|  | DRE | Code Review Per Size |
| Mean | 0.793 | 0.22 |
| SD | 0.1 | 0.05 |
| USL | 1.09348 | 0.37 |
| LSL | 0.49348 | 0.07 |

SUMMARY METRICS

| Metric | Planned Value | Actual Value | Remarks |
| --- | --- | --- | --- |
| Completed Modules / CRs | 6 | 6 | Material GM/Contractor, Nirmal FE Reports, Dhara UFW, Anusharavan RFI, Bharosa Web, Bharosa Mobile bug fix |
| In-Progress Tasks | 4 | 4 | O&M Billing Contractor Login, Material FE Mobile, FHTC FE Reports, CMMI L5 Documentation – targeted for completion by 28.02.2026 |

| Prepared by: | Mr. Dheeraj Motiyani, Sr. Business Analyst, MPSeDC | Date: | 30th January 2026 |
| --- | --- | --- | --- |
| Reviewed by: | Project Manager, Mr. Tapan Khandelwal | Date: |  |

Review Comments:

Project is progressing steadily during January 2026. Material Testing and Nirmal FE Mobile modules were successfully completed and moved to production. O&M Billing Contractor Login, Material FE Mobile, FHTC FE Reports, and CMMI L5 Documentation remain in progress and are targeted for completion by 28.02.2026. No critical risks remain open; two CR-related risks (O&M Billing Contractor Login, FHTC FE Reports) are under active monitoring pending closure of their respective change requests. Timely follow-up advised on CMMI L5 external review scheduling with MQAS.

Page 1 of 1 | Jal Rekha – Project Status Report | January 2026