## Sheet1
CR No. | Module | Sub-module | CR Raised By | Logging Date | Change Request Description | Impact Analysis (Technical) | Implementation Date | Status
OB-3001 | O&M Billing | Contractor Dashboard – Summary View | Contractor Operations | 2025-12-06 | Add Quick Summary Dashboard for Contractor Login: Display key metrics on contractor home page: (1) Villages assigned (count), (2) Meter readings pending this month, (3) Data entry deadline countdown, (4) Water quality tests pending, (5) Expenditure entries pending. Add visual progress bar showing monthly data completion % (e.g., "3 of 5 villages submitted = 60% complete"). Quick action buttons: "Enter Meter Reading," "Submit Expenditure," "Upload Test Report." | UI/UX Changes: Design dashboard layout with metric cards and progress indicators. Add color-coded status badges (Green: Completed, Yellow: Pending, Red: Overdue). Database: Query aggregation for pending entries by contractor and village. Create view for contractor summary metrics. Backend/API: New API endpoint /api/v1/contractor/dashboard/summary returning: villages_assigned, readings_pending, deadline_countdown, tests_pending, expenditure_pending, completion_percentage. Performance: Cache summary metrics (5-minute TTL) to reduce DB load. Frontend: Integrate progress bar component; add real-time countdown timer. Impact: Minor – new dashboard section; no existing functionality affected. Effort: 4 days (UI: 1.5 days, Backend API: 1 day, Caching: 0.5 days, Testing: 1 day). | 2025-12-31 | Completed
OB-3002 | O&M Billing | GP Member Verification – Bulk Approve Feature | Gram Panchayat Operations | 2025-12-07 | Enable Bulk Approval for GP Members: Allow GP member to select multiple villages' meter readings (checkbox selection) and approve all at once with single comment applicable to all. Reduces verification time for GPs managing multiple villages (e.g., "All readings verified and approved - no anomalies detected"). Add "Approve All" button (available only if all selected readings pass anomaly checks). Display summary before bulk approval: "You are about to approve [X] meter readings. Proceed?" | UI/UX Changes: Add multi-select checkboxes to meter reading list. Add "Approve All" button visible when ≥2 items selected. Add bulk action confirmation dialog. Database: No schema changes needed. Backend Logic: Implement batch approval API endpoint /api/v1/gp/verify/bulk-approve accepting array of reading_ids and common_comment. Update all reading records with approval status, timestamp, and common comment appended (optional). Add log entry for each approved reading in audit trail. Validation: Ensure no reading in batch has anomaly_flag = CRITICAL (if any critical anomaly, block bulk approval). UI: Progress indicator for bulk approval operation (if processing >10 items). Impact: Minor – batch operation logic; no existing functionality affected. Effort: 3 days (UI: 1 day, Backend: 1 day, Testing: 1 day). | 2026-01-02 | Completed
OB-3003 | O&M Billing | GM Billing Review – Role-Based Approval Matrix | Scheme Administration | 2025-12-08 | Implement Role-Based Approval Authority Matrix: Create configurable approval authority rules: (1) Scheme with ≤ 50 villages: Approved by GM alone (no District approval needed), (2) Scheme with 51-150 villages: Requires GM + District approval, (3) Scheme > 150 villages: Requires GM + District + HQ approval. Add rule: Monthly total O&M > Rs. 1 Crore → Auto-requires HQ approval regardless of village count. Add rule: Total penalties > Rs. 50 lakhs → Requires District + HQ approval. Configuration UI for HQ Admin to edit approval rules (change thresholds, add new rules). Display approval authority requirement on GM dashboard: "This billing requires approval from: GM ✓ → District → HQ (Pending)" | Business Logic: Implement approval rule engine (if-else logic or rules engine framework). Rules stored in database table approval_authority_rules with fields: rule_id, scheme_size_threshold, o_m_amount_threshold, penalty_amount_threshold, required_approval_levels (array). Database: Add table approval_authority_rules with version control (rule_version, effective_date, created_by, modified_by). Add column required_approval_level (integer: 1=GM only, 2=GM+District, 3=GM+District+HQ) to billing_master table. Backend/API: Implement rule evaluation logic in billing calculation workflow. New endpoint /api/v1/admin/approval-rules for HQ Admin to CRUD rules. UI: Add rule configuration page (HQ Admin only) with form to define thresholds and approval levels. GM dashboard displays approval authority chain dynamically. Impact: Moderate – introduces approval logic complexity; requires careful testing. Effort: 6 days (Rule Engine: 2 days, Database: 1 day, Backend Logic: 1 day, UI Configuration: 1 day, Testing: 1 day). | 2026-01-05 | Completed
OB-3004 | O&M Billing | Report Generation – Scheduled Email Reports | Reporting & Analytics | 2025-12-09 | Enable Scheduled Email Reports to Stakeholders: System automatically generates and emails monthly abstract report to: (1) GM on 11th of month (auto-generated when all villages approved), (2) District Admin on 12th of month with district-wide summary, (3) HQ office on 13th of month with state-wide analysis. Allow configuration of recipient list per role (via HQ Admin settings). Include report summary in email body + PDF attachment. Add "View in Portal" link in email to view full interactive report. Track email delivery status (Sent, Failed, Bounced) for audit. Resend failed emails with retry logic (max 3 retries over 24 hours). | Scheduler/Jobs: Implement scheduled jobs using Quartz Scheduler or APScheduler: (1) Generate report job at 6 AM on 11th, 12th, 13th of each month. (2) Email delivery job with retry logic. Report Generation: Reuse existing abstract report generation logic (FR-16 from SRS). Create separate report templates: GM view (scheme-level detail), District view (district-wide summary), HQ view (state-wide analysis). Email Service: Integrate email service (SMTP) with HTML email template. Attachment generation using PDF library (iText, ReportLab). Database: Add table scheduled_reports_config with fields: report_type, recipient_list (JSON), schedule_datetime, enabled_flag. Add table email_delivery_log for tracking: report_id, recipient_email, delivery_status, sent_datetime, failure_reason, retry_count. UI: HQ Admin settings page to configure recipients and enable/disable scheduled reports. Email delivery log viewer for audit. Error Handling: If report generation fails, alert HQ Admin and log error. If email delivery fails, retry with exponential backoff. Impact: Moderate – introduces scheduler dependency and email service integration. Effort: 7 days (Scheduler Setup: 1.5 days, Report Templates: 1.5 days, Email Service: 1 day, Database: 1 day, UI Config: 1 day, Error Handling: 0.5 days, Testing: 0.5 days). | 2026-01-08 | Completed
OB-3005 | O&M Billing | Master Data – Contractor & GP Member Assignment | User Management | 2025-12-10 | Create Assignment Management UI for Scheme Administrators: Allow GM to assign villages to contractors and GPs via drag-drop or list interface. Display current assignments and allow modification before month's data entry starts. Add bulk assignment feature: "Assign villages [X, Y, Z] to Contractor [Name]" using multi-select. Add validation: Contractor must be marked "Active" to receive assignments. Auto-deactivate contractor if marked "Inactive" (prevent further assignments). Show assignment history: "Village A was assigned to Contractor X on [date], previously assigned to Contractor Y." Generate assignment report: "Monthly Assignment Summary – All villages with assigned contractors/GPs as of [date]." | UI/UX Changes: Design assignment dashboard with drag-drop (or list selection) interface. Contractor pool on left, villages list on right. Add "Bulk Assign" modal for multi-select. Database: Add table contractor_village_assignment with fields: contractor_id (FK), village_id (FK), assignment_date, assignment_end_date (null if active), assigned_by, assignment_status (Active/Inactive). Add table gp_member_assignment similar structure. Create view for current active assignments. Backend/API: New endpoints: (1) GET /api/v1/assignments/village/[village_id] – get current contractor/GP. (2) POST /api/v1/assignments/village/[village_id]/assign – update assignment. (3) GET /api/v1/assignments/history/[village_id] – get assignment history. (4) GET /api/v1/assignments/report – generate assignment report. Validation: Check contractor_status = Active before assignment. Check village not already assigned to another contractor. Audit: All assignment changes logged in audit trail. UI Feedback: Confirmation messages and success notifications. Impact: Minor – new management interface; no impact on billing logic. Effort: 5 days (UI Design: 1.5 days, Database: 1 day, Backend API: 1.5 days, Reports: 0.5 days, Testing: 0.5 days). | 2026-01-10 | Completed
OB-3006 | O&M Billing | Data Quality – Meter Reading Validation Rules | Data Integrity | 2025-12-11 | Enhance Meter Reading Validation with Custom Business Rules: Implement configurable validation rules: (1) KL supply should not increase >50% from previous month (flag as warning, allow override by GP). (2) If previous month KL = 0, current month must be >0 (reject if not). (3) Meter reading sequence: current_reading > previous_month_reading (strictly increasing). (4) If meter marked non-functional, KL must be 0 (reject if not). (5) If gap between readings > 40 days, mark as "Late Reading" (warning, allow with comment). (6) QA flagging: If anomaly_count for village >= 3 in last 3 months, flag as "Requires Field Inspection" in abstract report. Allow HQ Admin to define custom rules via rules configuration UI. | Business Logic: Implement validation rule engine using rule evaluation framework. Rules stored in database table meter_reading_validation_rules with fields: rule_id, rule_name, rule_condition (expression), rule_severity (ERROR/WARNING/INFO), rule_priority, enabled_flag, created_by. Database: Add column validation_rule_violations (array of rule_ids violated) to meter_readings table. Add column field_inspection_required (boolean) to village_master table. Create table field_inspection_recommendations with village_id, recommendation_date, reason (JSON), inspection_status. Backend: Implement rule evaluator that applies all enabled rules to each meter reading submission. If ERROR-level rule violated, reject submission. If WARNING-level rule violated, allow with user acknowledgment. UI: Display rule violations on meter reading entry form with explanations and "Override" button for WARNINGs. Configuration UI: HQ Admin page to view, edit, enable/disable rules. Rule testing sandbox (enter test data, see which rules would trigger). Reports: Include "Field Inspection Recommendations" in abstract report if any village flagged. Impact: Moderate – introduces complex validation logic. Testing required for all rule combinations. Effort: 8 days (Rule Engine: 2 days, Database: 1 day, Backend Implementation: 2 days, UI Display: 1 day, Config UI: 1 day, Testing: 1 day). | 2026-01-12 | Completed
OB-3007 | O&M Billing | Penalty Management – SLA-Based Auto-Penalty Calculation | Penalty System | 2025-12-12 | Implement SLA-Based Automatic Penalty Trigger: When complaint resolution time exceeds SLA (7 days target): Auto-calculate SLA breach penalty = Rs. 1,000 per day of breach (configurable). Example: If complaint received on day 1, resolved on day 12 → 5 days late → Penalty = Rs. 5,000. Add penalty directly to monthly penalty sheet without manual entry. Notify GM: "SLA Breach Penalty: Rs. [X] for [Y] complaints (see details below)." GP can contest penalty with justification (e.g., "Parts unavailable, vendor delayed delivery by 3 days") → Routes to GM for review and potential relaxation. Allow penalty calculator configuration: change penalty rate per day, SLA target days, excluded complaint types (e.g., "Major repair" might have extended SLA). | Business Logic: Auto-penalty trigger implemented in nightly batch job or real-time on complaint resolution. When complaint.resolution_date is recorded: Check (resolution_date - received_date) > sla_target_days. If yes: Calculate breach_days = (resolution_date - received_date) - sla_target_days. Penalty_amount = breach_days × penalty_rate_per_day. Create penalty record with type = "SLA_BREACH," linked to complaint_id. Database: Add table sla_penalty_config with fields: penalty_rate_per_day (default: 1000), sla_target_days (default: 7), excluded_complaint_types (JSON array), effective_date. Add column auto_penalty_flag (boolean) to penalty table (default: True for SLA breaches). Add column linked_complaint_id (FK) to penalty table. Nightly Job: Query complaints resolved in current month. For each complaint: Check if resolution_time > SLA. If yes, auto-create penalty record. Update penalty sheet. GM Dashboard: Show "Auto-Generated Penalties" section separately from manual penalties. Penalty Contest Workflow: GP can click "Contest" on auto-penalty → Opens form: "Reason for contesting SLA breach penalty," supporting documents upload. Routes to GM for review. GM can approve contest (remove penalty) or deny (keep penalty). Configuration UI: HQ Admin can update SLA target days, penalty rate, excluded complaint types. Impact: Moderate – introduces penalty auto-generation logic; requires testing for edge cases. Effort: 7 days (Business Logic: 2 days, Database: 0.5 days, Nightly Job: 1 day, Penalty Contest Workflow: 1.5 days, Config UI: 1 day, Testing: 1 day). | 2026-01-15 | Completed
OB-3008 | O&M Billing | Expenditure Tracking – Multi-Currency Support | Financial Management | 2025-12-13 | Add Multi-Currency Expenditure Support (Future State for Interstate Billing): Allow expenditure entry in local currency (INR) and international currency (USD, GBP, EUR) if required for equipment imports. Add currency conversion field: "Exchange Rate on [date]: 1 USD = Rs. [X]." Store both original currency amount and INR-equivalent in database. Display both in reports: "Spare Parts: USD 1,000 (INR 83,000 @ 1 USD = 83 INR on [date])." Historical exchange rates maintained for compliance (in case auditor asks for conversion rate used). Add configuration for admin to update exchange rates. Allow category-wise currency preferences (e.g., "Equipment" typically in USD, "Manpower" in INR). | Database: Add columns to expenditure table: currency_code (ISO 4217: INR, USD, GBP, EUR), amount_in_currency (decimal), exchange_rate_used (decimal), amount_in_inr (calculated), exchange_rate_date (date when rate fetched). Create table exchange_rates_history with fields: currency_code, rate_date, inr_rate, source (RBI API / Manual Entry), updated_by. Backend Logic: On expenditure submission: If currency != INR, fetch latest exchange rate (or use manually entered rate if available). Calculate amount_in_inr = amount_in_currency × exchange_rate_used. Exchange Rate Service: Integration with RBI (Reserve Bank of India) API or manual entry. Scheduler job to fetch daily exchange rates from RBI API. Fallback to last known rate if API unavailable. UI/UX: Expenditure entry form: Add currency dropdown. If non-INR selected, show exchange rate field (pre-filled with latest rate, editable). Display both currency amounts in confirmation. Reports: Display both original currency and INR-equivalent amounts. Add note on report: "All amounts converted to INR using exchange rate on [date]." Configuration UI: HQ Admin page to manually update exchange rates if needed, view exchange rate history. Impact: Minor – new fields and display logic; no impact on existing INR transactions. Effort: 5 days (Database: 0.5 days, Exchange Rate Service: 1 day, Backend Logic: 1 day, UI: 1.5 days, Testing: 1 day). | 2026-01-18 | Completed
OB-3009 | O&M Billing | Audit & Compliance – Compliance Checklist Report | Governance | 2025-12-14 | Generate Monthly Compliance Checklist Report: Automated report verifying monthly billing process compliance with regulatory requirements: (1) ✓ All meter readings submitted and verified by [date]. (2) ✓ GP member verification completed for all villages. (3) ✓ No meter readings with unresolved critical anomalies. (4) ✓ All penalty relaxations approved by required authority. (5) ✓ Water quality tests conducted and documented. (6) ✓ Expenditure documentation complete. (7) ✓ No billing freeze violations (edits after freeze date). (8) ✓ SLA compliance % >= 90% for complaint redressal. (9) ✓ Audit trail maintained for all data modifications. (10) ✓ No data integrity violations detected. Report generated automatically after billing finalization. If any item fails (✗), list violations and required remediation actions. Route report to District Admin and HQ for compliance sign-off. | Report Generation: Automated compliance check queries: (1) Count of meter readings submitted = count of villages. (2) Count of GP verifications = count of readings. (3) Query for critical anomalies: anomaly_level = 'CRITICAL'. (4) Query for unapproved relaxations. (5) Query for water quality tests: count >= count of villages. (6) Query for expenditure completeness: all required fields filled. (7) Query billing_freeze_violations: any edit after freeze_date. (8) Calculate SLA_compliance = (Resolved Complaints / Total Complaints) × 100. (9) Query audit_log for completeness. (10) Data integrity checks: checksums validation. Database: Create view compliance_checklist that aggregates all compliance metrics. Report Template: PDF report with checklist layout. Green checkmarks for passed checks, red X for failed checks. Workflow: Route completed report to District Admin and HQ Admin for digital sign-off (accept/reject with comments). UI: HQ Dashboard displays compliance status dashboard. Drill-down to see detailed checklist. Notifications: Email report to District Admin and HQ upon completion. Impact: Minor – reporting and query logic; no data changes. Effort: 6 days (Compliance Queries: 1.5 days, Report Template: 1 day, Workflow Integration: 1 day, UI Dashboard: 1 day, Testing: 1.5 days). | 2026-01-20 | Completed
OB-3010 | O&M Billing | Knowledge Management – In-App Help & Training Resources | User Support | 2025-12-15 | Implement Comprehensive In-App Help System: Context-sensitive help tooltips on every form field (hover to show tip). Video tutorials embedded in portal: 3-5 minute videos for each major workflow (meter reading entry, GP verification, GM approval, penalty relaxation, report export). Help documentation wiki accessible from "Help" menu with searchable articles. Interactive tutorials: Step-by-step guided walkthroughs for complex workflows (e.g., "Penalty Relaxation Process: 5 Steps"). Chatbot (basic FAQ bot) to answer common questions (future phase). Track user interactions: Which help articles/videos most viewed? Which workflows generate most support requests? → Used for continuous improvement. User feedback: "Was this help article useful?" survey on each help article. | UI/UX: Design help icon (?) on every form field. Tooltip component on hover. Add "Help" menu in top nav. Video player integration (YouTube embed or self-hosted). Content Management: Create help article repository (wiki-style). Search functionality for articles. Video Hosting: Upload tutorial videos to YouTube or self-hosted video server. Embed via iframe. Interactive Tutorials: Design guided tour component using Shepherd.js or similar library. Step-by-step highlighting of form fields with explanatory text. Chatbot: Implement basic rule-based chatbot (future phase). Analytics: Track help article views, video watch time, tutorial completion %. Database: Add table help_articles with fields: article_id, title, content (HTML), created_date, updated_date, view_count, helpful_rating (avg). Add table video_tutorials with: video_id, title, url, category, duration_minutes, view_count. Add table user_interactions_log for analytics. UI Feedback: "Was this helpful?" buttons on articles with rating system (1-5 stars). Dashboard: HQ Admin can view help analytics dashboard. Impact: Minor – documentation and support feature; no impact on system functionality. Effort: 6 days (Content Creation: 2 days, UI Implementation: 1.5 days, Video Embedding: 1 day, Analytics: 1 day, Testing: 0.5 days). | 2026-01-22 | Completed

## Sheet2
30-12-25
1) 24 piu data should be shown to kapil admin id
After save and submit.
2). 1 village multiple check should not shown 2 times
3). GM. Piu name and contractor name not coming correctly
4) agreement value
5) multiple village not come
6) additional facilities issue after logout login .. no does not change
7) scheme. Change karne par purani wali scheme ka data show ho rha hai ... Refresh nhi ho rha hai ... Then we have to logout then it will show.. loader API issue
8) CPI base Yr and consider month CPI ... After that upload text box will come..
Then calculation happen instantly
9) remark should come at end
10) then additional affected HSCs should come in report below but no of HSC is coming
11) complaint resolved date ..
12)Type of complaint - Demand that cannot be fulfilled as per the agreement
13) event above 48 hours should not get edit and count increase happen after 48 hours
14) Penalty Relaxation spelling correct it
15) Reason for Relaxation only become mandatory after Clicking Yes
All above fields should be visible in below report and upload documents show in report
16) power consumption page - upload document (electricity bills of intake, IPS, wtp ) in single pdf
17) additional facilities - CPI increament should show in manpower penalty column
In Manpower - save then non editable freeze
Mobile = < Manpower and apply check
18) upload supporting doc ( sub meter reading proof )

## Sheet3
2025-10-12
From the four notebook images, the handwritten points that can be clearly extracted are:
Page 1 – GM / Contractor related
1. Village wise MWSR (Approved) – report.ppl-ai-file-upload.s3.amazonaws​
2. UFWs (update) – show all details and related reports.ppl-ai-file-upload.s3.amazonaws​
3. GM screen – buttons: Save as Draft, Next, Save & Submit.ppl-ai-file-upload.s3.amazonaws​
4. VFW (likely Village/Feeder Wise) view.ppl-ai-file-upload.s3.amazonaws​
5. Label changes and UI/UX changes requested.ppl-ai-file-upload.s3.amazonaws​
6. Document upload – status “locked” when done.ppl-ai-file-upload.s3.amazonaws​
7. Final number of HSG provided – to be shown to Admin/GM.ppl-ai-file-upload.s3.amazonaws​
8. In “Scheme Details” under Contractor:
Part (B) “zero” section should be disabled.
Part (A) to be in “view only” mode.
Normal Monthly Report / Water Monthly Report should show in O&M Approved Report – Village wise MWSR.ppl-ai-file-upload.s3.amazonaws​
Page 2 – Quarter, financial year, currency, uploads
1. Q1: April–June; Q2: July–September (quarter definitions).ppl-ai-file-upload.s3.amazonaws​
2. “Financial year” – disable editing after 2026 (after years).ppl-ai-file-upload.s3.amazonaws​
3. Currency notation to be in ₹ (Rs) format.ppl-ai-file-upload.s3.amazonaws​
4. Upload Work Order copy – sections A, B, C.ppl-ai-file-upload.s3.amazonaws​
5. Info icon tooltip on hover for “Extension / Payment” related field.ppl-ai-file-upload.s3.amazonaws​
6. Part (B) “zero” handling.ppl-ai-file-upload.s3.amazonaws​
7. In Part (A) Preview – No Document Upload case handling.ppl-ai-file-upload.s3.amazonaws​
8. Auto logout (logout automatically) after inactivity.ppl-ai-file-upload.s3.amazonaws​
Page 3 – Reports, water quality, mandatory fields
1. List shows status – Pending / Save as Draft / Submit.ppl-ai-file-upload.s3.amazonaws​
2. Uploaded documents to be visible in list view and in “Save & Next”.ppl-ai-file-upload.s3.amazonaws​
3. “O&M Bill PDF + Print” option.ppl-ai-file-upload.s3.amazonaws​
4. Buttons on form: Save & Next, Back, Submit.ppl-ai-file-upload.s3.amazonaws​
5. Water Quality Report to show on O&M Billing – Normal Report.ppl-ai-file-upload.s3.amazonaws​
6. Clarification: which consolidated report to use for KQ wise / which report.ppl-ai-file-upload.s3.amazonaws​
7. Mandatory “*” mark and pressure unit field – Hg / mKL (pressure unit clarification).ppl-ai-file-upload.s3.amazonaws​
8. Success message text: “Record added successfully” instead of just “Submit”.ppl-ai-file-upload.s3.amazonaws​
9. Edit option – keep record on hold but show “Record added in list”.ppl-ai-file-upload.s3.amazonaws​
10. Complaint redressal – only one District should show (by census; district allotted to contractor).ppl-ai-file-upload.s3.amazonaws​
11. Complaint redressal form:
Auto-filled from “Residual Pressure” and disable reset/other buttons.
Ask Kapil for relation with district (note).ppl-ai-file-upload.s3.amazonaws​
12. Complaint Date field.ppl-ai-file-upload.s3.amazonaws​
13. Penalty relaxation – default value “No”.ppl-ai-file-upload.s3.amazonaws​
Page 4 – Old bill, reports, decimals, agreement volume
1. Complaint redressal – move to first page (as per actual bill).ppl-ai-file-upload.s3.amazonaws​
2. Summary of bills:
Once old bill is completed, no modification allowed.
First complete old bills, then discuss new month bills.ppl-ai-file-upload.s3.amazonaws​
3. If Q1 is done, then Q2 values to auto-fill (quarter linkage).ppl-ai-file-upload.s3.amazonaws​
4. GM O&M Bill – 10/12 months; Kapil → GM O&M mapping (note).ppl-ai-file-upload.s3.amazonaws​
5. All reports in HSC – one-time entry as per Census population; total value will come in next bill.ppl-ai-file-upload.s3.amazonaws​
6. TTL (total) – allow 2 decimal places.ppl-ai-file-upload.s3.amazonaws​
7. Agreemented Daily Volume field.ppl-ai-file-upload.s3.amazonaws​
8. Deduction on Sundays / “Inactive” – disable based on MP O&M board decision.ppl-ai-file-upload.s3.amazonaws​
9. UI/UX – HSG count to match with Census; No. of HSG provided.ppl-ai-file-upload.s3.amazonaws​
10. Contractor → Scheme Details – read-only, visible with date of GM.ppl-ai-file-upload.s3.amazonaws​
11. Part A – decimal / 1 day; Save As (note for saving behavior).ppl-ai-file-upload.s3.amazonaws​
12. “Mouse over / hover” help text – additional functional facility.ppl-ai-file-upload.s3.amazonaws​
1. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/8bb74787-28e2-41b9-968f-cc64d4fe749d/image.jpg?AWSAccessKeyId=ASIA2F3EMEYEUF4R3FFV&Signature=Qv0Tzu%2FrmZ25xYevHBMFbwETgIM%3D&x-amz-security-token=IQoJb3JpZ2luX2VjEP3%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJGMEQCIFM1USWcMNdz4G0iAacimBsW7KK3S6KiVDW2vzBd2yPzAiBQ7Pgpj22KcNghzGaOKB6FI0t%2FSdNidWsRNUlkmCu64Cr8BAjG%2F%2F%2F%2F%2F%2F%2F%2F%2F%2F8BEAEaDDY5OTc1MzMwOTcwNSIMCTZvRvyUEzTXL22qKtAE7y4HmYjPLc9gYxou6GfEMVeY8ztC1XgYpYDq7ImjxfGpnW7iB3Dg6fK3PyIMdnxtMrZEbdG5ZOc9I0cOlKWibThTaKde4UgNTU%2BYqGzX5q5RskmTbM6fnw07scQH3%2BapDLDsByaS7trg7srTDX9A64bl3u6gfeN%2BCyEGQhDwsBqTS%2Btbkjk0mghlf%2B5vp8AqEBFNv6zypVZ%2BhS%2B7aIAtDt8q%2FQPXeqXMB6ydkBOoqBNoX92vb9BhBOeNgK4IGE%2FfmL%2BBCwF0JvRR%2FJQona04qA6TKx5G%2FF8Xp%2FQ1kNQTkz5JG85F5jvrPDJ532A5I%2FLQAR9O4KCH%2BRQiUwNHpfBsiUD0SgV5y3bX7QVsG4M94uLDOiRQCpeZ%2FvtDa2AoJyKhQ%2BK7EpCzq%2BPYNPYf7%2Bvo2mB4LjTNx0lQv9sszGOKNCyFyTbaU2qVTCgbCTptoNhEljywjm3VYIV8bf9kM31fy9em8nacF1lekhpmKq5BxfGPBWYbjFMutJ9aeHqL1UnIafXW8lOxVMMhKo6FeENx7N1116DEFQ6jBWs4IGFTeUNz%2BtvXFTQblYM%2B2wQsOzKR3G%2Fn6O5fbQF1lC%2BxPCa1jpSzO0UfgLHl%2FgPyvf48WipxzTaG82022Q49JE7VCRh%2BOGuu8OWwu8VCygJXSOW5SA3qvojQdecwtPSCC1dUunAsTCQ4%2Fq%2BJImOxIVhgPdb%2F9gX4NTm6ZAv%2BNTvbdQppFdOympLp9essD1vPkWVEojUgrNxfTp5fxbjOnWGoSX8U%2BnHVoeuUhnInDZAJ25XpSjDT3NLKBjqZARHRdXCBkWoYmGjsRa8dqw%2F%2F1LrTlgVFhWrESjf22tBWH9DubnnXFsQnir6ydWD40gacqR756WazraVhWUxus%2BpUuaabf5N%2BQtSleBeUoDgGGaAsQfYp34CmvFEUPoMKTxrINm8uzfNgccz0yqFAt4MXCDZQqDgCrQjBZdJfqRjkSZpvxifbLRQuLZIik9Sj31q8S6p2m8JgJw%3D%3D&Expires=1767159192
2. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/9f8a7dd6-ffd2-4f50-ac5e-0fd50ad4265f/image.jpg?AWSAccessKeyId=ASIA2F3EMEYEUF4R3FFV&Signature=hMUKzkygHHHB1BVXIJKR4F6sz9M%3D&x-amz-security-token=IQoJb3JpZ2luX2VjEP3%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJGMEQCIFM1USWcMNdz4G0iAacimBsW7KK3S6KiVDW2vzBd2yPzAiBQ7Pgpj22KcNghzGaOKB6FI0t%2FSdNidWsRNUlkmCu64Cr8BAjG%2F%2F%2F%2F%2F%2F%2F%2F%2F%2F8BEAEaDDY5OTc1MzMwOTcwNSIMCTZvRvyUEzTXL22qKtAE7y4HmYjPLc9gYxou6GfEMVeY8ztC1XgYpYDq7ImjxfGpnW7iB3Dg6fK3PyIMdnxtMrZEbdG5ZOc9I0cOlKWibThTaKde4UgNTU%2BYqGzX5q5RskmTbM6fnw07scQH3%2BapDLDsByaS7trg7srTDX9A64bl3u6gfeN%2BCyEGQhDwsBqTS%2Btbkjk0mghlf%2B5vp8AqEBFNv6zypVZ%2BhS%2B7aIAtDt8q%2FQPXeqXMB6ydkBOoqBNoX92vb9BhBOeNgK4IGE%2FfmL%2BBCwF0JvRR%2FJQona04qA6TKx5G%2FF8Xp%2FQ1kNQTkz5JG85F5jvrPDJ532A5I%2FLQAR9O4KCH%2BRQiUwNHpfBsiUD0SgV5y3bX7QVsG4M94uLDOiRQCpeZ%2FvtDa2AoJyKhQ%2BK7EpCzq%2BPYNPYf7%2Bvo2mB4LjTNx0lQv9sszGOKNCyFyTbaU2qVTCgbCTptoNhEljywjm3VYIV8bf9kM31fy9em8nacF1lekhpmKq5BxfGPBWYbjFMutJ9aeHqL1UnIafXW8lOxVMMhKo6FeENx7N1116DEFQ6jBWs4IGFTeUNz%2BtvXFTQblYM%2B2wQsOzKR3G%2Fn6O5fbQF1lC%2BxPCa1jpSzO0UfgLHl%2FgPyvf48WipxzTaG82022Q49JE7VCRh%2BOGuu8OWwu8VCygJXSOW5SA3qvojQdecwtPSCC1dUunAsTCQ4%2Fq%2BJImOxIVhgPdb%2F9gX4NTm6ZAv%2BNTvbdQppFdOympLp9essD1vPkWVEojUgrNxfTp5fxbjOnWGoSX8U%2BnHVoeuUhnInDZAJ25XpSjDT3NLKBjqZARHRdXCBkWoYmGjsRa8dqw%2F%2F1LrTlgVFhWrESjf22tBWH9DubnnXFsQnir6ydWD40gacqR756WazraVhWUxus%2BpUuaabf5N%2BQtSleBeUoDgGGaAsQfYp34CmvFEUPoMKTxrINm8uzfNgccz0yqFAt4MXCDZQqDgCrQjBZdJfqRjkSZpvxifbLRQuLZIik9Sj31q8S6p2m8JgJw%3D%3D&Expires=1767159192
3. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/6de0c545-251b-4a91-b62c-d99ceb5b3362/image.jpg?AWSAccessKeyId=ASIA2F3EMEYEUF4R3FFV&Signature=s697x1wngwJSuniB65fDizTvJh4%3D&x-amz-security-token=IQoJb3JpZ2luX2VjEP3%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJGMEQCIFM1USWcMNdz4G0iAacimBsW7KK3S6KiVDW2vzBd2yPzAiBQ7Pgpj22KcNghzGaOKB6FI0t%2FSdNidWsRNUlkmCu64Cr8BAjG%2F%2F%2F%2F%2F%2F%2F%2F%2F%2F8BEAEaDDY5OTc1MzMwOTcwNSIMCTZvRvyUEzTXL22qKtAE7y4HmYjPLc9gYxou6GfEMVeY8ztC1XgYpYDq7ImjxfGpnW7iB3Dg6fK3PyIMdnxtMrZEbdG5ZOc9I0cOlKWibThTaKde4UgNTU%2BYqGzX5q5RskmTbM6fnw07scQH3%2BapDLDsByaS7trg7srTDX9A64bl3u6gfeN%2BCyEGQhDwsBqTS%2Btbkjk0mghlf%2B5vp8AqEBFNv6zypVZ%2BhS%2B7aIAtDt8q%2FQPXeqXMB6ydkBOoqBNoX92vb9BhBOeNgK4IGE%2FfmL%2BBCwF0JvRR%2FJQona04qA6TKx5G%2FF8Xp%2FQ1kNQTkz5JG85F5jvrPDJ532A5I%2FLQAR9O4KCH%2BRQiUwNHpfBsiUD0SgV5y3bX7QVsG4M94uLDOiRQCpeZ%2FvtDa2AoJyKhQ%2BK7EpCzq%2BPYNPYf7%2Bvo2mB4LjTNx0lQv9sszGOKNCyFyTbaU2qVTCgbCTptoNhEljywjm3VYIV8bf9kM31fy9em8nacF1lekhpmKq5BxfGPBWYbjFMutJ9aeHqL1UnIafXW8lOxVMMhKo6FeENx7N1116DEFQ6jBWs4IGFTeUNz%2BtvXFTQblYM%2B2wQsOzKR3G%2Fn6O5fbQF1lC%2BxPCa1jpSzO0UfgLHl%2FgPyvf48WipxzTaG82022Q49JE7VCRh%2BOGuu8OWwu8VCygJXSOW5SA3qvojQdecwtPSCC1dUunAsTCQ4%2Fq%2BJImOxIVhgPdb%2F9gX4NTm6ZAv%2BNTvbdQppFdOympLp9essD1vPkWVEojUgrNxfTp5fxbjOnWGoSX8U%2BnHVoeuUhnInDZAJ25XpSjDT3NLKBjqZARHRdXCBkWoYmGjsRa8dqw%2F%2F1LrTlgVFhWrESjf22tBWH9DubnnXFsQnir6ydWD40gacqR756WazraVhWUxus%2BpUuaabf5N%2BQtSleBeUoDgGGaAsQfYp34CmvFEUPoMKTxrINm8uzfNgccz0yqFAt4MXCDZQqDgCrQjBZdJfqRjkSZpvxifbLRQuLZIik9Sj31q8S6p2m8JgJw%3D%3D&Expires=1767159192
4. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/81ffc335-e9a4-4426-9401-7b95b8b1bf65/image.jpg?AWSAccessKeyId=ASIA2F3EMEYEUF4R3FFV&Signature=7pcyqhR%2BuqE4mJR01ERGmmsJJ48%3D&x-amz-security-token=IQoJb3JpZ2luX2VjEP3%2F%2F%2F%2F%2F%2F%2F%2F%2F%2FwEaCXVzLWVhc3QtMSJGMEQCIFM1USWcMNdz4G0iAacimBsW7KK3S6KiVDW2vzBd2yPzAiBQ7Pgpj22KcNghzGaOKB6FI0t%2FSdNidWsRNUlkmCu64Cr8BAjG%2F%2F%2F%2F%2F%2F%2F%2F%2F%2F8BEAEaDDY5OTc1MzMwOTcwNSIMCTZvRvyUEzTXL22qKtAE7y4HmYjPLc9gYxou6GfEMVeY8ztC1XgYpYDq7ImjxfGpnW7iB3Dg6fK3PyIMdnxtMrZEbdG5ZOc9I0cOlKWibThTaKde4UgNTU%2BYqGzX5q5RskmTbM6fnw07scQH3%2BapDLDsByaS7trg7srTDX9A64bl3u6gfeN%2BCyEGQhDwsBqTS%2Btbkjk0mghlf%2B5vp8AqEBFNv6zypVZ%2BhS%2B7aIAtDt8q%2FQPXeqXMB6ydkBOoqBNoX92vb9BhBOeNgK4IGE%2FfmL%2BBCwF0JvRR%2FJQona04qA6TKx5G%2FF8Xp%2FQ1kNQTkz5JG85F5jvrPDJ532A5I%2FLQAR9O4KCH%2BRQiUwNHpfBsiUD0SgV5y3bX7QVsG4M94uLDOiRQCpeZ%2FvtDa2AoJyKhQ%2BK7EpCzq%2BPYNPYf7%2Bvo2mB4LjTNx0lQv9sszGOKNCyFyTbaU2qVTCgbCTptoNhEljywjm3VYIV8bf9kM31fy9em8nacF1lekhpmKq5BxfGPBWYbjFMutJ9aeHqL1UnIafXW8lOxVMMhKo6FeENx7N1116DEFQ6jBWs4IGFTeUNz%2BtvXFTQblYM%2B2wQsOzKR3G%2Fn6O5fbQF1lC%2BxPCa1jpSzO0UfgLHl%2FgPyvf48WipxzTaG82022Q49JE7VCRh%2BOGuu8OWwu8VCygJXSOW5SA3qvojQdecwtPSCC1dUunAsTCQ4%2Fq%2BJImOxIVhgPdb%2F9gX4NTm6ZAv%2BNTvbdQppFdOympLp9essD1vPkWVEojUgrNxfTp5fxbjOnWGoSX8U%2BnHVoeuUhnInDZAJ25XpSjDT3NLKBjqZARHRdXCBkWoYmGjsRa8dqw%2F%2F1LrTlgVFhWrESjf22tBWH9DubnnXFsQnir6ydWD40gacqR756WazraVhWUxus%2BpUuaabf5N%2BQtSleBeUoDgGGaAsQfYp34CmvFEUPoMKTxrINm8uzfNgccz0yqFAt4MXCDZQqDgCrQjBZdJfqRjkSZpvxifbLRQuLZIik9Sj31q8S6p2m8JgJw%3D%3D&Expires=1767159192
5. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/b1606183-3e58-4dbf-ac3e-8f94a5615b78/WhatsApp-Image-2025-12-11-at-10.11.37-AM.jpg
6. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/5491e8c4-9ea3-4407-82ba-6665a736deb7/WhatsApp-Image-2025-12-11-at-10.11.37-AM-1.jpg
7. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/bca11221-a969-4ae8-b124-59e8f5aab884/WhatsApp-Image-2025-12-11-at-10.11.39-AM.jpg
8. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/17a64d77-2157-4abe-b5aa-7a96ed83e1fa/WhatsApp-Image-2025-12-11-at-10.11.36-AM.jpg
9. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/5b57c2e0-91ab-4dd6-873f-f040edffef8a/WhatsApp-Image-2025-12-11-at-10.11.40-AM.jpg
10. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/57d9cc9d-ebbf-4867-8c79-349e3066bb87/WhatsApp-Image-2025-12-11-at-10.11.39-AM-2.jpg
11. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/183f5f39-6568-4a7f-89a1-6ec91cd28277/WhatsApp-Image-2025-12-11-at-10.11.38-AM-1.jpg
12. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/efe7f3c5-e52b-4156-891a-522139ef8946/Monthly-Meeting-with-MD-Sir-MOM-05th-December.docx
13. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/a33554ff-480b-4e28-9f5b-4a0948a3f43a/WhatsApp-Image-2025-12-11-at-10.11.38-AM.jpg
14. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/68c22f2d-72c8-4f2a-ab90-d77a529d68b7/WhatsApp-Image-2025-12-11-at-10.11.39-AM-1.jpg
15. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/9ba0f5db-9a45-4d48-a3c0-159134bc0b24/O-M-Billing-SCrenshots-of-contractor-login.docx
16. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/b6f45c35-9d8a-4114-84ca-a74804827758/CR-document-O-M-Billing.docx
17. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/32d71f32-a596-4e13-842d-56d5a8bea528/O-M-Billing-screenshots-of-GM-login.docx
18. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/de7c8148-3df0-4ef8-92fe-cbc3fecc78bc/O-M-Billing-Change-Request-Log-1.xlsx
19. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/e8ca9b35-ee9b-431f-b72d-e3a17ef7ac90/CR-document-O-M-Billing.docx
20. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/c41d7d76-596b-4ff8-ba26-74b3875036dd/image.jpg
21. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/images/90700967/14ea5eff-e8c2-48c0-b23c-a4188c218a6c/image.jpg
22. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/69a56854-2a8e-4370-a0a6-1e5205382555/CR-document-O-M-Billing.docx
23. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/35e6021d-3703-4662-b537-a0bdfcddf19b/O-M-Billing-CR-Log.docx
24. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/0759b027-3c74-4e98-b02b-4a2e52fcf0f1/O-M-Billing-SCrenshots-of-contractor-login.docx
25. https://ppl-ai-file-upload.s3.amazonaws.com/web/direct-files/attachments/90700967/5e271f95-c088-4d75-8242-00fecd7e870f/O-M-Billing-screenshots-of-GM-login.docx
26. https://agi-prod-file-upload-public-main-use1.s3.amazonaws.com/14ea5eff-e8c2-48c0-b23c-a4188c218a6c