## CR Logs
CHANGE REQUEST LOG
CR No. | Module | Sub-module | CR Raised By | Logging Date | Change Request description | Impact analysis (Technical) | Implementation Date | Status
1001 |  |  | Department | 2025-04-26 |  |  |  | Completed / Done
1002 |  |  | Department | 2025-04-26 |  |  |  | Completed / Done
1003 | DMF | Administrative Section | Department | 2025-04-26 | 1. DMF Part A: Nodal Department → District 2. DMF Part B: Department → Directorate → District (for AS) | 1. Data Model / Master Hierarchy Updates: Modify the existing entity relationship mapping for DMF Part A and Part B. Part A: Direct linkage between selected Nodal Department and District. Part B: Introduce additional layer - Directorate between Department and District. Update or extend the database schema or master tables (if not already present) to reflect: Directorate as a master entity. Mapping between Department → Directorate. Mapping between Directorate → District. 2. Form Logic / Dropdown Bindings: Part A: On selecting Nodal Department, dynamically load Districts mapped under it. Part B: On selecting Department, load related Directorates. On selecting Directorate, load respective Districts. Cascading dropdown logic required. 3. Backend / API Adjustments: Update form submission logic to capture and validate new mapping hierarchy. Update any relevant APIs fetching department-wise or directorate-wise data. Ensure backward compatibility for existing records or provide data migration scripts if needed. 4. Access Control / Validation: Ensure that selections follow new hierarchy and mismatch combinations are disallowed. Validation rules to ensure District selection depends on correct lineage. 5. UI/UX Changes: Form redesign (if needed) to accommodate three-level hierarchy in Part B. Tooltips or guidance messages may be added to explain new hierarchy flow to users. 6. Reporting / Downstream Systems: Check and update reports/export formats if they rely on the old structure. Revise any analytics dashboards using administrative mapping logic. 7. Testing Considerations: Thorough testing of: New selection flow for both Part A and Part B. Data integrity checks for updated vs. legacy entries. Cross-browser functionality of cascading dropdowns. |  | Completed / Done
1004 | DMF | Project Work Status Details: | Department | 2025-04-26 | 1. Replace "Current Bill Amount" and "Total Bill Amount" with "Fund Released Amount". 2. Add a new field: "Actual Cost of Project" (visible when "Yet to Start" is selected). 3. New field " Amount Spent on Projects Till Date " to be added . | 1. UI/UX Changes: Field Replacement: Replace two existing fields (Current Bill Amount, Total Bill Amount) with a single field Fund Released Amount. Update form labels, tooltips, and layout accordingly. New Conditional Field – “Actual Cost of Project”: Add a new input field that appears dynamically only when the Project Status is set to "Yet to Start". Implement dynamic visibility logic in the frontend. New Field – “Amount Spent on Projects Till Date”: Add new input field always visible in the form under the relevant section. Update form validations if applicable. 2. Database Schema Changes: Remove (or deprecate) columns: current_bill_amount and total_bill_amount if not used elsewhere. Add new columns: fund_released_amount actual_cost_of_project amount_spent_till_date Ensure data type is consistent with other monetary fields (e.g., decimal(15,2)). 3. Backend Logic Updates: Update form submission and update logic to: Save and validate the newly added fields. Omit or map deprecated fields appropriately if existing data is impacted. Conditional saving logic for actual_cost_of_project to trigger only when the status is "Yet to Start". 4. Report / API Updates: Update downstream reports, dashboards, and APIs to: Reflect Fund Released Amount in place of previous fields. Include new fields (Actual Cost, Amount Spent Till Date) in output where needed. 5. Data Migration (if needed): If historical values exist for Current Bill Amount and Total Bill Amount, migrate or archive as necessary. Optionally, map their average/sum to Fund Released Amount if required by the department. 6. Testing Considerations: Functional testing for: Conditional visibility logic. Validation rules for monetary inputs. Regression testing for modules dependent on project work status. Role-based access testing (if these fields are editable only by specific users). |  | Completed / Done
1005 | DMF | Data Migration | Department |  | 1. First Round of Filtering 1. A master sheet will be developed by the MPSeDC Team on the portal, integrating DMF project data from both the old State Portal and the National Portal. 2. Projects will be selected based on their Project ID from both portals to ensure accurate matching. 3. Project details finalization will be done through dropdown or check box options. Manual entries will not be permitted. 4. After finalization the project details. All data will be backed up in the master sheet. 5. This process will initially be implemented across 10 districts: Singrauli, Betul, Katni, Satna, Chhindwara, Maihar, Anuppur, Balaghat, Pandhurna, and Shahdol—covering approximately 12,000 DMF projects out of an estimated 17,000 projects, as per National Portal records. 6. Duplicate projects will be reviewed and removed after confirmation. 7. Successfully matched data will be migrated to the new State Portal. 2. Second Round of Filtering 1. A second round of data filtering will be conducted for districts other than the above-mentioned 10 districts. | 1. Operational Impact Streamlined Data Consolidation: By integrating data from both the old State Portal and the National Portal into a master sheet, duplication and inconsistency will be minimized. Standardized Data Entry: Dropdown and checkbox-based selection will eliminate manual entry errors, enhancing accuracy and uniformity. Restricted Manual Intervention: No manual data entry may delay correction of minor mismatches or inconsistencies not covered by dropdown options. 2. Technical Impact Improved Data Matching Logic: Using unique Project IDs from both portals ensures accurate mapping and de-duplication. Data Backup and Security: Backup to a master sheet ensures recoverability and audit trails. Integration Complexity: Integrating two separate systems (State and National Portals) may involve compatibility issues or mismatched schema formats. 3. Organizational Impact Phased Implementation (10 Districts Initially): Risk is minimized by limiting the initial rollout, allowing the team to identify and fix issues before full-scale deployment. Resource Allocation Requirement: Additional manpower and coordination may be required in initial districts for validation and review. 4. User Impact Improved User Experience (Post-Migration): Cleaner, deduplicated, and verified data will improve usability and reporting. Temporary User Confusion: Users in pilot districts may face short-term confusion during transition and data unavailability until migration is complete. 5. Data Quality & Governance Impact Enhanced Data Reliability: Matching and de-duplication improve the overall quality of the DMF database. Audit Readiness: Backed-up and standardized data sets support better monitoring and audit compliance. 6. Future Scalability Scalable Framework for Other Districts: The second round of filtering prepares the portal for eventual full-state migration, leveraging lessons from the pilot phase. |  | Completed / Done
1006 | MSS |  | Department |  | 1) District wise report need to be prepared for all mines (Major/Minor) along with the status (Active/Inactive) and share it with district users for verification and freeze all mines at Surveillance system. | 1. District-wise Mine Report Generation Backend: Implement logic to fetch mine data categorized by: District Mine Type (Major/Minor) Mine Status (Active/Inactive) Ensure data is accurate and synchronized with master mine database. Database: Verify that all mines are mapped with districts and status flags. Add indexing on district, mine_type, and status fields for performance. Frontend: Create report view/download interface (PDF/Excel). Enable district-level users to view and verify reports. Sharing & Review: Implement a workflow or notification system to notify district users for verification. |  | Completed / Done
1007 | MSS |  | Department |  | 2) Mine freezing functionality need to developed by next week. | 2. Mine Freezing Functionality Function Logic: Add a new field/flag in the mine master table: is_frozen (boolean). Once mines are verified, allow admins or district users to “freeze” mines — making them non-editable. UI/UX: Display status of each mine (Frozen/Not Frozen). Add "Freeze Mine" button/action for authorized users. Access Control: Only specific roles (e.g., District User, Admin) can freeze. Once frozen, disable update/delete functionality on those records unless unfrozen by Super Admin. Audit Trail: Maintain logs: who froze the mine, when, and any attempt to modify frozen mines. |  | Completed / Done
CR: Change Request (includes enhancements / minor changes / problems)
CI: Configuration Item
Status: |  |  | Pending/Impact Analysis/Approved/Rejected/Closed
Impact Analysis (Technical) : Please Log Effort for wach Impact mentioned bewlo)
Code File
No Data Base Object impacted
Impact on existing functionalit & Archi