# Project Management Process

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

Revision History

| Date | Version | Description | Prepared by | Reviewed & approved by |
| --- | --- | --- | --- | --- |
| 14-06-2021 | 1.0 | First Baseline Version | SEPG Team | SEPG Head |

Table of Contents

1	Purpose	1

2	Scope	1

3	Intent	1

4	Value	1

5	Organization of the Document	1

6	General Description of the Process	2

6.1	The Process Decomposition	2

6.2	The Process Overview	2

6.2.1	Project Planning	2

6.2.2	Project Monitoring and Control	2

7	Project Planning	2

7.1	Introduction	2

7.2	Glossary of Terms	2

7.3	Entry Criteria	2

7.4	Inputs	3

7.5	Roles and Responsibilities	3

7.6	Tasks	3

7.7	Outputs	5

7.8	Exit Criteria	5

7.9	Formats & Guidelines	5

7.10	References	5

8	Project Monitoring and Control	5

8.1	Introduction	5

8.2	Glossary of Terms	6

8.3	Entry Criteria	6

8.4	Inputs	6

8.5	Roles and Responsibilities	6

8.6	Tasks	6

8.7	Project Progress Monitoring	6

8.8	Project tracking:	6

8.9	Milestone Reviews	7

8.10	Outputs	7

8.11	Exit Criteria	7

8.12	Formats & Guidelines	7

8.13	References	7

# Purpose

In an era of fast changing technologies, short product cycles, and keen competition in a global economy, organizations all over the world place a lot of emphasis on project management. Timely completion of projects with optimal use of resources will not only influence the profitability of an organization, but also bring competitive advantages to the beneficiary of the project i.e. the customer.

The purpose of this process is to lay down a set of tasks as per international standards, which will be followed in COE & SSDI for planning and execution of software projects.

# Scope

This process is initiated at the beginning of a project (project initiation phase) once the contract review according to the “Business Development and customer engagement” process is complete and the project is finally handed to the project manager.

It includes identification of various resources required for completion of the project as per the agreed scope of work and acceptance criteria.

It results in a Project Plan to be tracked and updated throughout the project life cycle.

This process also aids in monitoring the project activities during its lifecycle.

# Intent

The intent of this process is to ensure Project Plan related to budget, schedule, resource requirement and quality is prepared and project is tracked accordingly. Project risks are identified and tracked.

# Value

The Value of this process is to achieve desired outcome within optimized cost and schedule and with desired level of quality.

Key measures

| Measure | Computation mechanism | Source of information |
| --- | --- | --- |
| Schedule Variance | (Actual End date-Planned end date)/(Planned end date-Planned start date) | Project Schedule |
| Effort Variance | (Actual effort-Planned Effort)/Planned Effort | Project Schedule with effort breakup |
| Defect removal effectiveness | (Internal defect)/(Internal defects+ External defects) | Defect Log |

*Internal defects=Review defects (SRS, Design, Code, test cases) + Testing defects

*External defects=UAT defect + Production defects

# Organization of the Document

The next Section gives the process decomposition diagram and gives general description of the chapters to be covered in this Process.

The subsequent Section describes each of the chapters separately in detail like Introduction, Entry Criteria, Inputs, Roles and Responsibilities, Tasks, Output, Exit Criteria, Formats and guidelines, References, Glossary, etc.

# General Description of the Process

## The Process Decomposition

The Project Management process comprises of two chapters, illustrated in the process decomposition diagram shown below:

Project Management Process

Project Planning

Project Monitoring & Control

## The Process Overview

### Project Planning

This chapter consists of initiating a project and planning each component activity in a project situation, estimating the related effort, resource requirements and time, evaluating various management issues e.g. project risks, methodology, tools, staffing, logistics etc., defining the project schedule, and setting of targets. This also includes the configuration management planning and quality control planning for the project.

Project Plan is prepared and base lined in the early stages of the project (project initiation phase) which essentially involves the preparation of the Project Plan (PP), which includes the configuration management plan, quality plan and metrics plan for the project and the organization of resources to start work on the project. This also takes care of the various start-up activities in a project that are undertaken before the project team members actually start working on project deliverables. Some examples are: setting up the project organization, setting up the work environment, and training of the team members, setting norms for client interfacing, etc.

### Project Monitoring and Control

The task of managing the day-to-day project work and controlling the project progress so as to drive it to meet the project objectives is the essence of Project Monitoring. This comprises of functions like monitoring of work progress, quality management, issue resolution and furnishing project progress, cost and critical information to the management.

# Project Planning

## Introduction

Software project activities and commitments are planned and documented. Documented software estimates are used in planning and tracking software projects. Individuals and affected groups agree to their commitments related to software projects. The Project Planning Process enables the Project Manager to prepare a Project plan that enables effective management of the complete software project. This plan lays the foundation for good project management. The Project Planning process must help in effective control over activities/tasks and resources within a project. This in turn translates into timely delivery of products within optimum resources.

## Glossary of Terms

PM – Project Manager

PI- Project Initiation

## Entry Criteria

- Project Initiation Note

- Changes in the schedule, schedule or budget that require an update of the Project Plan

## Inputs

One or more of the following:

- System Enhancement Request

- Contract

- Scope of work

- Proposal

- Organization Process Assets

## Roles and Responsibilities

- Project Manager to create the plans and update as and when necessary

- Senior Management to approve the Plans.

## Tasks

On receiving the Project Initiation Note, the designated Project Manager shall call for a kickoff meeting to initiate the project. The PM may invite other stakeholders like QA support functions. The project and the commitments shall be discussed. The PM shall prepare the Project Plan (consisting of project plan / quality plan / configuration management plan/metrics plan) according to Project Plan Template in the initial stages of the project. Project Manager may also involve QA Group in the preparation and review of Project Plan, as appropriate. The following should be described in the Project Plan:

  - The scope and objectives of the project.

  - Define the Customer.

  - Identify the communication channels between the Project team and the Client. The names, phone numbers, addresses, fax numbers and email addresses of the contact persons should be clearly mentioned in the Project Plan.

  - Identify the PLC model to be used. Depending upon the scope of work relevant life cycle phases applicable to the project are identified. For details please refer to the Software Development process.

  - Identify the project deliverables along with the details of the team members responsible.

  - List the project receivables along with the details of responsible person and put the receivables under configuration control.

  - Define Acceptance Criteria as agreed with the client /define the internal acceptance criteria for the project in objective terms, as appropriate.

  - Initial estimates and thereafter any changes in the estimates of size, effort and cost are derived according to the Estimation Process. Review the estimation sheets and the associated documents made at the time of preparing the initial estimate should be considered for reviewing the estimates. Revise the above estimates, if required, due to any change in underlying proposal. Take into consideration the past experience of the organization in similar projects from the software process database, make assumptions as appropriate and document them.

  - Identify resource requirement for each activity/task. Explicitly assign responsibility for identified software work products and activities.

  - Identify the functional reporting relationships within a project and refer it to Project Organization Chart based on resource requirements.

  - Identify Team Members. The team members should be identified based on the skill requirements, their experience and availability. Try to map each role to a member and one member may have multiple roles. The identified team members shall be aware of their roles, responsibilities, authority and value of QA Member in the project team.

  - List the assumptions for planning the project. These must include all items, which are not within the control of the Project Manager and may have major impact on the project. Clearly distinguish between items within control of XYZ and those external to it.

  - Define Risk Management methodology. Risks associated with cost, schedule, resources and technical aspects of the project should be identified and mitigation strategy adjusted as and when additional information is available. The identified risks and their mitigation plans must be tracked on a regular basis.

  - Identify the Development Environment in terms of:

    - Hardware

    - The hardware needs are to be identified in terms of processing power, number of nodes and type of hardware.

    - Networking

    - Networking capabilities, in terms of data traffic, testing requirements need to be identified.

    - System software and Development tools

    - System software and development tools, based on the project requirements need to be identified along with the number of copies required.

    - Infrastructure

  - Identify the Testing Environment in terms of:

    - Hardware

    - The hardware needs are to be identified in terms of processing power, number of nodes and type of hardware.

    - Networking

    - Networking capabilities, in terms of data traffic, testing requirements need to be identified.

    - System software and Development tools

    - System software and development tools, based on the project requirements need to be identified along with the number of copies required.

    - Infrastructure

  - Identify the list of items to be backed up along with the frequency of backup. This must be clearly documented in the Project Plan.

  - Training Prerequisite, if any.

    - The training needs should be identified for each team member along with indication whether it is mandatory or preferred training. The time when the training is required should also be mentioned.

    - The Training in-charge should be informed about the training needs.

  - Identify the technique used for project monitoring and control along with the frequency of preparing Project Status Reports. Refer Project Monitoring and Control Process for details.

  - Identify activities/task within each phase of PLC. These are controllable units for which time and resources can be estimated. For a project the activities/tasks could be detailed as they come closer in time horizon i.e. immediate next phase or activities falling in the next three months.

  - The detailed activities for each phase should also include review dates for each configuration item at the end of every PLC phase.

  - Estimate time required for each activity/task.

  - Identify milestones/ software work product and associate them with criteria so that control points for project monitoring and control are clear.

  - Define project vision, identify all stakeholders, analyze stakeholders and plan how they can be involved in an effective manner.

  - Plan for transition of the project to maintenance at the end of development.

Use a project planning and monitoring tool like MS Project to define these activities/tasks dependencies, critical paths and milestones. Calculate the project schedule by giving a project start date. The schedule should be maintained as Configuration Item. A Configuration Item is any item that affects the quality of the software product, and is also subject to change. They may be technical documents, plans, programs, data etc.

Define Software Quality Plan. This quality plan should include:

- Review check points

- Identify or define the standards to be used for Requirement Analysis

- Identify or define the standards to be used for Design

Coding

- Testing

- Implementation

- Testing strategies and types of testing should be defined.

- Identify the role and responsibility of the person for acceptance testing.

- Quality Assurance and Quality Control roles must be clearly identified.

- Define the frequency of SQA process and product audits. Normally PQA activities will not be reviewed with customer’s QA members, however if required in a project, review of PQA activities with customer QA members will be mentioned in the PQA section of the Project Plan.

Prepare the Software Configuration Management Plan (may be a part of PP) according to the Software Configuration Management Process.

Prepare metrics plan according to the Metrics process and the PMP template.

Organize and conduct a formal project kick off meeting to initiate the project and may also invite the members of other project groups / head of support functions like HR, Quality assurance, etc. In the kickoff meeting draft Project management plan is presented by the PM and the project’s proposed commitments like technical goals/ objectives/schedule/resources/processes, etc. is discussed.

- Roles and responsibilities with respect to project for every member attending the meeting should be clarified

- The commitments made to the individuals and groups external to the organization, if any, are discussed with Senior Management and documented in the Project Plan

- Critical dependencies between Project scope of work and the resources are identified and discussed.

The Project Plan will be reviewed, base lined after getting approval from senior management.

## Outputs

- Base lined Project Plan/Charter.

## Exit Criteria

- Base lined Project Plan/Charter.

## Formats & Guidelines

- Project Plan/Charter template

- Estimation Sheet

## References

- Estimation Process

- Configuration Management process

- Software development Life Cycle Guidelines

# Project Monitoring and Control

## Introduction

The project plan provides a road map for a software project manager. As the project execution begins, the project manager should focus on monitoring and controlling the project. The scope of this process is to monitor the project progress, analyze the project variance, manage the resources and project schedule and prepare periodic reports. MS-Project may be utilized to prepare the project schedule and to track the project. This is an umbrella activity and is carried out throughout the life cycle of the project.

## Glossary of Terms

- PSR: Project Status Report

## Entry Criteria

- Periodically - project monitoring as mentioned in the Project Plan

- When there are changes to scope/requirements of the project

- When there are changes to effort

## Inputs

One or more of the following:

- Base lined Project Plan

- Data from Team members

- Changes to the project scope/schedule/resources

## Roles and Responsibilities

- Project Manager to make the Project Status Report and conduct project team meetings.

- Senior management to review the periodic project status reports.

## Tasks

## Project Progress Monitoring

The progress of the project is monitored on the basis of the Project Plan. Timesheets and Project Review Meetings with the team members are also used to monitor the progress of the project. The Project Team Meetings will be conducted on a periodic basis (at least monthly)/ at the end of every phase. In addition to this, Project Manager can also conduct a special Project Team Meeting in case of any specific need.  Project Manager also reviews the progress of the project at the end of identified milestones. The Project Team Meetings (between the Project Manager and the team members) should include the following:

- Status of technical activities.

- Requirements management

- Software Quality Assurance activities.

- Software Configuration Management activities

- Support required from other groups

- Status of risks

- Any other critical resources required for the project

- Status of project deliverables and changes to deliverables.

## Project tracking:

- Collect data based on timesheets Project Review Meetings with the team members. Based on this data, the project schedule updated with actual data.

- Track the planned estimates for size, effort and cost against actual throughout the Project Life Cycle. Corrective actions are taken as appropriate.

- Project planned technical activities are tracked against the actual. The critical dependencies and critical paths in schedule is updated accordingly with the revised planned dates of the activities.

- Any changes to the allocated requirements are tracked according to Configuration Management Process.

- The metrics data for the project is tracked regularly throughout the project life cycle with the help of metrics data sheets. On a periodic basis the PM prepares the metrics data sheet and submits it to the QA Group. At the project level, PM analyses the metrics data and takes corrective actions accordingly.

- In addition to variance and delivery related issues, issues related to safety, health, environment will also be tracked

- The changes in the project’s resource (hardware, software, tools, people, training, etc.) /other commitments are tracked and communicated to the project group and respective function heads.

- The software risks associated with cost, resource, schedule and technical aspects are tracked.  Refer to risk management guidelines for details.

- In case of transition of project to operations and support phase, transition plan progress is also monitored.

PM to make Project Status Reports on a monthly basis and submit to senior management.

Depending upon the requirements of the project client specific reports/client meetings are conducted according to the frequency defined in the Project Plan.

Based on the comments of the Senior Management on the Project Status Report plan for corrective actions and accordingly revise the Project Plan. Also fine tune the Monitoring Parameters based on changes in Project Plan, whenever that happens.

At the time of Project Closure Project Manager shall arrange a formal closing meeting among all the team members. Lessons learned from the project (good and bad), especially those likely to be of use in future to the organization are emphasized and documented in post project analysis form.

All the project-related information shall be archived properly. Proper backups shall be taken and the retention period should be defined.

All the software planning data, re-planning data and the actual measurement data are archived for use by ongoing and future projects. The metrics data sheet is filled up on a fortnightly basis and is submitted to QA Group for storing in measurement repository.

## Milestone Reviews

At the end of each major milestone, the Project Manager sends communication to the key stakeholders including senior management. Thereafter the data is presented in the next project status report and the same is reviewed.

## Outputs

- Project Status Report

- Revised Project Plan

## Exit Criteria

- Project Status Report is made for the period.

- Final exit when Project Status Report is made upon project closure.

## Formats & Guidelines

- Project Status Report-Dev Template

- Project Status Report-Services Template

- Risk Management Guidelines

## References

- Configuration Management Process

- Metrics Process