# Project Status Report

Project: Jal Rekha

Govt. of Madhya Pradesh

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

Revision History

| Version | Date | Description | Prepared by | Reviewed by |
| --- | --- | --- | --- | --- |
| 1.0 | 30th December 2025 | Status report including completed activities, delays, and next steps | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal |

# Project Status Report

| Project Code: MPSEDC/MPSSDI (GIS)/2025/00423 | Project Name: Jal Rekha |
| --- | --- |
| Client: 8, Arera Hills, Bhopal, Madhya Pradesh 462027 |  |
| Business Analyst: Mr. Dheeraj Motiyani | Service Project Manager: Mr. Tapan Khandelwal |
| Planned Activities; Activities Completed; Schedule Variance; Effort Variance; DRE (%). Bharosa Factory Testing Mobile; Completed; On Schedule; Within Effort; 75%. Bharosa Factory Testing CR Report View; Completed; On Schedule; Within Effort; 67%. Material Testing GM Contractor login; Completed; On Schedule; Within Effort; 80%. Material Testing FE Login; Completed; On Schedule; Within Effort; 83%. O&M Billing module – CR _ Contractor Login; In progress; On Schedule; Within Effort; 78%. FHTC Module – CR FE Reports; Completed; On Schedule; Within Effort; 67%. O&M Billing & Dhara - Security Vulnerability - Sonarcube & SVN; Completed; On Schedule; Within Effort; 100% & 75%. Nirmal Raw Water CR; Completed; On Schedule; Within Effort; 77%. Sahbhagita CR; Completed; On Schedule; Within Effort; 77%. |

Risk Management:

Risk Management:

| Risk Description | Risk Mitigation Plan | Status |
| --- | --- | --- |
| Anusharavaan RFI stage updations and report modifications may cause incorrect approval status or missing RFI records across schemes. | Perform peer review of all query changes, validate RFI reports (Pending/In-Progress/Approved) with sample schemes, and maintain rollback script to previous RFI logic along with manual tracking sheet for critical RFIs. | Closed |
| Bharosa Factory Testing Web CR may lead to incomplete or wrongly mapped factory test details (components, quantities, failures, documents). | Use comprehensive test scenarios for all component/sub-component combinations, review DB design and mappings, and allow interim capture of inspection results in controlled Excel template for critical factories. | Closed |
| Bharosa Factory Testing Mobile changes (draft, APIs, history) may fail in production causing interruption in on-site inspections. | Conduct end-to-end testing on staging, run pilot rollout with limited FEs, monitor via logs, and provide fallback to web entry at PIU office if mobile submission fails. | Closed |
| Bharosa report view CR (web and mobile) may produce inconsistent summary counts or wrong TPIA assignment visibility. | Cross-verify report outputs with DB queries, align functions used by both channels, and share reconciled “official” factory testing summary from DB for audit until reports stabilize. | Closed |
| New Material Testing GM/Contractor workflow may cause approval bottlenecks or mis-routing of material inspections. | Validate workflow with end-to-end test cases, review routing functions and master configuration, and provide manual override facility at PIU to reassign or force-close stuck inspections. | Closed |
| Material Testing FE mobile login and security fixes may affect geofence validations or data sync leading to missed tests. | Perform security and field testing with sample sites, monitor crashlytics and API logs, and allow FE to capture readings offline and submit later via supervised web interface if app fails. | Closed |
| FHTC GM/Contractor and FE report CRs may result in wrong scheme–village mapping or Samagra linkage impacting beneficiary decisions. | Peer-review SQL, reconcile outputs with earlier reports, validate Samagra multiple-family cases, and maintain cross-checked beneficiary list for critical schemes until new reports are stable. | Closed |
| O&M Billing GM and Contractor CRs may introduce new billing, CPI, or penalty calculation errors across PIUs. | Create detailed test matrix for all billing scenarios, run parallel calculation with prior version, and keep option to revert to previous formula set for one cycle if major defect arises. | Closed |
| Security vulnerability fixes (SonarCube/SVN, encryption, XSS) in O&M and Dhara may cause regression or performance issues. | Deploy in batches with regression pack, monitor DB and app performance post-release, and keep ability to toggle specific security rule or rollback DB package in coordination with security team. | Closed |
| Dhara CR reports and meter-mapping changes may produce inconsistent water-supply analytics for some schemes. | Validate reports (DWSR, MWSR, UFW etc.) against sampled ground data, run peer review on queries, and provide access to legacy report version for cross-verification during first month. | Closed |
| Nirmal WTP/OHT/Beneficiary and Raw-water report CRs may impact report performance and correctness across multiple drill-downs. | Optimize and index heavy queries, roll out complex reports in stages with monitoring, and offer CSV export and offline analysis if on-screen report fails for very large datasets. | Closed |
| Sahbhagita report and approval-flow CRs may misrepresent NGO performance or cause video upload/approval failures. | Run end-to-end NGO workflow scenarios, verify Approved/Rejected/No-Action counts with sample data, and use temporary manual consolidation of NGO progress if report discrepancies are found. | Closed |

Quantitative Information:

| AS-IS | Productivity | Code_Rate | Test_Rate |
| --- | --- | --- | --- |
| Mean | 0.1668 | 0.2606 | 1.0753 |
| SD | 0.005 | 0.021 | 0.064 |
| UCL | 0.18312 | 0.325 | 0.6918 |
| LCL | 0.15025 | 0.1961 | 0.3083 |
| Target | Productivity |  |  |
| Mean | 0.18 |  |  |
| SD | 0.05 |  |  |
| What if | Productivity | Code_Rate | Test_Rate |
| Mean | 0.17929 | 0.32 | 0.7 |
| SD | 0.050 | 0.050 | 0.050 |
| USL | 0.32929 | 0.47 | 0.85 |
| LSL | 0.02929 | 0.17 | 0.55 |

CYCLE TIME :

| AS-IS | Cycle time | Code_CT | Test_CT |
| --- | --- | --- | --- |
| Mean | 0.8012 | 0.3141 | 0.1876 |
| SD | 0.117 | 0.086 | 0.059 |
| UCL | 1.1518 | 0.5709 | 0.3643 |
| LCL | 0.4506 | 0.0573 | 0.011 |
| Target | Cycle time |  |  |
| Mean | 0.72108 |  |  |
| SD | 0.25 |  |  |
| What if | Cycle time | Code_CT | Test_CT |
| Mean | 0.72402 | 0.25 | 0.17 |
| SD | 0.25 | 0.1 | 0.5 |
| USL | 1.47402 | 0.55 | 1.67 |
| LSL | -0.02598 | -0.05 | -1.33 |

DRE:

| AS-IS | DRE | Code Review Per Size |
| --- | --- | --- |
| Mean | 0.778 | 0.1992 |
| SD | 0.086 | 0.062 |
| UCL | 1.0368 | 0.384 |
| LCL | 0.5197 | 0.0145 |
| Target | DRE |  |
| Mean | 0.80 |  |
| SD | 0.10 |  |
| What if | DRE | Code Review Per Size |
| Mean | 0.793 | 0.22 |
| SD | 0.1 | 0.05 |
| USL | 1.09348 | 0.37 |
| LSL | 0.49348 | 0.07 |

| Completed Modules | 8 | 8 | All listed live modules delivered |
| --- | --- | --- | --- |
| In-Progress Tasks | 1 | 1 | Targeted for completion by 31.12.2025 |
| Prepared by: Mr. Dheeraj Motiyani, Sr. Business Analyst, MPSeDC |  |  | Date: |
| Reviewed by: Project Manager, Mr. Tapan Khandelwal |  |  | Date: |
| Review Comments: Project is progressing steadily. Some modules are delayed due to external dependencies (Play Store, infra approval). Timely follow-up advised. |  |  |  |