## Sheet1
Sr. No. | Module Name | Criticality Status | CR | Size USP FP | Planned Effort (Person Hrs) | Actual Effort (Person Hrs) |  | Module Start Date | Module End Date | SRS Start Date | SRS End Date | Design Start Date | Design End Date | Development Start Date | Development End Date | Testing Start Date | Testing End Date | UAT Submission Start Date | UAT Submission End Date | Go Live | Requirement Efforts | Design Actual Efforts | Coding Actual Effort | Code Review Actual Effort | Testing Actual Effort | Requirement Review Efforts | Design Review Efforts | Requirement Review Defects | Design Review Defects | Code Review Defects | Internal Testing Defects | UAT Defects | Production Defects | Issues | Dependencies
1 | Anusharavan | High | No | 0 | 630 | 527 | Planned Actual | 01/02/2024 01/02/2024 | 15/03/2024 19/03/2024 | 01/02/2024 01/02/2024 | 09/02/2024 09/02/2024 | 09/02/2026 10/02/2026 | 12/02/2026 11/02/2026 | 12/02/2024 12/02/2024 | 29/02/2024 08/03/2024 | 11/03/2024 11/03/2024 | 15/03/2024 19/03/2024 | 20/03/2024 20/03/2024 | 25/03/2024 27/03/2024 | 28/03/2024 28/03/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 1
2 | CMMI Statistical Analysis | Medium | No | 0 | 0 | 0 | Planned Actual | 31/01/2026 01/02/2026 |  | 31/01/2026 01/02/2026 | 02/02/2026 02/02/2026 | 03/02/2026 03/02/2026 | 04/02/2026 04/02/2026 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Dhara Change Request - FE / Mobile User | Not defined | Yes | 0 | 0 | 0 | Planned Actual | 12/08/2025 13/08/2025 | 24/08/2025 24/08/2025 | 12/08/2025 13/08/2025 | 16/08/2025 16/08/2025 | 14/08/2025 15/08/2025 | 18/08/2025 18/08/2025 | 17/08/2025 18/08/2025 | 24/08/2025 24/08/2025 | 23/08/2025 24/08/2025 | 24/08/2025 24/08/2025 | 23/08/2025 24/08/2025 | 24/08/2025 24/08/2025 | 24/08/2025 28/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Bharosa Factory Testing - Web | Medium | No | 5 | 637 | 570.5 | Planned Actual | 09/10/2025 10/10/2025 | 16/10/2025 16/10/2025 | 09/10/2025 10/10/2025 | 11/10/2025 11/10/2025 | 11/10/2025 11/10/2025 | 12/10/2025 12/10/2025 | 13/10/2025 13/10/2025 | 15/10/2025 15/10/2025 | 14/10/2025 15/10/2025 | 16/10/2025 16/10/2025 | 14/10/2025 15/10/2025 | 16/10/2025 16/10/2025 | 17/10/2025 17/10/2025 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0
5 | Dhara TL Change request | Not defined | No | 0 | 0 | 0 | Planned Actual | 04/06/2025 07/04/2025 | 12/04/2025 12/04/2025 | 04/06/2025 07/04/2025 | 08/04/2025 08/04/2025 | 07/04/2025 08/04/2025 | 09/04/2025 09/04/2025 | 07/04/2025 08/04/2025 | 10/04/2025 10/04/2025 | 09/04/2025 11/04/2025 | 12/04/2025 12/04/2025 | 10/04/2025 11/04/2025 | 12/04/2025 12/04/2025 | 11/04/2025 12/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1) Change Reading entries - All options provided to TL also after FE
6 | Nirmal Change request - WTP, OHT Report | Medium | Yes | 0 | 0 | 0 | Planned Actual | 08/07/2025 09/07/2025 | 14/07/2025 14/07/2025 | 08/07/2025 09/07/2025 | 10/07/2025 10/07/2025 | 09/07/2025 10/07/2025 | 11/07/2025 11/07/2025 | 11/07/2025 | 14/07/2025 14/07/2025 | 12/07/2025 12/07/2025 | 14/07/2025 14/07/2025 | 11/07/2025 12/07/2025 | 14/07/2025 14/07/2025 | 14/07/2025 14/07/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Dhara Contractor Report View | Not defined | No | 0 | 0 | 0 | Planned Actual | 06/03/2025 04/06/2025 | 08/06/2025 08/06/2025 | 06/03/2025 04/06/2025 | 04/06/2025 04/06/2025 | 03/06/2025 04/06/2025 | 04/06/2025 04/06/2025 | 04/06/2025 05/06/2025 | 06/06/2025 06/06/2025 | 06/06/2025 07/06/2025 | 08/06/2025 08/06/2025 | 06/06/2025 07/06/2025 | 08/06/2025 08/06/2025 | 07/06/2025 08/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | NIrmal - Change request - WTP, OHT, Beneficiary Report | High | Yes | 0 | 0 | 0 | Planned Actual | 03/11/2025 05/11/2025 | 27/11/2025 27/11/2025 | 03/11/2025 05/11/2025 | 08/11/2025 07/11/2025 | 08/11/2025 08/11/2025 | 10/11/2025 10/11/2025 | 10/11/2025 11/11/2025 | 22/11/2025 22/11/2025 | 22/11/2025 23/11/2025 | 27/11/2025 27/11/2025 | 23/11/2025 23/11/2025 | 27/11/2025 27/11/2025 | 26/11/2025 27/11/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Master All Web Reports | Not defined | No | 0 | 0 | 0 | Planned Actual | 15/03/2025 15/03/2025 | 28/03/2025 28/03/2025 | 15/03/2025 15/03/2025 | 16/03/2025 16/03/2025 | 15/03/2025 16/03/2025 | 17/03/2025 17/03/2025 | 16/03/2025 17/03/2025 | 26/03/2025 26/03/2025 | 25/03/2025 26/03/2025 | 28/03/2025 28/03/2025 | 25/03/2025 26/03/2025 | 28/03/2025 28/03/2025 | 29/03/2025 29/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Cube Testing - SQC/TPIA | Medium | No | 3 | 47 | 47 | Planned Actual | 02/04/2026 02/04/2026 | 07/04/2026 07/04/2026 | 02/04/2026 02/04/2026 | 04/04/2026 03/04/2026 | 03/04/2026 03/04/2026 | 05/04/2026 04/04/2026 | 04/04/2026 04/04/2026 | 07/04/2026 06/04/2026 | 06/04/2026 06/04/2026 | 07/04/2026 07/04/2026 | 06/04/2026 06/04/2026 | 07/04/2026 07/04/2026 | 08/04/2026 08/04/2026 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
11 | Department Meetings | Not defined | No | 13 | 78 | 72.5 | Planned Actual | [13 empty] | 38 | 0 | 16 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Master Change Request - FE Pipeline Mater | Medium | Yes | 0 | 0 | 0 | Planned Actual | 04/08/2025 05/08/2025 | 13/08/2025 13/08/2025 | 04/08/2025 05/08/2025 | 06/08/2025 06/08/2025 | 05/08/2025 06/08/2025 | 07/08/2025 07/08/2025 | 07/08/2025 08/08/2025 | 12/08/2025 12/08/2025 | 12/08/2025 12/08/2025 | 13/08/2025 13/08/2025 | 11/08/2025 12/08/2025 | 13/08/2025 13/08/2025 | 13/08/2025 13/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Dhara Security | High | No | 0 | 0 | 0 | Planned Actual | 07/12/2025 10/12/2025 | 18/12/2025 18/12/2025 | 07/12/2025 10/12/2025 | 12/12/2025 11/12/2025 | 10/12/2025 11/12/2025 | 13/11/2025 12/11/2025 | 12/12/2025 13/12/2025 | 17/12/2025 16/12/2025 | 15/12/2025 16/12/2025 | 18/12/2025 18/12/2025 | 16/12/2025 16/12/2025 | 24/12/2025 18/12/2025 | 16/12/2025 18/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Dhara CR - Reports (MWSR,DWSR, UFW) | Medium | Yes | 6 | 157 | 141 | Planned Actual | 13/03/2026 13/03/2026 | 26/03/2026 24/03/2026 | 13/03/2026 13/03/2026 | 16/03/2026 13/03/2026 | 16/03/2026 16/03/2026 | 20/03/2026 19/03/2026 | 20/03/2026 19/03/2026 | 24/03/2026 22/03/2026 | 24/03/2026 22/03/2026 | 26/03/2026 24/03/2026 | 24/03/2026 23/03/2026 | 26/03/2026 25/03/2026 | 27/03/2026 27/03/2026 | 18 | 0 | 107 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Master Change request - Schema | Medium | Yes | 6 | 74 | 73.5 | Planned Actual | 18/03/2026 18/03/2026 | 25/03/2026 24/03/2026 | 18/03/2026 18/03/2026 | 20/03/2026 19/03/2026 | 18/03/2026 18/03/2026 | 20/03/2026 19/03/2026 | 18/03/2026 19/03/2026 | 23/03/2026 19/03/2026 | 23/03/2026 24/03/2026 | 25/03/2026 24/03/2026 | 23/03/2026 24/03/2026 | 25/03/2026 24/03/2026 | 25/03/2026 25/03/2026 | 8 | 0 | 65.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Nirmal FE Mobile | High | No | 0 | 1243 | 1058.5 | Planned Actual | 28/02/2025 28/02/2025 | 15/04/2025 15/04/2025 | 28/02/2025 28/02/2025 | 07/03/2025 07/03/2025 | 06/03/2025 07/03/2025 | 12/03/2025 12/03/2025 | 13/03/2025 14/03/2025 | 05/04/2025 05/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 15/04/2025 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 5
17 | O&M Billing Security | High | No | 0 | 0 | 0 | Planned Actual | 09/12/2025 10/12/2011 | 14/12/2025 14/12/2025 | 09/12/2025 10/12/2011 | 11/12/2025 11/12/2025 | 11/12/2025 11/12/2025 | 12/12/2025 12/12/2025 | 12/12/2025 12/12/2025 | 13/12/2025 13/12/2025 | 13/10/2025 13/10/2025 | 14/12/2025 14/12/2025 | 13/02/2026 13/02/2026 | 14/02/2026 14/02/2026 | 13/12/2025 14/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Anusharavan CR | Medium | Yes | 0 | 39 | 21 | Planned Actual | 08/11/2025 11/11/2025 | 20/11/2025 20/11/2025 | 08/11/2025 11/11/2025 | 19/11/2025 12/11/2025 | 11/11/2025 12/11/2025 | 13/11/2025 13/11/2025 | 12/11/2025 14/11/2025 | 17/11/2025 17/11/2025 | 16/11/2025 18/11/2025 | 20/11/2025 20/11/2025 | 17/11/2025 18/11/2025 | 20/11/2025 20/11/2025 | 18/11/2025 20/11/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Sopan Sopan Document Upload & Chat | Not defined | No | 0 | 0 | 0 | Planned Actual | 05/01/2025 02/05/2025 | 16/05/2025 16/05/2025 | 05/01/2025 02/05/2025 | 03/05/2025 03/05/2025 | 02/05/2025 03/05/2025 | 04/05/2025 04/05/2025 | 03/05/2025 04/05/2025 | 12/05/2025 12/05/2025 | 12/05/2025 13/05/2025 | 16/05/2025 16/05/2025 | 12/05/2025 13/05/2025 | 16/05/2025 16/05/2025 | 13/05/2025 16/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Bharosa CR Factory Testing Web | High | Yes | 3 | 28 | 24 | Planned Actual | 01/11/2025 03/11/2025 | 25/11/2025 25/11/2025 | 01/11/2025 03/11/2025 | 06/11/2025 06/11/2025 | 06/11/2025 06/11/2025 | 09/11/2025 09/11/2025 | 09/11/2025 10/11/2025 | 20/11/2025 20/11/2025 | 20/11/2025 21/11/2025 | 25/11/2025 25/11/2025 | 20/11/2025 21/11/2025 | 26/11/2025 25/11/2025 | 26/11/2025 26/11/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Master CR - Scheme Village & OHT Master | High | Yes | 3 | 140 | 140 | Planned Actual | 11/03/2026 11/03/2026 | 19/03/2026 19/03/2026 | 11/03/2026 11/03/2026 | 13/03/2026 12/03/2026 | 13/03/2026 12/03/2026 | 16/03/2026 13/03/2026 | 13/03/2026 13/03/2026 | 17/03/2026 16/03/2026 | 16/03/2026 17/03/2026 | 19/03/2026 19/03/2026 | 20/03/2026 20/03/2026 | 20/03/2026 20/03/2026 | 22/03/2026 22/03/2026 | 10 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Sahbhagita Change Request -GM / PM | Medium | Yes | 0 | 0 | 0 | Planned Actual | 15/10/2025 15/10/2025 | 22/10/2025 22/10/2025 | 15/10/2025 15/10/2025 | 16/10/2025 16/10/2025 | 16/10/2025 17/10/2025 | 18/10/2025 18/10/2025 | 18/10/2025 19/10/2025 | 21/10/2025 21/10/2025 | 19/10/2025 20/10/2025 | 22/10/2025 22/10/2025 | 19/10/2025 20/10/2025 | 22/10/2025 22/10/2025 | 20/10/2025 22/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Daily Inspection | Medium | No | 0 | 104 | 88 | Planned Actual | 25/12/2023 25/12/2023 | 16/02/2024 16/02/2024 | 25/12/2023 25/12/2023 | 05/01/2024 05/01/2024 |  |  | 08/02/2024 08/02/2024 | 13/02/2024 13/02/2024 | 14/02/2024 14/02/2024 | 16/02/2024 16/02/2024 | 19/02/2024 19/02/2024 | 21/02/2024 23/02/2024 | 26/02/2024 28/02/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
24 | FHTC (Functional Household Tap Connection) FE Reports | Medium | No | 0 | 547 | 475 | Planned Actual | 18/08/2025 18/08/2025 | 27/09/2025 26/09/2025 | 18/08/2025 18/08/2025 | 22/08/2025 22/08/2025 | 21/08/2025 23/08/2025 | 26/08/2025 26/08/2025 | 27/08/2025 29/08/2025 | 13/09/2025 13/09/2025 | 18/09/2025 19/09/2025 | 27/09/2025 26/09/2025 | 17/09/2025 19/09/2025 | 26/09/2025 26/09/2025 | 26/02/2026 26/02/2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1
25 | Sopan Contractor | High | No | 0 | 1612 | 1387.5 | Planned Actual | 25/03/2025 28/03/2025 | 30/04/2025 30/04/2025 | 25/03/2025 28/03/2025 | 31/03/2025 31/03/2025 | 01/04/2025 01/04/2025 | 04/04/2025 04/04/2025 | 04/04/2025 05/04/2025 | 22/04/2025 22/04/2025 | 22/04/2025 23/04/2025 | 30/04/2025 30/04/2025 | 22/04/2025 23/04/2025 | 30/04/2025 30/04/2025 | 23/04/2025 30/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 2
26 | Nirmal Change request | Not defined | Yes | 0 | 0 | 0 | Planned Actual | 13/05/2025 13/05/2025 | 26/05/2025 26/05/2025 | 13/05/2025 13/05/2025 | 14/05/2025 14/05/2025 | 14/05/2025 15/05/2025 | 16/05/2025 16/05/2025 | 17/05/2025 17/05/2025 | 23/05/2025 23/05/2025 | 23/05/2025 24/05/2025 | 26/05/2025 26/05/2025 | 23/05/2025 24/05/2025 | 26/05/2025 26/05/2025 | 26/05/2025 26/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Bharosa Factory Testing Mobile | Not defined | No | 0 | 0 | 0 | Planned Actual | 20/10/2025 22/10/2025 | 30/10/2025 30/10/2025 | 20/10/2025 22/10/2025 | 23/10/2025 23/10/2025 | 23/10/2025 24/10/2025 | 25/10/2025 25/10/2025 | 25/10/2025 25/10/2025 | 28/10/2025 28/10/2025 | 27/10/2025 28/10/2025 | 30/10/2025 30/10/2025 | 27/10/2025 28/10/2025 | 30/10/2025 30/10/2025 | 30/10/2025 30/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | O&M Billing - Change request GM | High | Yes | 6 | 51 | 50 | Planned Actual | 02/11/2025 06/11/2025 | 22/11/2025 22/11/2025 | 02/11/2025 06/11/2025 | 08/11/2025 08/11/2025 | 07/11/2025 08/11/2025 | 10/11/2025 10/11/2025 | 13/11/2025 13/11/2025 | 19/11/2025 19/11/2025 | 19/11/2025 20/11/2025 | 22/11/2025 22/11/2025 | 20/11/2025 20/11/2025 | 24/11/2025 22/11/2025 | 21/11/2025 22/11/2025 | 8 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Dhara Admin | Not defined | No | 0 | 0 | 0 | Planned Actual | 11/02/2025 11/02/2025 | 03/03/2025 03/03/2025 | 11/02/2025 11/02/2025 | 15/02/2025 15/02/2025 | 18/02/2025 | 18/02/2025 18/02/2025 | 18/02/2025 19/02/2025 | 26/02/2025 26/02/2025 | 26/02/2025 27/02/2025 | 03/03/2025 03/03/2025 | 26/02/2025 27/02/2025 | 03/03/2025 03/03/2025 | 27/02/2025 03/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Cube Testing CR | Medium | Yes | 6 | 70 | 70 | Planned Actual | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 30/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 28/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 30/04/2026 30/04/2026 | 2 | 0 | 56 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | NIrmal - Change Request - Raw water Report | High | Yes | 0 | 0 | 0 | Planned Actual | 03/12/2025 05/12/2025 | 14/12/2025 14/12/2025 | 03/12/2025 05/12/2025 | 06/12/2025 06/12/2025 | 06/12/2025 06/12/2025 | 09/12/2025 08/12/2025 | 08/12/2025 08/12/2025 | 12/12/2025 12/12/2025 | 11/12/2025 12/12/2025 | 14/12/2025 14/12/2025 | 11/12/2025 12/12/2025 | 17/12/2025 14/12/2025 | 17/12/2025 17/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | SVS Water Supply Monitoring | Medium | No | 22 | 70 | 67 | Planned Actual | 12/05/2026 12/05/2026 | 21/05/2026 20/05/2026 | 12/05/2026 12/05/2026 | 13/05/2026 12/05/2026 | 13/05/2026 13/05/2026 | 15/05/2026 14/05/2026 | 14/05/2026 14/05/2026 | 18/05/2026 17/05/2026 | 18/05/2026 18/05/2026 | 21/05/2026 20/05/2026 | 18/05/2026 18/05/2026 | 21/05/2026 20/05/2026 | 22/05/2026 22/05/2026 | 25 | 0 | 40 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Cube Testing Requirement | Medium | No | 0 | 200 | 180 | Planned Actual | 23/12/2025 24/12/2025 |  | 23/12/2025 24/12/2025 | 25/12/2025 25/12/2025 | 25/12/2025 26/12/2025 | 27/12/2025 27/12/2025 | 28/12/2025 | [6 empty] | 12 | 0 | 0 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Dhara Change Request - GM PIU User/ TL | Medium | Yes | 6 | 73 | 73 | Planned Actual | 01/07/2025 03/07/2025 | 12/08/2025 12/08/2025 | 01/07/2025 03/07/2025 | 11/07/2025 11/07/2025 | 11/07/2025 12/07/2025 | 18/07/2025 18/07/2025 | 21/07/2025 22/07/2025 | 04/08/2025 04/08/2025 | 01/08/2025 01/08/2025 | 12/08/2025 12/08/2025 | 01/08/2025 01/08/2025 | 12/08/2025 12/08/2025 | 01/08/2025 12/08/2025 | 17 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | O&M Billing Change request O&M Billing | Medium | Yes | 0 | 0 | 0 | Planned Actual | 29/09/2025 29/09/2025 | 31/10/2025 31/10/2025 | 29/09/2025 29/09/2025 | 03/10/2025 03/10/2025 | 03/10/2025 04/10/2025 | 08/10/2025 08/10/2025 | 08/10/2025 09/10/2025 | 21/10/2025 21/10/2025 | 24/10/2025 24/10/2025 | 31/10/2025 31/10/2025 | 23/10/2025 24/10/2025 | 31/10/2025 31/10/2025 | 30/10/2025 31/10/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Dhara GM PIU User Change request | Not defined | Yes | 6 | 30 | 22 | Planned Actual | 08/05/2025 10/05/2025 | 27/05/2025 27/05/2025 | 08/05/2025 10/05/2025 | 11/05/2025 11/05/2025 | 10/05/2025 11/05/2025 | 13/05/2025 13/05/2025 | 13/05/2025 14/05/2025 | 24/05/2025 24/05/2025 | 23/05/2025 24/05/2025 | 27/05/2025 27/05/2025 | 23/05/2025 24/05/2025 | 27/05/2025 27/05/2025 | 24/05/2025 27/05/2025 | 4 | 0 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | AI Module - FHTC Tap Connection | Medium | No | 9 | 96 | 69 | Planned Actual | 08/05/2026 08/05/2026 | 24/05/2026 23/05/2026 | 08/05/2026 08/05/2026 | 12/05/2026 11/05/2026 | 09/05/2026 09/05/2026 | 12/05/2026 11/05/2026 | 11/05/2026 11/05/2026 | 20/05/2026 19/05/2026 | 18/05/2026 18/05/2026 | 24/05/2026 23/05/2026 | 18/05/2026 18/05/2026 | 24/05/2026 23/05/2026 | 25/05/2026 25/05/2026 | 4 | 0 | 60 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Sahbhagita | Medium | No | 0 | 0 | 0 | Planned Actual | 08/09/2025 08/09/2025 | 16/09/2025 16/09/2025 | 08/09/2025 08/09/2025 | 09/09/2025 09/09/2025 | 09/09/2025 10/09/2025 | 11/09/2025 11/09/2025 | 12/09/2025 13/09/2025 | 15/09/2025 15/09/2025 | 14/09/2025 15/09/2025 | 16/09/2025 16/09/2025 | 14/09/2025 15/09/2025 | 16/09/2025 16/09/2025 | 15/09/2025 16/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Sahbhagita PM | Not defined | No | 0 | 0 | 0 | Planned Actual | 22/06/2025 22/06/2025 | 24/06/2025 24/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 24/06/2025 | 24/06/2025 24/06/2025 | 23/06/2025 24/06/2025 | 24/06/2025 24/06/2025 | 23/06/2025 24/06/2025 | 24/06/2025 24/06/2025 | 24/06/2025 24/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Master Change Request - GM / Contractor | Not defined | Yes | 3 | 0 | 0 | Planned Actual | 01/07/2025 01/07/2025 | 19/07/2025 19/07/2025 | 01/07/2025 01/07/2025 | 04/07/2025 04/07/2025 | 04/07/2025 05/07/2025 | 07/07/2025 07/07/2025 | 06/07/2025 07/07/2025 | 15/07/2025 15/07/2025 | 14/07/2025 15/07/2025 | 19/07/2025 19/07/2025 | 14/07/2025 15/07/2025 | 19/07/2025 19/07/2025 | 19/07/2025 19/07/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Data Visualization | Medium | No | 0 | 0 | 0 | Planned Actual | 05/01/2024 06/01/2024 | 31/01/2024 31/01/2024 | 05/01/2024 06/01/2024 | 07/01/2024 07/01/2024 | 08/01/2024 09/01/2024 | 12/01/2024 12/01/2024 | 15/01/2024 15/01/2024 | 25/01/2024 25/01/2024 | 26/01/2024 26/01/2024 | 31/01/2024 31/01/2024 | 03/02/2024 05/02/2024 | 07/02/2024 09/02/2024 | 10/02/2004 12/02/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Master Contractor | Not defined | No | 0 | 0 | 0 | Planned Actual | 03/11/2025 11/03/2025 | 31/03/2025 31/03/2025 | 03/11/2025 11/03/2025 | 12/03/2025 12/03/2025 | 12/03/2025 13/03/2025 | 14/03/2025 14/03/2025 | 14/03/2025 15/03/2025 | 25/03/2025 25/03/2025 | 25/03/2025 26/03/2025 | 31/03/2025 31/03/2025 | 25/03/2025 26/03/2025 | 31/03/2025 31/03/2025 | 31/03/2025 31/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Sahbhagita Report | Medium | No | 0 | 10 | 10 | Planned Actual | 19/11/2025 22/11/2025 | 01/12/2025 01/12/2025 | 19/11/2025 22/11/2025 | 23/11/2025 23/11/2025 | 23/11/2025 23/11/2025 | 24/11/2025 24/11/2025 | 27/11/2025 25/11/2025 | 28/11/2025 28/11/2025 | 01/12/2025 28/11/2025 | 01/12/2025 01/12/2025 | 28/11/2025 28/11/2025 | 03/12/2025 01/12/2025 | 28/11/2025 01/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Master GM | Medium | No | 0 | 941 | 778.5 | Planned Actual | 15/02/2025 18/02/2025 | 08/03/2025 08/03/2025 | 15/02/2025 18/02/2025 | 29/01/2025 20/02/2025 | 19/02/2025 20/02/2025 | 21/02/2025 21/02/2025 | 21/02/2025 22/02/2025 | 05/03/2025 05/03/2025 | 05/03/2025 06/03/2025 | 08/03/2025 08/03/2025 | 05/03/2025 06/03/2025 | 08/03/2025 08/03/2025 | 08/03/2025 08/03/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 1
45 | Dashboard | Medium | No | 3 | 327 | 281.5 | Planned Actual | 28/03/2024 01/04/2024 | 08/04/2024 08/04/2024 | 28/03/2024 01/04/2024 | 01/04/2024 01/04/2024 |  |  | 02/04/2024 02/04/2024 | 05/04/2024 06/04/2024 | 08/04/2024 08/04/2024 | 08/04/2024 08/04/2024 | 09/04/2024 09/04/2024 | 10/04/2024 10/04/2024 | 10/04/2024 11/04/2024 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Sopan Change Request - GM Document Upload & Reports | Medium | Yes | 0 | 0 | 0 | Planned Actual | 11/08/2025 12/08/2025 | 07/09/2025 07/09/2025 | 11/08/2025 12/08/2025 | 13/08/2025 13/08/2025 | 12/08/2025 12/08/2025 | 14/08/2025 14/08/2025 | 19/08/2025 20/08/2025 | 29/08/2025 29/08/2025 | 02/09/2025 03/09/2025 | 07/09/2025 07/09/2025 | 02/09/2025 03/09/2025 | 07/09/2025 07/09/2025 | 07/09/2025 07/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Bharosa CR Factory Testing Mobile | High | Yes | 8 | 25 | 25 | Planned Actual | 18/11/2025 19/11/2025 | 05/12/2025 05/12/2025 | 18/11/2025 19/11/2025 | 20/11/2025 20/11/2025 | 20/11/2025 21/11/2025 | 23/11/2025 23/11/2025 | 24/11/2025 24/11/2025 | 30/11/2025 30/11/2025 | 30/11/2025 01/12/2025 | 05/12/2025 05/12/2025 | 30/11/2025 01/12/2025 | 05/12/2025 05/12/2025 | 04/12/2025 05/12/2025 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Dhara | High | No | 0 | 2657 | 2322 | Planned Actual | 20/09/2024 20/09/2024 | 16/10/2024 16/10/2024 | 20/09/2024 20/09/2024 | 21/09/2024 22/09/2024 | 22/09/2024 22/09/2024 | 24/09/2024 24/09/2024 | 25/09/2024 25/09/2024 | 11/10/2024 11/10/2024 | 14/10/2024 14/10/2024 | 16/10/2024 16/10/2024 | 16/10/2024 17/10/2024 | 21/10/2024 21/10/2024 | 22/10/2024 23/10/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 4 | 6
49 | All Public Reports on Dashboard | Medium | No | 6 | 4 | 4 | Planned Actual | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 13/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 14/05/2026 14/05/2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Dhara GM PIU User | Not defined | No | 0 | 0 | 0 | Planned Actual | 15/02/2025 16/02/2025 | 15/04/2025 15/04/2025 | 15/02/2025 16/02/2025 | 23/02/2025 23/02/2025 | 26/02/2025 27/02/2025 | 03/03/2025 03/03/2025 | 03/03/2025 04/03/2025 | 05/04/2025 05/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 06/04/2025 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | FHTC GM / Contractor Reports | Medium | Yes | 3 | 8 | 8 | Planned Actual | 02/11/2025 04/11/2025 | 14/11/2025 14/11/2025 | 02/11/2025 04/11/2025 | 05/11/2025 05/11/2025 | 04/11/2025 05/11/2025 | 06/11/2025 06/11/2025 | 05/11/2025 06/11/2025 | 11/11/2025 11/11/2025 | 11/11/2025 12/11/2025 | 14/11/2025 14/11/2025 | 11/11/2025 12/11/2025 | 14/11/2025 14/11/2025 | 12/11/2025 14/11/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | Sopan All Web User | Not defined | No | 0 | 0 | 0 | Planned Actual | 28/05/2025 05/06/2025 | 28/06/2025 28/06/2025 | 28/05/2025 05/06/2025 | 07/06/2025 07/06/2025 | 07/06/2025 08/06/2025 | 10/06/2025 10/06/2025 | 10/06/2025 11/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 23/06/2025 | 28/06/2025 28/06/2025 | 22/06/2025 23/06/2025 | 28/06/2025 28/06/2025 | 23/06/2025 28/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Bharosa CR Report View | High | Yes | 0 | 0 | 0 | Planned Actual | 07/12/2025 10/12/2025 | 14/12/2025 14/12/2025 | 07/12/2025 10/12/2025 | 11/12/2025 11/12/2025 | 11/12/2025 11/12/2025 | 12/12/2025 12/12/2025 | 12/12/2025 12/12/2025 | 13/12/2025 13/12/2025 | 13/12/2025 13/12/2025 | 14/12/2025 14/12/2025 | 11/12/2025 13/12/2025 | 14/12/2025 14/12/2025 | 13/12/2025 14/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Cube Testing - GM | Medium | No | 0 | 57 | 51 | Planned Actual | 31/03/2026 31/03/2026 | 10/04/2026 09/04/2026 | 31/03/2026 31/03/2026 | 04/04/2026 03/04/2026 | 03/04/2026 03/04/2026 | 06/04/2026 05/04/2026 | 05/04/2026 06/04/2026 | 08/04/2026 09/04/2026 | 08/04/2026 08/04/2026 | 10/04/2026 09/04/2026 | 08/04/2026 08/04/2026 | 10/04/2026 09/04/2026 | 13/04/2026 13/04/2026 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
55 | User & Role Management | High | No | 0 | 10 | 10 | Planned Actual | 20/11/2024 21/11/2024 | 26/12/2024 26/12/2024 | 20/11/2024 21/11/2024 | 25/11/2024 25/11/2024 | 26/11/2024 27/11/2024 | 30/11/2024 30/11/2024 | 02/12/2024 02/12/2024 | 20/12/2024 20/12/2024 | 23/12/2024 23/12/2024 | 26/12/2024 26/12/2024 | 27/12/2024 27/12/2024 | 31/12/2024 31/12/2024 | 02/01/2025 02/01/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0
56 | Dhara Change Request Reports | Medium | Yes | 3 | 22 | 22 | Planned Actual | 08/11/2025 08/11/2025 | 14/11/2025 13/11/2025 | 08/11/2025 08/11/2025 | 10/11/2025 09/11/2025 | 09/11/2025 09/11/2025 | 11/11/2025 10/11/2025 | 10/11/2025 10/11/2025 | 13/11/2025 12/11/2025 | 12/11/2025 12/11/2025 | 14/11/2025 13/11/2025 | 11/11/2025 12/11/2025 | 14/11/2025 13/11/2025 | 12/11/2025 13/11/2025 | 6 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | FHTC Change request FHTC | Not defined | Yes | 9 | 247 | 247 | Planned Actual | 13/10/2025 14/10/2025 | 29/10/2025 29/10/2025 | 13/10/2025 14/10/2025 | 16/10/2025 16/10/2025 | 15/10/2025 16/10/2025 | 18/10/2025 18/10/2025 | 18/10/2025 19/10/2025 | 24/10/2025 24/10/2025 | 25/10/2025 26/10/2025 | 29/10/2025 29/10/2025 | 25/10/2025 26/10/2025 | 29/10/2025 29/10/2025 | 26/10/2025 29/10/2025 | 1 | 0 | 220 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0
58 | Asset Mapping | High | No | 0 | 987 | 928 | Planned Actual | 01/01/2024 01/01/2024 | 26/01/2024 26/01/2024 | 01/01/2024 01/01/2024 | 02/02/2026 02/01/2024 | 02/01/2024 02/01/2024 | 04/01/2024 03/01/2024 | 02/01/2024 03/01/2024 | 19/01/2024 19/01/2024 | 22/01/2024 22/01/2024 | 26/01/2024 26/01/2024 | 27/01/2024 29/01/2024 | 31/01/2024 05/02/2024 | 06/02/2024 07/02/2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
59 | O&M Billing Contractor | Medium | No | 0 | 0 | 0 | Planned Actual | 01/09/2025 01/09/2025 | 19/09/2025 19/09/2025 | 01/09/2025 01/09/2025 | 03/09/2025 03/09/2025 | 03/09/2025 04/09/2025 | 06/09/2025 06/09/2025 | 05/09/2025 06/09/2025 | 14/09/2025 14/09/2025 | 13/09/2025 14/09/2025 | 19/09/2025 19/09/2025 | 13/09/2025 14/09/2025 | 19/09/2025 19/09/2025 | 14/09/2025 19/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | CMMI Documents | Not defined | No | 5 | 852 | 774.5 | Planned Actual | 02/12/2025 04/12/2025 |  | 02/12/2025 04/12/2025 | 06/12/2025 06/12/2025 | 06/12/2025 07/12/2025 | 09/12/2025 09/12/2025 | [7 empty] | 107 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | Cube Testing - FE | Medium | No | 8 | 132 | 120 | Planned Actual | 09/03/2026 09/03/2026 | 10/04/2026 09/04/2026 | 09/03/2026 09/03/2026 | 14/03/2026 12/03/2026 | 12/03/2026 12/03/2026 | 20/03/2026 19/03/2026 | 20/03/2026 20/03/2026 | 31/03/2026 30/03/2026 | 31/03/2026 31/03/2026 | 10/04/2026 09/04/2026 | 31/03/2026 31/03/2026 | 10/04/2026 09/04/2026 | 11/04/2026 11/04/2026 | 8 | 0 | 62 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
62 | Dhara TL | Not defined | No | 0 | 0 | 0 | Planned Actual | 20/03/2025 21/03/2025 | 05/04/2025 05/04/2025 | 20/03/2025 21/03/2025 | 22/03/2025 22/03/2025 | 22/03/2025 23/03/2025 | 24/03/2025 24/03/2025 | 23/03/2025 25/03/2025 | 02/04/2025 02/04/2025 | 02/04/2025 03/04/2025 | 05/04/2025 05/04/2025 | 02/04/2025 03/04/2025 | 05/04/2025 05/04/2025 | 03/04/2025 05/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | Sahbhagita Change Request | Medium | Yes | 3 | 23 | 23 | Planned Actual | 12/05/2026 12/05/2026 | 14/05/2026 14/05/2026 | 12/05/2026 12/05/2026 | 12/05/2026 12/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 13/05/2026 13/05/2026 | 14/05/2026 14/05/2026 | 15/05/2026 15/05/2026 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | Dhara FE / Mobile User | Not defined | No | 0 | 0 | 0 | Planned Actual | 15/02/2025 16/02/2025 | 15/04/2025 15/04/2025 | 15/02/2025 16/02/2025 | 23/02/2025 23/02/2025 | 26/02/2025 27/02/2025 | 03/03/2025 03/03/2025 | 03/03/2025 04/03/2025 | 05/04/2025 05/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 05/04/2025 06/04/2025 | 15/04/2025 15/04/2025 | 06/04/2025 15/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | O&M Billing - Change Request Contractor | High | Yes | 28 | 259 | 249 | Planned Actual | 27/11/2025 01/12/2025 | 02/01/2026 02/01/2026 | 27/11/2025 01/12/2025 | 04/12/2025 04/12/2025 | 04/12/2025 04/12/2025 | 07/12/2025 07/12/2025 | 09/12/2025 10/12/2025 | 24/12/2025 24/12/2025 | 25/12/2025 26/12/2025 | 02/01/2026 02/01/2026 | 26/12/2025 26/12/2025 | 03/01/2026 02/01/2026 | 07/01/2026 07/01/2026 | 18 | 16 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | Nirmal Change Request - Beneficiary Report | Medium | Yes | 3 | 20 | 20 | Planned Actual | 01/09/2025 03/09/2025 | 08/09/2025 08/09/2025 | 01/09/2025 03/09/2025 | 04/09/2025 04/09/2025 | 03/09/2025 04/09/2025 | 05/09/2025 05/09/2025 | 06/09/2025 06/09/2025 | 07/09/2025 07/09/2025 | 06/09/2025 07/09/2025 | 08/09/2025 08/09/2025 | 06/09/2025 07/09/2025 | 08/09/2025 08/09/2025 | 08/09/2025 08/09/2025 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | Sahbhagita FE | Not defined | No | 0 | 0 | 0 | Planned Actual | 15/06/2025 17/06/2025 | 27/06/2025 27/06/2025 | 15/06/2025 17/06/2025 | 17/06/2025 17/06/2025 | 17/06/2025 18/06/2025 | 19/06/2025 19/06/2025 | 19/06/2025 20/06/2025 | 25/06/2025 25/06/2025 | 25/06/2025 26/06/2025 | 27/06/2025 27/06/2025 | 25/06/2025 26/06/2025 | 27/06/2025 27/06/2025 | 27/06/2025 27/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Material Testing - GM/Contractor Login | Medium | No | 13 | 584 | 471 | Planned Actual | 08/12/2025 12/12/2025 | 30/12/2025 30/12/2025 | 08/12/2025 12/12/2025 | 15/12/2025 15/12/2025 | 14/12/2025 15/12/2025 | 17/12/2025 17/12/2025 | 16/12/2025 17/12/2025 | 25/12/2025 25/12/2025 | 25/12/2025 26/12/2025 | 30/12/2025 30/12/2025 | 25/12/2025 26/12/2025 | 30/12/2025 30/12/2025 | 26/12/2025 30/12/2025 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1
69 | Sopan GM | Not defined | No | 0 | 0 | 0 | Planned Actual | 04/05/2025 07/04/2025 | 10/05/2025 10/05/2025 | 04/05/2025 07/04/2025 | 10/04/2025 10/04/2025 | 10/04/2025 11/04/2025 | 14/04/2025 14/04/2025 | 14/04/2025 15/04/2025 | 03/05/2025 03/05/2025 | 03/05/2025 04/05/2025 | 10/05/2025 10/05/2025 | 03/05/2025 04/05/2025 | 10/05/2025 10/05/2025 | 04/05/2025 10/05/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | Master FE Mobile | Not defined | No | 0 | 0 | 0 | Planned Actual | 10/04/2025 10/04/2025 | 12/04/2025 12/04/2025 | 10/04/2025 10/04/2025 | 11/04/2025 11/04/2025 | 10/04/2025 10/04/2025 | 11/04/2025 11/04/2025 | 11/04/2025 11/04/2025 | 12/04/2025 12/04/2025 | 12/04/2025 12/04/2025 | 12/04/2025 12/04/2025 | 12/04/2025 12/04/2025 | 12/04/2025 12/04/2025 | 12/04/2025 12/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | FHTC CR FE Reports | Medium | Yes | 0 | 0 | 0 | Planned Actual | 01/12/2025 03/12/2025 | 09/12/2025 09/12/2025 | 01/12/2025 03/12/2025 | 04/12/2025 04/12/2025 | 04/12/2025 04/12/2025 | 05/12/2025 05/12/2025 | 04/12/2025 05/12/2025 | 07/12/2025 07/12/2025 | 07/12/2025 07/12/2025 | 09/12/2025 09/12/2025 | 02/12/2025 03/12/2025 | 09/12/2025 09/12/2025 | 03/12/2025 09/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | Sopan Change Request - Contractor (Web / Mobile) | Medium | Yes | 0 | 0 | 0 | Planned Actual | 01/07/2025 01/07/2025 | 04/08/2025 04/08/2025 | 01/07/2025 01/07/2025 | 05/07/2025 05/07/2025 | 05/07/2025 06/07/2025 | 11/07/2025 11/07/2025 | 11/07/2025 12/07/2025 | 26/07/2025 26/07/2025 | 25/07/2025 26/07/2025 | 04/08/2025 04/08/2025 | 25/07/2025 26/07/2025 | 04/08/2025 04/08/2025 | 04/08/2025 04/08/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Sahbhagita GM | Medium | No | 0 | 298 | 258 | Planned Actual | 19/06/2025 17/06/2025 | 23/06/2025 23/06/2025 | 19/06/2025 17/06/2025 | 18/06/2025 18/06/2025 | 17/06/2025 18/06/2025 | 19/06/2025 19/06/2025 | 19/06/2025 19/06/2025 | 22/06/2025 22/06/2025 | 22/06/2025 23/06/2025 | 23/06/2025 23/06/2025 | 22/06/2025 23/06/2025 | 23/06/2025 23/06/2025 | 23/06/2025 23/06/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 3
74 | O&M Billing GM | Medium | No | 10 | 2022 | 1773 | Planned Actual | 28/07/2025 28/07/2025 | 29/08/2025 29/08/2025 | 28/07/2025 28/07/2025 | 03/08/2025 03/08/2025 | 03/08/2025 04/08/2025 | 07/08/2025 07/08/2025 | 06/08/2025 07/08/2025 | 21/08/2025 21/08/2025 | 22/08/2025 22/08/2025 | 29/08/2025 29/08/2025 | 21/08/2025 22/08/2025 | 29/08/2025 29/08/2025 | 29/08/2025 29/08/2025 | 30 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 4 | 0
75 | Dhara Change Request - Admin / Contractor Report View | Not defined | Yes | 0 | 0 | 0 | Planned Actual | 01/09/2025 01/09/2025 | 25/09/2025 25/09/2025 | 01/09/2025 01/09/2025 | 03/09/2025 03/09/2025 | 03/09/2025 04/09/2025 | 06/09/2025 06/09/2025 | 08/09/2025 09/09/2025 | 18/09/2025 18/09/2025 | 19/09/2025 20/09/2025 | 25/09/2025 25/09/2025 | 19/09/2025 20/09/2025 | 25/09/2025 25/09/2025 | 20/09/2025 25/09/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | Material Testing - FE Login | Medium | No | 0 | 30 | 30 | Planned Actual | 17/12/2025 19/12/2025 | 31/12/2025 31/12/2025 | 17/12/2025 19/12/2025 | 21/12/2025 21/12/2025 | 20/12/2025 21/12/2025 | 23/12/2025 23/12/2025 | 22/12/2025 23/12/2025 | 28/12/2025 28/12/2025 | 27/12/2025 28/12/2025 | 31/12/2025 31/12/2025 | 27/12/2025 28/12/2025 | 31/12/2025 31/12/2025 | 28/12/2025 31/12/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | Nirmal Contractor Login | Not defined | No | 0 | 0 | 0 | Planned Actual | 04/02/2025 02/04/2025 | 26/04/2025 26/04/2025 | 04/02/2025 02/04/2025 | 03/04/2025 03/04/2025 | 04/04/2025 04/04/2025 | 07/04/2025 07/04/2025 | 08/04/2025 08/04/2025 | 18/04/2025 18/04/2025 | 19/04/2025 19/04/2025 | 26/04/2025 26/04/2025 | 19/04/2025 19/04/2025 | 26/04/2025 26/04/2025 | 26/04/2025 26/04/2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Cube Testing - Contractor | Medium | No | 3 | 68 | 64 | Planned Actual | 23/03/2026 23/03/2026 | 05/04/2026 04/04/2026 | 23/03/2026 23/03/2026 | 25/03/2026 24/03/2026 | 26/03/2026 26/03/2026 | 29/03/2026 28/03/2026 | 29/03/2026 29/03/2026 | 02/04/2026 01/04/2026 | 01/04/2026 02/04/2026 | 05/04/2026 04/04/2026 | 02/04/2026 03/04/2026 | 07/04/2026 05/04/2026 | 08/04/2026 08/04/2026 | 8 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
79 | Site Security Audit | Medium | No | 3 | 16 | 16 | Planned Actual | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 28/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 28/04/2026 28/04/2026 | 29/04/2026 29/04/2026 | 30/04/2026 30/04/2026 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | O&M Billing Workflow b/w O&M GM & Higher officials | Medium | No | 5 | 27 | 27 | Planned Actual | 20/09/2025 21/09/2025 | 29/09/2025 29/09/2025 | 20/09/2025 21/09/2025 | 22/09/2025 22/09/2025 | 21/09/2025 22/09/2025 | 23/09/2025 23/09/2025 | 22/09/2025 23/09/2025 | 26/09/2025 26/09/2025 | 25/09/2025 26/09/2025 | 29/09/2025 29/09/2025 | 25/09/2025 26/09/2025 | 29/09/2025 29/09/2025 | 26/09/2025 29/09/2025 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Nirmal GM | Not defined | No | 3 | 8 | 8 | Planned Actual | 15/04/2025 15/04/2025 | 21/04/2025 21/04/2025 | 15/04/2025 15/04/2025 | 15/04/2025 15/04/2025 | 16/04/2025 16/04/2025 | 16/04/2025 16/04/2025 | 16/04/2025 17/04/2025 | 19/04/2025 19/04/2025 | 18/04/2025 19/04/2025 | 21/04/2025 21/04/2025 | 18/04/2025 19/04/2025 | 21/04/2025 21/04/2025 | 22/04/2025 22/04/2025 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Sahbhagita Change Request -GM / PM / Reports | Medium | Yes | 3 | 36 | 36 | Planned Actual | 02/12/2025 04/12/2025 | 11/12/2025 11/12/2025 | 02/12/2025 04/12/2025 | 05/12/2025 05/12/2025 | 04/12/2025 05/12/2025 | 06/12/2025 06/12/2025 | 05/12/2025 06/12/2025 | 09/12/2025 09/12/2025 | 08/12/2025 09/12/2025 | 11/12/2025 11/12/2025 | 08/12/2025 09/12/2025 | 11/12/2025 11/12/2025 | 09/12/2025 11/12/2025 | 2 | 0 | 24 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sheet2
Key Milestones
Sr. No. | Module Name | Key Milestones | Planned Date | Actual Date | Criticality | Status
1 | Master GM | 1) Scheme village master data (Link Scheme, PIU, GP, Village) Bulk Meter village & O&M of village Mapped 2) Edit or deactivate Master records of villages 3) OHT village master - a) associate village mapping of the scheme b) Component data goes to Dhara for assignment to the FE 4) WTP Meter mapping | 03/10/2025 | 08/03/2025 | Medium - Important but manageable risks | Delivered On Scheduled
2 | Jal Samadhan | This module allows citizens to raise complaints regarding water supply issues, water clarity, or other related concerns. It facilitates efficient grievance redressal, ensuring timely resolution of complaints. | 24/04/2026 | 16/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled
3 | Dhara Admin | 1) Register Meter under a Scheme. 2) Form design validation with scheme/asset linking. 3) Bulk data Upload of Meter Excel parsing. 4) Validation rules, and multiple meter entry creation. 5) View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report | 03/05/2025 | 01/03/2025 | High - Requires urgent attention | Delivered On Scheduled
4 | Dhara GM PIU User | 1) The PIU GM maps villages and bulk meters related to the OHT in the master and adds the WTP, Intake meter. 2) Assign Bulk Meter to the FE under a scheme 3) Assign OHT component meter-reading tasks to Field Engineers under a scheme. 4) Assign WTP Components meter-reading tasks to Field Engineers under a scheme. 5) Verify field data reading for each component per day. 6) Check and Edit the reading entries. 7) Approve readings with comments. 8) Development of Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report. 9) OHT Component delete option given PIU GM ID | 05/04/2025 | 03/04/2025 | High - Requires urgent attention | Delivered On Scheduled
5 | Asset Mapping | Users shall enabled to reposition OHTs, Intakes, and WTPs to their correct geographic locations, in case of discrepancies. | 27/06/2025 | 24/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
6 | Sahbhagita GM | 1) GM map ISA Project Managers (PMs) to Schemes | 24/06/2025 | 20/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
7 | Master All Web Reports | 1) Reports a) CWGM, b) CWPM c) RWPM d) Distribution Pipe 2) Scheme Covered Villages Report | 30/03/2025 | 28/03/2025 | High - Requires urgent attention | Delivered On Scheduled
8 | Dhara Change Request Reports | 1) Report Format change and Drill down functionality. 2) Change Reading entries - Options provided to GM also after TL & FE. 3) Intake WTP OHT Range functionality for mobile development | 30/05/2025 | 27/05/2025 | High - Requires urgent attention | Delivered On Scheduled
9 | Master Contractor | 1) Pipe line master details - shown in anusharan module generate request for RFI to contractor (on Mobile) 2) Contractor upload pipeline master component data as per the defiined schema. 3) The GM approves or edits the pipeline master data. | 04/05/2025 | 31/03/2025 | High - Requires urgent attention | Delivered On Scheduled
10 | Asset Mapping | Feature to delete and rename OHTs if required | 26/05/2025 | 26/05/2025 | Medium - Important but manageable risks | Delivered On Scheduled
11 | Sopan Sopan Document Upload & Chat | 1) Upload Panchnama and other supporting documents & Submit 2) Chat functionality with Contractor | 20/05/2025 | 16/05/2025 | Medium - Important but manageable risks | Delivered On Scheduled
12 | Sopan GM | 1) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date OHT 2) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date WTP 3) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date Intake 4) Check all Scheme & component details, Freeze Actual plan date & Fill actual work start and end date IPS | 14/05/2025 | 10/05/2025 | High - Requires urgent attention | Delivered On Scheduled
13 | Dhara TL | 1) The entries are edited by TL if entry are filled wrong by FE . 2) The entries filled by the FE are verified and approved by the TL, and then forwarded to the GM 3) View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report | 04/10/2025 | 05/04/2025 | High - Requires urgent attention | Delivered On Scheduled
14 | Sopan Contractor | 1) OHT Work plan start, plan end date against each stage and Submit 2) Intake work plan start, plan end date against each stage and Submit 3) WTP work plan start, plan end date against each stage and Submit 4) IPS work plan start, plan end date against each stage and Submit | 05/05/2025 | 30/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
15 | Sopan Contractor | 1) Conventional & Precast separate option provided for OHT Work plan start, plan end date on each stage 2) Delete option provided for wrong entry in conventional & then entry in precast OHT 3) Changes in WTP and IPS Forms at each stage 4) Mobile apk changed for - OHT completed in Sopan will not be shown in RFI request Anusharavan module for contractor login 5) Sopan IPS Component updated | 10/08/2025 | 04/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
16 | Sopan Change Request - GM Document Upload & Reports | 1) If contractor filled wrong details then GM can edit and can update actual date and freeze option at each stage 2) Drill down functionality, Plan date and actual date by each OHT wise in the reports - Mapping, Monitoring, & Report 3) Drill down functionality, Plan date and actual date by each WTP wise in the reports - Mapping, Monitoring, & Report 4) Drill down functionality, Plan date and actual date by each Intake wise in the reports - Mapping, Monitoring, & Report 5) Prepare the report with total Panchanama count and total uploaded design data 6) Changes in Panchnama and design drawing separated into pdf format with upload feature 7) CMMI Documentation | 06/09/2025 | 05/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
17 | Nirmal FE Mobile | 1) FE Login - Geofence components for app - API 2) FE login - Collect Water Samples from components 3) FE login - Submit sample and send it to contractor offline 4) FE collect the sample of Intake, WTP, OHT and Benificary | 25/04/2025 | 15/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
18 | Sopan Contractor | New Features : Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | 12/08/2025 | 07/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
19 | Dhara Change Request Reports | 1) Change Reading entries - All options provided to TL also after FE | 04/12/2025 | 12/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
20 | Dhara | Change Request - Dhara Reports 1) Redesigning the pages of Jal Rekha 2) View Updated / Changed Water Supply Reports - a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report 3) Updating Meter Mapping as per Department 4) work on dhara module wtp to village meter reading | 15/11/2025 | 13/11/2025 | Medium - Important but manageable risks | Delivered On Scheduled
21 | Anusharavan CR | RFI Stage Updations and Reports Modifications 1) Redesigning the new inner pages of Jal Rekha 2) RFI : MBR Changes for schemes 3) Update Inline Query to Funtion & Query Type Changes 4) Work On RFI Report - Pending, In Progress or send for approval 5) Database-level analysis and design for activity approval workflow. 6) Anusharavan Report Modification | 22/11/2025 | 20/11/2025 | Medium - Important but manageable risks | Delivered On Scheduled
22 | Bharosa Factory Testing - Web | Bharosa CR - Factory Testing Web 1) Redesigning the inner pages of Jal Rekha 2) Wireframe creation for Bharosa module Factory testing 3) Create Web Page for Bharosa FactoryTesting Survey Inspection with All Details 4) Adding additional list of Factory Testing details into - Component, Sub component, Ordered Quantity, Inspected Quantity, Quantity Failed, Remarks and relevant documents, & images for Inspection 8) Development in Bharosa Module Add New option in all Subcomponent and Items and mapped data 9) Creating Test Scenarios for BHAROSA web 10) Creating new function and table in bharosa web module 11) Database Table/ Function Creation 12) Bug fixing at the database level and mapping of new master data records. | 26/11/2025 | 25/11/2025 | High - Requires urgent attention | Delivered On Scheduled
23 | Bharosa Factory Testing Mobile | Bharosa CR - Factory Testing Mobile 1) Factory testing screens design 2) Factory Testing - Draft Activity 3) Add Scheme In Factory Testing 4) Factory testing api integration 5) Bharosa Factory testing and production deployment 6) Factory testing history api integration for production 7) Bharosa FE login issue & Bharosa Module new Mobile Insert API discussion and creation 8) Create Bharosa Module Insert and Get API foe mobile Application | 05/12/2025 | 01/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
24 | Bharosa CR Report View | CR - Report View 1) Change request in Bharosa Module (Factory Testing) Mobile report 2) Change Request in Bharosa Module Web Report 3) Bharosa Assign components to TPIA function discussion with database team. 4) Change request on existing functions in Database | 17/12/2025 | 14/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
25 | Material Testing - GM/Contractor Login | GM/Contractor Login 1) Contractor send request to GM for approval. GM can approve or reject 2) GM send to SQC and SQC assign to FE for testing of Material 3) FE submitted inspection send to GM for approval. GM can approve or reject 4) Web UI design and API integration 5) Database schema, master tables design & Function development 6) Material Testing Web Report namely Pending At PiU 7) Development of Insert API for Material Testing and Check on Postman and Database values 8) Test Case Creation-Contractor Workflow(Material Testing) 9) Functions to fetch - ESR details, Scheme list, ESR list , User list and scheme list | 02/01/2026 | 30/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
26 | Material Testing - GM/Contractor Login | FE Login 1) FE Login can perform Material testing at Geofenced Lat/Long of site. 2) Mobile FE login UI design and API integration 3) FE login - Database schema, master tables design & Function development 4) Sync API creation for Material Testing for multiple dropdown. 5) Test Case Creation-Contractor Workflow(Material Testing) 6) Cross-Site Scripting: DOM Bug fixing in Jal Rekha (On JS files) for Security Audit | 02/01/2026 | 31/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
27 | FHTC (Functional Household Tap Connection) FE Reports | GM / Contractor Reports 1) Created test scenarios for FETCH Module(FE and GM LOGIN) 2) Report Updates Required for GM and Contractor Modules 3) Analyzed and fixed SQL queries & updated database table and function 4) Performed PostgreSQL query development and optimization. | 19/11/2025 | 14/11/2025 | Medium - Important but manageable risks | Delivered On Scheduled
28 | FHTC (Functional Household Tap Connection) FE Reports | CR - FE / Reports 1) FE Login - Report Modification 2) New web page creation/ Modification 3) FHTC Bug fixing for village scheme mapping 4) FHTC UI Change On Survey Page as requested from department 5) Samagra multiple family id issue | 13/12/2025 | 09/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
29 | Cube Testing Requirement | Cube Testing Requirement & Sanitization 1) Cube testing requirement gathering and analysis 2) Cube testing wireframe creation | 31/12/2025 | 30/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
30 | O&M Billing GM | Change Request GM 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit 2) Kapil id should be renamed to - "GM PIU O&M" 3) For 1 village multiple time mapping should not be shown 4) GM PIU and contractor name not coming correctly 5) Agreement value column name and data should come correctly 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | 28/11/2025 | 22/11/2025 | High - Requires urgent attention | Delivered On Scheduled
31 | O&M Billing - Change Request Contractor | Change Request Contractor 1) Contractor -Billing 2) CPI Base year and month calculation happen instantly 3) Remark should come at the end in below report columns 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report 5) Complaint resolved date - it is "Resolved" word please check 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement 7) Event before 48 hours should not get edited and count increase happen after 48 hours 8) Reason for relaxation only become mandatory after clicking YES 9) Penalty Relaxation spelling correct it 10) All above fields should be visible in below reports and upload documents show in report 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label 14) Bulk User MWSR , Dhara Report To Implement 15) Implement New Functionality & New Pages Database Side | 07/01/2026 | 02/01/2026 | High - Requires urgent attention | Delivered On Scheduled
32 | Nirmal FE Mobile | Change request - WTP, OHT, Beneficiary Report 1) WTP Report parameter changes 2) Nirmal Reports (Beneficiary, OHT, WTP, RawWater) 3) Change Request in Nirmal Reports all OHT,WTP and Raw Water addition of 2 more drill down 4) Beneficiary Report water test report changes at different parameter level 5) Change Request in Beneficiary Report addition of Action remarks 6) Change Request in Nirmal Reports addition of 2 more drill down Beneficiary Water Test report 7) Increase filter of components in existing filter, show reports accordingly. 8) Show OHT with OHT village mapping in reports. 9) Addition of Action remarks by contractor and GM in drill down reports . UI Changes of Reports on link button click, UI Changes for Action Remarks as per chat box and one more drill down reports to be shown for "still pending test cases". 10) Popup tables are applied on action button for both contractor and GM. 11) Search options & comments box on all reports 12) Removal of Inline queries from Jal Nigam Service Database class for Web all pages and check them in Postman as well check the Jalnigam Portal. Almost 25 inline queries are removed and checked in postman. 13) New Query Type in the Nirmal module to fetch Component Master Details – Based on Scheme ID And PIU ID 14) New query in jalnigam nirmal data maping - WTP_Samples_Tested_Detail – To display detailed testing data for samples collected from Water Treatment Plants (WTP). 15) New query type to get - Beneficiary_Testing_Report_Tested_List – To fetch tested water sample details collected from beneficiary points and same with OHT | 30/11/2025 | 27/11/2025 | High - Requires urgent attention | Delivered On Scheduled
33 | Nirmal FE Mobile | Raw water Report 1) Range facility provided for Date option 2) 5) Nirmal Raw water testing and WTP reports discussion and creation on Web 2) According to Water sample ID provided search option in the report 3) Nirmal Raw water data mapping - RawWater_Samples_Tested_Detail – To fetch testing details of raw water samples before treatment. 6) Addition of 2 columns and drill down also for the same passed and failed records. 7) Addition of bell icon on all comments popup. Text change from remarks to FE Remarks in all reports and all popup. 8) Search options & comments box on all reports 9) Contractor/FE login - WTP, Intake buffer increase to 200 meter for Raw water sample collection. | 17/12/2025 | 14/12/2025 | High - Requires urgent attention | Delivered On Scheduled
34 | Dhara | Security Vulnerability - Sonarcube & SVN 1) Play console crashlytics & vulnerability 2) Testing- All Module UI 3) Created and updated PostgreSQL Queries . 4) Implement Password Encryption in jal rekha database for all users 5) Function/SP development and modification 6) Dhara Report Query Optimization and Validation. 7) Redesigning & deployment page on live server of Jal Rekha | 24/12/2025 | 18/12/2025 | High - Requires urgent attention | Delivered On Scheduled
35 | Sahbhagita GM | Sahbhagita Reports 1) Report Modification shown 2) Sahbhagita New Page for Approval of Survey Reports 3) Sahabhagita Video Functionality updations for size, format 4) Sahbhagita Page : Frm_Ngo_Summary_Reports As per discussion need Approved , Rejected and No Action on the report count . 5) Update with new service for dropdown of Village on the basis of dist_cd and video enhancements | 03/12/2025 | 01/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
36 | Sahbhagita GM | Change Request -GM / PM 1) Sahbhagita report view chnages village wise triggers - Get_VillageForApproval 2) Need extra dropdown for Village in the page : Frm_Ngo_Survey_Approval 3) Update with a new service and functionality to make ISA dependent on Scheme and District (filter flow: PIU → Scheme → ISA → Village). 4) Update Shabhagita ISA Bill Form | 14/12/2025 | 11/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
37 | FHTC (Functional Household Tap Connection) FE Reports | FE/Reports: 1) FE Login - Visit Each Village Household API Integration 2) FE login - Connection Tap check, Update and upload with Beneficiary & Tap Photo 3) FE login - Connection rejected (Not proper) then send it to GM & contractor 4) FE login - Connection accepted then send it to GM 5) API Whitelisting 6) NIC API Integration 7) HSC Report with all details and photo of beneficiary (mandatory) for FHTC 8) FE send rejected Tap Connection send to Contractor | 22/09/2025 | 19/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
38 | FHTC CR FE Reports | Change Request FHTC: 1) Earlier we used NIC services for API Integration. Now updated to Samagra API 2) Updated APK through API to integrate with Samagra 3) Updated Entries for New HSC Report 4) Contractor updates the beneficiary tap connection with photograph to GM | 30/10/2025 | 29/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
39 | O&M Billing GM | GM: 1) GM of O&M module Login and fill basic details 2) GM Advance form details SLBM features & other additional functionalities, scheme status 3) GM Scheme status and financial calculation for billing 4) GM uploads documents and data is fetched from Dhara and Nirmal module 5) GM under a scheme assign it to a Contractor 6) Contractor generate Bill 7) GM PIU or SQC Edit it and forward to GM of O&M then to PMC 8) All can check remarks then forward to Deputy Manager will only process final bill amount with further remarks 9) PMC recommendations letter annexure duly verified | 05/09/2025 | 28/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
40 | O&M Billing GM | CONTRACTOR: 1) Contractor Basic details, Advance details 2) Fill Financial Calculations as per CPI 3) O&M Billing PIU and SQC page development 4) O&M Billing Manpower page development & Residual Pressure SP 5) O&M Mapping Bulk users, Gross Bill Deduction, & Net Payable Bill 6) O&M Billing Process for RM & Village & Mapping Management Norms 7) Dhara water supply entries from Portal | 22/09/2025 | 19/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
41 | O&M Billing GM | Workflow b/w O&M GM & Higher officials: 1) Establish flow between GM, Contractor 2) GM O&M, CGM, PD, CFO, CA then MD final approval of bill and status 3) Retrieve all RA bill data correctly & Prepare test data in om_ra_bill table 4) RA Bill is based on scheme id & contractor id, always choose bill month & increment after first year and next month 1 days 5) Edit option and resend to PIU GM then GM send to Contractor. | 26/09/2025 | 26/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
42 | O&M Billing - Change request GM | Change request O&M Billing: 1) Save as Draft at time of entry by GM 2) Census Population location hierarchy needs to be corrected and Next change to make Census population open 3) SLBM Section fields Quality, Quantity, Pressure, UFW, and Complaint, an "Other" option should be added to both the Norms and Penalty dropdowns 4) Changes for Penalty label (Name, Radio button) 5) Type of Increment for CPIW & Yearly calculation changes 6) Scheme Status section ( View Document, Eligibility Increment, Year month update for O & M start & end date) 7) GST services option open for O &M 8) Document upload Yes/No where if done then freeze the screen | 03/11/2025 | 31/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
43 | Bharosa Factory Testing - Web | Factory Testing Web: 1) Assign Components to concerned Role 2) Review and visualize generated report of test samples 3) New Vendor to be added 4) Create API and Service for Bharosa insert and get Inspector Details | 19/10/2025 | 16/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
44 | Bharosa Factory Testing - Web | Factory Testing Mobile: 1) Bharosa Factory testing module entry 2) Fetch Components details as assigned by GM 3) Fill Details on Mobile app of inspector & Component to be tested 4) Upload Doc, Images and Videos 5) Increased count of Inspector | 31/10/2025 | 30/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
45 | CMMI Statistical Analysis | 1) Conventional & Precast separate option provided for OHT Work plan start, plan end date on each stage 2) Delete option provided for wrong entry in conventional & then entry in precast OHT 3) Changes in WTP and IPS Forms at each stage 4) Mobile apk changed for - OHT completed in Sopan will not be shown in RFI request Anusharavan module for contractor login 5) Sopan IPS Component updated | 10/08/2025 | 04/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
46 | CMMI Statistical Analysis | Change Request - GM Document Upload & Reports 1) If contractor filled wrong details then GM can edit and can update actual date and freeze option at each stage 2) Drill down functionality, Plan date and actual date by each OHT wise in the reports - Mapping, Monitoring, & Report 3) Drill down functionality, Plan date and actual date by each WTP wise in the reports - Mapping, Monitoring, & Report 4) Drill down functionality, Plan date and actual date by each Intake wise in the reports - Mapping, Monitoring, & Report 5) Prepare the report with total Panchanama count and total uploaded design data 6) Changes in Panchnama and design drawing separated into pdf format with upload feature 7) CMMI Documentation | 30/10/2025 | 27/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
47 | Dhara Change Request Reports | 1) Updated Habitation Mapping functionality to each OHT or by OHT wise and provided VC training 2) Assigned functionality to FE Mobile user 3) CWGM/CWPM (WTP) functionality added for inside and outside scheme villages mapping and provided VC training 4) Month wise open/close records - To approve/fill meter reading month wise of each component - Intake 5) Month wise open/close records - To approve/fill meter reading month wise of each component - OHT 6) Month wise open/close records - To approve/fill meter reading month wise of each component - WTP 7) Month wise open/close records - To approve/fill meter reading month wise of each component - Bulk User 8) Intake,wtp,oht and Village meter reading modification in web 9) update meter survey for Intake,wtp,oht and Village 10) For WTP added meters 11) Now all village and habitation open for OHT mapping in the scheme 12) CMMI Documentation | 20/08/2025 | 12/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
48 | Dhara Change Request Reports | 1) Assigned Habitation wise mapping to FE 2) Updated few changes in the parameters of meter - Meter functional, Meter not functional, Meter replace, No water supply where default value was set. 3) Assigned WTP meter where entries are repeated for OHT mapping | 30/08/2025 | 28/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
49 | Dhara Change Request Reports | 1) View Updated / Changed Water Supply Reports - a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report 2) Drill down features for all reports & correct mapping data 3) Updated changes in Reports ( DWSR, MWSR, Village wise , scheme wise, UFWR) 4) Updated Bulk user report & Dhara Report added at Home Screen of Jal Rekha Portal on public domain 5) CMMI Documentation | 30/09/2025 | 25/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
50 | O&M Billing Security | 1) Analyzed and fixed SQL queries & updated database table and function 2) Performed PostgreSQL query development and optimization. 3) Security Sanitization - Cross-Site Scripting: DOM Bug fixing in Jal Rekha (On JS files) for Security Audit | 16/12/2025 | 14/12/2025 | Medium - Important but manageable risks | Delivered On Scheduled
51 | CMMI Documents | Documentation 1) Data Collection for Cycle 3 2) Baseline 2 and RCA documentation 3) Document Creation & CMMI Review Meeting Baseline RCA & Plan 4) CMMI Documentation for Cycle 2 5) CMMI Documentation RCA, Action Plan, Artifact, and DC Sheet 6) CMMI Documentation & SEPG meeting & induction training 7) CMMI L5 Document (5 Why Analysis) 8) Working on CMMIL5 cycle 2 document & DRE Defect sheet 9) CMMIL5 Estimation Sheet for all modules 10) CMMIL5 Documentation- Requirement, Code and Design defects update | 03/01/2026 | 01/01/2026 | Medium - Important but manageable risks | Delivered On Scheduled
52 | Master Change Request - GM / Contractor | 1) Mapping village and its components with Water supply through other Scheme of PIU 2) Pipeline master zone numbers are added at contractor level 3) Edit functionality provided to contractor before final submission 4) Updated Bulk Meter village mapping 5) Mapping through habitation of scheme village and OHT 6) Mapping outside scheme village also map 7) WTP meter mapping option added for all 147 schemes 8) CMMI Documentation | 22/07/2025 | 19/07/2025 | Medium - Important but manageable risks | Delivered On Scheduled
53 | Master Change Request - FE Pipeline Mater | 1) Updated Pipeline master data integration with RFI Module at various stage 2) Mapping habitations and data issues at PIU level | 19/08/2025 | 13/08/2025 | Medium - Important but manageable risks | Delivered On Scheduled
54 | Nirmal Change request - WTP, OHT Report | 1) WTP Report parameter changes 2) Contractor/FE login - WTP, Intake buffer increase to 200 meter for Raw water sample collection on | 21/07/2025 | 15/07/2025 | Medium - Important but manageable risks | Delivered On Scheduled
55 | Nirmal Change Request - Beneficiary Report | 1) Range facility provided for Date option 2) According to Water sample ID provided search option in the report | 08/09/2025 | 08/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
56 | Sahbhagita Report | 1) Report Modification shown | 18/09/2025 | 16/09/2025 | Medium - Important but manageable risks | Delivered On Scheduled
57 | Sahbhagita Change Request -GM / PM / Reports | 1) GM login - Sahbhagita report view chnages village wise triggers 2) PM - Video Upload option in sahbhagita activity | 30/10/2025 | 29/10/2025 | Medium - Important but manageable risks | Delivered On Scheduled
58 | Dhara Change Request - FE / Mobile User | 1) Check on 4 parameters of meter - Meter functional, Meter not functional, Meter replace, No water supply) 2) Mobile Dev -Capture meter readings ( with numeric value, date, and remarks (Reading entry with validations, offline cache, and data persistence) & capture and upload photos of the meter ( Verify File/photo capture, compression, and upload workflow) 3) If Network not available - Save readings offline and sync later (Offline-first design, local storage, and sync logic) | 04/05/2025 | 15/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
59 | Dhara Contractor Report View | View Water Supply Reports a) DWSR Report b) MWSR Report c) Scheme wise report d) village wise report e) Bulk user reports f) UFW Report | 06/09/2025 | 08/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
60 | Master FE Mobile | 1) Add OHT name in anusharan module generate request for RFI to contractor (on Mobile) | 14/04/2025 | 12/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
61 | Master Change request - Schema | 1) Modify the schema 2) Mobile app anusharan module changes inside Master | 28/04/2025 | 25/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
62 | Nirmal Contractor Login | 1) Contractor login - Check Samples collected from field 2) Contractor login - After Performing Lab test, update it on portal 3) Contractor login - Submit the report on portal | 30/04/2025 | 26/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
63 | Nirmal GM | GM Login - Shall be able to check the reports - & Defects | 24/04/2025 | 21/04/2025 | Medium - Important but manageable risks | Delivered On Scheduled
64 | Nirmal Change request | 1) Report parameter changes 2) Mobile app functionality of OHT Intake WTP chnages 3) Nirmal & Dhara contractor functionality and User management | 30/05/2025 | 26/05/2025 | Medium - Important but manageable risks | Delivered On Scheduled
65 | Sahbhagita PM | 2) Sahbhagita report view | 24/06/2025 | 24/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
66 | Sahbhagita FE | 3) Fill the Sahbhagita activity & upload the data activity & changes updated | 30/06/2025 | 27/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
67 | Sopan All Web User | 1) OHT - Mapping, Monitoring, & Report 2) WTP - Mapping, Monitoring, & Report 3) Intake - Mapping, Monitoring, & Report | 16/06/2025 | 14/06/2025 | Medium - Important but manageable risks | Delivered On Scheduled
68 | SVS Water Supply Monitoring | MP PHE SVS Daily water supply monitoring Daily supply of water at GP level New Module creation in Jal Rekha API fetch from Panchayat Darpan NIC Integrate Village master data Requirement & wireframe preparation | 22/05/2026 | 21/05/2026 | Medium - Important but manageable risks | Delivered On Scheduled
69 | All Public Reports on Dashboard | All Reports are now public and can be accessed through Jal rekha portal | 14/05/2026 | 14/05/2026 | Medium - Important but manageable risks | Delivered On Scheduled
70 | Sahbhagita Change Request | Sahbhagita CR - Sahbhagita Activity require review from CP Manager and Payment approval from ISA Sahbhagita Activities should be integrated with Payment functionality | 15/05/2026 | 15/05/2026 | Medium - Important but manageable risks | Delivered On Scheduled
71 | AI Module - FHTC Tap Connection | ML model implementation on the tap connection monitoring buffer region, and other validations Data Processing of FHTC Tap connections using AI models Machine Learning Predictive Model Implementation | ML model implementation on the tap connection monitoring buffer region, and other validations | Data Processing of FHTC Tap connections using AI models | Machine Learning Predictive Model Implementation | 25/05/2026 | 24/05/2026 | Medium - Important but manageable risks | Delivered On Scheduled
ML model implementation on the tap connection monitoring buffer region, and other validations
Data Processing of FHTC Tap connections using AI models
Machine Learning Predictive Model Implementation
72 | Cube Testing CR | Mandatory Mulitple Image Upload functionality New web page creation/ Modification Option for manual entry for Components | Mandatory Mulitple Image Upload functionality | New web page creation/ Modification | Option for manual entry for Components | 30/04/2026 | 29/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled
Mandatory Mulitple Image Upload functionality
New web page creation/ Modification
Option for manual entry for Components
73 | Site Security Audit | Jal rekha Site Fortify Security Audit | Jal rekha Site Fortify Security Audit | 30/04/2026 | 29/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled
Jal rekha Site Fortify Security Audit
74 | Cube Testing - FE | Cube Testing Functionality FE survey the cube at 7th and 28th day Survey report submission with validations | 11/04/2026 | 10/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled
75 | Cube Testing - Contractor | Creation of Cube Inspection by Contractor Prod/CR/UAT Testing (Including prod issue validation) | Creation of Cube Inspection by Contractor | Prod/CR/UAT Testing (Including prod issue validation) | 08/04/2026 | 07/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled
Creation of Cube Inspection by Contractor
Prod/CR/UAT Testing (Including prod issue validation)
76 | Cube Testing - GM | Prod/CR/UAT Testing (Including prod issue validation) RFI request status update and see the list | Prod/CR/UAT Testing (Including prod issue validation) | RFI request status update and see the list | 13/04/2026 | 11/05/2026 | Medium - Important but manageable risks | Delivered with Delay
Prod/CR/UAT Testing (Including prod issue validation)
RFI request status update and see the list
77 | Dhara CR - Reports (MWSR,DWSR, UFW) | Requirement gathering of Report changes in Dhara reports Updation and recreate fetch - DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW | Requirement gathering of Report changes in Dhara reports | Updation and recreate fetch - DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW | 27/03/2026 | 26/03/2026 | Medium - Important but manageable risks | Delivered On Scheduled
Requirement gathering of Report changes in Dhara reports
Updation and recreate fetch - DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW
78 | Master CR - Scheme Village & OHT Master | Scheme Village OHT Mapping & Report Updations | 22/03/2026 | 20/03/2026 | High - Requires urgent attention | Delivered On Scheduled
79 | Master Change request - Schema | Bulk Consumer Master (Add-Update-Get) Dhara Mapped Summary report - Changes in Abstract report Dhara Master DWSR Updations In Bulk Consumer Master - add delete functionality | Bulk Consumer Master (Add-Update-Get) | Dhara Mapped Summary report - Changes in Abstract report | Dhara Master DWSR Updations | In Bulk Consumer Master - add delete functionality | 25/03/2026 | 24/03/2026 | Medium - Important but manageable risks | Delivered On Scheduled
Bulk Consumer Master (Add-Update-Get)
Dhara Mapped Summary report - Changes in Abstract report
Dhara Master DWSR Updations
In Bulk Consumer Master - add delete functionality
80 | Cube Testing - SQC/TPIA | 1) approval workflow to be followed with GM SQC TPIA | 08/04/2026 | 08/04/2026 | Medium - Important but manageable risks | Delivered On Scheduled