## CR Register May-Jun 2026
JAL REKHA PROJECT — CHANGE REQUEST REGISTER ¦ May–June 2026
Project: Jal Rekha ¦ Client: Govt. of MP – PHED ¦ Contract: MPSEDC/MPSSDI(GIS)/2025/00423 ¦ Cycle: 4 ¦ Sprint: Jal Rekha/16 (01 May 2026–31 May 2026) & Jal Rekha/17 (01 Jun 2026–30 Jun 2026)
Prepared by: Dheeraj Motiyani, Sr. BA, MPSeDC ¦ Reviewed by: Tapan Khandelwal, SPM ¦ Sources: MD Sir MoM 9-Jun-2026, 16-Jun-2026; June Month CR Tracker; Handwritten Notes
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks | MoM Ref. | Sprint
1 | CR-JR-MAY-001 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – E-Sign Integration via CDAC for all parties (Firm/FE-eSign, Web & Mobile). CDAC integration for e-sign on Bill, Submission Letter, and Tax Invoice. FE (e-sign) → Web & Mobile flow. | O&M Billing | E-Sign – CDAC Integration | Web & Mobile – Bill Workflow | CDAC API integration required. Affects Firm, FE, TL, GM PIU login flows. Bill PDF and submission letter to carry e-sign. System-generated bill – physical sign NOT required. | Open |  | Pending | High | High | 40 | CDAC Rakesh Sir to coordinate. FE (e-sign) ↔ Web/Mobile dual flow. | MoM 16-Jun-2026 | Jal Rekha/17
2 | CR-JR-MAY-002 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Contractor RA Bill: Abstract generation from Contractor login. Select Bill → Generate Abstract → Tag all villages automatically. | O&M Billing | Contractor Bill – Abstract | Contractor Login – Bill Workflow | Abstract screen added under Contractor login for RA billing. Links to selected bill and tags all villages. GM/SQC approval chain unaffected. | In Progress |  | Pending | High | Medium | 24 | Abstract linked to 8th Bill; Tag all villages flag needed. | MoM 16-Jun-2026 (Notes) | Jal Rekha/16
3 | CR-JR-MAY-003 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – GST No. Integration with O&M Billing Jal Rekha portal. GST number to be captured and linked at firm/contractor level. | O&M Billing | GST Integration | Contractor / GM PIU Login | GST No. field added at contractor master level. Appears on bill PDF and abstract. Rakesh Sir to validate GST API/manual entry approach. | Open |  | Pending | Medium | Low | 12 | GST No. (150/215) – Rakesh Sir to confirm data source. | MoM 16-Jun-2026 | Jal Rekha/17
4 | CR-JR-MAY-004 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – TL Recommendation Letter to be E-Office generated (system-generated). TL (PMC) → E-Office → Account Office Jal Rekha. | O&M Billing | TL Recommendation Letter – E-Office | TL (PMC) & Account Office Login | TL recommendation letter generated from E-Office system, not manual upload. Integration with Account Office Jal Rekha to be established. | Open |  | Pending | High | High | 32 | TL SQC integration also required. E-Office API/link to be confirmed. | MoM 16-Jun-2026 | Jal Rekha/17
5 | CR-JR-MAY-005 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Bill PDF consolidation: approx. 19–20 documents merged into one PDF (GM, SQC, Firm, Form 27A, MB, Abstract). 3-month combined PDF for static docs; monthly for variable docs. | O&M Billing | Bill PDF Merge – All Documents | All Logins – Bill Generation | Merged PDF includes: 1.GM letter, 2.SQC letter, 3.Firm docs, 4.Form 27A, 5.MB, 6.Abstract. Static docs = 1 copy for 3 months; variable = per month. Total ~19–20 docs. | In Progress |  | Approved | High | Medium | 20 | Landscape issue in O&M Bill PDF also fixed in this CR. | MoM 16-Jun-2026 (Day 1 Notes) | Jal Rekha/16
6 | CR-JR-MAY-006 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | O&M Billing – Workflow Redesign: Firm → GM PIU (direct). Dual path: (1) Firm → GM PIU → GM O&M. (2) Firm → GM PIU → TL SQC → GM PIU → GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD. | O&M Billing | Billing Workflow Redesign | Firm, GM PIU, TL SQC, GM O&M, All Hierarchy | Two workflow paths defined. "Manage Bill" option used for GM PIU. "View Pending Bills" accessible before Pending stage. Ref: O&M_Billing_Workflow diagrams and process flow PDF. | In Progress |  | Pending | High | High | 48 | Use Manage Page (not old flow). Refer O&M Billing Workflow PDF + JPEG diagrams. | MoM 9-Jun-2026 & 8-Jun Notes | Jal Rekha/17
7 | CR-JR-MAY-007 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | Sahbhagita – Multi-select dropdown for bill selection. RA(1) to RA(12) bill range with Withhold Bills option. | Sahbhagita | Multi-Select Bill Dropdown | Sahbhagita Login – Bill Management | Sahbhagita module: multi-select in bill dropdown. RA Bill range RA(1)–RA(12). Withhold Bills toggle added. | Open |  | Pending | Medium | Low | 12 | Generate Abstract → Select Bill → Tag all villages. Village-wise & Combined Activities in scope. | MoM 9-Jun-2026 (Notes) | Jal Rekha/17
8 | CR-JR-MAY-008 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | O&M Billing – Contractor mistakes visible to SQC/TL and GM. Show all records on all IDs for GM and SQC. Merge PDF of all O&M documents. | O&M Billing | Contractor Mistake Visibility & PDF Merge | GM, SQC, TL Logins | Contractor error entries visible across SQC/TL and GM logins. All records shown on all IDs. O&M merged PDF available per bill. | Open |  | Pending | Medium | Medium | 16 | Related to Bill PDF CR (CR-JR-MAY-005). SQC 7L/4–GM mapping check needed. | MoM Notes 1-Jun (O&M) | Jal Rekha/17
9 | CR-JR-MAY-009 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | Dhara – Approved report data entry should NOT change once approved. UI lock for GM PIU. GM PIU/TL can ADD (not edit). GM can add new penalty point on Contractor bill. | Dhara | Approved Report Lock – Entry Freeze | GM PIU Login – Report Approval | Once GM PIU approves Dhara report, entry locked across all logins. GM PIU/TL can add info but cannot edit Contractor data. Penalty by GM is addable on top. | In Progress |  | Approved | High | High | 28 | GM can add new point (Penalty applied). Cannot edit existing Contractor-generated bill data. | MoM Notes 1-Jun (Dhara) | Jal Rekha/16
10 | CR-JR-MAY-010 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | Dhara – OHT/WTP/Intake: Base Capacity column to be added in reports. Ref: Dhara_report_formate_27_05_2026.xlsx. | Dhara | Report Column – Base Capacity (OHT/WTP/Intake) | GM/PIU Login – MWSR/DWSR Reports | Base Capacity column for OHT, WTP, Intake in Dhara reports (MWSR, DWSR, Approved Reports). Ref: Dhara_report_format_27_05_2026.xlsx and DHARA_corrections.xlsx. | In Progress |  | Approved | Medium | Low | 16 | Ref: Dhara_report_formate_27_05_2026.xlsx and DHARA_corrections.xlsx for column mapping. | MoM Notes 1-Jun (OHT/WTP) | Jal Rekha/16
11 | CR-JR-MAY-011 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | O&M Billing – RA Bill No. format and ISA → ISA flow for Customized Report. Approved Bill → RA 1 to 12 Bill No. Contractor login. | O&M Billing | RA Bill Numbering – Customized Report | Contractor Login – Report View | ISA → ISA with CP Manager (Approved/Rejected/No Action). RA Bill numbering cycles 1–12. Customized report view for Contractor. Ref: OM_RA_Bill_Report.pdf. | Open |  | Pending | Medium | Low | 12 | Approved Bill → RA 1 to 12. Contractor view ISA-to-ISA flow. | MoM Notes 5-Jun | Jal Rekha/17
12 | CR-JR-MAY-012 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Future Scope: Photo Scan → Face/Background AI Model (CP Manager). Video option. Duplicate/Repeated photo detection → flag message to CP Manager. | Sahbhagita | AI Photo Verification – CP Manager | CP Manager Login | Photo/video capture at CP Manager login. AI model (face + background). Duplicate/repeated → show flag: "Already Used Before". Future scope item. | Open |  | Pending | Low | High | 60 | Future scope. AI model (Photo Scan face + background). Video in scope. | MoM Notes 5-Jun (Sahbhagita) | Future Sprint
13 | CR-JR-MAY-013 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Hyperlink: Village Name → Village Activity Document Preview popup. Two hyperlinks: (1) Village Name, (2) Village Activity Document (Reviewed). | Sahbhagita | Hyperlink – Village Activity Document Preview | Sahbhagita Report View | Village Name clickable hyperlink. On click: popup showing Village Activity Document with preview. Two separate hyperlink areas. | In Progress |  | Approved | Medium | Low | 10 | Popup with village activity doc preview. | MoM Notes 5-Jun & 6-Jun | Jal Rekha/17
14 | CR-JR-MAY-014 | MD Sir | Dheeraj Motiyani | 08-Jun-2026 | O&M Billing (Aaklan) – GM (PIU Login) & GM (O&M) / Deputy O&M: View Pending Bills and Manage Bills. Bills already generated shown in table. | O&M Billing (Aaklan) | Pending Bills View – GM Logins | GM PIU & GM O&M Login | GM PIU: View Pending Bills, Manage Bill under O&M. GM O&M: View Pending Bills + Manage Bill. Already generated bills shown in table. Ref: 18-Jun handwritten flow. | In Progress |  | Approved | High | Medium | 20 | Aaklan module O&M section. GM PIU & GM O&M/Deputy flows defined. | MoM 18-Jun Notes | Jal Rekha/17
15 | CR-JR-MAY-015 | MD Sir | Dheeraj Motiyani | 09-Jun-2026 | O&M Billing – Document Upload Screen: Firm: Firm Submission Letter, Tax Invoice, Any Other (Multiple). TL/SQC: SQC Recommendation Letter, Third Party Water Quality Test Report (Multiple + Remark). GM PIU: PIU Recommendation Letter, Signed Form 27A, Signed Scanned MB, Signed Abstract, Signed Monthly Bill Sheet (Multiple), Any Other Docs (Multiple + Remark). | O&M Billing | Document Upload Screen Design | Firm, TL/SQC, GM PIU Logins | Upload UI: Download + View PDF buttons per doc type. Multiple upload for Water Quality Test Report, Monthly Bill Sheet, Any Other Docs. Remark field for selected doc types. | In Progress |  | Approved | High | Medium | 32 | Ref: Handwritten wireframe (Contractor/Firm, TL SQC, GM PIU sections). Upload + Download + View PDF per doc. | Notes 9-Jun (Wireframe scan) | Jal Rekha/17
16 | CR-JR-MAY-016 | MD Sir | Dheeraj Motiyani | 10-Jun-2026 | FHTC/Asset Mapping – Village LGD Code: no LGD = Habitation. BISAC: Junction to Junction Map Asset & Track. Pipeline Mapping (Asset). NIC (Asset ID) = BISAC. OHT Asset already done. | FHTC / Asset Mapping | Village LGD Code & BISAC Asset Mapping | Asset Mapping – BISAC Integration | No LGD code → Habitation in system. BISAC J-to-J map for asset tracking. Pipeline mapping via NIC Asset ID. OHT asset mapping done; remaining components to complete. | In Progress |  | Pending | High | High | 36 | 1 Scheme = 250 OHT. 175×250 scale. NIC Asset ID (BISAC). Pipeline mapping pending. | MoM 9-Jun-2026 & Notes 3-Jun | Jal Rekha/17
17 | CR-JR-MAY-017 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Sahbhagita – Report: Category → Activity. Village Wise (32/27 activities) & Combined (22). Filter: V, C, A. Category V/C/A cross-filter. Ref: Sahbhagita_master_activity_matched.xlsx. | Sahbhagita | Activity Report – Village/Combined Category Filter | Sahbhagita Report Module | Report shows Village Wise (32 listed, 27 unique) and Combined (22). Category filter: V=Village, C=Combined, A=All. Sub-activity linked. Ref: Sahbhagita master activity doc. | In Progress |  | Approved | High | Medium | 24 | Village 32/27 activities; Combined 22; V/C/A cross-filter. Ref master activity matched xlsx. | MoM Notes 18-Jun (Sahbhagita) | Jal Rekha/17
18 | CR-JR-MAY-018 | Department | Dheeraj Motiyani | 22-May-2026 | Anusharavaan – Save as Draft functionality at FE Login. FE saves inspection data as draft before final submission, preventing data loss on connectivity issues. | Anusharavaan | Save as Draft – FE Login | FE Mobile App – RFI Inspection | Draft save button on FE inspection form. Draft stored locally (offline-first) and synced on connectivity restored. Draft visible only to FE until submitted. FE must review before final submit. | In Progress |  | Approved | High | Medium | 20 | Offline-first draft. Synced on reconnection. FE cannot submit from Draft without review. | Internal CR – Module Tracker | Jal Rekha/16
19 | CR-JR-MAY-019 | Department / Testing Team | Dheeraj Motiyani | 22-May-2026 | FHTC – Report Issues: FE inspection date missing in reports; loop re-inspection list showing incorrect records; column mismatch between UI and DB; GM/Contractor data discrepancy. | FHTC | Report Issues – Multiple Fixes | FHTC Reports – FE, GM, Contractor Login | Issues: (1) FE inspection date not in FHTC reports. (2) Loop re-inspection list – incorrect records. (3) Column mismatch UI↔DB. (4) GM/Contractor report data discrepancy. All to be fixed and moved to UAT/Prod. | In Progress |  | Approved | High | Medium | 24 | Ref: FHTC_CR_June Module tracker. FE inspection date, loop re-inspection, column alignment all in scope. | Internal CR – FHTC Module Tracker | Jal Rekha/16
20 | CR-JR-MAY-020 | MD Sir | Dheeraj Motiyani | 16-Jun-2026 | O&M Billing – Residual Pressure & Complaint Redressal screen changes. Pressure Threshold Report format update per OM_RA_Bill_Report.pdf. | O&M Billing | Residual Pressure & Complaint Redressal | GM PIU / O&M Login – RA Bill | Residual Pressure: columns per OM_RA_Bill_Report.pdf (District, Block, GP, Village, Consumer Name, Mobile, Measured Pressure, Remark, Affected HSCs, Days, Penalty calc). Complaint Redressal: label and status changes. | Open |  | Pending | Medium | Low | 14 | Ref: OM_RA_Bill_Report.pdf – Pressure_Threshold_Report. RA/19/50/2025-26/Q1/1 format. | MoM Notes 16-Jun (Point 11) | Jal Rekha/17
21 | CR-JR-MAY-021 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | Dhara – Non-Mandatory options go-live on 19th June across all logins: (1) Remark, (2) Photo Upload, (3) Forward, (4) Backward Options. | Dhara | Non-Mandatory Options – Go Live 19-Jun | All Logins – Dhara Module | Non-mandatory options (Remark, Photo Upload, Forward, Backward) enabled on 19-Jun across all logins. These actions do NOT block submission if not filled. | Completed | 19-Jun-2026 | Approved | High | Low | 12 | Go-live 19-Jun-2026 confirmed. Non-mandatory: Remark, Photo Upload, Forward, Backward. | MoM Notes (Point 10 – 19 June) | Jal Rekha/17
22 | CR-JR-MAY-022 | MD Sir / Kapil Sir | Dheeraj Motiyani | 16-Jun-2026 | SVS Water Supply Monitoring – New Module Initiation: Department meeting, Project PIN document, MoM creation. DB fields, workflow, and reports structure finalized. | SVS Water Supply Monitoring | New Module – Project Initiation | New Module – All Stakeholders | New module initiated. DB schema fields defined. Workflow: data entry → monitoring → report generation. Reports structure agreed. Web pages and DB functions development started. | In Progress |  | Pending | High | High | 48 | SVS Water Supply Monitoring Report – web page development started (Sprint 16). | Internal – Sprint 16 Timesheet | Jal Rekha/16
SUMMARY ¦ Total CRs: 22 ¦ Completed: 1 ¦ In Progress: 13 ¦ Open: 8 ¦ Total Effort: 560 Hrs ¦ Sprint: Jal Rekha/16 & /17

## Module Summary
CR Module Summary – May to June 2026 ¦ Jal Rekha Project
Module | No. of CRs | Completed | In Progress | Open | Total Effort (Hrs)
Anusharavaan | 1 | 0 | 1 | 0 | 20
Dhara | 3 | 1 | 2 | 0 | 56
FHTC | 1 | 0 | 1 | 0 | 24
FHTC / Asset Mapping | 1 | 0 | 1 | 0 | 36
O&M Billing | 10 | 0 | 4 | 6 | 250
O&M Billing (Aaklan) | 1 | 0 | 1 | 0 | 20
SVS Water Supply Monitoring | 1 | 0 | 1 | 0 | 48
Sahbhagita | 4 | 0 | 2 | 2 | 106
TOTAL | 22 | 1 | 13 | 8 | 560

## O&M Billing Workflow Ref
O&M Billing Workflow Reference ¦ Jal Rekha ¦ June 2026
Step | Actor / Role | Login Type | Action / Description
1 | FIRM (Contractor) | Contractor Login | Bill Generation + Submission Letter + Tax Invoice (along with: Electricity Bills, PHE Test Reports, etc.). Note: System-generated bill – e-sign via CDAC, physical sign NOT required.
2 | GM (PIU) | GM PIU Login | Forward to TL (CSC). View Pending Bills → Manage Bill. Upload: Signed MB, Generated Abstract (signed), Signed Bill Sheet (by GM PIU), Signed Form 27A, Signed Relaxation Letter (if any).
3 | TL (CSC) | TL CSC Login | Add/Edit each record. Issue Recommendation Letter.
4 | GM (PIU) – 2nd Stage | GM PIU Login | Add/Edit each record. Upload final set of signed docs.
5 | GM (O&M) | GM O&M Login | Manage Bill. View Pending Bills. Edit / Add / Resolution.
6 | DGM (O&M) | DGM O&M Login | Review and forward to TL PMC.
7 | TL (PMC) | TL PMC Login | Recommendation letter with supporting documents.
8 | GM (O&M) – Final | GM O&M Login | Upload: Pass Order Copy (Signed by DGM O&M) + Signed Letter from HO.
9 | CGM | CGM Login | Offices: Bhopal, Gwalior, Jabalpur, Rewa, Sagar, Indore, Ujjain.
10 | CA | CA Login | Review and process accounts.
11 | CFO | CFO Login | Financial review and approval.
12 | P.D. | PD Login | Project Director approval.
13 | MD | MD Login | Final Approval.