## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 10 | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 3 to 5 | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## Version History
Date | Version | Description | Prepared by | Reviewed & approved by
2025-01-03 | 1 | Size base Estimation Model First baseline | SEPG Team | SEPG Head
2026-06-16 | 1.4 | Cycle 4 (Jan-May 2026) Size based Estimation - All modules updated | SEPG Team | SEPG Head

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.16 | Point / per hour
|  | 1 Point | 6.25 Hours

## Anusharavan Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Anusharavan Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Anusharavan - RFI Module | RFI New Stages & Inspection Details | New stage addition in RFI workflow; FE inspection details form (PIU); Customize report fields; Stage dropdown update; History screen search enhancement; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; API Integrations: 3-5; Business rules: Stage transition validation across 2-3 data stores; Reports: Customized inspection report | 0 | 2 | 1 | 11
Anusharavan - CR Reports | CR - RFI Stage Updations and Reports Modifications | History screen search for Contractor & FE login; Post-fix verification pipeline details; FE inspection date in PIU pending page; Customized report update; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; Reports: Tabular with 1-2 data sources | 2 | 1 | 0 | 5
Anusharavan - UI Enhancement | UI Enhancement for Contractor & Field Engineer Login | Inner page layout redesign; Navigation menu update; Responsive design; Page performance optimization; Mobile App-UI: Responsive web design; No of input fields: 8-10 (display only); Exit scenario: 1; No of Validations: 3-5; mobile App-UI: Static/responsive screen | 1 | 1 | 0 | 4
Anusharavan - RFI Module | View Details, Log View & Inspection Request Form Enhancement | View details modal for RFI requests; Log view implementation; Inspection request form field enhancements; Form field rearrangement; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 2-3; Business rules: RFI log tracking; Prefilled fields: 10-30 | 1 | 2 | 0 | 7
Anusharavan - RFI Module | RFI Request Inspection Point Dialog and Pipeline Details on History Page | Inspection point dialog popup; Pipeline details rendering on history page; Geolocation integration; Route visualization; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; mobile App-UI: Screen with 2-4 internal components | 1 | 1 | 0 | 4
TOTAL ANUSHARAVAN ESTIMATION (CYCLE 4) | [5 empty] | 31
| Total Count |  |  |  |  | 31
| Productivity | 0.16
| Size | 31 | Point
| Effort | 193.75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 225.0406 | Man hours
| Permissible Range(Man hours) | 236.2927 | 213.7886

## Asset Mapping Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Asset Mapping Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Asset Mapping - Search & UI | Search Box for OHT on Map & UI Redesign | OHT search box on map; Geolocation-based filtering; Map redesign and deployment; Page live server deployment; No of input fields: 3-5; Exit scenario: 1-2; No of Validations: 2-3; API Integrations: 2-3; mobile App-UI: Screen with external map component | 1 | 1 | 0 | 4
Asset Mapping - Bug Fixes & Reports | Accuracy Field, Data Get Method & SQC/OHT/Contractor Reports | Accuracy field changes; GET method update; SQC and OHT village testing bug fixing; Report creation for SQC/TPIA/contractor login; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; Reports: Tabular report with 1 data source | 2 | 1 | 0 | 5
TOTAL ASSET MAPPING ESTIMATION (CYCLE 4) | [5 empty] | 9
| Total Count |  |  |  |  | 9
| Productivity | 0.16
| Size | 9 | Point
| Effort | 56.25 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 65.3344 | Man hours
| Permissible Range(Man hours) | 68.6011 | 62.0677

## Bharosa CR Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Bharosa CR Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Bharosa - Factory Testing Web | Upload Multiple Documents on Web & UI Updation | Multiple document upload on web; UI update in existing pages; Bug fixes; QAP document upload functionality; No of input fields: 5-10; Exit scenario: 2-3; No of Validations: 3-5; API Integrations: 3-5; Business rules: Document validation logic | 2 | 1 | 0 | 5
Bharosa - Factory Testing Web | Save as Draft, Image, Video Upload & Wireframing | Save as draft functionality; Image and video upload option; Wireframe design; Unit field addition and display; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; Prefilled fields: 10-30; API Integrations: 3-5; mobile App-UI: Screen with 2-4 internal components | 0 | 2 | 1 | 11
Bharosa - Factory Testing Mobile | CR Factory Testing Mobile - Multiple Document & QAP Download | Document upload in web during component assignment; Display on web; QAP documents download functionality; Save as draft for mobile; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 3-5; mobile App-UI: Screen with 2-4 internal components | 1 | 2 | 0 | 7
TOTAL BHAROSA CR ESTIMATION (CYCLE 4) | [5 empty] | 23
| Total Count |  |  |  |  | 23
| Productivity | 0.16
| Size | 23 | Point
| Effort | 143.75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 166.9656 | Man hours
| Permissible Range(Man hours) | 175.3139 | 158.6173

## Cube Testing Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Cube Testing Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Cube Testing - Contractor Login | Creation of Cube Inspection by Contractor & Requirement Gathering | Cube inspection creation form; Contractor RFI survey form API integration; Survey form UI; Contractor history list with pagination; Wireframing & workflow; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 2-3; Business rules: Inspection workflow across 2-3 data stores | 2 | 2 | 0 | 8
Cube Testing - FE Login | FE Sync API, Survey, Cube Inspection & Mobile Development | FE sync API integration; FE survey form; FE inspection (7/28 days check); Mobile FE login; Offline data; Inspection Request form Local DB & API; History & Detail screen; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 5+; mobile App-UI: Screen with 2-4 internal components; Business rules: 7-day/28-day rule check | 1 | 2 | 2 | 17
Cube Testing - GM / SQC / TPIA | GM Action Page, Summary Report & Function for RFI Status | GM action page; Customized report; Summary reports (7/28 days scenarios); Function for RFI request status update; Pending for action page; Bug fixing; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; API Integrations: 3-5; Reports: Dashboard summary type with 2-3 data sources | 1 | 2 | 1 | 12
Cube Testing - CR | SQC/TPIA Web Pages & API, CR Changes & Security Test Cases | SQC Login web pages & API; TPIA Login web pages & API; Bug fixing; Test scenarios; Security test cases; CR change impact analysis; FE inspection date addition; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; API Integrations: 3-5; Business rules: TPIA/SQC workflow across data stores | 1 | 2 | 1 | 12
Cube Testing - Requirement & Design | Requirement Gathering, Wireframing, Workflow & User Stories | Complete requirement gathering; Wireframe design for all logins (FE, Contractor, GM, SQC, TPIA); Workflow documentation; User stories creation; DB schema, Master & Design Tables; No of input fields: Not applicable; Exit scenario: Not applicable; No of Validations: Not applicable; Business rules: Requirement traceability | 4 | 1 | 0 | 7
Cube Testing - CR Module | CR - Component Entry, FE Inspection Date, Manual Entry & Security | FE inspection date addition on GM/SQC/TPIA web pages; Remove inspection date, calculate days from Casting Date; Remove District/Block/GP/Village compulsion for certain components; Mandatory multiple image upload functionality; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3 | 2 | 2 | 0 | 8
TOTAL CUBE TESTING ESTIMATION (CYCLE 4) | [5 empty] | 64
| Total Count |  |  |  |  | 64
| Productivity | 0.16
| Size | 64 | Point
| Effort | 400 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 464.6 | Man hours
| Permissible Range(Man hours) | 487.83 | 441.37

## Dhara Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Dhara Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Dhara - CR Reports (MWSR, DWSR, UFW) | UI Update, New Pages, MWSR/DWSR/UFW Report Development | UI update and bug fixes inner pages; New report pages (Approved Village MWSR, Bulk Consumer MWSR, DWSR, UFW); HSC Summary Report; DWSR Detailed & DateWise reports; OHT Meter Survey Report; No of input fields: 10-15 (filters); Exit scenario: 2 (View, Export); No of Validations: 5-10; API Integrations: 3-5; Reports: >3 data sources, multiple complex reports, DWSR/MWSR/UFW types | 0 | 2 | 2 | 16
Dhara - CR Reports (MWSR, DWSR, UFW) | CR - All Reports Public, Bulk Consumer Mapping, Security Audit | All components/reports changes (BULK, OHT, Scheme, DWSR based on Aaklan); Public page data visibility; DWSR public report enhancements; Add Bulk Consumer mapping; Meter reading survey (Intake, WTP, OHT, Bulk); Site security audit; No of input fields: 10-15; Exit scenario: 2; No of Validations: 10+; API Integrations: 5+; Business rules: Complex across multiple data stores; Reports: >3 data sources | 0 | 1 | 3 | 18
Dhara - GM PIU User Change Request | Dhara WTP Meter Reading Issue & Bulk Consumer Meter Reading CR | Requirement gathering for WTP meter reading issue (certain schemes); Intake meter reading survey form requirement change; Bulk consumer meter reading survey; Approved status flow (FE→GM→Contractor); Test case/scenarios creation; No of input fields: 5-10; Exit scenario: 2; No of Validations: 5-10; API Integrations: 2-3; Business rules: Meter reading validation across 2-3 data stores | 1 | 2 | 1 | 12
Dhara - Contractor Objection Module | Contractor Objection Module for Intake, WTP, ESR-OHT Meter Survey | New contractor objection pages (Intake, WTP, ESR/OHT meter survey); Objection popup with PDF upload; Service creation for contractor objection; Contractor objection API & database integration; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 3-5; Business rules: Objection workflow with approval; Data Migration: New tables and services | 0 | 1 | 2 | 13
TOTAL DHARA ESTIMATION (CYCLE 4) | [5 empty] | 59
| Total Count |  |  |  |  | 59
| Productivity | 0.16
| Size | 59 | Point
| Effort | 368.75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 428.3031 | Man hours
| Permissible Range(Man hours) | 449.7183 | 406.888

## FHTC Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | FHTC Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
FHTC - Change Request GM/Contractor/Reports | Re-Inspection (Loop) Functionality Web & Mobile, GM/Contractor Reports | Re-inspection loop for contractor, FE, SQC/TPIA; Re-inspection form UI & API; History screen, Accepted/Rejected list; Search functionality for FE & Contractor; View logs; Report filter column-level fixes; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 3-5; Business rules: Re-inspection workflow across multiple logins; mobile App-UI: Screen with 2-4 internal components | 1 | 2 | 2 | 17
FHTC - FE Reports | FHTC FE Reports, Mobile Sync Changes & History Screen | FE login history screen changes; Sync changes; API integration for FE module; FHTC Internal Testing & Bug Re-testing; Modified Excel export (dynamic file name, sheet name, header); No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; Reports: Parinam Report fix; mobile App-UI: Screen with 2-4 internal components | 2 | 2 | 0 | 8
TOTAL FHTC ESTIMATION (CYCLE 4) | [5 empty] | 25
| Total Count |  |  |  |  | 25
| Productivity | 0.16
| Size | 25 | Point
| Effort | 156.25 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 181.4844 | Man hours
| Permissible Range(Man hours) | 190.5586 | 172.4102

## Master Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Master Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Master - Change Request | Bulk Consumer Mapping, Scheme Village OHT, Bulk Meter Update & Reports | Dhara reports validate (Scheme, OHT, Bulk Consumer); Bulk Consumer Supply Mapping (meter_id added for WTP); OHT Village Mapping - Habitation Code Duplicate error fix; Scheme Village Mapping Census Population integration; Bulk Consumer delete/disable functionality; Bulk Meter Mapping (Insert-Edit-Update); Abstract Report development; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 10+; API Integrations: 3-5; Business rules: Validation rules across multiple data stores; Data Migration: Schema updates | 1 | 2 | 2 | 17
TOTAL MASTER ESTIMATION (CYCLE 4) | [5 empty] | 17
| Total Count |  |  |  |  | 17
| Productivity | 0.16
| Size | 17 | Point
| Effort | 106.25 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 123.4094 | Man hours
| Permissible Range(Man hours) | 129.5798 | 117.2389

## Material Testing Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Material Testing - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Material Testing - FE Login | Material Testing Mobile App - Merge, Test & Upload (FE) | Material Testing merge code; Test on mobile; Upload on Play Store; Regression and production testing; Build deployment; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; mobile App-UI: Screen with 2-4 internal components | 2 | 1 | 0 | 5
Material Testing - GM/Contractor Login | GM Login Web Pages, APIs, Functions, Mobile API & SQC/TPIA Login | GM login pending with PIU page; SQC/TPIA login web pages; Material testing Get Data API; Insert API with OHT ID parameter; Functions (fn_get_esr_details, etc.); Mobile API for FE login; Contractor inspection request form; Offline data list; Bug fixing; FE inspection date addition; No of input fields: 10-15; Exit scenario: 2-3; No of Validations: 10+; API Integrations: 5+; Business rules: Complex inspection workflow across multiple stores; mobile App-UI: Screen with 2-4 internal components | 1 | 2 | 3 | 22
TOTAL MATERIAL TESTING ESTIMATION (CYCLE 4) | [5 empty] | 27
| Total Count |  |  |  |  | 27
| Productivity | 0.16
| Size | 27 | Point
| Effort | 168.75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 196.0031 | Man hours
| Permissible Range(Man hours) | 205.8033 | 186.203

## Nirmal Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Nirmal Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Nirmal - Change Request - Reports | Nirmal Beneficiary, OHT, WTP, RawWater Reports with CR & UI Changes | 4 report types updated; Beneficiary report with parameter-level details (pH, TDS, Chlorine); Action Remarks chat box UI; Popup tables on action button; Drill-down levels (Beneficiary, OHT, WTP); Link button click UI; Search options on all reports; All changes moved to production; No of input fields: 8-10 (filters); Exit scenario: 2-3; No of Validations: 5-10; API Integrations: 3-5; Reports: >3 data sources with multiple complex charts and drill-down; mobile App-UI: Responsive UI with chat component | 0 | 2 | 2 | 16
Nirmal - FE Mobile | Nirmal FE Mobile Reports & Sync Bug Fixing | Debugging Nirmal sync issue; Nirmal reports (Beneficiary, OHT, WTP, RawWater) test report failed records highlighted; Code merge in UAT and Production; No of input fields: 5-10; Exit scenario: 2; No of Validations: 3-5; API Integrations: 2-3; mobile App-UI: Screen with 2-4 internal components; Reports: 2-3 data sources | 3 | 1 | 0 | 6
TOTAL NIRMAL ESTIMATION (CYCLE 4) | [5 empty] | 22
| Total Count |  |  |  |  | 22
| Productivity | 0.16
| Size | 22 | Point
| Effort | 137.5 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 159.7063 | Man hours
| Permissible Range(Man hours) | 167.6916 | 151.7209

## O&M Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | O&M Billing Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
O&M Billing - GM | CR GM: Census Flow, Bulk Mapping, Summary Page Changes, Scheme Reports | UI updates inner pages; Summary page changes (as discussed with client); Census Flow - auto-fetch from Scheme Village Master (remove manual add/delete); Bulk Consumer mapping enhancements; MWSR null fix; Bill number auto-generate; Abstract report generation PDF; Residual Pressure PDF; O&M Billing Wireframing update; No of input fields: 15-20; Exit scenario: 2-3; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 3-5; Business rules: Complex billing logic across multiple stores; Reports: Summary, Abstract, Residual Pressure reports | 0 | 2 | 2 | 16
O&M Billing - Contractor | CR Contractor: Dhara/Nirmal Reports, Village MWSR, DWSR, Summary Page & Approval | Approved Dhara/Nirmal reports integration in Contractor Bill; Village/Bulk/Supply Point MWSR reports; DWSR report in O&M Billing; Residual Pressure modification; Summary page (Gross O&M Bill, editable fields, CPI-IW, Yearly Factor, CPWI); Final Bill Submission; Net Payable Bill; Document Upload Tab (Save & Submit); Contractor Bill Approval Module; Draft & Final state management; No of input fields: 15-20; Exit scenario: 2-3; No of Validations: 10+; Prefilled fields: 30-50; API Integrations: 5+; Business rules: Complex billing calculation logic with CPI/CPWI across multiple data stores; Reports: >3 data sources, multiple complex reports | 0 | 1 | 3 | 18
O&M Billing - Workflow | O&M Billing Workflow between GM & Higher Officials | Workflow requirement understanding and analysis; Analysis of O&M billing workflow; New changes understanding; No of input fields: 5-10; Exit scenario: 1; No of Validations: 1-5; API Integrations: 2; Business rules: Single data store workflow | 2 | 1 | 0 | 5
TOTAL O&M ESTIMATION (CYCLE 4) | [5 empty] | 39
| Total Count |  |  |  |  | 39
| Productivity | 0.16
| Size | 39 | Point
| Effort | 243.75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 283.1156 | Man hours
| Permissible Range(Man hours) | 297.2714 | 268.9598

## Sahbhagita Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Sahbhagita Module - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Sahbhagita - Change Request GM/PM/Reports | Sahbhagita Report Modifications, Approval Module, Save as Draft | Survey Approval page: NGO count segregation fix; Role-based PIU dropdown & search validation; CP Manager RA Bill Approval; Modification on Sahbhagita report; Save as Draft functionality; No of input fields: 8-10 (filters); Exit scenario: 2-3; No of Validations: 3-5; API Integrations: 2-3; Reports: Enhanced tabular with 2-3 data sources | 2 | 2 | 0 | 8
TOTAL SAHBHAGITA ESTIMATION (CYCLE 4) | [5 empty] | 8
| Total Count |  |  |  |  | 8
| Productivity | 0.16
| Size | 8 | Point
| Effort | 50 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 58.075 | Man hours
| Permissible Range(Man hours) | 60.9787 | 55.1713

## CMMI Doc Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | CMMI Documentation - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
CMMI Doc - Phase 1 & 2 | CMMI Phase 1 & 2 Documentation: Statistical Analysis, Size Estimation | Streamlining Phase 1 and Phase 2 documents; Statistical analysis; Data Collection Cleaning and Model Preparation; Size-based Estimation documents; Other CMMI L5 documents; Training and Sessions; Internal & External Meetings with MQAS agency; No of input fields: 15-20; Exit scenario: 2 (Save, Approve); No of Validations: 10+; Business rules: CMMI L5 standards compliance across multiple data sources; Reports: Phase 1 & 2 comprehensive reports | 0 | 2 | 2 | 16
CMMI Doc - Phase 3 | CMMI Phase 3 Documentation: Audit Preparation & Review | Streamlining Phase 3 documents for CMMI L5 Audit; Review meetings for CMMI L5 Benchmark Appraisal calls and interviews; Organizing documents over SVN Repository; Showcasing Minitab, Promot and SVN tools; Preparing for CMMI L5 Audit interviews; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Business rules: CMMI L5 compliance; Reports: Phase 3 audit readiness report | 0 | 1 | 2 | 13
CMMI Doc - Phase 4 | CMMI Phase 4 Documentation: January to May 2026 Alignment | Working and aligning CMMI L5 Documentation for Phase 4; Enhancements and updating Promot with internal team efforts; Documentation according to CMMI L5 structure; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; Business rules: CMMI L5 standards; Reports: Phase 4 documentation summary | 0 | 2 | 1 | 11
TOTAL CMMI DOC ESTIMATION (CYCLE 4) | [5 empty] | 40
| Total Count |  |  |  |  | 40
| Productivity | 0.16
| Size | 40 | Point
| Effort | 250 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 290.375 | Man hours
| Permissible Range(Man hours) | 304.8938 | 275.8562

## SVS Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | SVS Water Supply Monitoring - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
SVS - Water Supply Monitoring | Daily Water Supply Monitoring Module - Requirement, Design, DB & Reports | Daily water supply module flow & wireframe; Department meeting & Project PIN document; API consuming from NIC Panchayat Darpan; Village master incorporation; Table & Function for Har Ghar Jal Yojana; DB function for reports; Site Fortify Security Audit; SVS Water Supply Monitoring Report; No of input fields: 10-15; Exit scenario: 2; No of Validations: 5-10; API Integrations: 3-5; Business rules: Water supply tracking across village data stores; Reports: Monitoring report with 2-3 data sources | 1 | 2 | 1 | 12
TOTAL SVS ESTIMATION (CYCLE 4) | [5 empty] | 12
| Total Count |  |  |  |  | 12
| Productivity | 0.16
| Size | 12 | Point
| Effort | 75 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 87.1125 | Man hours
| Permissible Range(Man hours) | 91.4681 | 82.7569

## AI Module Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | AI Module FHTC - Cycle 4
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
AI Module - FHTC Tap Connection | ML Model Implementation: Tap Connection Monitoring & Image Processing | ML model implementation for tap connection monitoring buffer region; FHTC Tap Connection AI validation; Machine Learning Predictive Model; Dataset preprocessing and annotation on Roboflow and local; Image processing in tap connection; Model retraining on RF-DETR; Bulk image testing; No of input fields: Not applicable; Exit scenario: Not applicable; No of Validations: Model accuracy validation; API Integrations: 2-3 (AI model, image processing); Business rules: Complex ML logic with multiple data processing stores; mobile App-UI: External AI component integration | 0 | 1 | 2 | 13
TOTAL AI MODULE ESTIMATION (CYCLE 4) | [5 empty] | 13
| Total Count |  |  |  |  | 13
| Productivity | 0.16
| Size | 13 | Point
| Effort | 81.25 | Man hours
| VAF | 1.01
| Risk contingency | 0.05
| Project Management | 0.1
| Total Planned effort | 94.3719 | Man hours
| Permissible Range(Man hours) | 99.0905 | 89.6533