## Version
Version | Date | Description | Prepared by | Reviewed by
1.3 | 2025-12-28 | Initial CR Draft | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal

## Anusharavan CR
CHANGE REQUEST LOG - CHANGE REQUEST ANUSHARAVAAN MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: January 2026 - May 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-ANU-001 | RFI-UPDT-2025-001 | Business Analyst | Senior BA | 08-11-2025 | Redesign new inner pages of Jal Rekha RFI module with improved navigation | Jal Rekha | Anusharavaan | UI/UX Redesign | High - Affects user experience and navigation efficiency across all users | In Progress | 20-11-2025 | Approved | High | Low
IMPACT AREA BREAKDOWN
Impact Area | Count | Percentage
UI/UX Redesign | 1
Report Generation | 1
Database Performance | 1
Workflow Management | 1
Database Architecture | 1
Reporting & Analytics | 1
PRIORITY BREAKDOWN
Priority Level | Count | Percentage
High | 3
Medium | 3
APPROVAL STATUS BREAKDOWN
Status | Count | Percentage
Approved | 4
Pending | 2
IMPLEMENTATION STATUS BREAKDOWN
Status | Count | Percentage
In Progress | 3
Completed | 1
Planned | 2
IMPLEMENTATION TIMELINE - ANUSHARAVAAN MODULE
CR No. | CR Code | Logging Date | Target Implementation Date
CR-ANU-001 | RFI-UPDT-2025-001 | 08-11-2025 | 20-11-2025
CR-ANU-002 | RFI-UPDT-2025-002 | 11-11-2025 | 15-11-2025
CR-ANU-003 | RFI-UPDT-2025-003 | 12-11-2025 | 25-11-2025
CR-ANU-004 | RFI-UPDT-2025-004 | 15-11-2025 | 02-12-2025
CR-ANU-005 | RFI-UPDT-2025-005 | 18-11-2025 | 05-12-2025
CR-ANU-006 | RFI-UPDT-2025-006 | 21-11-2025 | 22-11-2025
CMMI LEVEL 5 COMPLIANCE CHECKLIST
Control Point | Status | Evidence | Comments
Change Request Formalization | Compliant | CR Registry with unique IDs | All CRs have CR codes and logging dates
Impact Assessment | Compliant | Detailed impact analysis for each CR | Impact areas and scope clearly defined
Approval Workflow | Compliant | Approval status tracked for each CR | 4 approved, 2 pending - formal workflow
Implementation Tracking | Compliant | Implementation dates and status | All CRs have target dates and status
Risk Management | Compliant | Risk levels assigned to each CR | Low/Medium risk levels documented
Configuration Management | Compliant | CR database maintained | Comprehensive CR registry established

## Asset Mapping CR
CHANGE REQUEST LOG - CHANGE REQUEST Asset Mapping MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: January 2026 - May 2026
Asset Mapping
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
[6 empty] | Jal Rekha | Asset Mapping

## Bharosa CR
CHANGE REQUEST LOG - CHANGE REQUEST Bharosa MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
Bharosa – Factory Testing Web
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-BHR-FTW-001 | BHR-FTW-2025-001 | Business Analyst | Senior BA | 2025-03-11 | Redesign inner pages of Jal Rekha for Bharosa Factory Testing to improve navigation, consistency, and readability. | Jal Rekha | Bharosa – Factory Testing Web | UI/UX Redesign | High – Directly affects usability for all factory testing web users, reducing navigation errors and training effort. | Completed | 20-11-2025 | Approved | High | Medium
Bharosa – Factory Testing Mobile
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
Bharosa – Factory Testing Reports (CR – Report View)
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level

## Dhara CR
CHANGE REQUEST LOG - CHANGE REQUEST Dhara MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-DHARA-RPT-001 | DHARA-RPT-2025-001 | Business Analyst | Senior BA | 2025-08-11 | Redesign Dhara pages of Jal Rekha to align with updated UI standards and navigation for water supply reports. | Jal Rekha | Dhara – Reports | UI/UX – Dhara Pages | Medium – Improves usability of Dhara pages and reduces navigation issues for stakeholders. | Completed | 13-11-2025 | Approved | Medium | Low

## FHTC CR
CHANGE REQUEST LOG - CHANGE REQUEST FHTC MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: January 2026 - May 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-FHTC-GM-001 | FHTC-GM-2025-001 | QA Team | QA Lead | 2025-04-11 | Create detailed test scenarios for FHTC FETCH module covering FE and GM login, report access flows, negative cases, and regression set. | Jal Rekha | FHTC – GM/Contractor Reports | Test Design & Coverage | Medium – Ensures adequate regression coverage for FETCH module before and after CR deployment. | Completed | 14-11-2025 | Approved | High | Medium

## Master CR
CHANGE REQUEST LOG - CHANGE REQUEST Master MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: January 2026 - May 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
[6 empty] | Jal Rekha | Master

## Material CR
CHANGE REQUEST LOG - CHANGE REQUEST Material MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: January 2026 - May 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
Material

## Nirmal CR
CHANGE REQUEST LOG - CHANGE REQUEST Nirmal MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-NIR-WTP-001 | NIR-WTP-2025-001 | Business Analyst | Senior BA | 2025-05-11 | Apply WTP report parameter changes in Nirmal as per latest departmental requirement. | Jal Rekha | Nirmal – WTP/OHT/Beneficiary | Reporting – WTP | Medium – Keeps WTP reporting aligned with current parameters used by department. | Completed | 27-11-2025 | Approved | Medium | Low

## O& M Billing CR
CHANGE REQUEST LOG - CHANGE REQUEST O&M Billing MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: November 2025 - January 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-OMB-GM-001 | OMB-GM-2025-001 | Business Analyst | Senior BA | 2025-06-11 | Show GM 24 PIUs data to Kapil admin user after save and submit with proper access control in O&M Billing. | Jal Rekha | O&M Billing – GM | Access & Visibility | Medium – Provides Kapil admin consolidated visibility of GM 24 PIUs billing data post submission. | Completed | 22-11-2025 | Approved | Medium | Medium

## Sahbhagita CR
CHANGE REQUEST LOG - CHANGE REQUEST Sahbhagita MODULE
Project: Jal Rekha | Department: Public Health Engineering | Period: - January 2026 - May 2026
CR No. | CR Code | CR Raised By | Requirement Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Implementation Status | Implementation Date | Approval Status | Priority | Risk Level
CR-SHB-RPT-001 | SHB-RPT-2025-001 | Business Analyst | Senior BA | 22-11-2025 | Modify Sahbhagita survey reports as per new layout and updated data requirements. | Jal Rekha | Sahbhagita – Reports | Reporting – Layout & Data | Medium – Aligns survey report layout and contents with the latest departmental format. | Completed | 2025-03-12 | Approved | Medium | Low