## Change Requests
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Module Names in Hindi | HSC – परिणाम Parinam | Done
O&M – आकलन Aaklan
Master – विस्तृत Vistrit
2 | Dhara | 1. Dhara Report approve Villiage wise or OHT wise for a Range of 10 days each | In Progress
|  | 2. OHT Meter survey - divivde into 2 columns i) OHT Reading ii) OHT Water supply Status | In Progress
|  | 3. FE Entry TL can add remarks and finally GM only can approve it | In Progress
|  | 4. CWGM village mapping directly link to WTP | In Progress
3 | Bharosa | 1. Factory Testing - Add sub component item and its matching electrical component (updated list need to be provided by department | In Progress
|  | 2 Factory Testing - Add "Any Other" option in Sub component drop down and then Surveyor can write name in textbox | In Progress
4 | Nirmal & it's Reports | 1. Action on failed samples - into 2 columns i) failed sample rectified ii) failed sample pending | In Progress
|  | 2. Document upload by contractor will be approved by GM ( action on failed samples) | In Progress
|  | 3 "Raw water wise test report" name change to "Raw water test report" | Done
|  | 4 Remove 2 columns - No of samples failed and No of samples passed | In Progress
|  | 5 WTP Water test report - change 0.2 to 0.5 level of chlorine | In Progress
|  | 6 Remark comments for failed samples | Done
|  | 7. In Nirmal Final Report results failed parameter should appear in "RED Color" | In Progress
5 | RFI | 1 RFI transfer to new SQC | In Progress
|  | 2 Sorting to be done on - Reinspections and Rejected RFI's | In Progress
|  | 3 Contractor should see FE's Comments | In Progress
6 | Sahbhagita | 1) Show video at PM Manager ID login also, as it is visible to GM login | Done
7 | Issues | 1) Contractor when mapping - SQC/TPIA then their mobile number should be shown with their ID | In Progress
|  | 2) Chindwara and Ujjain issue of village not showing mapping issue | In Progress
|  | 3) Where Habitation not available there we can show village name | In Progress
|  | 4) When reading is 0 zero & showing no water supply - Remove that condition | In Progress
|  | 5) Anmol DeGM Chhatarpur - Sorting to be done on - Reinspections and Rejected RFI's & Contractor should see FE's Comments | In Progress
|  | 6) SQC's can Reset Password feature | In Progress
8 | O&M Billing - GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit | Done
|  | 2) Kapil id should be renamed to - "GM PIU O&M" | Done
|  | 3) For 1 village multiple time mapping should not be shown | Done
|  | 4) GM PIU and contractor name not coming correctly | Done
|  | 5) Agreement value column name and data should come correctly | Done
|  | 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" | Done
|  | 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | Done
9 | O&M Billing - Contractor | 1) Contractor -Billing | In Progress
|  | 2) CPI Base year and month calculation happen instantly | In Progress
|  | 3) Remark should come at the end in below report columns | In Progress
|  | 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report | In Progress
|  | 5) Complaint resolved date - it is "Resolved" word please check | In Progress
|  | 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement | In Progress
|  | 7) Event before 48 hours should not get edited and count increase happen after 48 hours | In Progress
|  | 8) Reason for relaxation only become mandatory after clicking YES | In Progress
|  | 9) Penalty Relaxation spelling correct it | In Progress
|  | 10) All above fields should be visible in below reports and upload documents show in report | In Progress
|  | 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf | In Progress
|  | 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check | In Progress
|  | 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label | In Progress

## Sheet1
Action Plan
S. No. | Module/Activity | Tasks | Owner
1 | FHTC | 1. Samagra API integration with FHTC | Development Team
2. Connection installed? (Radio button) i) Inside Premise & ii) Outside Premise
3. Accept or Reject ( Remark Mandatory for Reject option)
4. Reject Remark visible to Contractor
2 | Nirmal | 1. Raw water sample ( No limit to parameter) -> remove validation of Pass or Fail | Development Team
2. PPM b/w <0.2 to 5/10 from WTP
3. No Provision of Weekly & Monthly report - Report FE
4. Provide range for WTP till 200 meter and OHT till 50 meter.
3 | Bharosa | 1. Vendor where component wise material visible & provide one more option for vendor– “Any Other” | Development Team
2. FE can upload video upto 5 MB size only.
4 | Sahabhagita | 1. FE can upload video upto 5 MB of the Village – Activity of work & can upload photo as well. | Development Team
2. Can upload video on both mobile app and web portal as well.