Project Status Report

Project Status Report

Project: Jal Rekha

Govt. of Madhya Pradesh

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

Revision History

| Version | Date | Description | Prepared by | Reviewed by |
| --- | --- | --- | --- | --- |
| 1.0 | 28th February 2026 | Status report including completed activities, delays, and next steps | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal |

# Project Status Report

| Project Code: | MPSEDC/MPSSDI (GIS)/2025/00423 | Project Name: | Jal Rekha |
| --- | --- | --- | --- |

| Client: | 8, Arera Hills, Bhopal, Madhya Pradesh 462027 |
| --- | --- |

| Business Analyst: | Mr. Dheeraj Motiyani | Service Project Manager: | Mr. Tapan Khandelwal |
| --- | --- | --- | --- |

PLANNED ACTIVITIES – FEBRUARY 2026

| Planned Activities | Activities Completed | Schedule Variance | Effort Variance | DRE (%) |
| --- | --- | --- | --- | --- |
| CMMI L5 – Documentation (Code Review Docs, Cycle 3 Prep, UI-level Module Docs) | In Progress | On Schedule | Within Effort | N/A |
| O&M Billing GM – Bulk User Summary, Auto-generate RA Bill No., Wireframing Updation | Completed | On Schedule | Within Effort | 77% |
| O&M Billing – CR Contractor (Residual Pressure, Complaint Redressal, Summary Page, CPWI Mapping) | In Progress | On Schedule | Within Effort | 78% |
| Material Testing – GM/Contractor Login (FE Login History, Mobile Development, API Integration) | Completed | On Schedule | Within Effort | 80% |
| Anusharavan – UI Enhancement, View Details/Log View, Inspection Request Form Enhancement | Completed | On Schedule | Within Effort | 67% |
| Nirmal FE Mobile – Reports Production Move, FRC Test Data Fix, OHT Contractor Login Issue | Completed | On Schedule | Within Effort | 75% |
| Bharosa Factory Testing Web – UI Bug Fixes, Sidebar Icons | Completed | On Schedule | Within Effort | 100% |
| Dhara – Village Wise MWSR, Bulk Consumer MWSR, GM Approval & Billing Integration | In Progress | On Schedule | Within Effort | 66% |
| FHTC – FE Reports Update & UI Enhancement | Completed | On Schedule | Within Effort | Approx 70% |
| Dashboard – Bug Fixes & UI Update in Inner Pages | Completed | On Schedule | Within Effort | N/A |
| Sopan Contractor – OHT Mapping & Production WTP Scheme Bug Fix | Completed | On Schedule | Within Effort | N/A |
| Daily Inspection – View Logs Display Bug Fix | Completed | On Schedule | Within Effort | N/A |

RISK MANAGEMENT

| Risk Description | Risk Mitigation Plan | Status |
| --- | --- | --- |
| CMMI L5 documentation (Code Review docs, Cycle 3 prep, UI-level module docs across Dhara/Nirmal/Master/Sopan/Sahbhagita/FHTC/O&M) may face inconsistency or delay due to volume and multi-module coordination. | Maintained structured document tracking over SVN repository, assigned dedicated documentation slots per module, and ran periodic internal review to ensure consistency before MQAS submission. | Open – Monitoring |
| O&M Billing GM CR (Bulk User Summary, Auto-generate RA Bill No., Wireframing) may introduce bill-numbering duplication or summary calculation errors. | Validated RA Bill No. auto-generation logic with test cases across multiple schemes, cross-checked Bulk User Summary output against manual calculation, and retained rollback to manual bill-numbering for one cycle if needed. | Closed |
| O&M Billing Contractor CR (Residual Pressure PDF, Complaint Redressal, Summary Page, CPWI Mapping) in progress may cause incomplete bill submission or PDF generation failures for contractors. | Running phased UAT for each contractor-side tab (Residual Pressure, Complaint Redressal, Summary), validating PDF generation across sample bills, and providing manual PDF export fallback at PIU level until CR is fully closed. | Open – Monitoring |
| Material Testing GM/Contractor Login changes (FE Login History, Mobile Development, API Integration) may cause data sync mismatches between mobile and web after merge. | Performed field-level API integration testing with sample sites, validated FE Login History screen against web records, and kept manual web-entry fallback available if mobile sync fails. | Closed |
| Anusharavan UI Enhancement and Inspection Request Form changes may regress existing Contractor/FE View Details or Log View functionality. | Conducted peer review of UI and form changes, validated View Details/Log View screens across sample inspection records, and verified Play Store build before wider rollout. | Closed |
| Nirmal FE Mobile production move (Reports, FRC test data fix, OHT Contractor login issue) may cause incorrect residual chlorine values or sync issues for Agar Malwa and other schemes. | Cross-verified FRC test data fix against production data for affected schemes, resolved Agar Malwa OHT sync issue with targeted patch, and monitored post-release for similar issues across other PIUs. | Closed |
| Bharosa Factory Testing Web UI bug fixes and sidebar icon changes may affect existing navigation or module accessibility for TPIA/GM users. | Tested UI changes and sidebar icon additions on staging before production release, verified navigation paths for all user roles, and monitored user feedback post-release. | Closed |
| Dhara CR in progress (Village Wise MWSR, Bulk Consumer MWSR, GM Approval & Billing Integration) may produce inconsistent water-supply report data across schemes during transition. | Validated new report pages against sampled ground data, ran peer review on GM Approval and Billing Module integration logic, and retained access to legacy report version for cross-verification during rollout. | Open – Monitoring |
| FHTC FE Reports update and UI enhancement may impact Samagra-linked beneficiary report accuracy or display issues on updated UI. | Cross-checked updated FHTC reports against previous beneficiary data, validated UI enhancement across FE and GM logins, and maintained reconciled beneficiary list for critical schemes. | Closed |
| Dashboard bug fixes and UI updates in inner pages may cause layout or data-binding issues across different screen sizes or browsers. | Tested bug fixes across multiple browsers and screen resolutions, validated inner-page UI updates with sample data, and monitored for layout regressions post-release. | Closed |

DATE-WISE CHRONOLOGICAL MODULE & SUB-MODULE FUNCTIONALITY DETAIL – FEBRUARY 2026

| Module / Sub-Module | Date Range (February 2026) | Functionality / Activity Details | Hours Consumed |
| --- | --- | --- | --- |
| CMMI Documents | 02-Feb to 27-Feb-2026 | CMMI L5 Code Review documents for Bharosa & Material Testing; Cycle 3 document preparation; FHTC documentation; UI-level CMMI 5 documents for Dhara, Nirmal, Master, Sopan, Sahbhagita, FHTC, O&M. | 341.5 |
| O&M Billing GM | 02-Feb to 20-Feb-2026 | Bulk User Summary service creation, Auto-generate RA Bill No., GetDataByBillNo API resolution, Wireframing updation, Internal team meetings on Summary report changes. | 136.0 |
| Material Testing – GM/Contractor Login | 02-Feb to 27-Feb-2026 | Material Mobile API for FE Login (Anusharavan-aligned flow), GM Login web pages & service, SQC/TPIA login pages, Customized report for GM Login, FE Login History Screen UI & API Integration. | 92.0 |
| O&M Billing – CR Contractor | 06-Feb to 18-Feb-2026 | Bill number change request, Residual Pressure PDF modification, Complaint Redressal (incl. PDF), Summary Page for Gross O&M Bill, CPWI & Yearly Factor service creation. | 78.0 |
| Anusharavan | 04-Feb to 23-Feb-2026 | UI Enhancement for Contractor & FE Login, View Detail screen data display fix, Mobile API modification, View Details/Log View & Inspection Request Form Enhancement. | 49.0 |
| Nirmal – FE Mobile | 03-Feb to 26-Feb-2026 | Contractor-login-only scheme display implementation, UI/bug fixes in inner pages, production move after unit testing, FRC test data residual chlorine fix, Agar Malwa OHT Contractor login issue resolution. | 37.0 |
| Bharosa Factory Testing – Web | 20-Feb to 24-Feb-2026 | UI bug fixes as per documentation, sidebar module icon addition. | 21.0 |
| Dhara | 24-Feb to 28-Feb-2026 | New page & service creation for Approved Village Wise MWSR, Approved Bulk Wise Consumer MWSR Report development, GM Approval/Meter Function/Billing Module integration (Mobile App). | 20.0 |
| Dashboard | 24-Feb to 25-Feb-2026 | Bug fixes per bug sheet and UI update in inner pages. | 16.0 |
| FHTC – FE Reports | 05-Feb to 06-Feb-2026 | FHTC module report updates, UI enhancement, Mobile Application API integration. | 14.0 |
| O&M Billing – CR GM (HSC) | 05-Feb to 09-Feb-2026 | Residual Pressure PDF generation changes, Bulk report PDF generation, Abstract report changes. | 11.0 |
| Asset Mapping | 04-Feb to 05-Feb-2026 | OHT village mapping production data update fix, OHT search box on map (GET/SET data access methods). | 10.0 |
| Daily Inspection | 18-Feb-2026 | View Logs not displaying – mobile app bug fix. | 8.0 |
| Sopan Contractor | 11-Feb to 18-Feb-2026 | OHT mapping issue resolution, WTP scheme not binding in Contractor 110, SOPAN WTP production issue for Rewa Bansagar contractor. | 5.0 |
| Nirmal CR – Beneficiary Report | 26-Feb-2026 | Issue resolution in Nirmal Water Quality Report. | 4.0 |
| Department Meetings | 03-Feb to 27-Feb-2026 | VC with Tapan Sir on Nirmal report issues, Department VC for Jal Rekha modules, Server migration testing. | 3.5 |
| Cube Testing Requirement | 26-Feb-2026 | DB schema, Master and Design Table preparation. | 3.0 |
| Sahbhagita GM | 11-Feb-2026 | Live issue resolution – ISO not showing according to scheme. | 2.0 |

QUANTITATIVE INFORMATION (CYCLE 4 – CUMULATIVE THROUGH FEBRUARY 2026)

Productivity, Code Rate & Test Rate

| AS-IS |  |  |  |
| --- | --- | --- | --- |
|  | Productivity | Code_Rate | Test_Rate |
| Mean | 0.18452 | 0.31448 | 0.72905 |
| SD | 0.03006 | 0.01276 | 0.13391 |
| UCL | 0.20283 | 0.35277 | 1.13077 |
| LCL | 0.0225 | 0.27619 | 0.32734 |

| Target |  |
| --- | --- |
|  | Productivity |
| Mean | 0.20297 |
| SD | 0.05 |

| What If |  |  |  |
| --- | --- | --- | --- |
|  | Productivity | Code_Rate | Test_Rate |
| Mean | 0.19943 | 0.4 | 0.85 |
| SD | 0.05 | 0.05 | 0.05 |
| USL | 0.34943 | 0.55 | 1 |
| LSL | 0.04943 | 0.25 | 0.7 |

Cycle Time

| AS-IS |  |  |  |
| --- | --- | --- | --- |
|  | Cycle Time | Code_CT | Test_CT |
| Mean | 0.68252 | 0.27604 | 0.17336 |
| SD | 0.17128 | 0.09563 | 0.07439 |
| UCL | 1.19635 | 0.56292 | 0.39653 |
| LCL | 0.16869 | -0.01084 | -0.04981 |

Defect Removal Efficiency (DRE)

| AS-IS |  |  |
| --- | --- | --- |
|  | DRE | Code Review Per Size |
| Mean | 0.778 | 0.1992 |
| SD | 0.086 | 0.062 |
| UCL | 1.0368 | 0.384 |
| LCL | 0.5197 | 0.0145 |

| Target |  |
| --- | --- |
|  | DRE |
| Mean | 0.8 |
| SD | 0.1 |

| What If |  |  |
| --- | --- | --- |
|  | DRE | Code Review Per Size |
| Mean | 0.793 | 0.22 |
| SD | 0.1 | 0.05 |
| USL | 1.09348 | 0.37 |
| LSL | 0.49348 | 0.07 |

SUMMARY METRICS

| Metric | Planned Value | Actual Value | Remarks |
| --- | --- | --- | --- |
| Completed Modules / CRs | 8 | 8 | O&M Billing GM, Material Testing, Anusharavan, Nirmal FE Mobile, Bharosa Web, FHTC FE Reports, Dashboard, Sopan, Daily Inspection |
| In-Progress Tasks | 3 | 3 | CMMI L5 Documentation, O&M Billing Contractor CR, Dhara CR – targeted for completion by 31.03.2026 |

| Prepared by: | Mr. Dheeraj Motiyani, Sr. Business Analyst, MPSeDC | Date: | 28th February 2026 |
| --- | --- | --- | --- |
| Reviewed by: | Project Manager, Mr. Tapan Khandelwal | Date: |  |

Review Comments:

Project is progressing steadily during February 2026. O&M Billing GM, Material Testing GM/Contractor, Anusharavan, Nirmal FE Mobile, Bharosa Web, FHTC FE Reports, Dashboard, Sopan Contractor, and Daily Inspection modules were successfully completed and moved to production. CMMI L5 Documentation, O&M Billing Contractor CR, and Dhara CR (Village Wise MWSR, Bulk Consumer MWSR, GM Approval & Billing Integration) remain in progress and are targeted for completion by 31.03.2026. No critical risks remain open; three risks (CMMI L5 Documentation, O&M Billing Contractor CR, Dhara CR) are under active monitoring pending closure of their respective in-progress activities. Timely follow-up advised on CMMI L5 external review scheduling with MQAS and on Dhara report validation against ground data.

Page 1 of 1 | Jal Rekha – Project Status Report | February 2026