## July to October Cycle 2_V_1.11
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Defects | Recommendation of Review | Compliance Status | Date
1 |  | JAL REKHA | FHTC | FHTC | Tapan Khandelwal | Sunil Thakur | Missing Backend Role Validation (FE/GM/Contractor workflow controlled only at UI level) | Implement Role-Based Access Control (RBAC) at API layer, validate workflow state transitions, and log all status changes | Closed | 2025-08-22
2 | [6 empty] | Mandatory Beneficiary Photo validation not enforced at backend | Enforce photo validation at API level, validate file type & size, store securely with audit trail | Closed | 2025-08-28
3 | [6 empty] | No Proper API Logging & Change Control | Implement structured logging, add retry & timeout mechanism, maintain version control & approved Change Requests | Closed | 2025-09-11
4 |  |  |  | Change request FHTC |  |  | Requirement documents, RTM, and design documents may not be updated; integration risks not formally tested or approved | Update SRS, HLD/LLD, and RTM to reflect Samagra API changes; maintain integration test report, risk assessment, and formal approval before production deployment | Closed | 2025-10-23
5 |  |  | Dhara | Change Request - GM PIU User/ TL |  |  | Data mapping errors or unauthorized mapping changes | Implement role-based control, maintain mapping audit logs, and update SRS/RTM documentation | Closed | 2025-07-16
6 | [6 empty] | Incorrect approvals, backdated entries, lack of approval tracking | Enforce approval workflow, restrict month modification after closure, and maintain audit trail | Closed | 2025-07-24
7 | [6 empty] | Unauthorized data modification and data integrity issues | Implement role validation, log all modifications with timestamp & user ID, and maintain change history | Closed | 2025-08-01
8 |  |  |  | Change Request - FE / Mobile User |  |  | Incorrect default settings may cause wrong reporting and data inconsistency | Validate parameter changes at backend, update SRS/RTM & test cases, and maintain audit log for parameter modification | Closed | 2025-08-08
9 |  |  | Master | Change Request - GM / Contractor |  |  | Contractor edit functionality before final submission | Implement role-based validation at API level, restrict edit after submission lock, and maintain complete audit log (Old Value, New Value, User ID, Timestamp) | Closed | 2025-07-04
10 | [6 empty] | Village / Habitation / OHT / Outside Scheme mapping without strict control | Enforce workflow approval mechanism, prevent duplicate/cross-scheme mapping through backend validation, and maintain mapping history log | Closed | 2025-07-09
11 | [6 empty] | WTP meter mapping added for all 147 schemes without controlled validation | Perform bulk update validation with test report, maintain deployment approval (CR), and ensure rollback plan & version tagging before production release | Closed | 2025-07-15
12 |  |  |  | Change Request - FE Pipeline Mater |  |  | Pipeline master data integration with RFI module and habitation mapping at PIU level implemented without documented validation and impact analysis | Update SRS/RTM and design documents, perform integration testing with approval sign-off, and maintain audit trail for all mapping changes at PIU level | Closed | 2025-08-13
13 |  |  | Nirmal | Change request - WTP, OHT Report |  |  | WTP report parameter changes and buffer increase (200m) implemented without documented requirement update and validation impact analysis | Update SRS/RTM and design documents, validate buffer logic through test cases (boundary & GIS testing), obtain stakeholder approval, and maintain deployment/change approval record | Closed | 2025-07-15
14 |  |  |  | Change Request - Beneficiary Report |  |  |  |  | Closed
15 |  |  | Sahbhagita | Sahbhagita Reports |  |  | Report modification implemented without updated requirement documentation and testing evidence | Update SRS/RTM, revise report specification document, execute regression testing, and maintain approval & version control record before deployment | Closed | 2025-09-16
16 |  |  |  | Change Request -GM / PM |  |  | GM Sahbhagita report view changes and PM video upload functionality implemented without documented validation, storage policy, and access control review | Update SRS/RTM, implement role-based access & file size/type validation, ensure secure video storage with audit logging, and maintain UAT approval before production release | Closed | 2025-10-29
17 |  |  | Sopan | Change Request - Contractor (Web / Mobile) |  |  | OHT (Conventional & Precast), WTP, IPS form changes and delete functionality implemented without strict workflow control and impact analysis | Update SRS/RTM, restrict delete option with approval workflow, maintain audit log (old/new values), and conduct regression testing before release | Closed | 2025-07-15
18 | [6 empty] | Mobile APK logic change (Sopan OHT completion not shown in RFI module) implemented without documented integration validation | Perform integration testing with documented approval, update design documents, version tag APK release, and maintain change request record | Closed | 2025-08-01
19 |  |  |  | Change Request - GM Document Upload & Reports |  |  | GM edit & freeze functionality at each stage implemented without strict approval workflow and audit tracking | Implement role-based approval control, restrict edit after freeze, maintain detailed audit log (Old Date, New Date, User ID, Timestamp), and update SRS/RTM with approval flow documentation | Closed | 2025-08-12
20 | [6 empty] | Drill-down reports (OHT/WTP/Intake) and Panchnama/design PDF upload changes implemented without documented validation & data consistency checks | Perform regression testing, validate plan vs actual date logic, enforce file type/size validation for PDF uploads, and maintain UAT sign-off with version control record | Closed | 2025-09-07
21

## November to December Cycle 3_V_
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Defects | Recommendation of Review | Compliance Status | Date
1 |  | Jal Rekha | Anusharavaan | RFI Stage Updations and Reports Modifications | Tapan Khandelwal | Sunil Thakur | UI redesign of Jal Rekha inner pages implemented without usability validation and requirement traceability update | Update UI design document, conduct UAT for redesigned pages, and maintain version control with stakeholder approval | Closed | 2025-11-11
2 | [6 empty] | RFI (MBR changes & status-based report updates) implemented without documented workflow validation | Update SRS/RTM, validate status transitions (Pending/In Progress/Approval), and perform regression testing before deployment | Closed | 2025-11-14
3 | [6 empty] | Inline query and function changes done without impact analysis | Conduct database impact analysis, review performance & security implications, and maintain code review & change approval documentation | Closed | 2025-11-19
4 | [6 empty] | Database-level activity approval workflow designed without formal process documentation | Document workflow logic (state transitions), implement audit trail logging, and maintain integration test report with approval sign-off | Closed | 2025-11-20
5 |  |  | FHTC | GM / Contractor Reports | Tapan Khandelwal | Sunil Thakur | Report updates and FETCH module changes (FE/GM login) implemented without updated requirement traceability and regression testing evidence | Update SRS/RTM, execute regression test cases for FE & GM roles, and maintain signed test execution & approval record | Closed | 2025-11-10
6 | [6 empty] | SQL query fixes, database table/function updates, and PostgreSQL optimization performed without formal impact analysis and version-controlled DB change management | Conduct database impact analysis, maintain DB version scripts with rollback plan, document performance testing results, and ensure CR approval before deployment | Closed | 2025-11-12
7 |  |  |  | CR - FE / Reports |  |  | FHTC village scheme mapping bug fixes and Samagra multiple family ID issue handled without formal root cause analysis and integration validation | Perform root cause analysis (RCA), validate data integrity with Samagra API, maintain bug-fix documentation, and ensure impact testing with approved change record | Closed | 2025-12-09
8 |  |  | Dhara CR | Change Request - Dhara Reports | Tapan Khandelwal | Sunil Thakur | Jal Rekha page redesign and multiple water supply report updates implemented without documented requirement traceability and regression validation | Update SRS/RTM, conduct regression testing for all updated reports (DWSR, MWSR, Scheme, Village, Bulk User, UFW), obtain stakeholder sign-off, and maintain version control record | Closed | 2025-11-10
9 | [6 empty] | Meter mapping updates and Dhara module (WTP to Village meter reading) changes performed without formal impact analysis and workflow validation | Perform database impact analysis, validate meter mapping logic with test cases, maintain audit trail for mapping changes, and ensure approved change request before deployment | Closed | 2025-11-12
10 |  |  |  | Security Vulnerability - Sonarcube & SVN |  |  | Password encryption, Crashlytics vulnerability handling, and live deployment changes implemented without documented security review and penetration testing evidence | Conduct formal security assessment (VAPT), document encryption mechanism & key management policy, maintain security test report, and obtain deployment approval before production release | Closed | 2025-12-12
11 | [6 empty] | PostgreSQL query updates, Function/SP modifications, and Dhara report optimization performed without structured impact analysis and DB version control | Maintain database version scripts with rollback plan, document performance benchmarking results, conduct regression testing, and ensure approved change request before deployment | Closed | 2025-12-17
12 |  |  | Nirmal | Change request - WTP, OHT, Beneficiary Report | Tapan Khandelwal | Sunil Thakur | Multiple drill-down additions (OHT, WTP, Raw Water, Beneficiary) without documented workflow validation | Document drill-down hierarchy, validate data consistency at each level, and maintain UAT approval before release | Closed | 2025-11-07
13 | [6 empty] | Addition of Action Remarks (Contractor & GM) without audit tracking control | Implement role-based access, maintain audit log (User, Timestamp, Remarks History), and restrict post-approval edits | Closed | 2025-11-17
14 | [6 empty] | Increased component filters & OHT village mapping display without backend validation checks | Validate filter logic at API level, prevent duplicate/incorrect mapping, and test report accuracy with sample data | Closed | 2025-11-21
15 | [6 empty] | UI modifications (chat-box style remarks, popup tables, search & comments box) without usability & security validation | Conduct UI/UAT testing, validate input sanitization, and maintain documented approval for UI changes | Closed | 2025-11-26
16 |  |  |  | Change Request - Raw water Report |  |  | Date range filter added without validating boundary conditions and performance impact | Validate date range logic at backend, test large data scenarios, and document filter behavior in SRS | Closed | 2025-12-08
17 | [6 empty] | Search by Water Sample ID implemented without input validation & indexing analysis | Apply backend validation, prevent SQL injection, and optimize DB indexing for performance | Closed | 2025-12-10
18 | [6 empty] | RawWater_Samples_Tested_Detail query added without integration & data accuracy testing | Perform API & DB integration testing, validate sample data mapping, and maintain test execution report | Closed | 2025-12-11
19 | [6 empty] | Addition of columns and drill-down for passed/failed records without regression validation | Conduct regression testing, verify calculation logic, and document drill-down data consistency | Closed | 2025-12-12
20 |  |  | Sahbhagita | Sahbhagita Reports | Tapan Khandelwal | Sunil Thakur | NGO Summary report count logic (Approved/Rejected/No Action) added without data consistency validation | Validate status calculation logic at DB level and perform cross-verification testing | Closed | 2025-11-28
21 |  |  |  | Change Request -GM / PM |  |  | Lack of role-based access validation for approval pages | Implement RBAC at API level and log user actions with timestamp | Closed | 2025-12-08
22 | [6 empty] | Village-wise trigger change (Get_VillageForApproval) implemented without documented API validation & regression testing | Update API specification, validate trigger logic at backend, and conduct regression testing with approval record | Closed | 2025-12-10