## SOPAN
Internal Code Review-SOPAN
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Recommendation of Review | compliance status | date
1 |  | Jal Rekha | SOPAN | Contractor Login | Sunil Thakur | Leena Rane | 1.Contractor can select OHT / WTP / Intake / IPS from dropdown 2.Construction type (Pre-Cast / Conventional) selection validated 3.Planned Start Date and Planned Completion Date are mandatory 4.Logical date validation enforced 5.Contractor cannot modify records 6.Submitted data correctly routed to GM module | Closed
2 |  | Jal Rekha | SOPAN | GMLogin | Sunil Thakur | Leena Rane | 1.GM can view contractor-submitted records 2.GM can enter Actual Start Date and Actual Completion Date 3.GM can freez, approve, reject 4.Remarks mandatory for rejection / clarification 5.GM approval / rejection actions logged 6.GM–Contractor communication log maintained 7. Approval rules enforced through Business Rule Engine | Closed