## Sheet1
Revision History
Date | Version | Description | Prepared by | Reviewed or approved by
2025-11-09 | 1 | Initial BRTM for SRS v1.2 | Sr. Business Analyst | Project Lead

## FHTC_BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
FHTC-FR-01 | UC-FHTC-01 FE Login to FHTC Module | FE logs into the FHTC mobile app using credentials to access household survey and testing functions | UTC_FHTC_001 | TC.009, TC.010, TC.011, TC.012, TC.013, TC.014 | TC.001, TC.002, TC.003, TC.004, TC.005, TC.006, TC.007, TC.008 | FHTC User Manual | NA | 1.1.7.3
FHTC-FR-02 | UC-FHTC-02 – FE Reports – Household Visit | FE selects a village, loads the household list via API, and captures GPS location and visit status for each household visit. | UTC_FHTC_002 | TC.023, TC.024, TC.025, TC.026, TC.027, TC.028 | TC.015, TC.016, TC.017, TC.018, TC.019, TC.020, TC.021, TC.022 | FHTC User Manual | NA | 1.1.7.4
FHTC-FR-03 | UC-FHTC-03 Capture Tap Status, Beneficiary Details and Photos | FE examines a tap connection at household, records tap status (Proper/Not Proper), updates beneficiary information, and uploads beneficiary and tap photos. | UTC_FHTC_003 | TC.037, TC.038, TC.039, TC.040, TC.041 | TC.029, TC.030, TC.031, TC.032, TC.033, TC.034, TC.035, TC.036 | FHTC User Manual | BugID: 19785 | 1.1.7.4
FHTC-FR-04 | UC-FHTC-04 Send Rejected Connections to GM & Contractor | FE marks a tap connection as Not Proper (defective or missing), records mandatory rejection reason | UTC_FHTC_004 | TC.050, TC.051, TC.052, TC.053, TC.054, TC.055 | TC.042, TC.043, TC.044, TC.045, TC.046, TC.047, TC.048, TC.049 | FHTC User Manual | NA | 1.1.7.4
FHTC-FR-05 | UC-FHTC-05 Send Accepted Connections to GM | FE marks a tap connection as Proper (correctly installed), ensures all mandatory documentation is complete | UTC_FHTC_005 | TC.064, TC.065, TC.066, TC.067, TC.068 | TC.056, TC.057, TC.058, TC.059, TC.060, TC.061, TC.062, TC.063 | FHTC User Manual | BugID: 19787 | 1.1.7.4
FHTC-FR-06 | UC-FHTC-03 HSC Report with Mandatory Beneficiary Photo | HSC Report with Mandatory Beneficiary Photo | UTC_FHTC_006 | TC.077, TC.078, TC.079, TC.080, TC.081 | TC.069, TC.070, TC.071, TC.072, TC.073, TC.074, TC.075, TC.076 | FHTC User Manual | NA | 1.1.7.4
FHTC-FR-07 | UC-FHTC-02 API Whitelisting and Security Control | FHTC – Security & API | UTC_FHTC_007 | TC.089, TC.090, TC.091, TC.092, TC.093 | TC.082, TC.083, TC.084, TC.085, TC.086, TC.087, TC.088 | FHTC User Manual | NA | 1.1.7.4
FHTC-FR-08 | UC-FHTC-02 Replace NIC Integration with Samagra API | System shall replace NIC services with Samagra API for household data | UTC_FHTC_008 | TC.102, TC.103, TC.104, TC.105, TC.106 | TC.094, TC.095, TC.096, TC.097, TC.098, TC.099, TC.100, TC.101 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-09 | UC-FHTC-02 Update FHTC APK to Use Samagra API | Mobile APK shall be updated so FE devices use Samagra endpoints for household data, preserving offline-first behavior and providing version/upgrade handling. | UTC_FHTC_009 | TC.115, TC.116, TC.117, TC.118 | TC.107, TC.108, TC.109, TC.110, TC.111, TC.112, TC.113, TC.114 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-10 | UC-FHTC-04 Updated HSC Fields and Samagra Prefill | Updated HSC Fields and Samagra Prefill | UTC_FHTC_010 | TC.127, TC.128, TC.129, TC.130 | TC.119, TC.120, TC.121, TC.122, TC.123, TC.124, TC.125, TC.126 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-11 | UC-FHTC-02 GM Drill-down Monitoring Reports | GM Drill-down Monitoring Reports | UTC_FHTC_011 | TC.139, TC.140, TC.141, TC.142 | TC.131, TC.132, TC.133, TC.134, TC.135, TC.136, TC.137, TC.138 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-12 | UC-FHTC-03 Contractor Update of Tap Connection with Photograph to GM | Contractor Update of Tap Connection with Photograph to GM | UTC_FHTC_012 | TC.151, TC.152, TC.153 | TC.143, TC.144, TC.145, TC.146, TC.147, TC.148, TC.149, TC.150 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-13 | UC-FHTC-03 Inside/Outside Premise Connection Flag | Inside/Outside Premise Connection Flag | UTC_FHTC_013 | TC.162, TC.163 | TC.154, TC.155, TC.156, TC.157, TC.158, TC.159, TC.160, TC.161 | FHTC User Manual | NA | 1.1.7.5
FHTC-FR-14 | UC-FHTC-04 Reject Remark Visibility to Contractor | System shall ensure that rejection remarks recorded by FE/GM for tap connections are visible to the contractor in their interface to enable corrective action. | UTC_FHTC_014 | TC.172, TC.173, TC.174 | TC.164, TC.165, TC.166, TC.167, TC.168, TC.169, TC.170, TC.171 | FHTC User Manual | NA | 1.1.7.5

## O&M Billing_BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name: | Jalrekha - O&M Billing(Aaklan)
Date Updated On: | 22-02-2026
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
OM-FR-03 | UC-OMCR-03 Scheme Status and CPI-based Financial Calculation | Contractor selects CPI base year and month and sees all dependent amounts recalculated instantly | UTC-OM-C2-12, UTC-OM-C2-13, UTC-OM-C2-14, UTC-OM-C2-05 | TC.035, TC.036, TC.037, TC.040, TC.042, TC.044 | TC.031, TC.032, TC.033, TC.034, TC.038, TC.039, TC.041, TC.043, TC.045 | O&M User Manual | NA | 1.1.6.5
OM-FR-04 | UC-OMCR-04 Document Upload and Data Fetch from Dhara & Nirmal | O&M Billing – GM – Cross-module Data | UTC-OM-C2-21, UTC-OM-C2-22, UTC-OM-C2-23, UTC-OM-C2-24, UTC-OM-C2-45, UTC-OM-C2-46 | TC.048, TC.049, TC.050, TC.052, TC.054, TC.056, TC.058, TC.060 | TC.046, TC.047, TC.051, TC.053, TC.055, TC.057, TC.059 | O&M User Manual | NA | 1.1.6.5
OM-FR-06 | UC-OMCR-02 Scheme Assignment to Contractor – Profile | O&M Billing – Contractor – Profile | UTC-OM-C2-46, UTC-OM-C2-47, UTC-OM-C2-48 | TC.004, TC.005, TC.006 | TC.001, TC.002, TC.003 | O&M User Manual | BugID: 19798 | 1.1.6.5
OM-FR-07 | UC-OMCR-03 O&M Billing – Contractor – Finance | Contractor CPI-based Financial Inputs | UTC-OM-C2-12, UTC-OM-C2-13, UTC-OM-C2-14 | TC.010, TC.011, TC.012 | TC.007, TC.008, TC.009 | O&M User Manual | BugID: 19791 | 1.1.6.5
OM-FR-08 | UC-OMCR-02 Bill Generation | O&M Billing – Contractor – Bill Structure | UTC-OM-C2-15, UTC-OM-C2-16, UTC-OM-C2-17 | TC.016, TC.017, TC.018 | TC.013, TC.014, TC.015 | O&M User Manual | BugID: 19791 | 1.1.6.5
OM-FR-09 | UC-OMCR-02 Manpower & Residual Pressure Capture | O&M Billing – Contractor – Ops Data | UTC-OM-C2-04, UTC-OM-C2-05, UTC-OM-C2-06 | TC.022, TC.023, TC.024 | TC.019, TC.020, TC.021 | O&M User Manual | BugID: 19793 | 1.1.6.5
OM-FR-12 | UC-OMCR-02 Dhara Water-Supply Data Integration for Billing | O&M Billing – Contractor – Dhara Data | UTC-OM-C2-45 | TC.040, TC.041, TC.042 | TC.037, TC.038, TC.039 | O&M User Manual | NA | 1.1.6.5
OM-FR-13 | UC-OMCR-02 Save as Draft for GM Billing Forms | O&M Billing – GM – Save as Draft | UTC-OM-C2-01, UTC-OM-C2-02, UTC-OM-C2-03, UTC-OM-C2-27 | TC.046, TC.047, TC.048 | TC.043, TC.044, TC.045 | O&M User Manual | NA | 1.1.6.5
OM-FR-14 | UC-OMCR-02 Correct Census Population Hierarchy & Editable Values | O&M Billing – GM – Census & Hierarchy | UTC-OM-C2-04, UTC-OM-C2-05, UTC-OM-C2-06 | TC.052, TC.053, TC.054 | TC.049, TC.050, TC.051 | O&M User Manual | BugID: 19796, BugID: 19797 | 1.1.6.5
OM-FR-15 | UC-OMCR-07 "Other" Option in SLBM Norms & Penalty Dropdowns | O&M Billing – GM – SLBM "Other" | UTC-OM-C2-07, UTC-OM-C2-08, UTC-OM-C2-09, UTC-OM-C2-35 | TC.058, TC.059, TC.060 | TC.055, TC.056, TC.057 | O&M User Manual | NA | 1.1.6.5
OM-FR-16 | UC-OMCR-05 Penalty Label and Radio-button Changes | O&M Billing – GM – Penalty UI | UTC-OM-C2-10, UTC-OM-C2-11, UTC-OM-C2-30 | TC.064, TC.065, TC.066 | TC.061, TC.062, TC.063 | O&M User Manual | NA | 1.1.6.5
OM-FR-17 | UC-OMCR-03 CPI-W Increment Type and Yearly Calculation | System shall support multiple increment types based on CPI-W | UTC-OM-C2-12, UTC-OM-C2-13, UTC-OM-C2-14 | TC.070, TC.071, TC.072 | TC.067, TC.068, TC.069 | O&M User Manual | NA | 1.1.6.5
OM-FR-18 | UC-OMCR-04 Scheme Status Section with Documents & O&M Dates | O&M Billing – GM – Scheme Lifecycle | UTC-OM-C2-15, UTC-OM-C2-16, UTC-OM-C2-17 | TC.076, TC.077, TC.078 | TC.073, TC.074, TC.075 | O&M User Manual | NA | 1.1.6.5
OM-FR-19 | UC-OMCR-07 GST Services Option for O&M | System shall provide GST applicability and rate selection | UTC-OM-C2-18, UTC-OM-C2-19, UTC-OM-C2-20 | TC.082, TC.083, TC.084 | TC.079, TC.080, TC.081 | O&M User Manual | NA | 1.1.6.5
OM-FR-20 | UC-OMCR-05 Document Upload Yes/No with Screen Freeze | Document Upload Yes/No with Screen Freeze | UTC-OM-C2-21, UTC-OM-C2-22, UTC-OM-C2-23, UTC-OM-C2-24 | TC.088, TC.089, TC.090 | TC.085, TC.086, TC.087 | O&M User Manual | NA | 1.1.6.5
OM-FR-23 | UC-OMCR-07 Workflow Engine for Status & RA Bill Data | Workflow Engine for Status & RA Bill Data | UTC-OM-C2-41, UTC-OM-C2-42 | TC.106, TC.107, TC.108 | TC.103, TC.104, TC.105 | O&M User Manual | NA | 1.1.6.5
OM-FR-25 | UC-OMCR-04 Edit & Resend Bills to PIU GM and Contractor | O&M Billing – Workflow – Edit & Resend | UTC-OM-C2-41, UTC-OM-C2-42 | TC.118, TC.119, TC.120 | TC.115, TC.116, TC.117 | O&M User Manual | NA | 1.1.6.5
OM-FR-26 | UC-OMCR-04 PMC Recommendation Letter & Annexure Verification | O&M Billing – PMC – Recommendation | UTC-OM-C2-22, UTC-OM-C2-23 | TC.124, TC.125, TC.126 | TC.121, TC.122, TC.123 | O&M User Manual | NA | 1.1.6.5
OM-FR-27 | UC-OMCR-04 Meter Functional / Non-functional Flag | O&M Billing – Meter Status | UTC-OM-C2-07, UTC-OM-C2-08, UTC-OM-C2-09 | TC.130, TC.131, TC.132 | TC.127, TC.128, TC.129 | O&M User Manual | NA | 1.1.6.5
OM-FR-28 | UC-OMCR-01 KL Load Supply Capture | O&M Billing – Load Data | UTC-OM-C2-01, UTC-OM-C2-02 | TC.136, TC.137, TC.138 | TC.133, TC.134, TC.135 | O&M User Manual | NA | 1.1.6.5
OM-FR-21 | UC-OMCR-01 GM PIU/SQC Edit & Forward of Bills | System shall allow GM PIU and SQC to edit permitted bill fields, record remarks, and forward bills | UTC-OM-C3-01, UTC-OM-C3-02, UTC-OM-C3-03, UTC-OM-C3-04 | TC.094, TC.095, TC.096 | TC.091, TC.092, TC.093 | O&M User Manual | NA | 1.1.6.5
OM-FR-22 | UC-OMCR-01 Higher-official Approval Flow (GM O&M → CGM → PD → CFO → CA → MD → Deputy Manager) | System shall implement the full O&M approval hierarchy, allowing each role to review remarks | UTC-OM-C3-01, UTC-OM-C3-02, UTC-OM-C3-03, UTC-OM-C3-04 | TC.100, TC.101, TC.102 | TC.097, TC.098, TC.099 | O&M User Manual | NA | 1.1.6.5
OM-FR-23 | UC-OMCR-07 Workflow Engine for Status & RA Bill Data | Workflow Engine for Status & RA Bill Data | UTC-OM-C2-41, UTC-OM-C2-42, UTC-OM-C3-11 | TC.106, TC.107, TC.108 | TC.103, TC.104, TC.105 | O&M User Manual | NA | 1.1.6.5
OM-FR-24 | UC-OMCR-03 RA Bill Month Increment Logic | System shall generate RA bills by scheme and contractor with correct bill-month progression (first year, then next month plus one day as per rule), and maintain bill-month history. | UTC-OM-C2-13, UTC-OM-C2-14, UTC-OM-C3-30, UTC-OM-C3-31 | TC.112, TC.113, TC.114 | TC.109, TC.110, TC.111 | O&M User Manual | NA | 1.1.6.5
OM-FR-25 | UC-OMCR-04 Edit & Resend Bills to PIU GM and Contractor | O&M Billing – Workflow – Edit & Resend | UTC-OM-C2-41, UTC-OM-C2-42, UTC-OM-C3-15 | TC.118, TC.119, TC.120 | TC.115, TC.116, TC.117 | O&M User Manual | NA | 1.1.6.5
OM-FR-26 | UC-OMCR-04 PMC Recommendation Letter & Annexure Verification | O&M Billing – PMC – Recommendation | UTC-OM-C2-22, UTC-OM-C2-23, UTC-OM-C3-28 | TC.124, TC.125, TC.126 | TC.121, TC.122, TC.123 | O&M User Manual | NA | 1.1.6.5
OM-FR-27 | UC-OMCR-04 Meter Functional / Non-functional Flag | O&M Billing – Meter Status | UTC-OM-C2-07, UTC-OM-C2-08, UTC-OM-C2-09 | TC.130, TC.131, TC.132 | TC.127, TC.128, TC.129 | O&M User Manual | NA | 1.1.6.5
OM-FR-28 | UC-OMCR-01 KL Load Supply Capture | O&M Billing – Load Data | UTC-OM-C2-01, UTC-OM-C2-02, UTC-OM-C3-21 | TC.136, TC.137, TC.138 | TC.133, TC.134, TC.135 | O&M User Manual | NA | 1.1.6.5

## Bharosa BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
BH-FT-FR-01,BH-FT-FR-02 | UC- BH-01 -– Factory Testing Web – GM | Register Meter Against Scheme Component | UTC_RTC_01, UTC_RTC_02, UTC_RTC_03, UTC_RTC_04, UTC_RTC_05, UTC_RTC_06, UTC_RTC_07, UTC_RTC_08, UTC_RTC_09, UTC_RTC_10 | TC.004, TC.005, TC.006 | TC.001, TC.002, TC.003 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-02 | UC- BH-02Factory Testing Web – Assignment | GM Assign Components to Inspector/TPIA with Notifications | UTC_RTC_011, UTC_RTC_012, UTC_RTC_013, UTC_RTC_014, UTC_RTC_015, UTC_RTC_016, UTC_RTC_017 | TC.010, TC.011, TC.012 | TC.007, TC.008, TC.009 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-03 | UC- BH-03– Factory Testing Web – Reports | RQP User Form | NA | TC.016, TC.017, TC.018 | TC.013, TC.014, TC.015 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-04 | UC- BH-04Factory Testing Web – Vendor | Role Approval & Application Dashboard | UTC_RTC_018, UTC_RTC_019, UTC_RTC_020, UTC_RTC_021, UTC_RTC_022, UTC_RTC_023, UTC_RTC_024, UTC_RTC_025, UTC_RTC_026, UTC_RTC_027 | TC.022, TC.023, TC.024 | TC.019, TC.020, TC.021 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-05,BH-FT-FR-04 | UC- BH-05– System Integration – Inspectors | Inspector Master APIs (Insert/Get/Update) | UTC_RTC_028, UTC_RTC_029, UTC_RTC_030, UTC_RTC_031, UTC_RTC_032, UTC_RTC_033, UTC_RTC_034, UTC_RTC_035, UTC_RTC_036, UTC_RTC_037, UTC_RTC_038, UTC_RTC_039, UTC_RTC_040, UTC_RTC_041, UTC_RTC_042 | TC.028, TC.029, TC.030 | TC.025, TC.026, TC.027 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-06 | UC- BH-04System Integration – Components | System shall integrate with Master and Sopan component masters so that Bharosa maintains synchronized lists of components (OHT/WTP/IPS/Intake/Pipe) without duplicates or orphans. | NA | TC.034, TC.035, TC.036 | TC.031, TC.032, TC.033 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-07 | UC- BH-04 Generate Compliance Reports & Certificates | System shall generate compliance reports and test certificates from test data and vendor/component masters, support digital signing, and archive reports for the configured retention period. | UTC_RTC_043, UTC_RTC_044, UTC_RTC_045, UTC_RTC_046, UTC_RTC_047, UTC_RTC_048, UTC_RTC_049, UTC_RTC_050, UTC_RTC_051, UTC_RTC_052, UTC_RTC_053, UTC_RTC_054, UTC_RTC_055, UTC_RTC_056, UTC_RTC_057 | TC.040, TC.041, TC.042 | TC.037, TC.038, TC.039 | Bharosa User Manaul | BugID: 19806 | 1.1.7.5
BH-FT-FR-08 | UC- BH-04 – Factory Testing Web – Dashboard | System shall provide a summary dashboard for GM showing KPIs (total tests, pass/fail, pending) and component/vendor-wise summaries with export capability. | UTC_RTC_58, UTC_RTC_59, UTC_RTC_60, UTC_RTC_61, UTC_RTC_62, UTC_RTC_63, UTC_RTC_64, UTC_RTC_65, UTC_RTC_66, UTC_RTC_67, UTC_RTC_68, UTC_RTC_69, UTC_RTC_70, UTC_RTC_71, UTC_RTC_72 | TC.046, TC.047, TC.048 | TC.043, TC.044, TC.045 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-09 | UC- BH-02Factory Testing Mobile – Inspector | Mobile app shall allow inspectors to log in to the Bharosa Factory Testing module and access assigned tasks offline based on last successful sync. | UTC_RTC_073, UTC_RTC_074, UTC_RTC_075, UTC_RTC_076, UTC_RTC_077, UTC_RTC_078, UTC_RTC_079, UTC_RTC_080, UTC_RTC_081, UTC_RTC_082, UTC_RTC_083, UTC_RTC_084, UTC_RTC_085, UTC_RTC_086, UTC_RTC_087 | TC.052, TC.053, TC.054 | TC.049, TC.050, TC.051 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-10 | Factory Testing Mobile – Tasks | Fetch Assigned Component Details on Mobile | UTC_RTC_088, UTC_RTC_089, UTC_RTC_090, UTC_RTC_091, UTC_RTC_092, UTC_RTC_093, UTC_RTC_094, UTC_RTC_095, UTC_RTC_096, UTC_RTC_097, UTC_RTC_098, UTC_RTC_099, UTC_RTC_100, UTC_RTC_101, UTC_RTC_102 | TC.058, TC.059, TC.060 | TC.055, TC.056, TC.057 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-11, BH-FT-FR-12 | Factory Testing Mobile – Images & Document Testing | Record Inspector & Component Test Details | UTC_RTC_103, UTC_RTC_104, UTC_RTC_105, UTC_RTC_106, UTC_RTC_107, UTC_RTC_108, UTC_RTC_109, UTC_RTC_110, UTC_RTC_111, UTC_RTC_112, UTC_RTC_113, UTC_RTC_114, UTC_RTC_115, UTC_RTC_116, UTC_RTC_117 | TC.064, TC.065, TC.066, TC.070, TC.071, TC.072 | TC.061, TC.062, TC.063, TC.067, TC.068, TC.069 | Bharosa User Manaul | BugID: 19804 | 1.1.7.5
BH-FT-FR-13 | UC-BH-03Factory Testing Mobile – Inspectors |  | UTC_RTC_158, UTC_RTC_159, UTC_RTC_160, UTC_RTC_161, UTC_RTC_162, UTC_RTC_163, UTC_RTC_164, UTC_RTC_165, UTC_RTC_166, UTC_RTC_167, UTC_RTC_168, UTC_RTC_169, UTC_RTC_170, UTC_RTC_171, UTC_RTC_172 | TC.076, TC.077, TC.078 | TC.073, TC.074, TC.075 | Bharosa User Manaul | NA | 1.1.7.5
BH-FT-FR-14 | – System Integration – Bharosa Core | Complete information bharosa module | UTC_RTC_118, UTC_RTC_119, UTC_RTC_120, UTC_RTC_121, UTC_RTC_122 | TC.082, TC.083, TC.084 | TC.079, TC.080, TC.081 | Bharosa User Manaul | NA | 1.1.7.5

## Dhara BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
FR‑DHCR‑01 | UC-DHCR-01-OHT Habitation Mapping | GM/TL Map Habitations to OHT (Individual or OHT-wise) | UTC_DHA_UI_03, UTC_DHA_UI_04 | TC.004, TC.005 | TC.001, TC.002, TC.003 | Dhara User Manual | NA | 1.1.6.1
FR‑DHCR‑02 | UC-DHCR-02-OHT CWGM/CWPM Mapping | Mapping of components | UTC_DHA_UI_02, UTC_DHA_UI_04 | TC.009, TC.010 | TC.006, TC.007, TC.008 | Dhara User Manual | NA | 1.1.6.1
FR‑DHCR‑03 | UC-DHCR-02 Dhara CR – GM/PIU/TL – Habitation & Component Configuration | System shall provide month‑wise open/close control for Intake, OHT, WTP and Bulk User records so that meter readings are editable only in open months and read‑only after close/approval. | UTC_DHA_UI_07, UTC_DHA_UI_08, UTC_DHA_UI_09 | TC.014, TC.015 | TC.011, TC.012, TC.013 | Dhara User Manual | NA | 1.1.6.2
FR‑DHCR‑04 | UC-DHCR-03Dhara CR – GM/PIU/TL – Habitation & Component Configuration | System shall allow assignment of revised Intake/WTP/OHT/Village mappings to FE users so that only assigned components appear in the Dhara FE mobile task list. | UTC_DHA_UI_05, UTC_DHA_MOB_01 | TC.019, TC.020 | TC.016, TC.017, TC.018 | Dhara User Manual | NA | 1.1.6.2
FR‑DHCR‑05 | UC-DHCR-03Dhara CR – FE/Mobile – Meter Survey Behaviour Changes |  | UTC_DHA_MOB_02, UTC_DHA_MOB_03, UTC_DHA_MOB_04, UTC_DHA_MOB_05 | TC.024, TC.025 | TC.021, TC.022, TC.023 | Dhara User Manual | NA | 1.1.6.2
FR‑DHCR‑06 | UC-DHCR-03 Dhara CR – FE/Mobile – Meter Survey Behaviour Changes | Mobile survey form shall support updated meter conditions (Functioning, Not Functioning, Replaced, No Water Supply) with condition‑specific enabled fields, default values and mandatory validations. | UTC_DHA_MOB_02, UTC_DHA_MOB_03, UTC_DHA_MOB_04, UTC_DHA_MOB_05 | TC.029, TC.030 | TC.26, TC.027, TC.028 | Dhara User Manual | NA | 1.1.6.3
FR‑DHCR‑07 | UC-DHCR-01Dhara CR – FE/Mobile – Meter Survey Behaviour Changes | Mobile app shall list WTP meters repeated across multiple OHT mappings under each relevant OHT/line without duplication and allow separate readings. | UTC_DHA_MOB_03, UTC_DHA_MOB_04 | TC.034, TC.035 | TC.031, TC.032, TC.033 | Dhara User Manual | BugID: 19820 | 1.1.6.3
FR‑DHCR‑08 | UC-DHCR-03 Dhara CR – FE/Mobile – Meter Survey Behaviour Changes | Mobile survey logic for Intake, WTP, OHT and Village shall ensure fast save time, non‑negative consumption validation, history retention and protection against data loss/overwrite | UTC_DHA_MOB_03, UTC_DHA_MOB_04 | TC.039, TC.040 | TC.036, TC.037, TC.038 | Dhara User Manual | NA | 1.1.6.3
FR‑DHCR‑09 | UC-DHCR-03 Dhara CR – Web – Meter Reading Modification & WTP Meters | Admin Meter Reading Modification | UTC_DHA_UI_07, UTC_DHA_UI_08, UTC_DHA_UI_09 | TC.044, TC.045 | TC.041, TC.042, TC.043 | Dhara User Manual | Bug ID: 19818 | 1.1.6.3
FR‑DHCR‑10 | UC-DHCR-03 Dhara CR – WTP Meter Configuration | Admin web interface shall allow configuration of additional WTP meters and mapping to OHTs/lines so that surveys and reports include all meters without duplication or missing links. | UTC_DHA_UI_04 | TC.049, TC.050 | TC.046, TC.047, TC.048 | Dhara User Manual | NA | 1.1.6.3
FR‑DHCR‑11 | UC-DHCR-02 Dhara CR – Reports & Portal – Updated Dhara Reporting | Reports | UTC_DHA_RPT_01, UTC_DHA_RPT_02, UTC_DHA_RPT_03, UTC_DHA_RPT_04 | TC.054, TC.055 | TC.051, TC.052, TC.053 | Dhara User Manual | NA | 1.1.6.3
FR‑DHCR‑12 | UC-DHCR-02Dhara CR – Reports & Portal – Updated Dhara Reporting | Reports shall support drill‑down from scheme/OHT level to component/village/habitation level using corrected mapping so that quantities are traceable end‑to‑end with no orphan records. | UTC_DHA_RPT_01, UTC_DHA_RPT_02, UTC_DHA_RPT_03, UTC_DHA_RPT_04, UTC_DHA_RPT_05 | TC.059, TC.060 | TC.056, TC.057, TC.058 | Dhara User Manual | Bug ID: 19819 | 1.1.6.4
FR‑DHCR‑13 | UC-DHCR-02 Portal Home & Public Dhara View | Jal Rekha public portal home shall expose updated Dhara reports (including Bulk User and UFWR) via links, with up‑to‑date data and acceptable response time. | UTC_DHA_RPT_05 | TC.064. TC.065 | TC.061, TC.062, TC.063 | Dhara User Manual | NA | 1.1.6.4
FR‑DHCR‑14 | UC-DHCR-03 Dhara CR – Cross Module & Documentation | System and process shall ensure all revised Dhara features are reflected in FE/mobile assignments and that VC training records exist for the defined FE user base with no high‑severity UAT defects. | UTC_DHA_UI_05, UTC_DHA_MOB_01 | TC.069, TC.070 | TC.066, TC.067, TC.068 | Dhara User Manual | NA | 1.1.6.4
FR‑DHCR‑15 | UC-DHCR-03CMMI‑compliant Dhara CR Documentation |  | UTC_DHA_UI_04 | TC.074, TC.075 | TC.071, TC.072, TC.073 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-16 | UC-DHCR-02-LGD Codes for OHT Master and New Habitations | System shall store and maintain LGD codes for all OHT master records and support mapping of new village habitations to OHTs using LGD-based identification. | UTC_DHA_UI_04 | TC.079, TC.080 | TC.076, TC.077, TC.078 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-17 | UC-DHCR-01 Dhara – Village Mapping to Multiple OHTs | System shall allow a village (with multiple habitations) to be mapped to more than one OHT, with explicit | UTC_DHA_UI_03, UTC_DHA_UI_04 | TC.084, TC.085 | TC.081, TC.082, TC.083 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-18 | Dhara – Change Request – Meter as Entity | System shall treat Meter as a standalone entity that can be mapped to Village, OHT, WTP and other components via configuration, with clear relationships and without data duplication. | UTC_DHA_MOB_02, UTC_DHA_MOB_03, UTC_DHA_MOB_04, UTC_DHA_MOB_05 | TC.089, TC.090 | TC.086, TC.087, TC.088 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-19 | UC-DHCR-02Dhara – Change Request – Meter Mapping Rules | System shall enforce business rules for meter–component mapping (one-to-many/many-to-one as approved), preventing conflicting mappings and providing validation messages during assignment. | UTC_DHA_UI_05, UTC_DHA_MOB_01 | TC.094, TC.095 | TC.091, TC.092, TC.093 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-20 | UC-DHCR-02Village-wise Dhara Report Approval for 10-Day Range | System shall provide option to approve Dhara reports village-wise for configurable 10-day ranges, with status tracking per range and audit log of approver and date. | UTC_DHA_RPT_05 | TC.099, TC.100 | TC.096, TC.097, TC.098 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-21 | UC-DHCR-02 OHT-wise Dhara Report Approval for 10-Day Range | System shall provide option to approve Dhara reports OHT-wise for configurable 10-day ranges, ensuring that approval status is stored at OHT–period level and reflected in dashboards. | UTC_DHA_RPT_03, UTC_DHA_RPT_05 | TC.104, TC.105 | TC.101, TC.102, TC.103 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-22 | UC-DHCR-02 Dhara – Change Request – OHT Meter Survey | System shall redesign the OHT Meter Survey to capture and display data in two separate columns: “OHT Reading” (numeric) and “OHT Water Supply Status” (enumerated values like Water/No Water/Irregular). | UTC_DHA_MOB_04 | TC.109, TC.110 | TC.106, TC.107, TC.108 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-23 | Validation and Reporting on OHT Reading vs Status | System shall validate consistency between OHT Reading and OHT Water Supply Status (e.g., zero reading with “No Water”), and expose both fields in Dhara reports and exports. | UTC_DHA_MOB_04, UTC_DHA_RPT_03 | TC.114, TC.115 | TC.111, TC.112, TC.113 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-24 | UC-DHCR-02 Dhara – Change Request – Workflow (FE/TL/GM) | System shall allow TL to add/edit remarks against FE meter/data entries before forwarding for GM approval, with remarks stored along with user and timestamp. | UTC_DHA_UI_07, UTC_DHA_UI_08, UTC_DHA_UI_09 | TC.119, TC.120 | TC.116, TC.117, TC.118 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-25 | Dhara – Change Request – Approval Workflow | System shall restrict final approval of FE entries to GM role only, ensuring that TL can review and comment but cannot finalize approval, with clear status transitions (Draft → TL Reviewed → GM Approved/Rejected). | UTC_DHA_UI_08, UTC_DHA_UI_09 | TC.124, TC.125 | TC.121, TC.122, TC.123 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-26 | UC-DHCR-02 Direct CWGM Village Mapping to WTP | System shall provide functionality for CWGM village mapping to link villages directly with WTPs, ensuring consistency with Master module scheme–village–WTP relationships and making these links available in Dhara reports. | UTC_DHA_UI_03, UTC_DHA_RPT_05 | TC.129, TC.130 | TC.126, TC.127, TC.128 | Dhara User Manual | NA | 1.1.6.4
FR-DHCR-27 | UC-DHCR-03Dhara – Change Request – CWGM/WTP Consistency | System shall validate that Dhara water supply records (village-wise and OHT-wise) are consistent with CWGM village–WTP mappings and shall flag mismatches for correction by GM/TL | UTC_DHA_RPT_05 | TC.134, TC.135 | TC.131, TC.132, TC.133 | Dhara User Manual | NA | 1.1.6.4

## MASTER BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
MASTER-CR2-FR-01 | UC-MCR-01 Village & Component Mapping to Other Scheme of PIU | GM/Contractor – Village & Component Mapping | UTC_MAP_001,UTC_MAP_002 | TC.005, TC.006 | TC.001, TC.002, TC.003, TC.004 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-02 | UC-MCR-01 Outside-Scheme Village Mapping to Components | System shall provide search and selection for outside scheme villages and allow mapping to supply components | UTC_MAP_003,UTC_MAP_004 | TC.011, TC.012 | TC.007, TC.008, TC.009, TC.010 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-03 | UC-MCR-01 Habitation–OHT Mapping for Scheme Villages | Master – GM/Contractor – Habitation–OHT Mapping | UTC_MAP_005,UTC_MAP_006 | TC.017, TC.018 | TC.013, TC.014, TC.015, TC.016 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-04 | UC-MCR-01 Bulk Meter-to-Village Mapping Across Schemes | Master – GM/Contractor – Bulk Meter Village Mapping | UTC_MAP_007,UTC_MAP_008 | TC.023, TC.024 | TC.019, TC.020, TC.021, TC.022 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-05,MASTER-CR2-FR-06 | UC-MCR-05 Pipeline Master Zone Numbers at Contractor Level | Master – Contractor – Pipeline Zone Numbers | UTC_MAP_009,UTC_MAP_010 | TC.029, TC.030, TC.035, TC.036 | TC.025, TC.026, TC.027, TC.028, TC.031, TC.032, TC.033, TC.034 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-07 | UC-MCR-02 Pipeline Master Integration with RFI Module | Master – FE Pipeline – RFI Integration | UTC_MAP_011,UTC_MAP_012 | TC.041, TC.042 | TC.037, TC.038, TC.039, TC.040 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-08 | UC-MCR-01 Habitation-wise Data Issue Logging at PIU Level | System shall allow FEs to log habitation wise data issues at PIU level with issue type | UTC_MAP_013,UTC_MAP_014 | TC.047, TC.048 | TC.043, TC.044, TC.045, TC.046 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-09 | UC-MCR-01 WTP Meter Mapping for 147 Schemes | Master – GM/Contractor – WTP Meter Mapping | UTC_MAP_015,UTC_MAP_016 | TC.053, TC.054 | TC.049, TC.050, TC.051, TC.052 | Master User Manaul | BugID: 19833 | 1.1.6.6
MASTER-CR2-FR-10 | UC-MCR-03 Role and Permission Management for Master CR | Master – Admin – User Role Management | UTC_MAP_017,UTC_MAP_018 | TC.059,TC.060 | TC.053, TC.054, TC.057, TC.058 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-11 | UC-MCR-03 Master Data Validation and QA Engine | Master – GM – Master Data Validation & QA | UTC_MAP_019,UTC_MAP_020 | TC.065, TC.066 | TC.061, TC.062, TC.063, TC.064 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-12 | UC-MCR-03 Master Data Reporting with Drill-down and Export | System shall provide master data reports | UTC_MAP_021 | TC.071, TC.072 | TC.067, TC.068, TC.069, TC.070 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-13 | UC-MCR-03 Unified Master Mapping Workspace | Master – GM/Contractor – Consolidated Mapping | UTC_MAP_022 | TC.077, TC.078 | TC.073, TC.074, TC.075, TC.076 | Master User Manaul | NA | 1.1.6.6
MASTER-CR2-FR-14 | UC-MCR-03 CMMI-Compliant Documentation for Master CR | Master – Process Owner – CMMI Documentation | UTC_MAP_023,UTC_MAP_024 | TC.083, TC.084 | TC.079, TC.080, TC.081, TC.082 | Master User Manaul | NA | 1.1.6.6

## Nirmal BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
NIRMAL-CR-FR-01 | UC-NMCR-01Updated WTP Parameter Set in Reports | System User generates a WTP water quality report using the latest configured parameter | UTC-NWTP_024 | TC.004, TC.005 | TC.001, TC.002, TC.003 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-02 | UC-NMCR-01 Additional OHT Parameters in Reports | FE collects a raw water sample from WTP or Intake location, and the mobile app validates | UTC-NOHT_025 | TC.009, TC.010 | TC.006, TC.007, TC.008 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-03 | UC-NMCR-04 Parameter Versioning for Traceability | System Admin configures the geofence buffer distances for different component types (WTP: 200 m, OHT: 50 m) in a central configuration panel. | UTC-NOHT_026 | TC.014, TC.015 | TC.011, TC.012, TC.013 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-04 | UC-NMCR-04 Configurable Field Order in WTP/OHT Reports | User generates a Beneficiary water quality report using date-range and Water Sample ID filters to find specific samples or view samples from a custom period, with all filtered data exported to Excel/PDF | UTC-NBR_026 | TC.019, TC.020 | TC.016, TC.017, TC.018 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-05 | UC-NMCR-04 -200 m Geofence for WTP/Intake Raw Water Sampling | Admin updates WTP water quality parameter definitions (add new parameters, rename, reorder), manages parameter versions, and ensures legacy test data remains compatible with new parameter sets | UTC-NWTP_025 | TC.024, TC.025 | TC.021, TC.022, TC.023 | Nirmal User Manual | BugID: 19847 | 1.1.6.0
NIRMAL-CR-FR-06 | UC-NMCR-04 onfigurable Buffer Distance for Raw Water Sampling | FE collects a raw water sample at WTP/Intake location and records parameter values | UTC-NWTP_026 | TC.029, TC.030 | TC.026, TC.027, TC.028, | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-07 | UC-NMCR-03 Store and Display Sampling Distance from Source | System shall provide a centrally managed configuration setting for raw water | UTC-NRW_024 | TC.034, TC.035 | TC.031, TC.032, TC.033, | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-08 | UC-NMCR-04 Date Range Filter in Beneficiary Report | Nirmal – Change Request – Beneficiary Report | UTC-NBR_027 | TC.039, TC.040 | TC.036, TC.037, TC.038 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-09 | UC-NMCR-04 Water Sample ID Search in Beneficiary Report | Nirmal – Change Request – Beneficiary Report | UTC-NBR_028 | TC.044, TC.045 | TC.041, TC.042, TC.043 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-10 | UC-NMCR-04 Combined Filters for Date Range and Sample ID | Nirmal – Change Request – Beneficiary Report | UTC-NBR_029 | TC.049, TC.050 | TC.046, TC.047, TC.048 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-11 | UC-NMCR-04 Backward-Compatible Parameter and Filter Updates | Nirmal – Change Request – Reporting | UTC-NCR_01 | TC.054, TC.055 | TC.051, TC.052, TC.053 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-12 | UC-NMCR-01 Audit Log for Parameter Configuration Changes | Audit Log for Parameter Configuration Changes | UTC-NCR_02 | TC.059, TC.060 | TC.056, TC.057, TC.058 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-13 | UC-NMCR-06 Remove Pass/Fail Validation for Raw Water Samples | System shall remove mandatory Pass/Fail validation for raw water samples | UTC-NRW_025 | TC.064, TC.065 | TC.061, TC.062, TC.063 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-14 | UC-NMCR-01 PPM Range Rule for WTP Output | Nirmal – Change Request – WTP Parameters | UTC-NWTP_027 | TC.069, TC.070 | TC.066, TC.067, TC.068 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-15 | UC-NMCR-01 Provision for Weekly and Monthly Nirmal Reports | Nirmal – Change Request – Nirmal Reporting | UTC-NCR_03 | TC.074, TC.075 | TC.071, TC.072, TC.073 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-16 | UC-NMCR-04 Field Engineer Reporting View | Nirmal – Change Request – FE Reporting | UTC-NCR_04 | TC.079, TC.080 | TC.076, TC.077, TC.078 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-17 | UC-NMCR-03 Differential Range for WTP and OHT Sampling | Nirmal – Change Request – Geofence | UTC-NBR_030 | TC.084, TC.085 | TC.081, TC.082, TC.083 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-18 | UC-NMCR-04 Separate Reports for OHT, WTP, Beneficiaries | l – Change Request – Component Reports | UTC-NWTP_028 | TC.089, TC.090 | TC.086, TC.087, TC.088 | Nirmal User Manual | NA | 1.1.6.0
NIRMAL-CR-FR-19 | UC-NMCR-04 Date Range and Scheme Filters in Nirmal Reports | Nirmal – Change Request – Reporting Filters | UTC-NCR_05 | TC.094, TC.095 | TC.091, TC.092, TC.093 | Nirmal User Manual | NA | 1.1.6.0

## Sahbhagita BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
SAH-CR2-FR-01 | UC-SAH-01 Secure Login for | Sahbhagita – Contractor/GM – Login | UTC_SAH_SEC_01, UTC_SAH_SEC_02 | TC.008, TC.009, TC.010 | TC.001, TC.002, TC.003, TC.004, TC.005, TC.006, TC.007 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-02 | UC-SAH-02 Village-wise Sahbhagita Report View with Triggers | GM generates Sahbhagita participation reports with village-wise filters. | UTC_SAH_UI_02, UTC_SAH_UI_03, UTC_SAH_UI_04, UTC_SAH_UI_05, UTC_SAH_UI_06, UTC_SAH_UI_07, UTC_SAH_UI_10, UTC_SAH_SUM_01, UTC_SAH_SUM_02, UTC_SAH_SUM_03, UTC_SAH_SUM_04, UTC_SAH_SUM_05 | TC.017, TC.018, TC.019 | TC.011, TC.012, TC.013, TC.014, TC.015, TC.016 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-03 | UC-SAH-03 Video Upload in Sahbhagita Activity (Web & Mobile) | PM Upload Video Evidence for Sahbhagita Activity (5–10 MB) | UTC_SAH_UI_11, UTC_SAH_UI_14 | TC.026, TC.027, TC.028 | TC.020, TC.021, TC.022, TC.023, TC.024, TC.025 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-04 | UC-SAH-03 Enforce 5–10 MB Video Upload Limit | PM Upload Video Evidence for Sahbhagita Activity (5–10 MB) | UTC_SAH_UI_11, UTC_SAH_UI_12, UTC_SAH_UI_13 | TC.033, TC.034 | TC.029, TC.030, TC.031, TC.032 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-05 | UC-SAH-02 GM Generate Village-wise Sahbhagita Report with Triggers & Filters | GM generates Sahbhagita participation reports with village-wise filters. Village-wise triggers refresh data dynamically | UTC_SAH_UI_01, UTC_SAH_UI_02, UTC_SAH_UI_03, UTC_SAH_UI_04, UTC_SAH_UI_05, UTC_SAH_UI_06, UTC_SAH_UI_07, UTC_SAH_UI_09, UTC_SAH_SUM_07, UTC_SAH_SUM_08 | TC.039, TC.040 | TC.035, TC.036, TC.037, TC.038 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-06 | UC-SAH-03 Unified Media Handling for Sahbhagita Activities | PM uploads a short video (up to 10 MB, MP4/AVI/MOV format) as evidence of community participation in a Sahbhagita activity | UTC_SAH_UI_11, UTC_SAH_UI_12, UTC_SAH_UI_13, UTC_SAH_UI_14, UTC_SAH_UI_08 | TC.045, TC.046, TC.047 | TC.041, TC.042, TC.043, TC.044 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-07 | UC-SAH-01 Role-based Access to Sahbhagita CR Features | Contractor/GM/PM Login to Sahbhagita Module | UTC_SAH_SEC_01, UTC_SAH_APP_12, UTC_SAH_APP_13, UTC_SAH_APP_14, UTC_SAH_APP_15, UTC_SAH_APP_16, UTC_SAH_APP_18 | TC.052, TC.053 | TC.048, TC.049, TC.050, TC.051 | Sahbhagita user manual | NA | 1.1.7.0
SAH-CR2-FR-08 | SAH-CR2-FR-08CMMI L5 Documentation for Sahbhagita CR | Project team shall prepare and maintain complete CMMI Level-5 compliant documentation | 1.Each CR item should reference requirement, design doc and test-case IDs. 2.Traceability should show mapping from requirement → design → test → sign-off. 3.Approvals should be logged with user, date, and comments.

## Sopan BRTM
BI-DIRECTIONAL REQUIREMENT TRACEABILITY MATRIX
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
Requirement No. (Owner-BA) from User Story/ SRS etc. | Design Document (section nos. mapping to requirement) (Owner TL/SA) | Coding (specify the modules) (Owner - Developer) | Unit Test Case No. (Owner - Developer) | Integration Test Case No. (Owner - Tester) | System Test Case No. (Owner - Tester) | User Manual/Installation Guide Section (Owner - Tech Writer/BA) | UAT Defects Id (Owner - Test Manager/Tester) | Release Note (Specify the Release note Name / release version)
SOPAN-CR2-FR-01 | UC-SOPCR-01 Sopan – Contractor Web – OHT | System shall provide an OHT Type dropdown (Conventional/Precast) on contractor web OHT creation/edit screens, make it mandatory, persist the selected type, and validate before save. | UTC_SOP_UI_02 UTC_SOP_UI_03 UTC_SOP_UI_04 UTC_SOP_UI_05 UTC_SOP_UI_06 UTC_SOP_UI_07 UTC_SOP_UI_08 UTC_SOP_UI_09 UTC_SOP_UI_10 | TC.091, TC.092, TC.093, TC.094, TC.095 | TC.001, TC.002, TC.003, TC.004, TC.005, TC.006 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-02 | UC-SOPCR-02Delete Wrongly Entered OHT/IPS/WTP Records | System shall allow contractors to delete wrongly entered OHT/IPS/WTP records in allowed statuses using a controlled delete with confirmation, soft-delete/audit log, and exclusion from plans/reports. | NA | TC.096, TC.097, TC.098, TC.099, TC.100 | TC.007, TC.008, TC.009, TC.010, TC.011, TC.012 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-03 | UC-SOPCR-03Updated WTP Form Fields | System shall update WTP web forms (add/remove/rename fields) with revised validations and migration of existing data so that all mandatory WTP information is captured without data loss. | UTC_WM_PD_01 UTC_WM_PD_02 UTC_WM_PD_03 UTC_WM_PD_04 | TC.101, TC.102, TC.103, TC.104, TC.105 | TC.013, TC.014, TC.015, TC.016, TC.017, TC.018 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-04 | UC-SOPCR-03Updated IPS Form Fields | System shall update IPS web forms with revised fields and validations and ensure existing IPS data remains viewable and correctly mapped after form changes. | UTC_IPS_01 UTC_IPS_02 UTC_IPS_03 UTC_IPS_04 | TC.106, TC.107, TC.108, TC.109, TC.110 | TC.019, TC.020, TC.021, TC.022, TC.023, TC.024 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-05 | UC-SOPCR-02Sopan – Contractor Mobile – OHT | Mobile app shall support OHT Type (Conventional/Precast) selection for OHT creation, store it offline, and sync to server so that web and mobile maintain consistent OHT type data. | UTC_MOB_OHT_01 | TC.111, TC.112, TC.113, TC.114, TC.115 | TC.025, TC.026, TC.027, TC.028, TC.029, TC.030 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-06 | UC-SOPCR-02 Sopan – Contractor Mobile – WTP | Mobile WTP form shall align with updated web WTP fields, capture GPS and photos, support offline save, and sync all data (including media) reliably. | UTC_MOB_WHT_01 | TC.116, TC.117, TC.118, TC.119, TC.120 | TC.031, TC.032, TC.033, TC.034, TC.035, TC.036 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-07 | UC-SOPCR-02 Sopan – Contractor Mobile – IPS | Mobile IPS form shall match updated web IPS fields, capture GPS and photos, support offline usage, and sync IPS records and attachments correctly. | UTC_MOB_IPS_01 | TC.121, TC.122, TC.123, TC.124, TC.125 | TC.037, TC.038, TC.039, TC.040, TC.041, TC.042 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-08 | UC-SOPCR-02Updated IPS Component Fields in Mobile | System shall provide updated IPS component-level fields on mobile, allow multiple components per IPS, enforce mandatory validations, and show saved components in list view. |  | TC.126, TC.127, TC.128, TC.129, TC.130 | TC.043, TC.044, TC.045, TC.046, TC.047, TC.048 | Sopan user manual | NA | 1.1.6.9
SOPAN-CR2-FR-09 | Hide Completed OHT from RFI (Anusharavan | Integration shall ensure OHTs marked Completed in Sopan are not shown in Anusharavan RFI request lists, and become visible again only if status is changed back as per rules. |  | TC.131, TC.132, TC.133, TC.134, TC.135 | TC.049, TC.050, TC.051, TC.052, TC.053, TC.054 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-10 | GM Edit of Contractor Details and Actual Dates with Freeze | System shall allow GM to edit contractor structure details and actual dates where permitted, create audit trails of changes, and provide a freeze option per stage that blocks further contractor edits until unfrozen. | UTC_WM_07 UTC_WM_08 UTC_WM_09 UTC_WM_10 UTC_WM_11 UTC_WM_12 UTC_WM_13 UTC_WM_14 UTC_WM_15 UTC_WM_17 UTC_WM_18 UTC_WM_20 UTC_WM_21 UTC_WM_22 UTC_WM_23 | TC.136, TC.137, TC.138, TC.139, TC.140 | TC.055, TC.056, TC.057, TC.058, TC.059, TC.060 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-11 | UC-SOPCR-01Drill-down Plan vs Actual Reports for OHT/WTP/Intake | System shall provide mapping/monitoring reports with drill-down from summary to OHT/WTP/Intake-level details, showing plan and actual dates and enabling export with these fields | UTC_MMR_01 UTC_MMR_02 UTC_MMR_03 UTC_MMR_04 UTC_MMR_05 UTC_MMR_06 UTC_MMR_07 UTC_MMR_08 | TC.141, TC.142, TC.143, TC.144, TC.145 | TC.061, TC.062, TC.063, TC.064, TC.065, TC.066 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-12 | UC-SOPCR-01Sopan – GM Reports – Panchanama & Design | System shall generate reports showing total Panchanama count and total design drawing uploads with filters (scheme/PIU/date) and export capability. | UTC_PUR_01 UTC_PUR_02 UTC_PUR_03 UTC_PUR_04 UTC_PUR_05 UTC_PUR_06 UTC_PUR_07 UTC_PUR_08 | TC.146, TC.147, TC.148, TC.149, TC.150 | TC.067, TC.068, TC.069, TC.070, TC.071, TC.072 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-13 | Separate PDF (Panchanama) and DWG (Design) Upload | System shall provide separate upload controls for Panchanama PDFs and design DWG files, validate file types, store them separately, and list/view them by document type per asset. | UTC_WM_1 UTC_WM_2 UTC_WM_3 UTC_WM_4 | TC.151, TC.152, TC.153, TC.154, TC.155 | TC.073, TC.074, TC.075, TC.076, TC.077, TC.078 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-14 | Seamless Integration of Sopan CR Fields with Other Modules | System shall update APIs and integration logic so new Sopan fields (OHT type, updated WTP/IPS fields, dates, statuses) are consumed correctly by Jal Rekha modules (RFI/Anusharavan, Dhara, Nirmal, Master) with error logging and rollback on failures. |  | TC.156, TC.157, TC.158, TC.159, TC.160 | TC.079, TC.080, TC.081, TC.082, TC.083, TC.084 | Sopan user manual | NA | 1.1.7.1
SOPAN-CR2-FR-15 | UC-SOPCR-02CMMI Level-5 Documentation for Sopan CR2 | Project team shall produce full CMMI L5-compliant artefacts (requirements, design, test cases, execution results, UAT sign-offs) for all Sopan CR2 changes, ensuring complete traceability for audits. | 1.Each CR item should reference requirement, design doc and test-case IDs. 2.Traceability should show mapping from requirement → design → test → sign-off. 3.Approvals should be logged with user, date, and comments. |  |  | Sopan user manual | NA