## Main
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Module Names in Hindi | HSC – परिणाम Parinam | Done
O&M – आकलन Aaklan
Master – विस्तृत Vistrit
2 | Dhara | 1. Dhara Report approve Villiage wise or OHT wise for a Range of 10 days each | In Progress
|  | 2. OHT Meter survey - divivde into 2 columns i) OHT Reading ii) OHT Water supply Status | In Progress
|  | 3. FE Entry TL can add remarks and finally GM only can approve it | In Progress
|  | 4. CWGM village mapping directly link to WTP | In Progress
3 | Bharosa | 1. Factory Testing - Add sub component item and its matching electrical component (updated list need to be provided by department | In Progress
|  | 2 Factory Testing - Add "Any Other" option in Sub component drop down and then Surveyor can write name in textbox | In Progress
4 | Nirmal & it's Reports | 1. Action on failed samples - into 2 columns i) failed sample rectified ii) failed sample pending | In Progress
|  | 2. Document upload by contractor will be approved by GM ( action on failed samples) | In Progress
|  | 3 "Raw water wise test report" name change to "Raw water test report" | Done
|  | 4 Remove 2 columns - No of samples failed and No of samples passed | In Progress
|  | 5 WTP Water test report - change 0.2 to 0.5 level of chlorine | In Progress
|  | 6 Remark comments for failed samples | Done
|  | 7. In Nirmal Final Report results failed parameter should appear in "RED Color" | In Progress
5 | RFI | 1 RFI transfer to new SQC | In Progress
|  | 2 Sorting to be done on - Reinspections and Rejected RFI's | In Progress
|  | 3 Contractor should see FE's Comments | In Progress
6 | Sahbhagita | 1) Show video at PM Manager ID login also, as it is visible to GM login | Done
7 | Issues | 1) Contractor when mapping - SQC/TPIA then their mobile number should be shown with their ID | In Progress
|  | 2) Chindwara and Ujjain issue of village not showing mapping issue | In Progress
|  | 3) Where Habitation not available there we can show village name | In Progress
|  | 4) When reading is 0 zero & showing no water supply - Remove that condition | In Progress
|  | 5) Anmol DeGM Chhatarpur - Sorting to be done on - Reinspections and Rejected RFI's & Contractor should see FE's Comments | In Progress
|  | 6) SQC's can Reset Password feature | In Progress
8 | O&M Billing - GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit | Done
|  | 2) Kapil id should be renamed to - "GM PIU O&M" | Done
|  | 3) For 1 village multiple time mapping should not be shown | Done
|  | 4) GM PIU and contractor name not coming correctly | Done
|  | 5) Agreement value column name and data should come correctly | Done
|  | 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" | Done
|  | 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | Done
9 | O&M Billing - Contractor | 1) Contractor -Billing | In Progress
|  | 2) CPI Base year and month calculation happen instantly | In Progress
|  | 3) Remark should come at the end in below report columns | In Progress
|  | 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report | In Progress
|  | 5) Complaint resolved date - it is "Resolved" word please check | In Progress
|  | 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement | In Progress
|  | 7) Event before 48 hours should not get edited and count increase happen after 48 hours | In Progress
|  | 8) Reason for relaxation only become mandatory after clicking YES | In Progress
|  | 9) Penalty Relaxation spelling correct it | In Progress
|  | 10) All above fields should be visible in below reports and upload documents show in report | In Progress
|  | 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf | In Progress
|  | 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check | In Progress
|  | 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label | In Progress

## Book_1 pr
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Module Names in Hindi | HSC – परिणाम Parinam | Done
O&M – आकलन Aaklan
Master – विस्तृत Vistrit
2 | Dhara | 1. Dhara Report approve Villiage wise or OHT -Village wise for a Range of each | Done
|  | 2. OHT Meter survey - divivde into 2 columns i) OHT Reading ii) OHT Water supply Status | Done UAT Column add
3 | Bharosa | 1. Factory Testing - Add sub component item and its matching electrical component (updated list need to be provided by department | Done
|  | 2 Factory Testing - Add "Any Other" option in Sub component & Item drop down and then Surveyor can write name in textbox | Done
4 | Nirmal & it's Reports | 1. Action on failed samples - into 2 columns i) failed sample rectified & document upload by contractor will be approved by GM ( action on failed samples) | In Progress
|  | 2 "Raw water wise test report" name change to "Raw water test report" | Done
|  | 3 Remove 2 columns - No of samples failed and No of samples passed and Remove wise in the report | Done
|  | 4 WTP Water test report - change 0.2 to 0.5 level of chlorine | Done
|  | 7. In Nirmal Final Report results failed parameter should appear in "RED Color" | In Progress
5 | Anushravan | 1 RFI transfer to new SQC already discuss with Balkrishnan and he will send the details | In Progress
|  | 2 GM can remove SQC & TPIC RFIs & SQC TPIA can remove FE RFI's (if loop is not currently running) | Already Functional
|  | 3 Sorting to be done on - Reinspections and Rejected RFI's | Done
|  | 4 Contractor should see FE's Comments | Done
6 | Sahbhagita | 1) Show video at PM Manager ID login also, as it is visible to GM login | Done
7 | Issues | 1) Contractor when mapping - SQC/TPIA then their mobile number should be shown with their ID | Done
|  | 2) Chindwara and Ujjain issue of village not showing mapping issue | Done
3) Where Habitation not available there we can show village name
|  | 4) When reading is 0 zero & showing no water supply - Remove that condition | In Progress
|  | 5) DeGM Chhatarpur - Date on web & Sorting to be done on - Reinspections and Rejected RFI's & Contractor should see FE's Comments | Discussed Done
|  | 6) SQC's can Reset Password feature | Done

## O&M Bill
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | O&M Billing - GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit | Done
|  | 2) Kapil id should be renamed to - "GM PIU O&M" | Done
|  | 3) For 1 village multiple time mapping should not be shown | Done
|  | 4) GM PIU and contractor name not coming correctly | Done
|  | 5) Agreement value column name and data should come correctly | Done
|  | 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" | Done
|  | 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | Done
2 | O&M Billing - Contractor | 1) Contractor -Billing | In Progress
|  | 2) CPI Base year and month calculation happen instantly | In Progress
|  | 3) Remark should come at the end in below report columns | In Progress
|  | 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report | In Progress
|  | 5) Complaint resolved date - it is "Resolved" word please check | In Progress
|  | 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement | In Progress
|  | 7) Event before 48 hours should not get edited and count increase happen after 48 hours | In Progress
|  | 8) Reason for relaxation only become mandatory after clicking YES | In Progress
|  | 9) Penalty Relaxation spelling correct it | In Progress
|  | 10) All above fields should be visible in below reports and upload documents show in report | In Progress
|  | 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf | In Progress
|  | 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check | In Progress
|  | 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label | In Progress

## O&M Bill New CRs
S. No. | Module/Activity | New Change Requests | Description | Status(New Change Request)
1 | Aaklan (O & M Billing) | Date validation change for complaint entry | For Complaint Date, Complaint Receiving Date to Contractor, and Complaint Resolved Date, users can select dates only from the billing month and the immediate previous month. For Closing Date of Complaint in C.M. Portal, date selection is restricted strictly to the billing month only. | Pending
2 | Aaklan (O & M Billing) | Bulk Users deduction & insert functionality | Earlier, this page was used only to fetch and display data (GET only). No add or edit action was available. Now, in the Bulk Users section, two new columns are added: Deduction Applicable (Yes/No) and Deduction Amount. When deduction is applicable, the entered deduction amount will be deducted from the Gross Amount and the calculated value will be reflected in the Net Payable Bill. A remark will be mandatory and will be saved in the table. If deduction is not applicable, Net Payable Amount will be equal to the Gross Amount. Based on this saved action and remark, the next Village-level process will be carried forward. | Pending
3 | Aaklan (O & M Billing) | Village section enhancement with insert/update and dashboard visibility | Earlier, in the Village section, the “Enter No. of HSC” value was fetched automatically from the Census table and was read-only, and calculations were based on existing logic. Now, an additional new column will be introduced in the Village section. The “Enter No. of HSC” field will remain read-only as earlier. The newly added column will be visible on both Contractor and GM dashboards. Calculations will now be driven based on this new column. Insert and update functionality will be implemented for this section, requiring new backend functions. The entered and updated data will be stored in the database and will also be visible to the GM for review and monitoring. | Pending
4 | Aaklan (O & M Billing) | Clause-B field validation and disable logic | Earlier, if no pipeline was selected on the GM page, the system auto-filled zero (0) in the field and allowed the process to continue without mandatory uploads. Now, document upload under Clause-B is mandatory. However, if no pipeline is selected on the GM page, the Clause-B field and related upload options will be disabled (read-only) and the value will be automatically set to zero (0). Billing process will continue without validation error. | Pending