## INDEX
JAL REKHA – CYCLE 4 USER STORIES REGISTER (Jan 2026 – May 2026) Prepared for: CMMI Level 5 Audit ¦ Project: Jal Rekha ¦ Department: PHED, Madhya Pradesh
Sr. No. | Sheet Name | Module / Area | No. of User Stories | Total Effort (hrs)
1 | Anusharavan US | Anusharavan (RFI, Stages, Reports) | 8 | 250
2 | Asset Mapping US | Asset Mapping (GIS, Survey) | 3 | 53
3 | Bharosa US | Bharosa Factory Testing (Web + Mobile) | 5 | 191
4 | Cube Testing US | Cube Testing (Contractor / FE / GM / SQC) | 9 | 631
5 | Daily Inspection US | Daily Inspection | 2 | 20
6 | Dashboard US | Dashboard & Public Reports | 3 | 78
7 | Dhara US | Dhara (Reports, Meter, Mobile) | 10 | 915
8 | FHTC US | FHTC + AI Tap Connection | 5 | 365
9 | Master US | Master Module (GM / CR / Schema) | 4 | 226
10 | Material Testing US | Material Testing (GM / Contractor / FE) | 5 | 344
11 | Nirmal US | Nirmal (FE Mobile, GM, CR) | 4 | 153
12 | O&M Billing US | O&M Billing (GM / Contractor / Workflow) | 7 | 624
13 | Sahbhagita US | Sahbhagita (GM / CR / Reports) | 4 | 57
14 | SVS US | SVS Water Supply Monitoring – Har Ghar Jal | 15 | 104
15 | CMMI Doc US | CMMI Documentation + Dept Meetings | 4 | 756
16 | Site Security US | Site Security Audit | 2 | 32
17 | Sopan US | Sopan Contractor | 2 | 10
18 | User Role US | User & Role Management | 2 | 24
| TOTAL USER STORIES – CYCLE 4 |  | 94

## Anusharavan US
Jal Rekha – Cycle 4 User Stories ¦ Anusharavan (RFI, Stages, Reports) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Anusharavan – RFI Stage Changes | US-ANS-C4-001 | High | As a system user, I want new RFI stages added to the Anusharavan module so that the inspection workflow captures all required stages accurately. | AC1: New stages defined in RFI workflow config with role permissions; AC2: Stage transitions validated; AC3: Contractor and FE mobile app reflects new stages; AC4: GM dashboard shows stage-wise counts; AC5: Notifications triggered on each stage change | Done | Sprint 12-14 | 120
Anusharavan – RFI Stage Changes | US-ANS-C4-002 | High | As a Field Engineer (FE), I want PIU inspection details added to the RFI form so that I can capture field-level data accurately during inspection. | AC1: FE inspection fields (PIU, Date, GPS, Remarks) added; AC2: Mandatory validation enforced; AC3: Date auto-populated but editable; AC4: PIU-wise data visible in GM reports; AC5: Data persists across sessions | Done | Sprint 14 | 16
Anusharavan – Stage Updation | US-ANS-C4-003 | Medium | As a developer, I want existing RFI stages updated and History screen search enhanced so that users can quickly locate past inspection records. | AC1: History screen search functional by scheme, date, status; AC2: Results load <3 s; AC3: Pipeline details on History Detail screen verified; AC4: Play Store live build tested; AC5: No regression | Done | Sprint 13 | 21
Anusharavan – Report Creation | US-ANS-C4-004 | High | As a GM user, I want customised RFI reports with FE inspection details so that I can generate PIU-wise performance reports. | AC1: Report includes PIU, Inspector Name, Inspection Date columns; AC2: Filters by PIU, Scheme, Date Range; AC3: Excel and PDF export functional; AC4: Summary shows aggregate counts per PIU; AC5: Report loads <5 s for 500+ records | Done | Sprint 14-15 | 24
Anusharavan – Testing & Video | US-ANS-C4-005 | Medium | As a QA engineer, I want complete testing of Anusharavan module changes including a demo video so that all functionalities are validated before production. | AC1: Test cases created for all new stage and report changes; AC2: Internal pass rate 100% before UAT; AC3: UAT conducted with PHED; AC4: Production defects logged & resolved; AC5: Demo video covering new stages and reports | Done | Sprint 14 | 8
Anusharavan CR – FE Inspection PIU & Report | US-ANS-C4-006 | Medium | As a contractor, I want the updated RFI workflow with FE Inspection Date visible in PIU Pending-for-Action web page so that I can track pending inspections efficiently. | AC1: FE Inspection Date column added to PIU Pending for Action page; AC2: Data sourced correctly; AC3: Column sortable and filterable; AC4: Customised report updated; AC5: CR tested in staging before production | Done | Sprint 15 | 21
Anusharavan – UI Enhancement Contractor & FE Login | US-ANS-C4-007 | Low | As a UI/UX developer, I want the Anusharavan Contractor and FE login pages redesigned with card-based layout so that the user interface is consistent and mobile-responsive. | AC1: Card-based HTML design applied to all inner pages; AC2: Table alignment fixed on Approved Supply Point Wise Village MWSR page; AC3: Modal popup design corrected; AC4: Mobile responsiveness verified on Android; AC5: Deployed and regression-tested | Done | Sprint 14-15 | 16
Anusharavan – View Details, Log View & Inspection Request Enhancement | US-ANS-C4-008 | Medium | As an FE and GM user, I want enhanced View Details, Log View, and Inspection Request Form in Anusharavan so that all field activities are traceable. | AC1: View Details screen shows all stages with timestamps; AC2: Log View shows full audit trail per RFI; AC3: Inspection Request Form enhanced with new fields; AC4: Accuracy field changes applied; AC5: Tested on mobile and web | Done | Sprint 14 | 24

## Asset Mapping US
Jal Rekha – Cycle 4 User Stories ¦ Asset Mapping (GIS, Survey) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Asset Mapping – Bug Fixing & Redesign | US-AST-C4-001 | High | As a user, I want the Asset Mapping module redesigned and deployed to live server so that the interface is modern and all known bugs are resolved. | AC1: Redesigned pages deployed on live server; AC2: OHT search box functional with real-time filtering on map; AC3: All frontend bugs fixed; AC4: Accuracy field changes implemented; AC5: Data GET method updated per new specifications | Done | Sprint 13-14 | 30
Asset Mapping – Data Correction & Reports | US-AST-C4-002 | High | As an SQC/TPIA/Contractor user, I want dedicated report pages in Asset Mapping so that I can view and download survey and GIS data efficiently. | AC1: Reports created for SQC, TPIA, and Contractor login; AC2: Survey data download (D&D format) operational; AC3: Data correction tools available with audit trail; AC4: OHT village testing bug resolved; AC5: Move OHTs feature functional; AC6: Demo video created | Done | Sprint 15 | 15
Asset Mapping – SQC Login Data Visualisation | US-AST-C4-003 | Medium | As an SQC user, I want data visualisation and asset mapping views in SQC login so that I can audit GIS asset data independently. | AC1: SQC login shows district/block/village filtered asset map; AC2: Data visualisation charts for asset counts; AC3: Survey download available to SQC role; AC4: Internal testing completed; AC5: UAT signed off | Done | Sprint 15 | 8

## Bharosa US
Jal Rekha – Cycle 4 User Stories ¦ Bharosa Factory Testing (Web + Mobile) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Bharosa – Factory Testing Web CR | US-BHR-C4-001 | High | As a developer, I want multiple document upload functionality added to the Bharosa Factory Testing web module so that inspectors can attach all evidence in one submission. | AC1: Multiple file upload (PDF, DOC, JPG, PNG) with progress indicator; AC2: Max 10 files, ≤10 MB each; AC3: Documents viewable & downloadable; AC4: QAP document upload included; AC5: UI updated in existing pages; AC6: Post-deployment bugs fixed | Done | Sprint 12-13 | 78
Bharosa – Factory Testing DB & API | US-BHR-C4-002 | High | As a system architect, I want database architecture designed and service APIs created for Bharosa Factory Testing so that all web and mobile components are supported by a robust backend. | AC1: DB schema with master check; AC2: APIs for all Bharosa pages (web + mobile); AC3: Factory Testing Contractor Login mobile page created; AC4: Unit, SIT, and UAT completed; AC5: Test cases documented | Done | Sprint 13 | 40
Bharosa – Factory Testing UI & Wireframes | US-BHR-C4-003 | Medium | As a UI/UX designer, I want wireframes for Bharosa Factory Testing module and UI enhanced so that development has clear specifications and the deployed UI is consistent. | AC1: Wireframes for all screens (Inspector, GM, TPIA login); AC2: UI updated per wireframe; AC3: Unit input field and display added; AC4: Save as Draft, Image, Video upload implemented; AC5: Production deployment completed | Done | Sprint 13 | 24
Bharosa CR – Factory Testing Mobile | US-BHR-C4-004 | Medium | As a mobile user, I want QAP document download functionality on the Bharosa mobile app so that field users can access quality assurance documents offline. | AC1: QAP download added to mobile app; AC2: Works for PDF and DOC; AC3: Offline access after download; AC4: Internal testing zero critical defects; AC5: CR tested in production | Done | Sprint 15 | 25
Bharosa CR – Save as Draft & Document Upload | US-BHR-C4-005 | Medium | As a Bharosa inspector user, I want Save as Draft functionality and document upload enhancement in Bharosa so that partial inspections can be resumed without data loss. | AC1: Save as Draft saves form state; AC2: Drafted records visible in history list; AC3: Document upload duplicate validation applied; AC4: Final submission handling correct; AC5: UAT completed | Done | Sprint 15 | 24

## Cube Testing US
Jal Rekha – Cycle 4 User Stories ¦ Cube Testing (Contractor / FE / GM / SQC) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Cube Testing – Requirement Gathering & Design | US-CUBE-C4-001 | High | As a business analyst, I want Cube Testing requirements gathered and wireframes created so that the development team has complete specifications for implementation. | AC1: Requirement sessions with Civil Engineers, Lab Technicians, GM; AC2: Wireframes for web and mobile; AC3: Workflow documented (Sample Collection → Curing → 7-Day → 28-Day → Result → TPIA → GM); AC4: DB schema, master & design tables defined; AC5: Business logic APIs and SP development completed | Done | Sprint 13-14 | 130
Cube Testing – Development | US-CUBE-C4-002 | High | As a developer, I want Cube Testing database functions, stored procedures, and web pages created so that the full testing lifecycle is supported. | AC1: DB schema with query optimisation; AC2: New web pages per wireframes; AC3: Data validation implemented; AC4: Reports functional; AC5: Internal testing and production deployment; AC6: Test cases, scenarios, and test plan documents created | Done | Sprint 13-15 | 120
Cube Testing – Contractor Login | US-CUBE-C4-003 | High | As a contractor, I want to create cube inspection entries through the web application so that sample data is captured at the point of collection. | AC1: Contractor creates cube records (Component, Casting Date, Mix Design, Quantity); AC2: RFI Survey form API integrated; AC3: Survey form with pagination and contractor history list; AC4: Internal and UAT/Prod testing completed | Done | Sprint 14 | 64
Cube Testing – FE Login | US-CUBE-C4-004 | High | As a Field Engineer, I want to record and submit cube test results after 7-day and 28-day curing periods so that compressive strength data is captured accurately. | AC1: FE Sync API integrated; AC2: 7-day and 28-day check enforced before result submission; AC3: Cube inspection with GPS capture; AC4: FE Insert document fixed; AC5: End-to-end tested; AC6: Security test cases created | Done | Sprint 13-15 | 120
Cube Testing – GM / SQC / TPIA | US-CUBE-C4-005 | High | As a GM user, I want summary reports and Pending for Action page in Cube Testing so that I can monitor and approve cube test results across all schemes. | AC1: Summary reports for 7-day and 28-day scenarios; AC2: GM Action Page with Pending for Action; AC3: RFI request status update and list functional; AC4: Customised reports available; AC5: Production issues resolved | Done | Sprint 14 | 48
Cube Testing – SQC/TPIA Login | US-CUBE-C4-006 | High | As an SQC/TPIA user, I want web pages and APIs for SQC and TPIA login in Cube Testing so that I can verify and approve cube test results. | AC1: SQC login web pages and APIs; AC2: TPIA login web pages and APIs; AC3: Bug fixing completed; AC4: End-to-end testing completed; AC5: Test scenarios documented | Done | Sprint 14-15 | 47
Cube Testing CR – Mandatory Image Upload & Manual Component | US-CUBE-C4-007 | Medium | As a department stakeholder, I want change requests for Cube Testing implemented including mandatory multiple image upload and manual component entry so that data quality is enhanced. | AC1: Mandatory multiple image upload added; AC2: Manual entry for components where dropdown unavailable; AC3: New web page modifications per CR; AC4: CR tested in staging and production; AC5: All CR items closed | Done | Sprint 15-16 | 70
Cube Testing CR – Remove Inspection Date & Calculate Days from Casting | US-CUBE-C4-008 | Medium | As a QA engineer, I want the Cube Testing module to remove the manual inspection date field and automatically calculate 7-day or 28-day check validity from the Casting Date so that test validity is enforced without manual entry errors. | AC1: Inspection date field removed from Cube Testing form; AC2: Days calculation auto-computed from Casting Date only; AC3: 7-day and 28-day threshold enforced at API and UI level; AC4: FE cannot submit results before threshold days; AC5: Tested in staging and production | Done | Sprint 15-16 | 16
Cube Testing CR – Remove Compulsion for Structural Location on Non-Site Components | US-CUBE-C4-009 | Low | As a contractor, I want District/Block/GP/Village selection removed as mandatory for components like Intakewell, WTP, MBR, RWPM, CWPM so that I can raise cube inspections for non-site-specific components without barrier. | AC1: Mandatory location selection removed for Intakewell, WTP, MBR, RWPM, CWPM components; AC2: Location optional for these components; AC3: Village/GP mandatory only for site-specific components; AC4: Tested in staging and production | Done | Sprint 15-16 | 16

## Daily Inspection US
Jal Rekha – Cycle 4 User Stories ¦ Daily Inspection ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Daily Inspection – Development & Bug Fixes | US-DI-C4-001 | High | As a developer, I want Daily Inspection module bug fixes and new functionality implemented so that FE and GM users can perform inspections without technical issues. | AC1: Frontend, API, DB, and mobile bugs fixed with root cause documented; AC2: New web pages created per requirements; AC3: GET/SET data methods created/updated; AC4: DB architecture with master check designed; AC5: APIs for all new features; AC6: Production deployment and unit testing completed | Done | Sprint 12 | 12
Daily Inspection – Accuracy Field Changes | US-DI-C4-002 | Medium | As a mobile developer, I want accuracy field changes applied to Daily Inspection on Android so that GPS precision data is captured correctly. | AC1: Accuracy field added at API level and local DB; AC2: Accuracy data synced with web portal; AC3: Tested on multiple Android devices; AC4: No regression in existing inspection workflow; AC5: Deployed to production | Done | Sprint 14 | 8

## Dashboard US
Jal Rekha – Cycle 4 User Stories ¦ Dashboard & Public Reports ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Dashboard – Data Verification & Wireframe | US-DASH-C4-001 | High | As a PM user, I want Dashboard data verified and Excel reports modified for all Jal Rekha modules so that the management dashboard reflects accurate real-time data. | AC1: Data verification completed for all modules; AC2: Modified Excel reports generated; AC3: Wireframes created for new dashboard widgets; AC4: Requirement gathering documented; AC5: All KPIs tested for accuracy | Done | Sprint 13 | 30
Dashboard – All Public Reports | US-DASH-C4-002 | High | As a public user, I want all Jal Rekha module reports accessible on the public dashboard so that scheme performance data is transparently available. | AC1: Public reports enabled for all applicable modules; AC2: CR/Prod/UAT bug testing completed; AC3: Internal pass rate 100% before public access; AC4: Report load time <5 s; AC5: No authentication required for public reports | Done | Sprint 14-15 | 32
Dashboard – Sidebar Menu UI Improvement | US-DASH-C4-003 | Low | As a UI developer, I want the sidebar menu icons, scroll colour, and table alignment improved on the dashboard so that the visual design is consistent and mobile-responsive. | AC1: Sidebar menu icons updated; AC2: Scroll colour customised per theme; AC3: Table alignment fixed on inner pages; AC4: Sidebar fully mobile responsive; AC5: Unused CSS removed | Done | Sprint 13 | 16

## Dhara US
Jal Rekha – Cycle 4 User Stories ¦ Dhara (Reports, Meter, Mobile) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Dhara – Reports & UI Enhancement | US-DHR-C4-001 | High | As a GM user, I want updated DWSR, MWSR, UFW reports and new Approved Village Wise MWSR report so that I can monitor water supply performance at all levels. | AC1: DWSR Detailed and Datewise Report created; AC2: Approved Village Wise MWSR page with service; AC3: Bulk Consumer MWSR Report; AC4: HSC Summary Report developed; AC5: Date filter enhancement in DWSR; AC6: UFW Report data corrections applied | Done | Sprint 12-16 | 163
Dhara – UI Update & Bug Fixes | US-DHR-C4-002 | High | As a developer, I want Dhara module inner pages redesigned and existing bugs fixed so that users experience a consistent and error-free interface. | AC1: New UI applied to all Dhara inner pages; AC2: District data mismatch in DWSR DateWise Detailed Report fixed; AC3: WTP Meter Mapping issue and delete restriction fixed; AC4: Public Page visibility issue for PIU and Scheme 'ALL' resolved; AC5: SIT and UAT completed | Done | Sprint 12-16 | 120
Dhara – Meter Reading & Contractor Objection | US-DHR-C4-003 | High | As a GM and Contractor user, I want meter reading survey changes and contractor objection module implemented so that meter disputes are formally managed. | AC1: Contractor Objection Module UI and Modal for Intake, WTP, ESR/OHT; AC2: Objection API and DB integrated; AC3: Meter reading survey updated for intake, WTP, OHT, bulk (web and mobile); AC4: Approved status flow FE → GM → Contractor enforced; AC5: Bulk Consumer mapping added | Done | Sprint 15-16 | 141
Dhara CR – Reports (MWSR, DWSR, UFW) | US-DHR-C4-004 | High | As a QA analyst, I want requirement gathering and internal testing for Dhara report changes so that MWSR, DWSR, and UFW reports are accurate. | AC1: Requirement gathering of report changes documented; AC2: Updated and recreated fetch for DWSR, MWSR, Bulk Consumer, Approved Reports, UFW; AC3: Internal testing completed; AC4: DWSR public report enhancements deployed; AC5: JS modification for data loading issue resolved | Done | Sprint 14-16 | 236
Dhara – GM PIU User Change Request | US-DHR-C4-005 | High | As a GM PIU user, I want Dhara WTP meter reading issues resolved and intake meter reading survey changes implemented so that meter data is captured correctly. | AC1: WTP Meter Reading Issue resolved for affected schemes; AC2: Intake meter reading survey changes implemented; AC3: Bulk meter consumer reading survey updated; AC4: Test case and scenario creation completed; AC5: Staging and production deployment completed | Done | Sprint 15-16 | 91
Dhara – Mobile Application | US-DHR-C4-006 | High | As a field user, I want a mobile application developed for Dhara module so that meter readings and survey data can be captured in the field. | AC1: Dhara mobile app development completed; AC2: All meter survey types (Intake, WTP, OHT, Bulk) supported; AC3: GPS capture and offline mode functional; AC4: Data sync on connectivity; AC5: Mobile UAT/Prod testing; AC6: Knowledge transfer conducted | Done | Sprint 13 | 40
Dhara CR – OHT-WTP Village Meter Survey Rename & New Fields | US-DHR-C4-007 | High | As a GM and Contractor user, I want the OHT Meter Survey renamed to 'OHT-WTP Village Meter Survey' and new report fields added (Survey Date, Scheme, Component Name, Village Meter details, Reading Start/End, Total Clear Water Supplied, PE Remark) so that the survey captures complete village-level meter data. | AC1: Module renamed to 'OHT-WTP Village Meter Survey' across web and mobile; AC2: 13 new fields added including Survey Date, Scheme, Component Name, Village Meter Status, Reading Start/End, Total Clear Water (KL), PE Remark, GM Remark, Local Name; AC3: Conditional GM review flow (Objection / Approved / Any Concern) with Contractor Remark & Document upload; AC4: DB schema updated; AC5: Existing records migrated without loss; AC6: All 13 fields tested in staging and production | Done | Sprint 15-16 | 60
Dhara CR – GM Work Process Flow (Intake / WTP / OHT Meter Surveys) | US-DHR-C4-008 | High | As a GM user, I want a structured work process flow for reviewing Intake, WTP, and OHT-WTP Village Meter Survey pages after login so that GM can systematically review field data and take approval decisions. | AC1: GM navigates to Dhara Module and selects Intake, WTP, or OHT-WTP Village Meter Survey; AC2: Each page shows Survey Date, Scheme, Component, Total Water (KL), Meter Reading Start/End, FE/PE Remark; AC3: GM adds GM Review Remark before decision; AC4: Decision options: Objection (Contractor Remark + Document upload), Approved, Any Concern (Contractor Remark + Upload); AC5: Decision status with timestamp and GM user ID visible; AC6: Workflow tested end-to-end for all three survey types | Done | Sprint 15-16 | 40
Dhara CR – Contractor Objection Module – Intake & WTP | US-DHR-C4-009 | High | As a contractor, I want a dedicated Contractor Objection page for Intake Meter Survey and WTP Meter Survey so that I can raise objections against GM-reviewed readings with supporting documents. | AC1: New page Frm_DharaIntakeMeterSurveyForContractor.aspx created; AC2: New page Frm_DharaWTPMeterSurveyForContractor.aspx created; AC3: Contractor objection popup with survey details, contractor remark, and PDF upload; AC4: Services Update_contractor_objection_intake and Update_contractor_objection_wtp implemented; AC5: Row lock handling to prevent concurrent edits; AC6: End-to-end tested | Done | Sprint 16 | 16
Dhara CR – Contractor Objection Module – ESR/OHT | US-DHR-C4-010 | High | As a contractor, I want a dedicated Contractor Objection page for ESR/OHT Meter Survey so that I can raise objections with remarks and uploaded supporting documents. | AC1: New page Frm_DharaESRMeterSurveyForContractor.aspx developed; AC2: DharaESRMeterSurveyForContractor.js with modal handling and validation; AC3: Service Update_contractor_objection_esr implemented; AC4: Readonly mode for all survey fields in contractor objection popup; AC5: End-to-end testing of modal binding, validation, file upload, and data refresh | Done | Sprint 16 | 8

## FHTC US
Jal Rekha – Cycle 4 User Stories ¦ FHTC + AI Tap Connection ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
FHTC FE Reports – Development | US-FHTC-C4-001 | High | As a developer, I want FHTC FE report pages created, APIs integrated, and existing queries/SPs modified so that FE and GM users have accurate tap connection reports. | AC1: New FHTC web pages for FE reports; AC2: Mobile API integration; AC3: Query/SP creation and modification; AC4: SIT testing, test cases, test scenarios; AC5: UAT/Prod/CR testing completed | Done | Sprint 12 | 51
FHTC CR – Loop / Re-Inspection Functionality | US-FHTC-C4-002 | High | As a contractor and FE user, I want FHTC Loop (Re-Inspection) functionality implemented so that failed tap connections can be re-inspected through a structured flow. | AC1: Loop functionality for Contractor, FE, SQC, TPIA login implemented; AC2: Re-Inspection Form UI design and API data submission for FE completed; AC3: Re-Inspection List Screen with API integration for FE; AC4: History, Accepted List, Rejected List screens implemented; AC5: FHTC Loop tested in mobile and PIU side; AC6: View Logs functionality added | Done | Sprint 14-15 | 180
FHTC CR – Search & Reports | US-FHTC-C4-003 | Medium | As an FE and Contractor user, I want search functionality and customised summary report changes in FHTC so that I can locate specific tap connection records quickly. | AC1: Search functionality added to FE and Contractor login; AC2: Customised and summary report changes implemented; AC3: Report filter issues at column level resolved for GM/Contractor; AC4: Excel export with dynamic file name, sheet name, and hidden non-export columns; AC5: Staging and production regression tested | Done | Sprint 14-16 | 57
FHTC – AI Module Tap Connection | US-FHTC-C4-004 | Medium | As a data scientist, I want AI/ML models implemented for FHTC Tap Connection monitoring so that predictive analytics can identify non-functional connections proactively. | AC1: ML model implementation for tap connection monitoring buffer region completed; AC2: Data Processing of FHTC Tap connections using AI models done; AC3: Model trained on rfdetr with 2000 annotated tap images; AC4: Testing categorised into three outcome categories; AC5: Human detection model (YOLOv8x) integrated alongside custom tap model | WIP | Sprint 16 | 69
FHTC – UI Enhancement & Excel Export Standardisation | US-FHTC-C4-005 | Low | As a GM and contractor user, I want FHTC module UI enhanced and Excel exports standardised with module-wise file name, sheet name, and header title so that reports are professional and consistent. | AC1: FHTC Module UI enhanced across all login pages; AC2: Excel export includes dynamic file name (module-based); AC3: Sheet name and header title set per module; AC4: Non-export columns (Action, Image, Document) hidden in Excel; AC5: Changes deployed and tested in production | Done | Sprint 15 | 8

## Master US
Jal Rekha – Cycle 4 User Stories ¦ Master Module (GM / CR / Schema) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Master GM – Pipeline & Wireframes | US-MST-C4-001 | High | As a GM user, I want Pipeline Master data management with updated wireframes in the Master module so that infrastructure data is accurately maintained. | AC1: Pipeline Master data entry page created; AC2: New wireframes per department implemented; AC3: Wireframe approved by stakeholders; AC4: GET/SET data access methods created; AC5: SIT and UAT/Prod/CR testing completed | Done | Sprint 12 | 32
Master CR – Scheme Village OHT & Bulk Consumer | US-MST-C4-002 | High | As a data admin, I want Scheme Village OHT Mapping and Bulk Consumer Master updated with delete functionality so that master data management is complete. | AC1: Scheme Village OHT Mapping and Report updates; AC2: Bulk Consumer Master (Add-Update-Get-Delete) implemented; AC3: Dhara Mapped Summary report changes applied; AC4: Dhara Master DWSR updates; AC5: All master changes tested | Done | Sprint 13-16 | 140
Master CR – Bulk Consumer Meter Mapping | US-MST-C4-003 | High | As a developer, I want Bulk Consumer Supply Mapping enhanced with meter_id column for WTP and multiple mapping enabled so that bulk consumers can be mapped to multiple sources. | AC1: meter_id column added to Bulk Consumer mapping; AC2: Multiple mapping from the same source enabled; AC3: Urban records handled where vill_cd = 0; AC4: Validation and reset on Scheme change; AC5: Bulk Meter Update Fix applied; AC6: Tested in production | Done | Sprint 14-16 | 38
Master CR – Census Population Integration | US-MST-C4-004 | Medium | As a data admin, I want Census Population auto-fetched from Scheme Village Master instead of manual entry so that census data is always consistent with the master. | AC1: Manual Census Population add/delete removed from O&M Contract details; AC2: Auto-fetch from scheme village mapping implemented; AC3: Direct save flow in om_contract_census_population table; AC4: Old trigger logic disabled; AC5: Get_CensusByScheme shows saved data first, else fetches master | Done | Sprint 15 | 16

## Material Testing US
Jal Rekha – Cycle 4 User Stories ¦ Material Testing (GM / Contractor / FE) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Material Testing – GM/Contractor Login Development | US-MAT-C4-001 | High | As a development team, I want Material Testing module built with complete backend, frontend, and mobile support so that construction material quality is systematically recorded. | AC1: DB schema, master and design tables; AC2: Business Logic APIs for all workflows; AC3: GET/SET data access methods and SP development; AC4: New web pages and UI for GM and Contractor login; AC5: Mobile development for FE; AC6: SQC/TPIA login pages and APIs | Done | Sprint 12-15 | 250
Material Testing – GM/Contractor Login Testing | US-MAT-C4-002 | High | As a QA engineer, I want comprehensive testing of Material Testing module including wireframing, workflows, and production validation so that the module is ready for PHED. | AC1: Wireframing and workflow documentation; AC2: Requirement gathering with stakeholder sign-off; AC3: Test case and scenario creation for all login types; AC4: Internal, SIT, staging, and UAT/PROD/CR testing; AC5: All production bugs resolved | Done | Sprint 12-15 | 40
Material Testing – FE Login | US-MAT-C4-003 | High | As a Field Engineer, I want to receive material testing assignments and submit field test results through the mobile application so that testing data is captured at the site. | AC1: FE receives assignment notification on mobile; AC2: Test result entry with photo upload; AC3: GPS coordinates captured; AC4: Internal testing completed; AC5: UAT/Prod/CR testing completed | Done | Sprint 12-13 | 30
Material Testing CR – FE Inspection Date in GM/SQC/TPIA | US-MAT-C4-004 | Medium | As a GM/SQC/TPIA user, I want the FE Inspection Date field visible on all Material Testing web pages for GM, SQC, and TPIA login so that the inspection timeline is traceable. | AC1: FE Inspection Date column added to Material Testing web pages for GM login; AC2: FE Inspection Date added for SQC login; AC3: FE Inspection Date added for TPIA login; AC4: Date sourced correctly from inspection records; AC5: Tested and deployed | Done | Sprint 15 | 8
Material Testing – OHT Search & Sub-Component Search | US-MAT-C4-005 | Low | As a mobile user, I want OHT search and Sub-Component search functionality in Material Testing mobile so that users can quickly locate the asset or component they need. | AC1: OHT search functionality added to Material Testing mobile; AC2: Sub-Component search added (shared with Cube Testing); AC3: Results filtered correctly; AC4: Search works offline; AC5: Tested and deployed on Play Store | Done | Sprint 15 | 16

## Nirmal US
Jal Rekha – Cycle 4 User Stories ¦ Nirmal (FE Mobile, GM, CR) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Nirmal FE Mobile – Development | US-NRM-C4-001 | High | As a Field Engineer, I want the Nirmal mobile app enhanced with geofencing, new water sampling module, and WTP/Raw Water reporting so that water quality monitoring is comprehensive. | AC1: Water Sampling Collection by Contractor functional; AC2: Geofencing with 200m buffer for WTP/Intake sample collection; AC3: New Nirmal module on mobile; AC4: New web pages for Nirmal reports; AC5: Beneficiary, OHT, WTP, RawWater reports on web; AC6: SIT, UAT/Prod/CR testing | Done | Sprint 12 | 95
Nirmal FE Mobile – API & Wireframe | US-NRM-C4-002 | High | As a developer, I want API creation, UI updates, and unit testing for Nirmal FE mobile completed so that all Nirmal module endpoints are functional. | AC1: APIs for all Nirmal mobile endpoints; AC2: UI updated in existing mobile pages; AC3: Requirement gathering and wireframe completed; AC4: Unit testing for module; AC5: Testing completed with defect log | Done | Sprint 12-13 | 30
Nirmal GM – Report Modification | US-NRM-C4-003 | High | As a GM user, I want Nirmal reports created/modified and beneficiary report issue resolved so that water quality data is accurately represented. | AC1: Report creation/modification for GM Nirmal login; AC2: Beneficiary report issue fixed; AC3: Report loads <5 s for 1000+ records; AC4: Export to Excel/PDF functional; AC5: Report changes validated in production | Done | Sprint 12 | 8
Nirmal CR – Beneficiary & All Reports | US-NRM-C4-004 | High | As an FE and contractor user, I want Nirmal Beneficiary, OHT, WTP, and Raw Water reports updated per change request with remarks column and contractor-scheme filtering so that water quality reports are role-specific and complete. | AC1: Remarks column added to Beneficiary report for both contractor and GM login; AC2: Only contractor-login schemes shown in contractor view across all reports; AC3: Beneficiary Report UI popup changes applied; AC4: WTP, OHT, Raw Water reports updated with CR; AC5: All changes moved to production after unit testing; AC6: Residual chlorine disabled correctly in WTP intake FRC test | Done | Sprint 13 | 20

## O&M Billing US
Jal Rekha – Cycle 4 User Stories ¦ O&M Billing (GM / Contractor / Workflow) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
O&M Billing GM – Development & Reports | US-OM-C4-001 | High | As a GM user, I want O&M Billing module with new web pages, reports, and partial billing support developed so that billing operations are accurate and auditable. | AC1: New web pages and UI for GM login; AC2: Partial O&M Bills functionality; AC3: Frontend and DB bug fixes; AC4: GET/SET data access methods and APIs; AC5: DB architecture with master check; AC6: SIT and UAT/Prod/CR testing; AC7: Test cases and scenarios documented | Done | Sprint 12-15 | 222
O&M Billing GM – Requirement & CR | US-OM-C4-002 | High | As a BA/PM, I want requirement gathering, analysis, and change request implementation for O&M Billing GM module so that department expectations are met. | AC1: Requirement gathering for GM and Contractor flow; AC2: Internal meetings minuted; AC3: Census Population auto-fetched from Scheme Village Master; AC4: GM HSC Change implemented; AC5: Monitoring changes requirement documented | Done | Sprint 12-15 | 34
O&M Billing Workflow | US-OM-C4-003 | High | As a higher official, I want O&M Billing workflow between GM and higher officials defined and implemented so that billing approvals follow a structured escalation path. | AC1: Workflow documented (Contractor → GM → Higher Officials); AC2: Requirement gathering completed; AC3: Approval hierarchy with notifications; AC4: Workflow tested end-to-end; AC5: Workflow diagram approved by department | Done | Sprint 12 | 27
O&M Billing CR – Contractor | US-OM-C4-004 | High | As a contractor, I want bill generation flow, abstract page generation, complaint and pressure redressal sheets, and summary page changes implemented so that contractor billing is complete and compliant. | AC1: Contractor Bill generation flow updated with Approved Reports; AC2: Generate Abstract Page (Complaint Redressal Sheet) and Pressure Redressal Sheet enabled post Save & Submit; AC3: Generate Summary Page for Contractor; AC4: CR in Contractor Summary Page Abstract Report; AC5: Complaint Date column modification; AC6: Dhara Reports from Contractor side updated and validated | Done | Sprint 13-15 | 249
O&M Billing CR – Summary Page, Final Submission & Dynamic Buttons | US-OM-C4-005 | High | As a contractor, I want the O&M Billing Summary page to correctly show/hide Draft and Submit buttons based on bill submission status and prevent data modification after final submission so that billing integrity is maintained. | AC1: Draft and Save buttons hidden after final bill submission; AC2: Bulk, Village, Deduction Details buttons disabled post submission; AC3: Add/update operations in Residual Pressure, Complaint Redressal, and Power Consumption tabs restricted post submission; AC4: is_draft flag correctly returned by DB function; AC5: End-to-end testing for both Draft and Final states | Done | Sprint 14-15 | 40
O&M Billing CR – PDF Generation (Residual Pressure & Bulk Report) | US-OM-C4-006 | Medium | As a GM and contractor user, I want PDF generation for Residual Pressure and Bulk reports in O&M Billing so that billing documents can be formally printed and submitted. | AC1: PDF generation implemented for Residual Pressure report; AC2: PDF generation implemented for Bulk report; AC3: Dynamic RA Bill No auto-generated in PDF header; AC4: PDF service creation and modification completed; AC5: PDF tested and validated | Done | Sprint 15 | 20
O&M Billing CR – Power Consumption & CPWI Calculation | US-OM-C4-007 | Medium | As a GM user, I want Power Consumption tab calculation logic and CPWI/Yearly Factor mapping in O&M Billing so that utility cost data is accurately computed. | AC1: Power Consumption tab calculation logic updated; AC2: CPWI and Yearly Factor parameters mapped per bill; AC3: Data displayed on basis of bill context; AC4: Summary tab shows Gross O&M Bill with editable fields and correct totals; AC5: Save VillageDeductionDetails with Draft Save implemented | Done | Sprint 14-15 | 32

## Sahbhagita US
Jal Rekha – Cycle 4 User Stories ¦ Sahbhagita (GM / CR / Reports) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sahbhagita GM – Reports & Approval | US-SAH-C4-001 | High | As a GM user, I want Sahbhagita survey approval page and updated reports so that community participation surveys can be reviewed and approved formally. | AC1: New Survey Approval page with pending survey list; AC2: Approve and Reject buttons with mandatory remarks on rejection; AC3: Report modifications visible in Sahbhagita Reports menu; AC4: Frontend bug fixes applied; AC5: SIT and UAT/Prod/CR testing; AC6: Upload Activities through Web Portal functional | Done | Sprint 12 | 6
Sahbhagita CR – RA Bill & Save as Draft | US-SAH-C4-002 | High | As a PM user, I want RA Bill functionality on CP Manager and Save as Draft feature added to Sahbhagita module so that ISA billing and survey submissions are managed effectively. | AC1: RA Bill Functionality on CP Manager implemented; AC2: Save as Draft added to Sahbhagita forms; AC3: ISA Bill Form linked to Scheme and District; AC4: Bill amount auto-calculated; AC5: Report changes tested | Done | Sprint 14-16 | 23
Sahbhagita Report – New Web Page | US-SAH-C4-003 | Medium | As a developer, I want new Sahbhagita report web pages created so that GM and PM users can access community participation data in a structured format. | AC1: New web page for Sahbhagita reports; AC2: Updated columns (Activity Type, Participation Count, NGO, ISA, Video Evidence); AC3: Filter options (Date, Village, ISA, NGO); AC4: Export to Excel/PDF; AC5: Report load <3 s | Done | Sprint 12 | 6
Sahbhagita CR – NGO Count Segregation & PIU Dropdown | US-SAH-C4-004 | Medium | As a GM user, I want the Sahbhagita Summary Page NGO count segregation issue fixed and role-based PIU Dropdown applied in reports so that data is accurate and role-filtered. | AC1: NGO Count Segregation Issue on Summary Page fixed; AC2: Role-based PIU Dropdown applied in report search; AC3: Search Validation changes applied; AC4: Live issue of ISA not showing per scheme fixed; AC5: Changes tested and deployed in production | Done | Sprint 15-16 | 22

## SVS US
Jal Rekha – Cycle 4 User Stories ¦ SVS Water Supply Monitoring – Har Ghar Jal ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
SVS – Module Initiation & NIC API Integration | US-SVS-C4-001 | High | As a project manager, I want the SVS Water Supply Monitoring module initiated with formal requirement gathering and NIC Panchayat Darpan API finalised so that the development team has complete specifications and integration details before build begins. | AC1: Project module initiation meeting conducted and MoM documented; AC2: Requirement gathering sessions with PHE stakeholders; AC3: API endpoints and data contract from NIC Panchayat Darpan finalised; AC4: Village Master data structure confirmed and mapped to SVS fields; AC5: SVS Daily Water Supply Wireframe reviewed and approved; AC6: DB schema designed with field-level mapping | Done | Sprint 16 | 4
SVS – Daily Water Supply Data Entry Form | US-SVS-C4-002 | High | As a GP user or PHE field officer, I want a structured daily water supply data entry form with District, Block, GP, Village, and Household Connections pre-filled so that I can quickly record supply status. | AC1: Form displays District, Block, GP, Village based on logged-in user's jurisdiction; AC2: Household Connections Established (स्थापित घरेलू नल कनेक्शन) auto-populated from Village Master; AC3: Water Supply Date defaults to today's date; AC4: Mandatory field validation before submission; AC5: Submission confirmation shown; AC6: Record saved with user ID, timestamp, and village code | Done | Sprint 16 | 12
SVS – Water Supply Date Picker | US-SVS-C4-003 | High | As a GP user, I want a date picker control on the SVS water supply entry form so that I can accurately select the date of water supply without manual text entry errors. | AC1: Calendar date picker displayed for Water Supply Date (जल प्रदाय दिनांक); AC2: Default date = current system date; AC3: Future dates restricted; AC4: Date format DD-MM-YYYY in DB; AC5: Works on desktop and Android mobile browser; AC6: Date visible before submission | Done | Sprint 16 | 4
SVS – Water Supply Status – YES Flow | US-SVS-C4-004 | High | As a GP user, I want to record YES (हाँ) water supply status for my village on a given date so that the system reflects successful daily supply. | AC1: YES selectable from Water Supply Status field; AC2: No additional mandatory fields when YES selected; AC3: Record saved with status=YES, date, village code, user ID; AC4: Dashboard reflects YES count; AC5: GP and PHE login can view YES records in daily report; AC6: Reason/Remark field not shown when YES | Done | Sprint 16 | 8
SVS – Water Supply Status – NO Flow with Reason | US-SVS-C4-005 | High | As a GP user, I want to record NO (नहीं) supply status with a mandatory reason selection and remarks box so that the department can track and address supply failures with root cause data. | AC1: Selecting NO shows Reason dropdown (Tubewell Failure, OHT Not Filled, Motor Pump, Valve/Pump Operator, Electricity, Pipeline Damage, Any Other + Remarks); AC2: Reason mandatory when status=NO; AC3: Any Other opens free-text Remarks box (mandatory); AC4: Open Remarks box shown by default when NO; AC5: Record saved with status=NO, reason code, remarks; AC6: GM dashboard shows NO count with reason breakdown | Done | Sprint 16 | 8
SVS – Water Supply Status – PARTIAL Flow | US-SVS-C4-006 | High | As a GP user, I want to record PARTIAL (आंशिक) supply status with the number of connections that received water and a mandatory remarks box so that partial supply incidents are tracked with quantitative data. | AC1: PARTIAL status shows 'Connections Supplied Water' as mandatory numeric input; AC2: Connections supplied ≤ total HSC connections; AC3: Remarks box opens automatically when PARTIAL selected; AC4: Remarks mandatory for PARTIAL; AC5: Record saved with status=PARTIAL, connections count, remarks; AC6: Dashboard shows PARTIAL count and connections percentage | Done | Sprint 16 | 8
SVS – Partial Edit Feature | US-SVS-C4-007 | High | As a GP user or PHE officer, I want to partially edit a previously submitted daily water supply record so that data corrections can be made without deleting the full record. | AC1: Partial Edit available within configurable edit window (same day/24 hrs); AC2: Status, Reason (NO), Connections (PARTIAL), Remarks editable without changing Date or Village; AC3: Edit logs original and new values with editor user ID and timestamp; AC4: Edited records flagged 'Modified' in reports; AC5: Only authorised roles can edit; AC6: Beyond edit window requires supervisor approval | Done | Sprint 16 | 4
SVS – Default Hierarchy Selection by Login | US-SVS-C4-008 | High | As a logged-in GP or PHE user, I want District, Block, and GP auto-selected by default based on my login credentials so that I do not need to manually navigate the location hierarchy. | AC1: System identifies user's District, Block, GP from user profile on login; AC2: District/Block/GP pre-filled and locked for GP-level users; AC3: PHE/Block-level users see default but may change Block/Village within scope; AC4: District-level users see all Blocks and GPs; AC5: Default applied in all SVS forms; AC6: No manual re-selection required for GP user across daily submissions | Done | Sprint 16 | 4
SVS – Hindi Interface (MP Shasan Labels) | US-SVS-C4-009 | High | As an MP government user, I want the SVS water supply entry form to display field labels in Hindi (MP Shasan standard) so that GP-level and rural users can use the system in their native language. | AC1: All SVS form labels in bilingual or Hindi only based on language setting; AC2: Labels: 'जल प्रदाय दिनांक', 'जल प्रदाय की स्थिति', 'हाँ', 'नहीं', 'आंशिक', 'स्थापित घरेलू नल कनेक्शन'; AC3: Reason dropdown in Hindi; AC4: MP Shasan branding applied; AC5: Hindi rendering tested on Chrome and Android | Done | Sprint 16 | 4
SVS – Remove Unwanted Fields (JJM, Village Status, Hand Over Community) | US-SVS-C4-010 | Medium | As a PHE department stakeholder, I want the JJM field, Village Status field, and Hand Over Community field removed from the SVS supply monitoring form so that the form is focused and aligned to current department requirements. | AC1: JJM field removed from SVS data entry form and report columns; AC2: Village Status field removed; AC3: Hand Over Community field removed; AC4: DB columns retained but not exposed in UI/reports; AC5: Historical records accessible via admin view; AC6: Removal tested in staging; AC7: Report templates updated | Done | Sprint 16 | 4
SVS – Excel Report with LGD Code and Household Join | US-SVS-C4-011 | High | As a PHE data analyst or district officer, I want Excel downloadable reports from SVS that include the LGD Code and Household Connections data joined to each village record so that reports can be cross-referenced with national LGD data. | AC1: SVS Excel download includes LGD Code column; AC2: Household Connections Established joined from Village Master; AC3: LGD Code and Household data from IMS/Panchayat Darpan master; AC4: Excel columns: District, Block, GP, Village, LGD Code, HSC, Supply Date, Status, Reason, Connections Supplied, Remarks; AC5: Date range filter available; AC6: Excel download <10 s for 1000 records | Done | Sprint 16 | 8
SVS – Dashboard: Village / Block / District Level Monitoring | US-SVS-C4-012 | High | As a PHE department official, I want a SVS monitoring dashboard showing daily water supply status (YES / NO / PARTIAL counts) at village, block, and district level with drill-down navigation so that supply performance is visible at all governance levels. | AC1: Dashboard shows total villages vs supply submitted for selected date; AC2: Status breakdown: YES (green), NO (red), PARTIAL (amber), Not Submitted (grey); AC3: District → Block → GP → Village drill-down navigation; AC4: Date filter on dashboard; AC5: Reason for NO supply visible as sub-panel; AC6: Dashboard refreshes on demand; AC7: Accessible to PHE, GM, District, Block login with scope restriction; AC8: 1 Scheme = 1 Handpump monitoring aligned for SVS | Done | Sprint 16 | 16
SVS – Panchayat Sachiv DWSR Entry at Rural Level | US-SVS-C4-013 | High | As a Panchayat Sachiv, I want a dedicated Daily Water Supply Report (DWSR) entry form on the web portal so that I can record village-level water supply data for each SVS village under my Gram Panchayat on a daily basis. | AC1: DWSR entry form on web portal accessible to Panchayat Sachiv login; AC2: SVS scheme approach applied – 1 Village = 1 Scheme; AC3: Form pre-fills District, Block, GP, Village, HSC from user profile and Village Master; AC4: Water Supply Status options: Yes / No / Partial; AC5: No supply reason mandatory if No or Partial selected; AC6: Geo-tagged photo upload supported; AC7: Record saved with GP user ID, timestamp, and village code | Done | Sprint 16 | 8
SVS – DWSR Report Generation | US-SVS-C4-014 | High | As a PHE officer or Panchayat Sachiv, I want a DWSR (Daily Water Supply Report) generated from submitted data showing village-wise supply status, meter readings, and volumes so that daily performance can be formally reported. | AC1: DWSR report generated per GP per date; AC2: Columns: Village, SVS Code, Total HH, HSC Connections, HH Supplied, Supply Hours, Volume (kl), Schools, Status, Reason (if No); AC3: Block/District consolidated totals shown; AC4: Excel download available; AC5: Date range filter operational; AC6: Report loads <5 s for GP with up to 50 villages | Done | Sprint 16 | 8
SVS – DWSR Summary Report | US-SVS-C4-015 | High | As a district officer, I want a consolidated DWSR Summary Report at Block, GP, and District level so that I can monitor submission compliance and identify non-reporting GPs. | AC1: Summary Report available with tabs: Block-wise, GP-wise, Village-wise, 7-Day Trend; AC2: GP-wise submission status (Submitted / Partial / Not Reported) shown; AC3: SVS vs MVS supply performance comparison; AC4: Not Reported by GP count prominently displayed; AC5: Excel download of summary; AC6: Report accessible to District, Block, PHE, and GM roles | Done | Sprint 16 | 4

## CMMI Doc US
Jal Rekha – Cycle 4 User Stories ¦ CMMI Documentation + Dept Meetings ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
CMMI Doc – Data Collection Cycle 4 | US-CMMI-C4-001 | High | As a SEPG team member, I want to collect data for Cycle 4 (Jan to May 2026) so that I can measure project performance metrics and prepare CMMI Level 5 audit artifacts. | AC1: Data collection sheet with all required fields (Requirement, Design, Coding, Code Review, Testing Efforts); AC2: Data collected for all Cycle 4 modules; AC3: Defect data captured across all review stages; AC4: Productivity, DRE, and Cycle Time calculated automatically; AC5: Data validated for accuracy | Done | Sprint 12-16 | 108
CMMI Doc – Streamline Documentation | US-CMMI-C4-002 | High | As a quality manager, I want CMMI documentation streamlined for O&M Billing, Bharosa, and Material modules so that audit artifacts are consistent and complete. | AC1: Streamline documentation completed for O&M Billing, Bharosa, Material Testing; AC2: Documents reviewed per CMMI L5 standards; AC3: Induction training attended; AC4: Promote activity for CMMI L5 Audit completed; AC5: Documents archived with version control | Done | Sprint 13 | 60
CMMI Doc – Phase 1 to 4 Completion | US-CMMI-C4-003 | High | As a SEPG team member, I want CMMI documentation completed across all four phases for Cycle 4 so that the project is fully prepared for CMMI Level 5 audit. | AC1: Phase 1 (Planning, Estimation) documentation; AC2: Phase 2 (Requirements, Design); AC3: Phase 3 (Coding, Code Review); AC4: Phase 4 (Testing, Deployment); AC5: All phases reviewed by SEPG Head; AC6: Data collection Jan–May cycle baselined | Done | Sprint 12-16 | 531
Department Meetings – Requirement Gathering | US-CMMI-C4-004 | High | As a BA/PM, I want department meetings conducted for all module requirements and changes so that all stakeholder needs are documented and tracked. | AC1: Department meetings for all modules documented; AC2: New material and cube testing modules discussed; AC3: Requirement gathering for changes completed; AC4: Meeting minutes distributed within 24 hrs; AC5: Requirements tracked via traceability matrix | Done | Sprint 12-16 | 57

## Site Security US
Jal Rekha – Cycle 4 User Stories ¦ Site Security Audit ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Site Security Audit | US-SEC-C4-001 | High | As a security team member, I want Jal Rekha site Fortify security audit conducted so that all security vulnerabilities are identified and remediated before production. | AC1: Fortify audit configured and run on codebase; AC2: Critical and high severity vulnerabilities documented; AC3: Remediation plan with owners and timelines; AC4: Security audit report submitted to department; AC5: Dhara module specific security issues resolved | Done | Sprint 15 | 16
Site Security – Code-Level Vulnerability Fixes | US-SEC-C4-002 | High | As a developer, I want all critical and high vulnerabilities identified by Fortify remediated in the codebase so that Jal Rekha meets security compliance before production release. | AC1: All critical vulnerabilities patched; AC2: High severity vulnerabilities patched or accepted with documented risk; AC3: Fortify re-scan post-fix shows zero critical issues; AC4: Security fix code reviewed by senior developer; AC5: Changes deployed to production | WIP | Sprint 15-16 | 16

## Sopan US
Jal Rekha – Cycle 4 User Stories ¦ Sopan Contractor ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sopan Contractor – Development & Testing | US-SOP-C4-001 | High | As a contractor, I want the Sopan Contractor module with dashboard, data upload, and new web pages functional so that scheme-level contractor activities are properly managed. | AC1: Dashboard for Sopan Contractor; AC2: Upload Activities through Web Portal functional; AC3: New web pages and GET/SET data methods; AC4: OHT data correction; AC5: Database bug fixes; AC6: Requirement gathering; AC7: SIT, UAT/Prod/CR testing | Done | Sprint 13 | 6
Sopan CR – OHT Data Correction | US-SOP-C4-002 | Medium | As a data admin, I want OHT data correction functionality in Sopan so that incorrect OHT entries can be identified and fixed without affecting production data. | AC1: OHT data correction page available in Sopan module; AC2: Audit log maintained for all corrections; AC3: Only admin/superuser role can perform corrections; AC4: Correction tested in staging; AC5: Deployed and verified in production | Done | Sprint 13 | 4

## User Role US
Jal Rekha – Cycle 4 User Stories ¦ User & Role Management ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
User & Role Management – Testing | US-URM-C4-001 | High | As a QA engineer, I want functional and SIT testing of User and Role Management module completed so that all access controls and permissions are verified before release. | AC1: Functional testing for all user roles across all modules; AC2: SIT testing completed; AC3: Permission matrix verified; AC4: No unauthorised access identified; AC5: Test report submitted | Done | Sprint 14 | 12
User & Role Management – Role-Based Data Scope Enforcement | US-URM-C4-002 | High | As a system admin, I want role-based data scope enforcement applied to all Jal Rekha modules so that each user only sees data within their assigned geography and role. | AC1: District-level users see all data within their district only; AC2: Block-level users restricted to their block; AC3: GP-level users restricted to their GP; AC4: Contractor sees only their assigned schemes; AC5: Role-scope tested for Dhara, SVS, FHTC, Nirmal, O&M Billing; AC6: No cross-role data leakage | Done | Sprint 14-15 | 12